## OTOB
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [13 empty] | Highway Construction Projects Completed March 1, 2024–August 31, 2024
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | AUGUST | 31 | 2024 | 2023
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | CO BY THRD PRTY | AMOUNT PAID | UNDER OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | THIRD PARTY DAYS ADDED | UNDER OVER SCHEDULE
WACO | 0014-07-101 | HILL | SH 81 | 2023-09-01 | 3020549.2 | 164471.56 | 0 | 3218846.25 | 198297.05 | 75 | 75 | 0 | 0 | 0
AMARILLO | 0226-05-067 | DEAF SMITH | US 385 | 2023-09-03 | 5447354.4 | -122444.72 | 0 | 5792909.96 | 345555.56 | 91 | 120 | 21 | 0 | 29
AUSTIN | 0914-00-450 | TRAVIS | VA | 2023-09-04 | 5650620 | -1381686.72 | 0 | 4209423.38 | -1441196.62 | 160 | 234 | 79 | 0 | 74
EL PASO | 0374-02-122 | EL PASO | US 62 | 2023-09-06 | 103530 | 0 | 0 | 102486 | -1044 | 40 | 33 | 0 | 0 | -7
WACO | 0320-01-078 | BELL | SS 290 | 2023-09-06 | 384376 | -19500 | 0 | 395722.99 | 11346.99 | 75 | 53 | 0 | 0 | -22
YOAKUM | 0269-03-035 | LAVACA | US 77A | 2023-09-06 | 2082955.47 | 26693.76 | 0 | 1992284.45 | -90671.02 | 330 | 434 | 104 | 0 | 104
YOAKUM | 0913-00-108 | DEWITT | Various | 2023-09-06 | 665410.86 | 0 | 0 | 685718.81 | 20307.95 | 37 | 24 | 0 | 0 | -13
YOAKUM | 2350-01-070 | VICTORIA | SL 463 | 2023-09-06 | 571189.5 | 0 | 0 | 575668.5 | 4479 | 101 | 79 | 0 | 0 | -22
ABILENE | 0005-05-113 | HOWARD | IH 20 | 2023-09-07 | 6309354.48 | 3043.32 | 0 | 6366817.92 | 57463.44 | 48 | 34 | 0 | 0 | -14
ABILENE | 0974-06-016 | CALLAHAN | FM 604 | 2023-09-07 | 3777685.88 | 0 | 0 | 3854188.77 | 76502.89 | 183 | 143 | 0 | 0 | -40
FORT WORTH | 0080-02-061 | ERATH | US 377 | 2023-09-07 | 437790 | 417716.27 | 0 | 914012.2 | 476222.2 | 22 | 79 | 11 | 0 | 57
DALLAS | 0918-47-247 | DALLAS | CS | 2023-09-08 | 1374730 | 0 | 0 | 1374256.72 | -473.28 | 300 | 297 | 0 | 0 | -3
DALLAS | 0918-47-398 | DALLAS | Various | 2023-09-08 | 1681430.44 | 83633.68 | 0 | 1850112.83 | 168682.39 | 68 | 62 | 0 | 0 | -6
HOUSTON | 1257-01-053 | FORT BEND | FM 1092 | 2023-09-08 | 2396293.69 | -144245.87 | 0 | 2724070.51 | 327776.82 | 126 | 126 | 0 | 0 | 0
HOUSTON | 2898-01-012 | WALLER | FM 2855 | 2023-09-08 | 5061781.12 | -94392.79 | 0 | 4862466.24 | -199314.88 | 150 | 145 | 0 | 0 | -5
HOUSTON | 1685-05-128 | HARRIS | SH 6 | 2023-09-11 | 387860.68 | 80632.45 | 0 | 493561.61 | 105700.93 | 35 | 31 | 0 | 0 | -4
LUBBOCK | 0052-07-072 | LUBBOCK | US 84 | 2023-09-11 | 538624.6 | 0 | 0 | 535800.43 | -2824.17 | 80 | 72 | 0 | 0 | -8
LUBBOCK | 0439-01-025 | CASTRO | SH 194 | 2023-09-11 | 383370.2 | 44420 | 0 | 430899.12 | 47528.92 | 20 | 10 | 0 | 0 | -10
PARIS | 1487-01-008 | FANNIN | FM 1552 | 2023-09-11 | 1844734.62 | 5964.48 | 0 | 1925892.39 | 81157.77 | 96 | 122 | 0 | 0 | 26
SAN ANGELO | 0907-00-199 | TOM GREEN | Various | 2023-09-12 | 1784037.16 | 66836 | 0 | 1850876.16 | 66839 | 39 | 42 | 0 | 0 | 3
SAN ANTONIO | 0017-05-095 | MEDINA | IH 35 | 2023-09-12 | 2442867.71 | -97596.21 | 0 | 2385528.53 | -57339.18 | 466 | 477 | 11 | 0 | 11
PHARR | 0039-02-068 | HIDALGO | US 83 | 2023-09-13 | 6096123 | 230230.23 | 0 | 5837343.53 | -258779.47 | 320 | 338 | 27 | 0 | 18
AUSTIN | 0914-00-418 | TRAVIS | VA | 2023-09-14 | 2145700 | 417731.3 | 0 | 544901.24 | -1600798.76 | 730 | 13 | 0 | 0 | -717
BRYAN | 0186-06-091 | WASHINGTON | US 290 | 2023-09-14 | 1649907.2 | 38173.67 | 0 | 1654960.95 | 5053.75 | 86 | 105 | 0 | 0 | 19
SAN ANGELO | 0907-14-010 | COKE | CR | 2023-09-15 | 659587 | 6577.6 | 0 | 635599.34 | -23987.66 | 84 | 74 | 0 | 0 | -10
PHARR | 0684-02-014 | CAMERON | FM 511 | 2023-09-18 | 1147081.1 | 87839.13 | 0 | 1333910.17 | 186829.07 | 131 | 140 | 19 | 0 | 9
AUSTIN | 0016-02-149 | HAYS | IH 35 | 2023-09-19 | 13264542.3 | 617198.44 | 34160.43 | 14024549 | 725846.27 | 379 | 383 | 119 | 0 | 4
WACO | 0909-00-067 | MCLENNAN | Various | 2023-09-19 | 1849402.79 | 15913.52 | 0 | 1688054.17 | -161348.62 | 105 | 55 | 0 | 0 | -50
WACO | 0909-36-181 | BELL | CS | 2023-09-19 | 451322 | -2126.7 | 0 | 411969.04 | -39352.96 | 90 | 56 | 0 | 0 | -34
BEAUMONT | 0200-08-059 | TYLER | US 69 | 2023-09-20 | 1846631.83 | -434276.22 | 0 | 1630624.92 | -216006.91 | 82 | 79 | 0 | 0 | -3
BRYAN | 0917-00-051 | BRAZOS | VA | 2023-09-20 | 183906 | 30160 | 0 | 209695.08 | 25789.08 | 45 | 17 | 0 | 0 | -28
FORT WORTH | 0008-03-089 | PARKER | IH 20 | 2023-09-20 | 3921685.61 | 2539234.17 | 0 | 7041948.02 | 3120262.41 | 192 | 628 | 415 | 0 | 436
LUFKIN | 0390-05-006 | SAN AUGUSTINE | FM 2558 | 2023-09-20 | 1485266.77 | 0 | 0 | 1427751.37 | -57515.4 | 159 | 221 | 65 | 0 | 62
CORPUS CHRISTI | 0916-00-224 | NUECES | Various | 2023-09-21 | 2367405.63 | 130415.55 | 0 | 2291285.55 | -76120.08 | 62 | 98 | 27 | 0 | 36
AUSTIN | 1197-01-021 | HAYS | RM 150 | 2023-09-22 | 3601690.88 | 290835.66 | 0 | 4109049.14 | 507358.26 | 215 | 166 | 0 | 0 | -49
HOUSTON | 0912-00-644 | HARRIS | VA | 2023-09-22 | 1273417.93 | -574197.23 | 0 | 604086.32 | -669331.61 | 181 | 340 | 159 | 0 | 159
ODESSA | 0228-06-081 | ECTOR | US 385 | 2023-09-22 | 25331611.54 | 1174095.01 | 0 | 27534729.62 | 2203118.08 | 291 | 452 | 171 | 0 | 161
AUSTIN | 0152-03-062 | CALDWELL | US 183 | 2023-09-25 | 1315225 | 370073.47 | 0 | 1778911.14 | 463686.14 | 117 | 140 | 25 | 0 | 23
HOUSTON | 0271-16-160 | HARRIS | IH 610 | 2023-09-25 | 645779.25 | 1149137.02 | 0 | 2039717.89 | 1393938.64 | 208 | 87 | 0 | 0 | -121
SAN ANGELO | 2574-01-049 | TOM GREEN | CS | 2023-09-25 | 538601 | 24146 | 0 | 609953.5 | 71352.5 | 132 | 130 | 0 | 0 | -2
YOAKUM | 0913-21-052 | MATAGORDA | CR | 2023-09-25 | 648611.35 | 0 | 0 | 636160.69 | -12450.66 | 60 | 51 | 0 | 0 | -9
AMARILLO | 0275-01-205 | POTTER | IH 40 | 2023-09-26 | 15820658.82 | 971467.95 | 0 | 17412230.13 | 1591571.31 | 440 | 468 | 46 | 0 | 28
HOUSTON | 0598-02-119 | BRAZORIA | SH 288 | 2023-09-26 | 4797528.55 | 80207.9 | 80207.9 | 5122493.38 | 244756.93 | 171 | 182 | 23 | 23 | -12
ABILENE | 0650-01-034 | NOLAN | SH 153 | 2023-09-27 | 5924739.06 | 136210.94 | 0 | 6145786.77 | 221047.71 | 235 | 294 | 15 | 0 | 59
AUSTIN | 3210-01-019 | HAYS | FM 2770 | 2023-09-27 | 1394023.95 | 80014.86 | 0 | 1294734.24 | -99289.71 | 80 | 39 | 0 | 0 | -41
SAN ANTONIO | 0017-06-091 | FRIO | IH 35 | 2023-09-27 | 1300000 | 0 | 0 | 1330730.45 | 30730.45 | 56 | 44 | 0 | 0 | -12
AMARILLO | 2635-05-001 | RANDALL | SL 335 | 2023-09-28 | 45797690.54 | 675267.16 | 0 | 46071009.59 | 273319.05 | 764 | 871 | 87 | 0 | 107
AUSTIN | 0440-06-025 | TRAVIS | SH 130 | 2023-09-29 | 459288.6 | 3000 | 0 | 527541.26 | 68252.66 | 66 | 57 | 0 | 0 | -9
ATLANTA | 0062-04-051 | CASS | US 59 | 2023-10-02 | 504893.32 | 45082.16 | 0 | 522045.87 | 17152.55 | 90 | 81 | 0 | 0 | -9
AUSTIN | 0152-03-061 | CALDWELL | US 183 | 2023-10-02 | 5467487.08 | 0 | 0 | 5102910.86 | -364576.22 | 95 | 65 | 0 | 0 | -30
BEAUMONT | 2701-02-025 | ORANGE | FM 3247 | 2023-10-02 | 1011890.95 | -13352.25 | 0 | 1090559.61 | 78668.66 | 26 | 25 | 0 | 0 | -1
LUFKIN | 0176-02-125 | ANGELINA | BU 59G | 2023-10-02 | 1363053.76 | 31752 | 0 | 1397581.82 | 34528.06 | 95 | 92 | 4 | 0 | -3
LUFKIN | 0911-40-029 | TRINITY | VA | 2023-10-02 | 975968 | -3783.04 | 0 | 933915.37 | -42052.63 | 146 | 278 | 21 | 0 | 132
PHARR | 0255-08-108 | HIDALGO | IH 69C | 2023-10-02 | 9148469.99 | -97547.83 | 0 | 9021148.62 | -127321.37 | 192 | 142 | 0 | 0 | -50
TYLER | 0910-00-132 | SMITH | VA | 2023-10-02 | 402135.93 | -1704.91 | 0 | 355055.87 | -47080.06 | 49 | 20 | 0 | 0 | -29
AMARILLO | 0904-00-200 | POTTER | Various | 2023-10-03 | 781620.71 | 0 | 0 | 756098.59 | -25522.12 | 56 | 27 | 0 | 0 | -29
AUSTIN | 0511-03-013 | HAYS | RM 32 | 2023-10-03 | 1073849.51 | -28279.33 | 0 | 952581.79 | -121267.72 | 85 | 57 | 0 | 0 | -28
BEAUMONT | 1194-02-019 | HARDIN | FM 943 | 2023-10-03 | 1940016.09 | 0 | 0 | 1875235.37 | -64780.72 | 130 | 113 | 0 | 0 | -17
EL PASO | 0924-00-144 | EL PASO | VA | 2023-10-03 | 1343419.6 | 0 | 0 | 1366363.6 | 22944 | 200 | 273 | 0 | 0 | 73
PHARR | 1427-01-040 | HIDALGO | FM 1423 | 2023-10-03 | 5388775.4 | 78779.22 | 0 | 6182443.36 | 793667.96 | 100 | 112 | 15 | 0 | 12
YOAKUM | 0143-08-099 | DEWITT | US 87 | 2023-10-03 | 1692978.61 | 0 | 0 | 1623440.54 | -69538.07 | 45 | 21 | 0 | 0 | -24
YOAKUM | 0153-02-043 | GONZALES | US 183 | 2023-10-03 | 3013760 | -8007 | 0 | 2927761.5 | -85998.5 | 171 | 186 | 0 | 0 | 15
YOAKUM | 0420-02-051 | JACKSON | SH 172 | 2023-10-03 | 2881195.6 | 0 | 0 | 2852621.49 | -28574.11 | 90 | 58 | 0 | 0 | -32
YOAKUM | 0913-09-053 | WHARTON | CR | 2023-10-03 | 629675 | 18430 | 0 | 645721.4 | 16046.4 | 75 | 93 | 4 | 0 | 18
YOAKUM | 1113-01-028 | DEWITT | FM 766 | 2023-10-03 | 8812355.55 | -11351.32 | 0 | 8836952.07 | 24596.52 | 260 | 218 | 0 | 0 | -42
AMARILLO | 0238-04-038 | DALLAM | US 54 | 2023-10-04 | 8285085.51 | -73299.62 | 0 | 8851740.3 | 566654.79 | 127 | 103 | 0 | 0 | -24
AMARILLO | 0490-04-045 | ROBERTS | SH 70 | 2023-10-04 | 23349233.82 | 1181769.67 | 0 | 26743617.08 | 3394383.26 | 178 | 266 | 29 | 0 | 88
PARIS | 2277-01-010 | RAINS | FM 275 | 2023-10-04 | 4114424.46 | 0 | 0 | 4068225.83 | -46198.63 | 330 | 281 | 0 | 0 | -49
BEAUMONT | 0389-02-052 | CHAMBERS | SH 146 | 2023-10-05 | 1117845.7 | 189494.97 | 0 | 1336669.2 | 218823.5 | 162 | 295 | 117 | 0 | 133
PHARR | 0331-03-021 | CAMERON | FM 1421 | 2023-10-05 | 3309036.52 | 0 | 0 | 3431089.4 | 122052.88 | 76 | 76 | 0 | 0 | 0
AUSTIN | 0914-18-111 | BASTROP | CR | 2023-10-06 | 964123.3 | -82400 | 0 | 841628.33 | -122494.97 | 93 | 87 | 0 | 0 | -6
FORT WORTH | 0550-02-050 | ERATH | FM 8 | 2023-10-06 | 6087434.1 | 1009511.28 | 0 | 6594420.47 | 506986.37 | 214 | 204 | 0 | 0 | -10
FORT WORTH | 1990-01-020 | ERATH | FM 205 | 2023-10-06 | 9896354.05 | 932293.92 | 0 | 10358974.41 | 462620.36 | 234 | 332 | 93 | 0 | 98
DALLAS | 0918-46-299 | DENTON | CS | 2023-10-09 | 2851250.8 | 26400 | 0 | 2857466.29 | 6215.49 | 165 | 151 | 0 | 0 | -14
BRYAN | 0917-17-074 | GRIMES | CR | 2023-10-11 | 597985.3 | 0 | 0 | 625445.41 | 27460.11 | 81 | 81 | 0 | 0 | 0
PARIS | 0045-12-087 | RED RIVER | US 82 | 2023-10-11 | 2627582.9 | -9051.77 | 0 | 2528604.04 | -98978.86 | 218 | 223 | 14 | 0 | 5
PARIS | 0045-20-018 | FANNIN | US 82 | 2023-10-11 | 71637885.73 | 709724 | 0 | 75379203.72 | 3741317.99 | 928 | 949 | 0 | 0 | 21
PARIS | 0901-28-093 | HOPKINS | CR | 2023-10-11 | 608037.35 | 0 | 0 | 599130.55 | -8906.8 | 128 | 110 | 0 | 0 | -18
DALLAS | 1012-02-042 | COLLIN | FM 545 | 2023-10-12 | 8250437.86 | 14372.85 | 0 | 7886829.53 | -363608.33 | 450 | 437 | 0 | 0 | -13
WACO | 0836-02-078 | BELL | SH 195 | 2023-10-12 | 709467.86 | -44144.59 | 0 | 674492.09 | -34975.77 | 30 | 23 | 0 | 0 | -7
WACO | 0909-36-189 | BELL | CS | 2023-10-12 | 81987 | -5000 | 0 | 69144 | -12843 | 21 | 6 | 0 | 0 | -15
WICHITA FALLS | 0815-01-051 | COOKE | FM 372 | 2023-10-12 | 4347377.45 | 0 | 0 | 4862140.02 | 514762.57 | 85 | 72 | 0 | 0 | -13
DALLAS | 0092-06-108 | NAVARRO | IH 45 | 2023-10-13 | 3870961.8 | 203705 | 0 | 4309920.67 | 438958.87 | 249 | 249 | 20 | 0 | 0
AUSTIN | 0114-03-107 | TRAVIS | US 290 | 2023-10-16 | 505421.58 | 13894.5 | 0 | 513046.69 | 7625.11 | 44 | 31 | 0 | 0 | -13
BRYAN | 0049-09-094 | BRAZOS | BS 6R | 2023-10-16 | 2897017.81 | 81356.34 | 0 | 3110082.82 | 213065.01 | 65 | 54 | 0 | 0 | -11
HOUSTON | 0271-15-097 | HARRIS | IH 610 | 2023-10-16 | 3481497.4 | 2370424.61 | 0 | 5941358.06 | 2459860.66 | 272 | 265 | 0 | 0 | -7
LUBBOCK | 0294-02-023 | GAINES | US 180 | 2023-10-16 | 48813789.58 | 16651.91 | 0 | 49375604.54 | 561814.96 | 412 | 445 | 43 | 0 | 33
AUSTIN | 0273-04-046 | WILLIAMSON | US 183 | 2023-10-17 | 6654421.8 | -108835.2 | 0 | 6971723.11 | 317301.31 | 314 | 222 | 0 | 0 | -92
BROWNWOOD | 0054-09-042 | MILLS | US 84 | 2023-10-17 | 501967 | 13000 | 0 | 515022 | 13055 | 90 | 78 | 0 | 0 | -12
BRYAN | 1145-02-022 | LEON | FM 811 | 2023-10-17 | 9543192.09 | -351408.55 | 0 | 9295429.44 | -247762.65 | 278 | 286 | 4 | 0 | 8
HOUSTON | 0912-72-654 | HARRIS | Various | 2023-10-17 | 2085476.35 | 0 | 0 | 2146987.48 | 61511.13 | 37 | 58 | 21 | 0 | 21
AUSTIN | 0573-01-034 | BASTROP | SH 304 | 2023-10-18 | 9387685.84 | 129413.31 | 0 | 9245815.42 | -141870.42 | 193 | 188 | 0 | 0 | -5
YOAKUM | 0026-02-034 | FAYETTE | US 90 | 2023-10-18 | 2724321.52 | 22724.99 | 0 | 2742650.44 | 18328.92 | 175 | 163 | 0 | 0 | -12
YOAKUM | 0323-02-034 | FAYETTE | SH 95 | 2023-10-18 | 15550417.41 | -172833.21 | 0 | 15129055.16 | -421362.25 | 300 | 327 | 27 | 0 | 27
AUSTIN | 1201-02-025 | WILLIAMSON | FM 487 | 2023-10-19 | 2349410.23 | -259607.5 | 0 | 2083064.72 | -266345.51 | 74 | 43 | 0 | 0 | -31
DALLAS | 2374-03-096 | DALLAS | IH 20 | 2023-10-19 | 7163236.67 | 255442.32 | 0 | 7858479.35 | 695242.68 | 209 | 218 | 8 | 0 | 9
LUFKIN | 2893-01-018 | SHELBY | FM 947 | 2023-10-19 | 2185617.71 | 102189.68 | 0 | 2198960.97 | 13343.26 | 80 | 77 | 30 | 0 | -3
WACO | 0184-05-005 | CORYELL | BS 36E | 2023-10-19 | 1274745.89 | 92918.41 | 0 | 1391927.28 | 117181.39 | 60 | 68 | 0 | 0 | 8
AUSTIN | 0015-13-419 | TRAVIS | IH 35 | 2023-10-20 | 8677684.54 | 689124.57 | 0 | 9531573.3 | 853888.76 | 85 | 112 | 45 | 0 | 27
BEAUMONT | 0200-10-090 | HARDIN | US 69 | 2023-10-20 | 250000 | 0 | 0 | 250000 | 0 | 7 | 2 | 0 | 0 | -5
BEAUMONT | 0920-02-096 | LIBERTY | VA | 2023-10-20 | 388841.5 | 18705 | 0 | 356928.06 | -31913.44 | 99 | 117 | 20 | 0 | 18
PHARR | 0102-07-045 | BROOKS | SH 285 | 2023-10-22 | 11330610.73 | 67925 | 0 | 12063582.43 | 732971.7 | 138 | 296 | 158 | 0 | 158
AUSTIN | 1539-02-026 | TRAVIS | FM 1626 | 2023-10-23 | 10089973.35 | 146768.65 | 271511.74 | 10122527.27 | -238957.82 | 273 | 438 | 1 | 0 | 165
AUSTIN | 3136-01-196 | TRAVIS | SL 1 | 2023-10-24 | 1239172.95 | 71273.92 | 0 | 1258871.18 | 19698.23 | 25 | 23 | 0 | 0 | -2
LUFKIN | 2589-01-023 | ANGELINA | FM 2497 | 2023-10-24 | 5264189.37 | 54000 | 0 | 5339939.67 | 75750.3 | 145 | 324 | 159 | 0 | 179
ATLANTA | 0010-06-044 | TITUS | US 67 | 2023-10-25 | 10814286.76 | -51401.22 | 0 | 9723857.88 | -1090428.88 | 80 | 64 | 0 | 0 | -16
FORT WORTH | 1181-04-052 | JOHNSON | FM 917 | 2023-10-25 | 913114.46 | 0 | 0 | 699054.93 | -214059.53 | 64 | 63 | 0 | 0 | -1
ABILENE | 1155-03-011 | HOWARD | FM 1785 | 2023-10-26 | 8834075.61 | 116181.4 | 0 | 8826393.09 | -7682.52 | 324 | 318 | 0 | 0 | -6
AUSTIN | 0016-02-168 | HAYS | IH 35 | 2023-10-26 | 1151607.24 | 46693.95 | 0 | 1235717.85 | 84110.61 | 39 | 17 | 0 | 0 | -22
EL PASO | 0002-04-033 | HUDSPETH | SH 20 | 2023-10-26 | 3364597.35 | 690121.05 | 0 | 4018372.97 | 653775.62 | 180 | 100 | 0 | 0 | -80
YOAKUM | 0913-27-089 | VICTORIA | CS | 2023-10-26 | 62074.07 | 0 | 0 | 60074.07 | -2000 | 15 | 6 | 0 | 0 | -9
FORT WORTH | 0171-05-081 | TARRANT | SH 199 | 2023-10-27 | 65461507.43 | 22290867.67 | 3532091.7 | 88807685.78 | 19814086.65 | 919 | 2074 | 1155 | 0 | 1155
FORT WORTH | 0343-04-044 | ERATH | SH 108 | 2023-10-27 | 6936074.51 | 1488357.99 | 279196.22 | 8228038.19 | 1012767.46 | 278 | 406 | 156 | 0 | 128
FORT WORTH | 0422-03-084 | JOHNSON | US 67 | 2023-10-27 | 524586.5 | 0 | 0 | 413919.84 | -110666.66 | 64 | 111 | 45 | 0 | 47
SAN ANTONIO | 0517-03-035 | MCMULLEN | SH 16 | 2023-10-27 | 40124534.52 | -2221713.32 | 0 | 38353484.55 | -1771049.97 | 524 | 824 | 26 | 0 | 300
SAN ANTONIO | 0915-00-241 | BEXAR | Various | 2023-10-27 | 3546574.1 | 0 | 0 | 3169621.13 | -376952.97 | 165 | 151 | 0 | 0 | -14
SAN ANTONIO | 0915-17-073 | COMAL | CS | 2023-10-27 | 629837.17 | 87161.5 | 0 | 761423.43 | 131586.26 | 53 | 62 | 10 | 0 | 9
AUSTIN | 0914-05-213 | WILLIAMSON | CS | 2023-10-30 | 96975.55 | 41300.4 | 0 | 148034.1 | 51058.55 | 44 | 21 | 0 | 0 | -23
YOAKUM | 0089-19-013 | VICTORIA | BU 59-T | 2023-10-30 | 238957.94 | 18868.57 | 0 | 299591.54 | 60633.6 | 60 | 58 | 0 | 0 | -2
AMARILLO | 0168-07-049 | DEAF SMITH | US 60 | 2023-10-31 | 5647434.2 | 10200 | 0 | 5722521.36 | 75087.16 | 181 | 326 | 0 | 0 | 145
FORT WORTH | 0172-01-054 | TARRANT | BU 287P | 2023-10-31 | 1188709.84 | 50869.97 | 0 | 1322018.49 | 133308.65 | 151 | 163 | 16 | 0 | 12
PARIS | 0189-01-012 | RED RIVER | SH 37 | 2023-11-01 | 7781705.26 | 822978.23 | 0 | 9299857.78 | 1518152.52 | 223 | 242 | 19 | 0 | 19
WICHITA FALLS | 1356-01-029 | COOKE | FM 1201 | 2023-11-01 | 4085240.88 | 441436.2 | 0 | 4661844.91 | 576604.03 | 153 | 181 | 32 | 0 | 28
AMARILLO | 0379-03-026 | POTTER | SH 136 | 2023-11-02 | 6694352.15 | -41228.89 | 0 | 6612817.35 | -81534.8 | 207 | 239 | 0 | 0 | 32
ATLANTA | 0569-04-020 | HARRISON | SH 43 | 2023-11-03 | 2545187.72 | 5468.19 | 0 | 2967798.06 | 422610.34 | 128 | 299 | 2 | 0 | 171
LUBBOCK | 0053-01-131 | LUBBOCK | SS 331 | 2023-11-03 | 1570806.75 | 67067 | 0 | 1472585.73 | -98221.02 | 73 | 73 | 0 | 0 | 0
YOAKUM | 0265-07-051 | FAYETTE | SH 71 | 2023-11-05 | 1588831.86 | 38000 | 0 | 2025131.56 | 436299.7 | 75 | 98 | 23 | 0 | 23
YOAKUM | 0267-03-030 | FAYETTE | FM 609 | 2023-11-05 | 3404043.82 | 120891.3 | 0 | 3551667.81 | 147623.99 | 135 | 106 | 0 | 0 | -29
DALLAS | 0009-02-065 | DALLAS | SH 78 | 2023-11-06 | 2049364.32 | 123394.15 | 0 | 1969357.95 | -80006.37 | 102 | 158 | 0 | 0 | 56
ATLANTA | 1020-01-057 | BOWIE | FM 559 | 2023-11-07 | 225789.76 | 0 | 0 | 222878.14 | -2911.62 | 70 | 45 | 0 | 0 | -25
AUSTIN | 0914-00-475 | TRAVIS | Various | 2023-11-07 | 1109148.53 | -123399.47 | 0 | 1018003.01 | -91145.52 | 126 | 70 | 0 | 0 | -56
BROWNWOOD | 2786-01-018 | LAMPASAS | FM 2657 | 2023-11-07 | 2365646.87 | 5121.31 | 0 | 2313756.1 | -51890.77 | 50 | 45 | 0 | 0 | -5
ABILENE | 0263-01-021 | KENT | US 380 | 2023-11-09 | 10460911.96 | -75644.16 | 0 | 10559112.2 | 98200.24 | 103 | 103 | 0 | 0 | 0
AUSTIN | 2689-01-029 | TRAVIS | FM 2304 | 2023-11-09 | 2730040.2 | -196565.74 | 0 | 2433984.33 | -296055.87 | 57 | 23 | 0 | 0 | -34
BROWNWOOD | 0923-17-088 | COMANCHE | CR | 2023-11-09 | 1969718.25 | -1737.56 | 0 | 1979451.09 | 9732.84 | 225 | 235 | 0 | 0 | 10
DALLAS | 0280-02-040 | COLLIN | SH 78 | 2023-11-09 | 15143487.86 | 1064665.43 | 0 | 16488605.68 | 1345117.82 | 328 | 558 | 181 | 0 | 230
DALLAS | 0918-47-341 | DALLAS | CS | 2023-11-09 | 985988.81 | -26508.68 | 28366.94 | 941592.59 | -72763.16 | 57 | 92 | 0 | 0 | 35
PARIS | 1475-01-015 | HOPKINS | FM 1536 | 2023-11-09 | 3845345.39 | 178088.29 | 0 | 3951967.09 | 106621.7 | 192 | 190 | 0 | 0 | -2
CORPUS CHRISTI | 1121-01-022 | KARNES | FM 792 | 2023-11-10 | 1472197.11 | 148689.64 | 0 | 1626386.74 | 154189.63 | 93 | 93 | 38 | 0 | 0
FORT WORTH | 0444-02-023 | JACK | SH 114 | 2023-11-10 | 12812480.29 | 43126.6 | 0 | 11903276.11 | -909204.18 | 148 | 148 | 0 | 0 | 0
WICHITA FALLS | 0903-15-105 | COOKE | CR | 2023-11-13 | 1461248 | 0 | 0 | 1418448.91 | -42799.09 | 153 | 196 | 0 | 0 | 43
DALLAS | 1290-02-023 | ROCKWALL | SH 276 | 2023-11-14 | 2748754 | 120901.92 | 0 | 3015054.42 | 266300.42 | 68 | 68 | 0 | 0 | 0
HOUSTON | 0051-04-067 | GALVESTON | SH 87 | 2023-11-14 | 10994229.67 | 1670383.77 | 203228.44 | 12374440.06 | 1176981.95 | 210 | 359 | 70 | 0 | 149
HOUSTON | 0051-06-018 | HARRIS | SH 3 | 2023-11-14 | 2198720.36 | 130368.52 | 0 | 2430729.34 | 232008.98 | 72 | 65 | 0 | 0 | -7
LUBBOCK | 0130-05-086 | LUBBOCK | SH 114 | 2023-11-15 | 193635 | 49953.79 | 0 | 246363.59 | 52728.59 | 25 | 20 | 0 | 0 | -5
LUBBOCK | 0302-01-023 | PARMER | SH 86 | 2023-11-15 | 196115 | 0 | 0 | 193315 | -2800 | 44 | 26 | 0 | 0 | -18
SAN ANTONIO | 0073-02-080 | BEXAR | US 281 | 2023-11-15 | 4316413.23 | 347668.51 | 0 | 4667730.13 | 351316.9 | 123 | 223 | 67 | 0 | 100
SAN ANTONIO | 1167-01-011 | UVALDE | FM 1052 | 2023-11-15 | 1021333.41 | 0 | 0 | 956434.44 | -64898.97 | 47 | 47 | 0 | 0 | 0
BEAUMONT | 0028-15-056 | ORANGE | SH 87 | 2023-11-16 | 537329.15 | 741464.8 | 0 | 1397019.82 | 859690.67 | 41 | 161 | 123 | 0 | 120
BRYAN | 0166-03-033 | FREESTONE | SH 75 | 2023-11-16 | 4091805.2 | 214787.53 | 0 | 4814897.61 | 723092.41 | 259 | 247 | 0 | 0 | -12
DALLAS | 0196-02-131 | DENTON | IH 35E | 2023-11-16 | 2796046.88 | -189051.81 | 0 | 2608390.02 | -187656.86 | 71 | 74 | 3 | 0 | 3
FORT WORTH | 0902-00-312 | TARRANT | Various | 2023-11-16 | 4103210 | -4005.51 | 0 | 3425398.75 | -677811.25 | 365 | 365 | 0 | 0 | 0
PARIS | 0009-06-054 | HUNT | SH 66 | 2023-11-17 | 1642031.5 | 9134.3 | 0 | 1610341.43 | -31690.07 | 115 | 102 | 0 | 0 | -13
PARIS | 0135-06-039 | HUNT | US 380 | 2023-11-17 | 548338.8 | 7244.52 | 0 | 554701.33 | 6362.53 | 94 | 45 | 0 | 0 | -49
PARIS | 0510-04-013 | FANNIN | FM 898 | 2023-11-17 | 12209809.54 | -293901.34 | 0 | 12045610.92 | -164198.62 | 533 | 546 | 13 | 0 | 13
PHARR | 0039-02-063 | HIDALGO | CS | 2023-11-17 | 95994022.83 | 2393316.49 | 0 | 99972949.81 | 3978926.98 | 851 | 799 | 0 | 0 | -52
WACO | 0014-17-078 | HILL | FM 1242 | 2023-11-17 | 4783740.08 | 27081.56 | 0 | 4994930.68 | 211190.6 | 45 | 87 | 0 | 0 | 42
AUSTIN | 0115-04-055 | BASTROP | FM 20 | 2023-11-20 | 2547556.2 | 143767.93 | 0 | 2779331.86 | 231775.66 | 153 | 145 | 0 | 0 | -8
AUSTIN | 0807-01-032 | BASTROP | FM 535 | 2023-11-20 | 1577805.18 | 35572.83 | 0 | 1574162.56 | -3642.62 | 37 | 32 | 0 | 0 | -5
BROWNWOOD | 0923-00-069 | BROWN | Various | 2023-11-20 | 1992104.15 | -26644.09 | 0 | 1954077.07 | -38027.08 | 85 | 54 | 0 | 0 | -31
WACO | 0808-02-012 | FALLS | FM 413 | 2023-11-20 | 995631.79 | 140622.71 | 0 | 1140640.07 | 145008.28 | 75 | 84 | 30 | 0 | 9
WACO | 1054-01-009 | BOSQUE | FM 219 | 2023-11-20 | 5391495.03 | -301672.9 | 0 | 4818391.16 | -573103.87 | 120 | 130 | 0 | 0 | 10
WACO | 3521-01-022 | MCLENNAN | FM 2837 | 2023-11-20 | 290913.25 | -7538.08 | 0 | 279516.49 | -11396.76 | 45 | 41 | 0 | 0 | -4
ABILENE | 0033-04-072 | JONES | US 83 | 2023-11-21 | 5224759.64 | 56.75 | 0 | 5528548.9 | 303789.26 | 114 | 104 | 0 | 0 | -10
AUSTIN | 0286-01-057 | HAYS | SH 80 | 2023-11-22 | 7150482.88 | 50010.13 | 0 | 7461140.1 | 310657.22 | 210 | 187 | 0 | 0 | -23
CHILDRESS | 1235-01-012 | WHEELER | FM 1046 | 2023-11-22 | 6062196.88 | 282781.36 | 0 | 6396366.83 | 334169.95 | 170 | 210 | 30 | 0 | 40
DALLAS | 0197-03-054 | KAUFMAN | US 175 | 2023-11-27 | 12972960.9 | 1147989.66 | 0 | 13756419.48 | 783458.58 | 531 | 475 | 0 | 0 | -56
TYLER | 0910-00-121 | SMITH | Various | 2023-11-27 | 1937247.25 | 135346.05 | 0 | 2254109.06 | 316861.81 | 75 | 81 | 0 | 0 | 6
TYLER | 0910-07-089 | GREGG | Various | 2023-11-27 | 198617 | 0 | 0 | 199019 | 402 | 51 | 40 | 0 | 0 | -11
DALLAS | 0918-00-327 | DALLAS | VA | 2023-11-29 | 410372.07 | 0 | 0 | 428959.97 | 18587.9 | 95 | 88 | 0 | 0 | -7
WACO | 0055-06-036 | CORYELL | US 84 | 2023-11-29 | 341320 | 0 | 0 | 338541.33 | -2778.67 | 45 | 43 | 0 | 0 | -2
ABILENE | 0982-07-013 | HASKELL | FM 1720 | 2023-11-30 | 9371183.62 | 133199.66 | 0 | 8989553.48 | -381630.14 | 588 | 593 | 18 | 0 | 5
EL PASO | 0924-06-649 | EL PASO | VA | 2023-11-30 | 485120 | 51698.15 | 0 | 529583.15 | 44463.15 | 105 | 117 | 8 | 0 | 12
PARIS | 0045-11-044 | LAMAR | US 82 | 2023-11-30 | 1751101 | 16799.69 | 0 | 1792897.89 | 41796.89 | 79 | 74 | 0 | 0 | -5
SAN ANTONIO | 0100-03-086 | WILSON | US 181 | 2023-11-30 | 4783311.04 | 0 | 0 | 4435985.12 | -347325.92 | 192 | 87 | 0 | 0 | -105
AMARILLO | 0030-01-035 | OCHILTREE | US 83 | 2023-12-01 | 5571551.15 | 531729.15 | 0 | 6528088.3 | 956537.15 | 83 | 76 | 5 | 0 | -7
AUSTIN | 2211-01-026 | WILLIAMSON | RM 2338 | 2023-12-01 | 7570067.83 | 440441.82 | 0 | 8134925.6 | 564857.77 | 171 | 227 | 15 | 0 | 56
CHILDRESS | 0133-03-047 | KNOX | US 82 | 2023-12-01 | 2268300 | 97807.38 | 0 | 2366107.4 | 97807.4 | 240 | 381 | 146 | 0 | 141
DALLAS | 0581-02-151 | DALLAS | SL 12 | 2023-12-01 | 4659680.71 | 714945.57 | 0 | 4818244.23 | 158563.52 | 106 | 113 | 10 | 0 | 7
EL PASO | 0001-03-058 | EL PASO | SH 20 | 2023-12-01 | 3024946.56 | 132459.26 | 0 | 3469570.84 | 444624.28 | 280 | 275 | 25 | 0 | -5
EL PASO | 0002-06-059 | HUDSPETH | IH 10 | 2023-12-01 | 3140241 | 107501 | 6854.6 | 3191289 | 44193.4 | 220 | 204 | 0 | 0 | -16
EL PASO | 2121-04-124 | EL PASO | IH 10 | 2023-12-01 | 1536929.63 | 0 | 0 | 1577953.5 | 41023.87 | 36 | 23 | 0 | 0 | -13
ODESSA | 1183-01-014 | REEVES | FM 2119 | 2023-12-04 | 62350992.24 | 2100732.43 | 0 | 60322906.84 | -2028085.4 | 664 | 650 | 0 | 0 | -14
WACO | 2311-01-044 | MCLENNAN | FM 3051 | 2023-12-04 | 1210047.16 | 21061.42 | 0 | 1193084.6 | -16962.56 | 30 | 29 | 0 | 0 | -1
WICHITA FALLS | 1837-01-014 | ARCHER | FM 1954 | 2023-12-04 | 5282463.13 | 50470.46 | 0 | 5280441.79 | -2021.34 | 187 | 265 | 0 | 0 | 78
HOUSTON | 0110-03-085 | MONTGOMERY | SH 75 | 2023-12-05 | 3455793.59 | 8550.67 | 0 | 3821728.29 | 365934.7 | 53 | 58 | 5 | 0 | 5
LUFKIN | 0911-00-113 | ANGELINA | Various | 2023-12-05 | 439626 | 380087.33 | 0 | 868110.83 | 428484.83 | 106 | 122 | 46 | 0 | 16
PHARR | 0038-04-069 | ZAPATA | US 83 | 2023-12-07 | 549124.05 | 24707.95 | 0 | 567388.29 | 18264.24 | 100 | 94 | 0 | 0 | -6
ABILENE | 0034-02-050 | TAYLOR | US 83 | 2023-12-11 | 1760153.98 | -896 | 0 | 1841744.02 | 81590.04 | 56 | 29 | 0 | 0 | -27
BEAUMONT | 0932-01-090 | JEFFERSON | FM 365 | 2023-12-11 | 14655685.45 | 2116882.98 | 0 | 17086458.45 | 2430773 | 472 | 609 | 168 | 0 | 137
CORPUS CHRISTI | 0372-03-010 | SAN PATRICIO | BU 77T | 2023-12-11 | 777278.6 | 52970 | 0 | 817522.17 | 40243.57 | 58 | 63 | 12 | 0 | 5
CORPUS CHRISTI | 0447-05-075 | REFUGIO | FM 774 | 2023-12-11 | 2846446.81 | 0 | 0 | 2747123.47 | -99323.34 | 131 | 328 | 16 | 0 | 197
LAREDO | 0922-33-194 | WEBB | CR | 2023-12-11 | 1492184 | -21026.85 | 0 | 1471525.03 | -20658.97 | 78 | 68 | 0 | 0 | -10
FORT WORTH | 0902-90-057 | TARRANT | CS | 2023-12-12 | 1420252 | 18634.55 | 111856.09 | 1429370.31 | -102737.78 | 128 | 141 | 27 | 0 | 13
AUSTIN | 0016-01-133 | TRAVIS | SL 275 | 2023-12-13 | 1318917.45 | 104322.34 | 0 | 1552155.69 | 233238.24 | 118 | 107 | 0 | 0 | -11
AUSTIN | 0152-01-080 | TRAVIS | US 183 | 2023-12-13 | 2851509.1 | 3310.72 | 0 | 3353362.08 | 501852.98 | 180 | 210 | 21 | 0 | 30
AUSTIN | 0265-04-062 | BASTROP | SH 21 | 2023-12-13 | 50359853.46 | 1277736.87 | 0 | 53370091.19 | 3010237.73 | 785 | 913 | 128 | 0 | 128
BEAUMONT | 0920-13-036 | TYLER | CR | 2023-12-13 | 659766 | -45210 | 0 | 629815 | -29951 | 66 | 50 | 0 | 0 | -16
DALLAS | 0918-47-250 | DALLAS | CS | 2023-12-13 | 1403403.9 | 0 | 0 | 1347340.84 | -56063.06 | 300 | 269 | 0 | 0 | -31
HOUSTON | 0051-02-101 | HARRIS | SH 3 | 2023-12-13 | 13951959.6 | 18102.37 | 0 | 14445858.62 | 493899.02 | 600 | 626 | 22 | 0 | 26
WACO | 0209-01-073 | MCLENNAN | SL 2 | 2023-12-13 | 2132685.6 | 716752 | 0 | 2880742.24 | 748056.64 | 120 | 138 | 12 | 0 | 18
WACO | 0231-02-062 | CORYELL | BU 190E | 2023-12-13 | 4762516.85 | -275566.01 | 0 | 4213413.81 | -549103.04 | 300 | 410 | 44 | 0 | 110
WACO | 0258-08-037 | MCLENNAN | SH 6 | 2023-12-13 | 770035.18 | 11145.27 | 0 | 784545.97 | 14510.79 | 60 | 83 | 2 | 0 | 23
WICHITA FALLS | 0903-15-084 | COOKE | CR | 2023-12-13 | 2136179.06 | 0 | 0 | 2092198.84 | -43980.22 | 246 | 385 | 0 | 0 | 139
DALLAS | 1567-01-042 | DENTON | FM 720 | 2023-12-14 | 2648123.85 | 102361.46 | 0 | 2808996.51 | 160872.66 | 119 | 110 | 0 | 0 | -9
CORPUS CHRISTI | 0359-02-005 | GOLIAD | SH 119 | 2023-12-15 | 9793592.86 | 110496.26 | 0 | 10064229.33 | 270636.47 | 298 | 320 | 22 | 0 | 22
DALLAS | 0048-03-050 | ELLIS | US 77 | 2023-12-15 | 21683270.74 | 1961482.43 | 91256.61 | 22184888.59 | 410361.24 | 603 | 848 | 0 | 0 | 245
DALLAS | 0172-05-125 | ELLIS | US 287 | 2023-12-15 | 2840168.14 | 50647.68 | 0 | 2786604.36 | -53563.78 | 375 | 250 | 0 | 0 | -125
EL PASO | 2552-03-059 | EL PASO | SL 375 | 2023-12-15 | 1991402.25 | -2060.85 | 0 | 2009709.17 | 18306.92 | 32 | 35 | 5 | 0 | 3
LAREDO | 0018-06-211 | WEBB | IH 35 | 2023-12-15 | 402429.75 | 9879.98 | 0 | 402062.67 | -367.08 | 83 | 94 | 13 | 0 | 11
DALLAS | 0280-03-004 | COLLIN | BS 78-D | 2023-12-18 | 9596783.18 | 339762.57 | 0 | 9413913.73 | -182869.45 | 504 | 497 | 0 | 0 | -7
SAN ANTONIO | 0301-03-027 | FRIO | SH 85 | 2023-12-18 | 18027137.64 | -2210070.57 | 0 | 15894124.77 | -2133012.87 | 421 | 418 | -1 | 0 | -3
YOAKUM | 1090-05-018 | CALHOUN | FM 1593 | 2023-12-18 | 4811547.64 | -105208 | 0 | 4605789.9 | -205757.74 | 105 | 75 | 0 | 0 | -30
HOUSTON | 0050-09-095 | HARRIS | US 290 | 2023-12-20 | 1648298.34 | 1076842.47 | 0 | 2738107.27 | 1089808.93 | 135 | 135 | 0 | 0 | 0
LAREDO | 0018-04-063 | WEBB | IH 35 | 2023-12-20 | 11076278.32 | 416188.3 | 0 | 12085548.14 | 1009269.82 | 268 | 223 | 0 | 0 | -45
LUBBOCK | 0052-02-038 | BAILEY | US 70 | 2023-12-20 | 1422921.54 | 0 | 0 | 1374858.81 | -48062.73 | 12 | 12 | 0 | 0 | 0
LUBBOCK | 0052-05-047 | LAMB | US 84 | 2023-12-20 | 2196605.1 | 0 | 0 | 2216757.6 | 20152.5 | 167 | 128 | 0 | 0 | -39
LUBBOCK | 0783-01-107 | LUBBOCK | SL 289 | 2023-12-20 | 2477822 | -82575 | 0 | 2324816.43 | -153005.57 | 124 | 39 | 0 | 0 | -85
LUFKIN | 0809-04-057 | SAN AUGUSTINE | US 96 | 2023-12-20 | 3768563.09 | 310181.99 | 0 | 4105390.72 | 336827.63 | 102 | 171 | 66 | 0 | 69
PHARR | 0329-01-023 | JIM HOGG | FM 649 | 2023-12-20 | 3295335.75 | 0 | 0 | 3362174.21 | 66838.46 | 68 | 43 | 0 | 0 | -25
WACO | 0909-22-195 | MCLENNAN | Various | 2023-12-20 | 258695 | 6184.89 | 0 | 280470.7 | 21775.7 | 15 | 16 | 1 | 0 | 1
DALLAS | 0995-01-026 | NAVARRO | FM 637 | 2023-12-21 | 2712401.6 | 4850.3 | 0 | 2517853.28 | -194548.32 | 331 | 322 | 0 | 0 | -9
EL PASO | 0167-01-113 | EL PASO | US 54 | 2023-12-21 | 91166598.4 | 13306139.8 | 46745.62 | 111420129.92 | 20206785.9 | 722 | 1044 | 322 | 0 | 322
SAN ANTONIO | 0017-03-066 | BEXAR | IH 35 | 2023-12-21 | 319940 | 0 | 0 | 319710 | -230 | 62 | 36 | 0 | 0 | -26
WICHITA FALLS | 0249-03-055 | ARCHER | US 281 | 2023-12-21 | 10600584.04 | 0 | 0 | 10906347.55 | 305763.51 | 60 | 59 | 0 | 0 | -1
AUSTIN | 1535-01-015 | TRAVIS | FM 1625 | 2023-12-22 | 755872 | 451937.34 | 0 | 1216488.02 | 460616.02 | 16 | 16 | 16 | 0 | 0
BEAUMONT | 0368-04-033 | JEFFERSON | SH 124 | 2023-12-22 | 2659519.15 | 65196.78 | 0 | 2807982.45 | 148463.3 | 134 | 131 | 10 | 0 | -3
DALLAS | 0197-03-076 | KAUFMAN | US 175 | 2023-12-22 | 1587185.65 | -10611.46 | 0 | 1637031.54 | 49845.89 | 160 | 206 | 3 | 0 | 46
PHARR | 0921-02-445 | HIDALGO | CR | 2023-12-22 | 1554168.79 | 2246.16 | 0 | 1523851.02 | -30317.77 | 248 | 126 | 0 | 0 | -122
SAN ANGELO | 0035-03-054 | CONCHO | US 83 | 2023-12-22 | 16983573.32 | -87425.88 | 0 | 17244988.6 | 261415.28 | 72 | 68 | 0 | 0 | -4
WACO | 0015-01-252 | MCLENNAN | IH 35 | 2023-12-22 | 1969296.39 | -286187.9 | 0 | 1605401.14 | -363895.25 | 60 | 51 | 0 | 0 | -9
BEAUMONT | 0920-13-037 | TYLER | CR | 2023-12-27 | 746699.95 | 67750.01 | 0 | 835048.51 | 88348.56 | 60 | 109 | 4 | 0 | 49
BRYAN | 0315-05-026 | BRAZOS | SH 105 | 2023-12-27 | 23601410.92 | 10148535.65 | 0 | 33820093.8 | 10218682.88 | 443 | 893 | 458 | 0 | 450
HOUSTON | 0720-03-137 | HARRIS | SH 249 | 2023-12-27 | 2179891.9 | 312575.56 | 0 | 2629269.21 | 449377.31 | 284 | 275 | 0 | 0 | -9
WACO | 0093-05-053 | LIMESTONE | SH 14 | 2023-12-27 | 202509.15 | 0 | 0 | 199009.15 | -3500 | 30 | 39 | 0 | 0 | 9
AMARILLO | 0238-02-038 | HARTLEY | US 54 | 2023-12-28 | 35223786.9 | 1660204.64 | 0 | 39864465.5 | 4640678.6 | 465 | 640 | 36 | 0 | 175
AUSTIN | 0337-03-019 | WILLIAMSON | FM 1331 | 2023-12-28 | 173551.29 | 29625.22 | 0 | 203494.39 | 29943.1 | 43 | 24 | 0 | 0 | -19
BRYAN | 0456-01-047 | FREESTONE | FM 27 | 2023-12-28 | 14892846.02 | 81036.34 | 0 | 15250519.84 | 357673.82 | 330 | 456 | 72 | 0 | 126
TYLER | 0138-02-038 | RUSK | SH 42 | 2023-12-28 | 1527949.3 | 0 | 0 | 1599584.21 | 71634.91 | 24 | 22 | 0 | 0 | -2
TYLER | 0910-16-165 | SMITH | CS | 2023-12-28 | 233589 | 0 | 0 | 223177.95 | -10411.05 | 34 | 29 | 0 | 0 | -5
WACO | 0909-28-035 | BOSQUE | CR | 2023-12-28 | 799353.2 | 0 | 0 | 816263.4 | 16910.2 | 90 | 90 | 0 | 0 | 0
BROWNWOOD | 0923-06-086 | BROWN | CR | 2023-12-29 | 1592990.5 | -60 | 0 | 1595930.31 | 2939.81 | 148 | 139 | 0 | 0 | -9
DALLAS | 0095-03-107 | KAUFMAN | US 80 | 2023-12-29 | 21784893.28 | 593746.44 | 0 | 21326722.5 | -458170.78 | 248 | 245 | 0 | 0 | -3
DALLAS | 0918-46-330 | DENTON | Various | 2023-12-29 | 1094339 | 36303.21 | 0 | 1163304.44 | 68965.44 | 182 | 180 | 0 | 0 | -2
EL PASO | 0001-01-063 | EL PASO | SH 20 | 2023-12-29 | 2433661.19 | 182409.29 | 0 | 2512609.6 | 78948.41 | 193 | 215 | 22 | 0 | 22
SAN ANTONIO | 0915-00-200 | BEXAR | VA | 2023-12-29 | 477879.25 | 10631.25 | 0 | 508876.73 | 30997.48 | 144 | 181 | 30 | 0 | 37
ATLANTA | 0218-03-087 | CASS | US 59 | 2024-01-02 | 7622162.45 | 45143.28 | 0 | 7201695.02 | -420467.43 | 89 | 82 | 2 | 0 | -7
ATLANTA | 0218-04-119 | CASS | US 59 | 2024-01-02 | 11842462.04 | 0 | 0 | 10999681.75 | -842780.29 | 136 | 103 | 0 | 0 | -33
BRYAN | 1145-01-044 | LEON | FM 1511 | 2024-01-02 | 2035077.89 | -48180.33 | 0 | 1930988.99 | -104088.9 | 320 | 374 | 0 | 0 | 54
ODESSA | 0887-01-039 | MIDLAND | FM 307 | 2024-01-02 | 4744172.07 | 420977.71 | 0 | 5612068.89 | 867896.82 | 241 | 385 | 125 | 0 | 144
LUBBOCK | 0052-03-030 | BAILEY | US 84 | 2024-01-03 | 19522385.4 | 42574.4 | 0 | 19120011.69 | -402373.71 | 61 | 61 | 0 | 0 | 0
LUFKIN | 0911-00-106 | ANGELINA | VA | 2024-01-03 | 4121118.8 | 42225 | 0 | 3770544.13 | -350574.67 | 203 | 329 | 48 | 0 | 126
YOAKUM | 0515-01-071 | JACKSON | FM 616 | 2024-01-03 | 3684181.71 | 0 | 0 | 3655428.04 | -28753.67 | 180 | 102 | 0 | 0 | -78
AUSTIN | 0265-05-089 | BASTROP | SH 71 | 2024-01-04 | 1108815.55 | 0 | 0 | 1005384.26 | -103431.29 | 57 | 31 | 0 | 0 | -26
AUSTIN | 0573-01-041 | BASTROP | SH 304 | 2024-01-05 | 2515580.84 | 20675.52 | 0 | 2613826.25 | 98245.41 | 61 | 61 | 6 | 0 | 0
PHARR | 0684-03-022 | CAMERON | FM 1732 | 2024-01-05 | 6603453.6 | 221692.69 | 0 | 6888444.79 | 284991.19 | 350 | 342 | 0 | 0 | -8
SAN ANTONIO | 0915-00-234 | BEXAR | VA | 2024-01-05 | 1384853.99 | 85264.97 | 0 | 1406273.04 | 21419.05 | 152 | 139 | 0 | 0 | -13
ATLANTA | 0919-00-084 | CASS | Various | 2024-01-08 | 1889109.54 | 0 | 0 | 1933438.55 | 44329.01 | 66 | 98 | 0 | 0 | 32
LAREDO | 0022-06-052 | VAL VERDE | US 90 | 2024-01-09 | 6003079.86 | 77842.3 | 0 | 6444400.33 | 441320.47 | 110 | 104 | 0 | 0 | -6
SAN ANTONIO | 0024-04-068 | MEDINA | US 90 | 2024-01-09 | 3156212.6 | -67992.1 | 0 | 3044679.29 | -111533.31 | 68 | 67 | 0 | 0 | -1
ATLANTA | 0218-04-126 | CASS | US 59 | 2024-01-10 | 2198711.21 | -106028.79 | 0 | 2397049.12 | 198337.91 | 70 | 105 | 38 | 0 | 35
BEAUMONT | 0593-01-130 | LIBERTY | SH 105 | 2024-01-10 | 856006.94 | 48034.23 | 0 | 992763.85 | 136756.91 | 61 | 68 | 7 | 0 | 7
AUSTIN | 0286-01-061 | HAYS | SH 21 | 2024-01-11 | 1208195.86 | 274583.17 | 0 | 1555034.88 | 346839.02 | 40 | 32 | 0 | 0 | -8
AUSTIN | 0337-01-043 | WILLIAMSON | SH 29 | 2024-01-11 | 5548287.93 | 1333964.46 | 0 | 6591287.34 | 1042999.41 | 419 | 427 | 8 | 0 | 8
AUSTIN | 0471-02-079 | HAYS | SH 21 | 2024-01-11 | 2808195.5 | -196946.56 | 0 | 2966053.66 | 157858.16 | 64 | 29 | 0 | 0 | -35
LUBBOCK | 0067-02-074 | SWISHER | IH 27 | 2024-01-11 | 16314227.44 | -185660 | 0 | 17434138.07 | 1119910.63 | 63 | 70 | 14 | 0 | 7
DALLAS | 0817-01-024 | DENTON | FM 428 | 2024-01-12 | 8828849.78 | 746791.1 | 0 | 8450115.15 | -378734.63 | 440 | 472 | 33 | 0 | 32
LUBBOCK | 0905-00-117 | LUBBOCK | Various | 2024-01-12 | 881211.8 | 0 | 0 | 937701.8 | 56490 | 90 | 46 | 0 | 0 | -44
AUSTIN | 0113-07-071 | HAYS | US 290 | 2024-01-16 | 714499.94 | -1085.29 | 0 | 708724.74 | -5775.2 | 31 | 10 | 0 | 0 | -21
AUSTIN | 0366-01-082 | HAYS | SL 82 | 2024-01-16 | 406670.13 | -137423 | 0 | 252115.11 | -154555.02 | 14 | 11 | 0 | 0 | -3
AUSTIN | 0285-03-062 | HAYS | RM 12 | 2024-01-17 | 5093342.85 | 111416.2 | 0 | 4917384.39 | -175958.46 | 175 | 158 | 0 | 0 | -17
EL PASO | 2552-02-035 | EL PASO | SL 375 | 2024-01-18 | 3808795.44 | 20840.16 | 0 | 3726782.45 | -82012.99 | 156 | 192 | 45 | 0 | 36
SAN ANTONIO | 0915-00-210 | BEXAR | VA | 2024-01-18 | 2758844.47 | 137347.47 | 0 | 2812057.87 | 53213.4 | 322 | 698 | 203 | 0 | 376
BROWNWOOD | 0079-01-038 | BROWN | US 67 | 2024-01-19 | 3046555.05 | 98117.64 | 0 | 3792895.24 | 746340.19 | 131 | 216 | 82 | 0 | 85
BROWNWOOD | 1780-01-009 | MILLS | FM 1047 | 2024-01-19 | 1685450.98 | -2071.24 | 0 | 1740617.96 | 55166.98 | 134 | 134 | 0 | 0 | 0
WACO | 0185-05-003 | BELL | US 190 | 2024-01-19 | 4600000 | 214542.34 | 0 | 5112035.94 | 512035.94 | 60 | 57 | 0 | 0 | -3
WICHITA FALLS | 0822-01-021 | COOKE | FM 371 | 2024-01-22 | 7175268.12 | 29881.84 | 0 | 7312761.67 | 137493.55 | 260 | 252 | 0 | 0 | -8
AUSTIN | 0914-05-174 | WILLIAMSON | CR | 2024-01-23 | 769807.3 | -29849.28 | 0 | 738845.28 | -30962.02 | 85 | 75 | 0 | 0 | -10
CORPUS CHRISTI | 0916-00-233 | NUECES | VA | 2024-01-23 | 8086089.5 | 512722.16 | 0 | 8047825.08 | -38264.42 | 168 | 264 | 96 | 0 | 96
FORT WORTH | 0362-07-009 | PALO PINTO | FM 2951 | 2024-01-23 | 4867458.16 | 409026.62 | 0 | 5239077.03 | 371618.87 | 256 | 455 | 139 | 0 | 199
HOUSTON | 0271-17-178 | HARRIS | IH 610 | 2024-01-23 | 1794234.32 | -161718.5 | 0 | 1230353.79 | -563880.53 | 90 | 87 | 0 | 0 | -3
BROWNWOOD | 0011-09-075 | STEPHENS | US 180 | 2024-01-24 | 14954532.77 | 145887.11 | 0 | 14175054.68 | -779478.09 | 105 | 119 | 16 | 0 | 14
CORPUS CHRISTI | 0088-01-069 | BEE | US 59 | 2024-01-24 | 15920070.97 | 536951.88 | 0 | 16418463.54 | 498392.57 | 204 | 358 | 42 | 0 | 154
CORPUS CHRISTI | 0100-05-184 | KARNES | US 181 | 2024-01-24 | 6543322.7 | 592247.26 | 243000 | 7139803.73 | 353481.03 | 210 | 569 | 359 | 0 | 359
EL PASO | 0358-05-018 | BREWSTER | SH 118 | 2024-01-24 | 5327450.03 | 498911.76 | 0 | 6010586.85 | 683136.82 | 40 | 69 | 11 | 0 | 29
EL PASO | 0415-03-022 | JEFF DAVIS | SH 166 | 2024-01-24 | 9596240.05 | 757712.4 | 0 | 10278115.35 | 681875.3 | 60 | 78 | 20 | 0 | 18
EL PASO | 1046-01-030 | EL PASO | FM 659 | 2024-01-24 | 12904066.05 | 253763.17 | -185023.4 | 13322805.55 | 603762.9 | 377 | 684 | 169 | 0 | 307
LAREDO | 0161-03-024 | VAL VERDE | SS 239 | 2024-01-24 | 1703783.37 | 291357.17 | 0 | 1935196.32 | 231412.95 | 160 | 177 | 18 | 0 | 17
FORT WORTH | 0172-06-094 | TARRANT | SS 280 | 2024-01-25 | 2609024.16 | 682942.04 | 0 | 3468390.68 | 859366.52 | 235 | 343 | 124 | 0 | 108
LAREDO | 0300-01-105 | MAVERICK | US 277 | 2024-01-25 | 5512871.65 | -108567.48 | 0 | 5485457.03 | -27414.62 | 274 | 274 | 0 | 0 | 0
SAN ANTONIO | 0521-04-294 | BEXAR | IH 410 | 2024-01-25 | 315680 | 0 | 0 | 321310.91 | 5630.91 | 32 | 7 | 0 | 0 | -25
EL PASO | 0924-06-643 | EL PASO | CS | 2024-01-26 | 494880 | 0 | 0 | 490010 | -4870 | 80 | 26 | 0 | 0 | -54
HOUSTON | 0089-09-067 | FORT BEND | US 59 | 2024-01-26 | 37743798.55 | 368715.81 | 0 | 38141042.32 | 397243.77 | 1208 | 1445 | 240 | 0 | 237
HOUSTON | 1685-05-116 | HARRIS | SH 6 | 2024-01-26 | 8982210.95 | -359626.29 | 0 | 8281906.98 | -700303.97 | 224 | 204 | 0 | 0 | -20
ATLANTA | 3403-01-001 | CAMP | SL 255 | 2024-01-29 | 5634658.36 | 1485137.02 | 0 | 7358605.68 | 1723947.32 | 334 | 404 | 96 | 0 | 70
AUSTIN | 0151-03-042 | WILLIAMSON | SH 29 | 2024-01-30 | 3739221.06 | 0 | 0 | 3575759.01 | -163462.05 | 64 | 34 | 0 | 0 | -30
WACO | 0014-24-065 | HILL | IH 35 | 2024-01-30 | 6648201.5 | 146840.04 | 0 | 6819582.81 | 171381.31 | 128 | 74 | 0 | 0 | -54
LUFKIN | 0109-08-050 | TRINITY | SH 19 | 2024-01-31 | 599425.61 | 22628 | 0 | 635216.54 | 35790.93 | 73 | 45 | 0 | 0 | -28
BRYAN | 0955-01-027 | BURLESON | FM 166 | 2024-02-01 | 1378418 | 198091.34 | 0 | 1683762.09 | 305344.09 | 117 | 143 | 26 | 0 | 26
DALLAS | 0815-03-015 | DENTON | FM 424 | 2024-02-01 | 2064269.71 | 1525.8 | 0 | 2128898.68 | 64628.97 | 116 | 57 | 0 | 0 | -59
ODESSA | 0556-04-012 | PECOS | SH 349 | 2024-02-01 | 8865264.42 | 7220 | 0 | 9001870.74 | 136606.32 | 54 | 47 | 0 | 0 | -7
BEAUMONT | 0028-07-058 | JEFFERSON | US 90 | 2024-02-02 | 753374.01 | 26169.72 | 0 | 882765.41 | 129391.4 | 102 | 111 | 15 | 0 | 9
BROWNWOOD | 2570-01-011 | BROWN | FM 2632 | 2024-02-02 | 3196924.07 | 6991.94 | 0 | 3049508.02 | -147416.05 | 150 | 178 | 0 | 0 | 28
YOAKUM | 0446-04-014 | COLORADO | FM 1093 | 2024-02-02 | 5576114.35 | 0 | 0 | 5518436.48 | -57677.87 | 255 | 238 | 0 | 0 | -17
WACO | 1926-01-018 | CORYELL | FM 1829 | 2024-02-05 | 5068817.28 | 0 | 0 | 4713928.62 | -354888.66 | 60 | 26 | 0 | 0 | -34
TYLER | 0910-00-115 | SMITH | VA | 2024-02-06 | 2493889.72 | 405085.5 | 0 | 2714562.4 | 220672.68 | 66 | 123 | 24 | 0 | 57
AMARILLO | 0379-01-046 | HUTCHINSON | SH 136 | 2024-02-07 | 9504385.15 | -437441.6 | 0 | 9209653.74 | -294731.41 | 154 | 179 | 32 | 0 | 25
HOUSTON | 0508-01-354 | HARRIS | IH 10 | 2024-02-07 | 5653887.52 | 450971.04 | 0 | 6915461.22 | 1261573.7 | 254 | 252 | 0 | 0 | -2
AUSTIN | 0914-00-474 | TRAVIS | Various | 2024-02-08 | 124791.94 | 0 | 0 | 159779.68 | 34987.74 | 38 | 23 | 0 | 0 | -15
BROWNWOOD | 0007-03-109 | EASTLAND | IH 20 | 2024-02-08 | 8087544 | -294.5 | 0 | 8035110.03 | -52433.97 | 68 | 74 | 6 | 0 | 6
TYLER | 2274-01-011 | WOOD | FM 1804 | 2024-02-08 | 634567.65 | 0 | 0 | 587878.48 | -46689.17 | 57 | 59 | 0 | 0 | 2
WICHITA FALLS | 0156-05-064 | ARCHER | BU 82F | 2024-02-08 | 1786206.5 | 0 | 0 | 1866435.55 | 80229.05 | 85 | 77 | 0 | 0 | -8
YOAKUM | 2350-01-069 | VICTORIA | SL 463 | 2024-02-08 | 642089.92 | 0 | 0 | 661991.34 | 19901.42 | 55 | 60 | 0 | 0 | 5
ABILENE | 2034-01-013 | SCURRY | FM 1298 | 2024-02-09 | 1393947.05 | 17490 | 0 | 1402628.4 | 8681.35 | 80 | 80 | 0 | 0 | 0
AUSTIN | 2690-01-036 | WILLIAMSON | FM 971 | 2024-02-09 | 8428384.67 | 1133078.02 | 0 | 9807894.1 | 1379509.43 | 410 | 312 | 0 | 0 | -98
AUSTIN | 0805-04-035 | HAYS | RM 150 | 2024-02-12 | 482719.59 | 158003.75 | 0 | 594171.57 | 111451.98 | 17 | 14 | 0 | 0 | -3
WICHITA FALLS | 0903-06-026 | CLAY | CR | 2024-02-12 | 815142.41 | 0 | 0 | 825879.08 | 10736.67 | 153 | 54 | 0 | 0 | -99
AUSTIN | 1566-02-023 | WILLIAMSON | FM 1660 | 2024-02-13 | 1092800.16 | 0 | 0 | 1132903.03 | 40102.87 | 56 | 53 | 0 | 0 | -3
BROWNWOOD | 0182-01-017 | EASTLAND | SH 36 | 2024-02-13 | 2098184.02 | 325614.74 | 0 | 3249082.4 | 1150898.38 | 176 | 165 | 33 | 0 | -11
BROWNWOOD | 0183-01-053 | COMANCHE | SH 36 | 2024-02-13 | 1557595.5 | 98094.63 | 0 | 1585276.41 | 27680.91 | 114 | 125 | 16 | 0 | 11
HOUSTON | 0502-01-222 | HARRIS | SH 225 | 2024-02-13 | 1710939.65 | 709092.94 | 0 | 2668148.97 | 957209.32 | 165 | 337 | 138 | 0 | 172
LUBBOCK | 0053-06-031 | GARZA | US 84 | 2024-02-13 | 1791545.6 | 96595 | 0 | 1930713.78 | 139168.18 | 175 | 140 | 0 | 0 | -35
ABILENE | 0068-08-063 | HOWARD | BU 87M | 2024-02-15 | 6169362.05 | 0 | 0 | 6431626.13 | 262264.08 | 72 | 56 | 0 | 0 | -16
BEAUMONT | 0028-09-123 | ORANGE | IH 10 | 2024-02-16 | 15248084.1 | -251903 | 0 | 14298872.52 | -949211.58 | 75 | 58 | 0 | 0 | -17
CHILDRESS | 0133-03-038 | KNOX | US 82 | 2024-02-16 | 12684227.53 | 71777.2 | 0 | 13176888.4 | 492660.87 | 320 | 523 | 46 | 0 | 203
HOUSTON | 0114-11-079 | WALLER | US 290 | 2024-02-16 | 1227770 | 39247.11 | 0 | 1337297.86 | 109527.86 | 51 | 47 | 0 | 0 | -4
PHARR | 0039-12-252 | CAMERON | BU 77-X | 2024-02-16 | 3330767.38 | 58858.5 | 0 | 3421708.81 | 90941.43 | 263 | 345 | 82 | 0 | 82
WACO | 0258-08-038 | MCLENNAN | SH 6 | 2024-02-16 | 723086 | 51574.4 | 0 | 695966.75 | -27119.25 | 60 | 55 | 0 | 0 | -5
AUSTIN | 0015-13-396 | TRAVIS | IH 35 | 2024-02-19 | 24590929.4 | 4410874.61 | 0 | 29737811.19 | 5146881.79 | 376 | 561 | 187 | 0 | 185
ATLANTA | 0248-01-081 | TITUS | US 271 | 2024-02-20 | 5186944.38 | 467827.93 | 0 | 5465745.77 | 278801.39 | 72 | 101 | 15 | 0 | 29
AUSTIN | 1234-02-013 | BASTROP | FM 1100 | 2024-02-20 | 468554.78 | 68389.73 | 0 | 557639.93 | 89085.15 | 27 | 8 | 0 | 0 | -19
LUFKIN | 0911-38-075 | ANGELINA | Various | 2024-02-20 | 200685 | 0 | 0 | 200669 | -16 | 24 | 7 | 0 | 0 | -17
PARIS | 0901-19-205 | GRAYSON | CS | 2024-02-20 | 3051415.5 | 166165.93 | 0 | 3278519.17 | 227103.67 | 160 | 156 | 10 | 0 | -4
WACO | 0513-01-017 | CORYELL | SH 236 | 2024-02-20 | 5087623.2 | 103206.04 | 0 | 5208581.05 | 120957.85 | 165 | 170 | 15 | 0 | 5
DALLAS | 2461-01-010 | COLLIN | FM 2170 | 2024-02-21 | 3061581.78 | 10515.64 | 0 | 2766840.55 | -294741.23 | 132 | 109 | 0 | 0 | -23
DALLAS | 2982-01-007 | KAUFMAN | FM 1390 | 2024-02-22 | 7598568.1 | 567242.45 | 0 | 7949452.41 | 350884.31 | 253 | 376 | 73 | 0 | 123
WACO | 0909-39-134 | CORYELL | CR | 2024-02-22 | 673333 | 4031.14 | 0 | 671713.88 | -1619.12 | 75 | 78 | 0 | 0 | 3
WACO | 2038-01-031 | BELL | FM 2115 | 2024-02-22 | 7148926.49 | 251153.08 | 0 | 7020327.63 | -128598.86 | 105 | 199 | 83 | 0 | 94
ATLANTA | 0330-01-033 | BOWIE | SH 98 | 2024-02-23 | 3919948.8 | 454169.88 | 0 | 4509125.17 | 589176.37 | 287 | 311 | 6 | 0 | 24
CORPUS CHRISTI | 0916-26-021 | GOLIAD | CR | 2024-02-23 | 643104.49 | 0 | 0 | 645666.04 | 2561.55 | 77 | 77 | 0 | 0 | 0
FORT WORTH | 0080-04-100 | HOOD | US 377 | 2024-02-23 | 4495837.2 | -293546.6 | 0 | 4301450.24 | -194386.96 | 48 | 29 | 0 | 0 | -19
LAREDO | 0023-02-044 | KINNEY | US 90 | 2024-02-23 | 8058700.93 | -321538.25 | 0 | 7764999.92 | -293701.01 | 120 | 94 | 0 | 0 | -26
LUFKIN | 0064-04-045 | SAN AUGUSTINE | SH 21 | 2024-02-23 | 10737998.85 | 1000 | 0 | 10344025.06 | -393973.79 | 133 | 115 | 0 | 0 | -18
LUFKIN | 3248-01-007 | NACOGDOCHES | FM 1878 | 2024-02-23 | 5498351.51 | 75424.89 | 0 | 5368052.96 | -130298.55 | 228 | 131 | 0 | 0 | -97
FORT WORTH | 0250-01-038 | PALO PINTO | US 281 | 2024-02-26 | 201204.53 | 0 | 0 | 205839.52 | 4634.99 | 40 | 40 | 0 | 0 | 0
FORT WORTH | 0902-00-314 | TARRANT | VA | 2024-02-26 | 2816506.12 | 180013.16 | 0 | 3001455.87 | 184949.75 | 360 | 235 | 0 | 0 | -125
WACO | 0055-15-067 | MCLENNAN | US 84 | 2024-02-26 | 2174993.18 | 130390.92 | 0 | 2258382.58 | 83389.4 | 105 | 85 | 0 | 0 | -20
DALLAS | 2250-02-020 | DENTON | SL 288 | 2024-02-27 | 1362510.85 | 0 | 0 | 1326983.74 | -35527.11 | 98 | 96 | 0 | 0 | -2
SAN ANTONIO | 0521-02-042 | BEXAR | SL 13 | 2024-02-27 | 6683653.51 | 26708.4 | 0 | 7137334.34 | 453680.83 | 207 | 217 | 10 | 0 | 10
TYLER | 0927-01-030 | SMITH | FM 344 | 2024-02-27 | 1833547.83 | 206112.4 | 0 | 1955892.31 | 122344.48 | 195 | 195 | 0 | 0 | 0
YOAKUM | 0027-03-073 | COLORADO | FM 102 | 2024-02-27 | 3987940.97 | -217154.81 | 0 | 4030810.66 | 42869.69 | 120 | 108 | 0 | 0 | -12
YOAKUM | 0913-09-076 | WHARTON | CR | 2024-02-27 | 670423.18 | 0 | 0 | 663453.7 | -6969.48 | 120 | 85 | 0 | 0 | -35
YOAKUM | 0913-18-033 | JACKSON | CR | 2024-02-27 | 1898927.97 | 0 | 0 | 1882212.05 | -16715.92 | 189 | 119 | 0 | 0 | -70
YOAKUM | 1090-04-016 | JACKSON | FM 1593 | 2024-02-27 | 4530158.95 | -817250.3 | 0 | 3317080.85 | -1213078.1 | 90 | 26 | 0 | 0 | -64
ATLANTA | 0063-03-065 | PANOLA | US 59 | 2024-02-28 | 8864785.93 | 70838.54 | 0 | 8817431.02 | -47354.91 | 503 | 504 | 7 | 0 | 1
ATLANTA | 0495-08-136 | HARRISON | IH 20 | 2024-02-29 | 11381826 | -139693.15 | 0 | 11752052.23 | 370226.23 | 131 | 168 | 0 | 0 | 37
AUSTIN | 1754-02-029 | HAYS | RM 1826 | 2024-02-29 | 1052438.7 | 0 | 0 | 1138964.05 | 86525.35 | 25 | 9 | 0 | 0 | -16
EL PASO | 0924-00-130 | EL PASO | Various | 2024-02-29 | 1135875 | 5671.97 | 0 | 1165301.97 | 29426.97 | 120 | 108 | 7 | 0 | -12
FORT WORTH | 0008-12-095 | TARRANT | IH 20 | 2024-02-29 | 1729558.35 | 0 | 0 | 1729558.35 | 0 | 86 | 410 | 132 | 0 | 324
TYLER | 0910-00-134 | SMITH | Various | 2024-02-29 | 470054.6 | 18108 | 0 | 540692.56 | 70637.96 | 63 | 23 | 0 | 0 | -40
PARIS | 0435-01-080 | LAMAR | FM 38 | 2024-03-01 | 1748082.48 | 38531.29 | 0 | 1614657.69 | -133424.79 | 304 | 301 | 0 | 0 | -3
SAN ANTONIO | 0024-09-026 | BEXAR | SS 371 | 2024-03-01 | 428776 | 0 | 0 | 426886 | -1890 | 73 | 58 | 0 | 0 | -15
WACO | 0120-05-027 | HAMILTON | FM 218 | 2024-03-01 | 8071174.8 | 0 | 0 | 8235069.3 | 163894.5 | 60 | 53 | 0 | 0 | -7
WICHITA FALLS | 0802-02-069 | WICHITA | FM 369 | 2024-03-02 | 2851006.39 | 21519.59 | 0 | 2912957.94 | 61951.55 | 286 | 302 | 45 | 0 | 16
AMARILLO | 0275-11-083 | GRAY | IH 40 | 2024-03-04 | 10924179.85 | 497275.4 | 0 | 11489551.07 | 565371.22 | 120 | 192 | 82 | 0 | 72
AMARILLO | 0904-04-007 | OCHILTREE | CR | 2024-03-04 | 809347.54 | 0 | 0 | 812160.34 | 2812.8 | 70 | 46 | 0 | 0 | -24
AMARILLO | 2635-03-018 | RANDALL | SL 335 | 2024-03-04 | 42375492.4 | 2136330.15 | 0 | 45200068.96 | 2824576.56 | 720 | 1220 | 330 | 0 | 500
TYLER | 0206-01-050 | ANDERSON | US 79 | 2024-03-04 | 14425842.22 | -599629.98 | 0 | 14084242.19 | -341600.03 | 405 | 426 | 28 | 0 | 21
WACO | 0258-03-046 | HAMILTON | SH 6 | 2024-03-04 | 101962 | 0 | 0 | 93797 | -8165 | 30 | 8 | 0 | 0 | -22
WACO | 0831-01-019 | MCLENNAN | FM 939 | 2024-03-04 | 4553672.46 | -14215.9 | 0 | 4722502.52 | 168830.06 | 135 | 129 | 0 | 0 | -6
YOAKUM | 0370-05-052 | VICTORIA | BU 77-S | 2024-03-04 | 8004183.26 | 433198.48 | 133149 | 8935882.17 | 798549.91 | 270 | 409 | 194 | 20 | 119
YOAKUM | 0420-01-040 | JACKSON | SH 172 | 2024-03-04 | 864757 | 26348.07 | 0 | 732920.57 | -131836.43 | 120 | 174 | 12 | 0 | 54
YOAKUM | 0420-03-018 | CALHOUN | SH 172 | 2024-03-04 | 2118839.16 | 0 | 0 | 2013653.52 | -105185.64 | 90 | 66 | 0 | 0 | -24
YOAKUM | 0913-27-078 | VICTORIA | CR | 2024-03-04 | 988832.25 | 0 | 0 | 979136.55 | -9695.7 | 86 | 95 | 0 | 0 | 9
AMARILLO | 0238-03-065 | DALLAM | US 54 | 2024-03-05 | 486528.7 | -29544.6 | 0 | 442779.6 | -43749.1 | 87 | 87 | 0 | 0 | 0
ODESSA | 0906-00-219 | ECTOR | Various | 2024-03-05 | 1103053.92 | 161470.36 | 0 | 1275403.52 | 172349.6 | 36 | 30 | 0 | 0 | -6
FORT WORTH | 0008-02-077 | PARKER | US 180 | 2024-03-06 | 176530.71 | 0 | 0 | 169870.71 | -6660 | 40 | 40 | 0 | 0 | 0
HOUSTON | 0523-02-050 | WALLER | FM 362 | 2024-03-06 | 3607335.29 | 43261.08 | 0 | 3774475.97 | 167140.68 | 64 | 64 | 0 | 0 | 0
LAREDO | 1590-03-015 | MAVERICK | FM 481 | 2024-03-06 | 1482698.93 | -23588.95 | 0 | 1329235.05 | -153463.88 | 139 | 105 | 0 | 0 | -34
SAN ANGELO | 0035-05-061 | MENARD | US 83 | 2024-03-06 | 2146114.69 | -71388.19 | 0 | 2055603.81 | -90510.88 | 108 | 273 | 40 | 0 | 165
SAN ANTONIO | 0016-19-025 | COMAL | FM 482 | 2024-03-06 | 9397889.26 | -165616.52 | 0 | 8577378.12 | -820511.14 | 91 | 83 | 0 | 0 | -8
AUSTIN | 0016-02-171 | HAYS | IH 35 | 2024-03-07 | 6782284.35 | -953167.6 | 0 | 6109654.22 | -672630.13 | 80 | 49 | 0 | 0 | -31
LUBBOCK | 0068-04-041 | DAWSON | US 87 | 2024-03-07 | 1774772.5 | -97230 | 0 | 1553090.5 | -221682 | 84 | 83 | 0 | 0 | -1
WICHITA FALLS | 0043-08-084 | WICHITA | US 287 | 2024-03-07 | 5141357 | 318535.79 | 0 | 5501591.94 | 360234.94 | 300 | 549 | 249 | 0 | 249
AUSTIN | 1754-01-020 | TRAVIS | RM 1826 | 2024-03-08 | 1225398.05 | 72589.3 | 0 | 1360089.13 | 134691.08 | 45 | 25 | 0 | 0 | -20
EL PASO | 1314-02-014 | CULBERSON | RM 652 | 2024-03-08 | 17231368.56 | 505140.61 | 0 | 17642295.46 | 410926.9 | 300 | 544 | 88 | 0 | 244
LUFKIN | 0118-10-057 | SAN AUGUSTINE | SH 21 | 2024-03-08 | 5292158.61 | 882914.26 | 0 | 6486656.97 | 1194498.36 | 198 | 633 | 435 | 0 | 435
PARIS | 1154-01-020 | FANNIN | FM 824 | 2024-03-08 | 5973029.7 | 53980.13 | 0 | 5945811.66 | -27218.04 | 420 | 411 | 0 | 0 | -9
AUSTIN | 1537-01-017 | LEE | FM 1624 | 2024-03-11 | 1524020.33 | 139.04 | 0 | 1521538.53 | -2481.8 | 49 | 49 | 0 | 0 | 0
AUSTIN | 2102-01-077 | TRAVIS | RM 2244 | 2024-03-11 | 1189033.15 | -183960.7 | 0 | 990832.06 | -198201.09 | 32 | 13 | 0 | 0 | -19
SAN ANTONIO | 0291-03-076 | KERR | SH 16 | 2024-03-11 | 1294034.49 | 23998.71 | 0 | 1324889.52 | 30855.03 | 137 | 136 | 0 | 0 | -1
WICHITA FALLS | 0832-02-029 | WILBARGER | FM 925 | 2024-03-11 | 1277218.5 | 0 | 0 | 1323608 | 46389.5 | 132 | 121 | 0 | 0 | -11
ABILENE | 0032-07-036 | STONEWALL | US 83 | 2024-03-12 | 3582033.05 | 43731.73 | 0 | 3794243.06 | 212210.01 | 172 | 233 | 72 | 0 | 61
AUSTIN | 1200-05-018 | TRAVIS | FM 973 | 2024-03-12 | 791289.83 | 118379.12 | 0 | 891065.65 | 99775.82 | 17 | 10 | 0 | 0 | -7
BRYAN | 0049-08-065 | ROBERTSON | US 190 | 2024-03-12 | 8287389.92 | 3540128.65 | 0 | 13503442.88 | 5216052.96 | 298 | 368 | 75 | 0 | 70
CORPUS CHRISTI | 0916-00-216 | NUECES | VA | 2024-03-12 | 1431538.71 | 63984.25 | 0 | 1472019.55 | 40480.84 | 165 | 205 | 45 | 0 | 40
EL PASO | 0924-00-145 | EL PASO | Various | 2024-03-12 | 338675 | -9651.94 | 0 | 329773.06 | -8901.94 | 40 | 39 | 0 | 0 | -1
EL PASO | 0924-00-147 | EL PASO | VA | 2024-03-12 | 3567302.32 | -207645.36 | 0 | 3325478.88 | -241823.44 | 180 | 136 | 0 | 0 | -44
HOUSTON | 0912-72-610 | HARRIS | VA | 2024-03-12 | 2391849 | 406232.77 | 0 | 3117493.96 | 725644.96 | 192 | 119 | 0 | 0 | -73
ODESSA | 0003-07-064 | REEVES | IH 20 | 2024-03-13 | 5899356.22 | 187140.49 | 0 | 6264622.5 | 365266.28 | 245 | 173 | 0 | 0 | -72
SAN ANTONIO | 0016-05-122 | COMAL | IH 35 | 2024-03-13 | 9649347.92 | -64082.67 | 0 | 9237166.36 | -412181.56 | 114 | 110 | 0 | 0 | -4
BRYAN | 0114-09-077 | WASHINGTON | BU 290F | 2024-03-14 | 2697457.95 | 775260.14 | 0 | 3046666.41 | 349208.46 | 108 | 146 | 54 | 0 | 38
DALLAS | 2355-01-006 | KAUFMAN | FM 2451 | 2024-03-14 | 7647970.67 | 119780.65 | 0 | 7365660.61 | -282310.06 | 246 | 311 | 1 | 0 | 65
FORT WORTH | 0385-04-052 | HOOD | SH 144 | 2024-03-14 | 148929 | 3943.75 | 0 | 147316.75 | -1612.25 | 60 | 41 | 0 | 0 | -19
YOAKUM | 0432-01-067 | CALHOUN | SH 185 | 2024-03-14 | 3450815.38 | -81713.67 | 0 | 3588986.97 | 138171.59 | 75 | 74 | 0 | 0 | -1
ABILENE | 0908-00-112 | TAYLOR | Various | 2024-03-15 | 1087689 | 11305 | 0 | 1116001 | 28312 | 180 | 97 | 0 | 0 | -83
DALLAS | 2351-01-017 | COLLIN | FM 2478 | 2024-03-15 | 28053072.85 | 1091890.55 | 0 | 28934252.94 | 881180.09 | 584 | 583 | 0 | 0 | -1
PHARR | 1804-01-084 | HIDALGO | SS 115 | 2024-03-15 | 709268.05 | 0 | 0 | 695461.6 | -13806.45 | 138 | 24 | 0 | 0 | -114
ABILENE | 0157-04-057 | HASKELL | US 277 | 2024-03-18 | 5473497.38 | -263197.39 | 0 | 5594895.84 | 121398.46 | 103 | 156 | 0 | 0 | 53
DALLAS | 0442-02-169 | DALLAS | IH 35E | 2024-03-18 | 2531498.5 | 167664.2 | 0 | 2713983.98 | 182485.48 | 137 | 101 | 0 | 0 | -36
HOUSTON | 0271-10-012 | FORT BEND | US 90 | 2024-03-18 | 538631 | 0 | 0 | 516982.48 | -21648.52 | 90 | 39 | 0 | 0 | -51
HOUSTON | 0912-72-340 | HARRIS | CS | 2024-03-20 | 15109139.07 | 3574678.34 | 715674.25 | 18436119.01 | 2611305.69 | 361 | 531 | 170 | 95 | 75
PARIS | 0045-02-040 | GRAYSON | SH 56 | 2024-03-20 | 732932.05 | -40469.02 | 0 | 667220.8 | -65711.25 | 80 | 80 | 0 | 0 | 0
YOAKUM | 0143-08-088 | DEWITT | US 87 | 2024-03-20 | 15556720.89 | 102251.38 | 0 | 15762207.85 | 205486.96 | 450 | 449 | 0 | 0 | -1
FORT WORTH | 0747-05-047 | JOHNSON | FM 157 | 2024-03-21 | 473255 | 171175 | 0 | 654920 | 181665 | 64 | 43 | 0 | 0 | -21
PARIS | 0901-00-056 | LAMAR | VA | 2024-03-21 | 2201904 | 1500 | 0 | 2021982.51 | -179921.49 | 170 | 244 | 74 | 0 | 74
ABILENE | 0157-09-004 | HASKELL | US 277 | 2024-03-22 | 5949105.89 | 0 | 0 | 5487824.34 | -461281.55 | 74 | 99 | 0 | 0 | 25
BEAUMONT | 0920-00-152 | JEFFERSON | Various | 2024-03-22 | 1099185.6 | 15925 | 0 | 1123413.23 | 24227.63 | 58 | 58 | 0 | 0 | 0
CORPUS CHRISTI | 0102-01-088 | NUECES | SH 44 | 2024-03-22 | 37950858.4 | 897832.61 | 0 | 38944588.74 | 993730.34 | 645 | 714 | 85 | 0 | 69
DALLAS | 0047-14-087 | COLLIN | US 75 | 2024-03-22 | 453568 | 1825.39 | 0 | 441894.4 | -11673.6 | 65 | 64 | 0 | 0 | -1
SAN ANTONIO | 0595-02-024 | MEDINA | FM 1796 | 2024-03-22 | 1743784.5 | 0 | 0 | 1796025 | 52240.5 | 176 | 170 | 0 | 0 | -6
ABILENE | 0983-02-022 | FISHER | FM 419 | 2024-03-25 | 1468421.46 | 51517.67 | 0 | 1639973.35 | 171551.89 | 192 | 318 | 11 | 0 | 126
HOUSTON | 1062-04-022 | HARRIS | FM 2100 | 2024-03-25 | 43751962.99 | 2475788.94 | 490816.77 | 47283740.56 | 3040960.8 | 403 | 723 | 147 | 0 | 320
PARIS | 0901-28-097 | HOPKINS | CR | 2024-03-25 | 842684.36 | 0 | 0 | 868843.31 | 26158.95 | 128 | 47 | 0 | 0 | -81
HOUSTON | 0271-07-329 | HARRIS | IH 10 | 2024-03-26 | 6254711.5 | 723202.46 | 727902.21 | 6948479.86 | -34133.85 | 215 | 240 | 60 | 60 | -35
DALLAS | 0095-04-074 | KAUFMAN | US 80 | 2024-03-27 | 4616246.31 | -67105.51 | 0 | 4437942.07 | -178304.24 | 73 | 67 | 0 | 0 | -6
LUFKIN | 0931-04-034 | TRINITY | FS 357 | 2024-03-27 | 1648548.43 | 426338 | 0 | 1756268.94 | 107720.51 | 78 | 132 | 45 | 0 | 54
DALLAS | 0009-02-067 | DALLAS | SH 78 | 2024-03-28 | 6336366.93 | 123824.69 | 0 | 6716477.01 | 380110.08 | 435 | 503 | 68 | 0 | 68
DALLAS | 0095-05-064 | KAUFMAN | US 80 | 2024-03-28 | 1089055.5 | 4544.4 | 0 | 1058866.2 | -30189.3 | 103 | 44 | 0 | 0 | -59
PARIS | 0901-19-207 | GRAYSON | Various | 2024-03-28 | 1694730 | 13036.71 | 0 | 1729549.55 | 34819.55 | 109 | 81 | 0 | 0 | -28
PARIS | 1482-01-014 | FANNIN | FM 1550 | 2024-03-28 | 3637497.65 | 30971.45 | 0 | 3738708.22 | 101210.57 | 300 | 376 | 0 | 0 | 76
DALLAS | 0918-00-333 | DALLAS | VA | 2024-03-29 | 994600 | 0 | 0 | 991670.91 | -2929.09 | 160 | 148 | 0 | 0 | -12
EL PASO | 2121-04-120 | EL PASO | IH 10 | 2024-03-29 | 3267440.5 | 110200.4 | 0 | 3438203.71 | 170763.21 | 200 | 235 | 47 | 0 | 35
DALLAS | 0281-02-077 | COLLIN | SH 78 | 2024-04-01 | 1739804.4 | 47197.1 | 0 | 1786990.68 | 47186.28 | 99 | 68 | 0 | 0 | -31
DALLAS | 0918-00-356 | DALLAS | VA | 2024-04-01 | 3364193.43 | 394077.69 | 0 | 3783742.67 | 419549.24 | 214 | 270 | 59 | 0 | 56
HOUSTON | 0028-02-100 | HARRIS | US 90 | 2024-04-02 | 1486713.95 | 343284.05 | 0 | 1768491.09 | 281777.14 | 135 | 89 | 0 | 0 | -46
AUSTIN | 1755-01-022 | WILLIAMSON | RM 1869 | 2024-04-03 | 994595.84 | 58709.35 | 0 | 955450.79 | -39145.05 | 30 | 20 | 0 | 0 | -10
TYLER | 0083-06-040 | WOOD | SH 11 | 2024-04-03 | 24618622.08 | 1751970.68 | 0 | 24995211.49 | 376589.41 | 170 | 177 | 39 | 0 | 7
AUSTIN | 0914-21-032 | LEE | FD | 2024-04-04 | 1068091.55 | 248838.56 | 0 | 1298808.33 | 230716.78 | 37 | 28 | 0 | 0 | -9
AUSTIN | 0914-33-068 | HAYS | CR | 2024-04-05 | 17724255.98 | 753550.05 | 488478.61 | 18677824.88 | 465090.29 | 340 | 334 | 0 | 0 | -6
AUSTIN | 2100-01-069 | TRAVIS | RM 2222 | 2024-04-05 | 2999888.08 | 3000 | 0 | 3083415.87 | 83527.79 | 54 | 48 | 0 | 0 | -6
DALLAS | 1392-01-050 | COLLIN | FM 1378 | 2024-04-05 | 6227270.73 | -160131.06 | 0 | 6176342.63 | -50928.1 | 210 | 208 | 0 | 0 | -2
PHARR | 1586-01-079 | HIDALGO | FM 907 | 2024-04-05 | 5127397.9 | 0 | 0 | 5222522 | 95124.1 | 266 | 216 | 0 | 0 | -50
AUSTIN | 0015-13-382 | TRAVIS | IH 35 | 2024-04-08 | 124206530.55 | 6757349.32 | 37270.43 | 140212442.33 | 15968641.35 | 1028 | 1271 | 243 | 0 | 243
BROWNWOOD | 0714-02-018 | STEPHENS | PR 33 | 2024-04-08 | 960397.9 | 12578.1 | 0 | 952259.73 | -8138.17 | 134 | 162 | 24 | 0 | 28
BEAUMONT | 0028-13-141 | JEFFERSON | IH 10 | 2024-04-09 | 916598.5 | 423268.47 | 0 | 1284202.5 | 367604 | 49 | 66 | 23 | 0 | 17
BEAUMONT | 0920-00-136 | JEFFERSON | Various | 2024-04-09 | 464332.5 | 16847.46 | 0 | 457921.49 | -6411.01 | 43 | 43 | 0 | 0 | 0
SAN ANGELO | 0907-00-230 | TOM GREEN | Various | 2024-04-09 | 298966 | 4141.48 | 0 | 298435.48 | -530.52 | 34 | 23 | 0 | 0 | -11
WACO | 1191-03-033 | LIMESTONE | FM 1245 | 2024-04-09 | 2816412.46 | 0 | 0 | 2799733.11 | -16679.35 | 210 | 313 | 0 | 0 | 103
BROWNWOOD | 0054-04-124 | COLEMAN | US 84 | 2024-04-10 | 820790 | 28987.86 | 0 | 822321.46 | 1531.46 | 63 | 46 | 0 | 0 | -17
EL PASO | 0374-06-022 | HUDSPETH | US 62 | 2024-04-10 | 21060676.34 | 853573.39 | 0 | 22436392.06 | 1375715.72 | 420 | 335 | 0 | 0 | -85
EL PASO | 2121-02-162 | EL PASO | IH 10 | 2024-04-10 | 960423 | 148618 | 0 | 1094936.93 | 134513.93 | 54 | 47 | 0 | 0 | -7
HOUSTON | 0027-12-159 | FORT BEND | IH 69 | 2024-04-10 | 1099756.21 | 142547.36 | 0 | 1195318.42 | 95562.21 | 90 | 120 | 30 | 0 | 30
TYLER | 0910-12-142 | VAN ZANDT | CR | 2024-04-10 | 521961.28 | 26129.49 | 0 | 551610.36 | 29649.08 | 62 | 50 | 0 | 0 | -12
ATLANTA | 0495-08-121 | HARRISON | IH 20 | 2024-04-11 | 639848.46 | 5501.95 | 0 | 690054.85 | 50206.39 | 146 | 149 | 0 | 0 | 3
HOUSTON | 3256-03-096 | HARRIS | SL 8 | 2024-04-11 | 459158.8 | 26400 | 0 | 530473.52 | 71314.72 | 45 | 38 | 0 | 0 | -7
PARIS | 0136-07-052 | LAMAR | US 271 | 2024-04-11 | 1434042 | -429440.02 | 0 | 1023766.75 | -410275.25 | 121 | 121 | 0 | 0 | 0
PHARR | 0255-04-101 | BROOKS | US 281 | 2024-04-11 | 660180 | 0 | 0 | 605851 | -54329 | 128 | 13 | 0 | 0 | -115
WICHITA FALLS | 0802-02-070 | WICHITA | FM 369 | 2024-04-11 | 5448304.05 | 22234.56 | 0 | 5581161.09 | 132857.04 | 57 | 81 | 4 | 0 | 24
BEAUMONT | 0920-00-154 | LIBERTY | Various | 2024-04-12 | 561526.59 | 0 | 0 | 866111.06 | 304584.47 | 80 | 70 | 0 | 0 | -10
CORPUS CHRISTI | 0074-03-047 | SAN PATRICIO | IH 37 | 2024-04-12 | 1690176.8 | 54932.42 | 0 | 1713303.7 | 23126.9 | 170 | 210 | 40 | 0 | 40
CORPUS CHRISTI | 0916-00-221 | NUECES | VA | 2024-04-12 | 2575368.87 | 9941.57 | 0 | 2103854.07 | -471514.8 | 229 | 542 | 194 | 0 | 313
CORPUS CHRISTI | 0916-38-014 | ARANSAS | CS | 2024-04-12 | 4582972.16 | 187851.83 | 0 | 4509797.87 | -73174.29 | 309 | 569 | 163 | 0 | 260
LUBBOCK | 0067-11-047 | LUBBOCK | IH 27 | 2024-04-12 | 1738710 | 23284.98 | 0 | 1921863.98 | 183153.98 | 125 | 172 | 60 | 0 | 47
ATLANTA | 0248-04-072 | UPSHUR | US 271 | 2024-04-15 | 12013248.87 | 14261.45 | 0 | 12101275.47 | 88026.6 | 189 | 350 | 12 | 0 | 161
ABILENE | 0908-00-108 | TAYLOR | VA | 2024-04-16 | 1838800.64 | 91930.61 | 0 | 1986545.19 | 147744.55 | 184 | 184 | 0 | 0 | 0
FORT WORTH | 0314-02-054 | PALO PINTO | IH 20 | 2024-04-16 | 2356201.48 | 139903.27 | 0 | 2501538.25 | 145336.77 | 120 | 120 | 0 | 0 | 0
FORT WORTH | 1094-02-015 | TARRANT | FM 731 | 2024-04-16 | 358701.7 | -1447.95 | 0 | 357253.75 | -1447.95 | 86 | 60 | 0 | 0 | -26
AUSTIN | 0914-22-076 | CALDWELL | CR | 2024-04-17 | 777849.43 | 0 | 0 | 750474.26 | -27375.17 | 45 | 43 | 0 | 0 | -2
BRYAN | 2446-01-030 | BRAZOS | SH 30 | 2024-04-17 | 1790660.92 | 687445.11 | 0 | 2773211.32 | 982550.4 | 90 | 95 | 14 | 0 | 5
BROWNWOOD | 0054-06-105 | BROWN | US 67 | 2024-04-18 | 854513.15 | -1897.42 | 0 | 635684.33 | -218828.82 | 51 | 32 | 0 | 0 | -19
WICHITA FALLS | 0043-05-113 | WILBARGER | US 287 | 2024-04-18 | 1828753.26 | 0 | 0 | 1742784.16 | -85969.1 | 270 | 33 | 0 | 0 | -237
FORT WORTH | 0902-90-217 | TARRANT | CS | 2024-04-22 | 509265.25 | 2811.23 | 0 | 438611.31 | -70653.94 | 128 | 122 | 0 | 0 | -6
SAN ANTONIO | 0016-10-025 | COMAL | BS 46C | 2024-04-22 | 2079346.97 | 443309.31 | 0 | 2649229.18 | 569882.21 | 234 | 241 | 30 | 0 | 7
YOAKUM | 0144-04-046 | CALHOUN | SH 238 | 2024-04-22 | 3061750.05 | 4420 | 0 | 2874027.06 | -187722.99 | 241 | 323 | 84 | 0 | 82
YOAKUM | 0913-26-062 | COLORADO | CR | 2024-04-22 | 1385689.52 | 0 | 0 | 1353836.19 | -31853.33 | 287 | 213 | 0 | 0 | -74
YOAKUM | 1721-01-009 | AUSTIN | FM 1094 | 2024-04-22 | 9952579.14 | 238705.1 | 0 | 9974041.14 | 21462 | 300 | 295 | 0 | 0 | -5
HOUSTON | 0409-03-013 | WALLER | FM 1488 | 2024-04-23 | 505724.8 | -35399.13 | 0 | 497032.01 | -8692.79 | 17 | 24 | 0 | 0 | 7
SAN ANTONIO | 0915-00-237 | BEXAR | VA | 2024-04-23 | 1606331.22 | 0 | 0 | 1508215.05 | -98116.17 | 260 | 94 | 0 | 0 | -166
ATLANTA | 1231-01-069 | BOWIE | FM 989 | 2024-04-24 | 1902107.55 | 0 | 0 | 2061639.16 | 159531.61 | 33 | 33 | 0 | 0 | 0
TYLER | 0910-00-135 | SMITH | Various | 2024-04-24 | 783827.95 | 18568.45 | 0 | 769772.41 | -14055.54 | 105 | 102 | 1 | 0 | -3
ATLANTA | 0063-05-040 | PANOLA | US 59 | 2024-04-25 | 2134626.21 | 5598.17 | 0 | 2063563.36 | -71062.85 | 149 | 137 | 0 | 0 | -12
LAREDO | 0022-10-076 | VAL VERDE | US 90 | 2024-04-25 | 409635.3 | -9070.27 | 0 | 393657.03 | -15978.27 | 92 | 90 | 0 | 0 | -2
ATLANTA | 0919-00-092 | CASS | Various | 2024-04-26 | 142303.23 | 16269.9 | 0 | 158549.13 | 16245.9 | 20 | 8 | 0 | 0 | -12
BROWNWOOD | 0127-02-142 | EASTLAND | US 183 | 2024-04-26 | 16887011.55 | 3893026.51 | 0 | 20665272.56 | 3778261.01 | 790 | 1147 | 328 | 0 | 357
DALLAS | 2352-02-027 | DENTON | FM 2449 | 2024-04-26 | 2095541.43 | 237180.81 | 0 | 2105898.66 | 10357.23 | 108 | 107 | 0 | 0 | -1
HOUSTON | 1004-01-065 | BRAZORIA | FM 521 | 2024-04-26 | 532257.18 | 102239.41 | 0 | 617461.54 | 85204.36 | 27 | 21 | 0 | 0 | -6
SAN ANGELO | 0264-06-043 | TOM GREEN | US 277 | 2024-04-26 | 17420245.53 | -298409.11 | 0 | 17006870.28 | -413375.25 | 387 | 327 | 0 | 0 | -60
TYLER | 0910-08-080 | ANDERSON | Various | 2024-04-26 | 958749.25 | 44120 | 0 | 1052715.05 | 93965.8 | 63 | 30 | 0 | 0 | -33
WACO | 0382-01-047 | FALLS | SH 7 | 2024-04-26 | 2042766 | 270744.46 | 0 | 2351880.6 | 309114.6 | 105 | 158 | 53 | 0 | 53
YOAKUM | 0267-01-033 | FAYETTE | SH 237 | 2024-04-26 | 1212845.4 | 11255.12 | 0 | 1209429.91 | -3415.49 | 114 | 82 | 0 | 0 | -32
AUSTIN | 0016-02-152 | HAYS | IH 35 | 2024-04-29 | 21992737.11 | 808054.63 | 0 | 24122037.7 | 2129300.59 | 267 | 531 | 277 | 0 | 264
BRYAN | 0675-03-100 | LEON | IH 45 | 2024-04-30 | 13387149.52 | 233206.66 | 0 | 14151057.46 | 763907.94 | 180 | 124 | 0 | 0 | -56
FORT WORTH | 0014-16-283 | TARRANT | IH 35W | 2024-04-30 | 10273783.29 | -91628.38 | 0 | 11181033.92 | 907250.63 | 214 | 229 | 32 | 0 | 15
FORT WORTH | 0364-01-160 | TARRANT | SH 121 | 2024-04-30 | 642688 | 0 | 0 | 593550 | -49138 | 64 | 64 | 0 | 0 | 0
FORT WORTH | 0902-38-133 | PARKER | CS | 2024-04-30 | 990945.55 | 2774.36 | 0 | 969492.97 | -21452.58 | 118 | 303 | 0 | 0 | 185
FORT WORTH | 0902-90-117 | TARRANT | CS | 2024-04-30 | 6339142.79 | 16347.34 | 15827.34 | 6472379.78 | 117409.65 | 192 | 297 | 106 | 0 | 105
FORT WORTH | 1179-02-039 | PARKER | FM 920 | 2024-04-30 | 5187250.2 | 944162.6 | 0 | 6074319.76 | 887069.56 | 126 | 449 | 131 | 0 | 323
SAN ANTONIO | 0072-08-143 | BEXAR | SL 345 | 2024-04-30 | 6416001.69 | 666833.19 | 0 | 7666083.14 | 1250081.45 | 180 | 133 | 0 | 0 | -47
WACO | 0231-02-066 | CORYELL | IH 14 | 2024-04-30 | 9294253.44 | -769687.01 | 0 | 9470921.97 | 176668.53 | 147 | 140 | 0 | 0 | -7
EL PASO | 0104-10-006 | PRESIDIO | US 67 | 2024-05-01 | 6854362.5 | 3098122.41 | 0 | 9878157.49 | 3023794.99 | 260 | 533 | 245 | 0 | 273
LUBBOCK | 0905-00-110 | LUBBOCK | VA | 2024-05-01 | 4034018.84 | 433885 | 0 | 4753898.55 | 719879.71 | 408 | 316 | 5 | 0 | -92
PARIS | 0045-12-091 | RED RIVER | US 82 | 2024-05-01 | 19399613.07 | -625102.77 | 0 | 18707733.2 | -691879.87 | 140 | 140 | 0 | 0 | 0
ABILENE | 0006-05-125 | TAYLOR | IH 20 | 2024-05-03 | 5489128.81 | 72163.9 | 0 | 5813782.81 | 324654 | 95 | 88 | 10 | 0 | -7
CHILDRESS | 0925-00-092 | CHILDRESS | Various | 2024-05-03 | 637223.85 | 21710.7 | 0 | 671010.7 | 33786.85 | 25 | 9 | 0 | 0 | -16
LUFKIN | 1157-01-018 | ANGELINA | FM 841 | 2024-05-03 | 5264676.9 | -63029.17 | 0 | 4990026.05 | -274650.85 | 312 | 301 | 0 | 0 | -11
ODESSA | 1188-02-100 | MIDLAND | SL 250 | 2024-05-03 | 18245177.99 | -75541.87 | 0 | 18363376.58 | 118198.59 | 295 | 442 | 162 | 0 | 147
WACO | 1662-02-013 | HILL | FM 339 | 2024-05-03 | 2487780.12 | 16561.4 | 0 | 2393064.59 | -94715.53 | 165 | 134 | 3 | 0 | -31
SAN ANTONIO | 0915-00-202 | BEXAR | VA | 2024-05-05 | 676228.05 | 8033.86 | 0 | 685057.06 | 8829.01 | 135 | 166 | 0 | 0 | 31
DALLAS | 0048-04-104 | ELLIS | IH 35E | 2024-05-06 | 2002539.82 | 157062.6 | 0 | 2217777.53 | 215237.71 | 155 | 116 | 0 | 0 | -39
DALLAS | 0364-02-024 | DALLAS | SH 121 | 2024-05-06 | 173621 | 3389 | 0 | 175876 | 2255 | 46 | 28 | 0 | 0 | -18
SAN ANGELO | 0160-01-036 | SUTTON | US 277 | 2024-05-06 | 8455478.52 | -232535.32 | 0 | 7270221.18 | -1185257.34 | 178 | 335 | 40 | 0 | 157
SAN ANGELO | 0160-02-025 | SUTTON | US 277 | 2024-05-06 | 19351496.83 | -780611.73 | 0 | 19160946.22 | -190550.61 | 342 | 499 | 0 | 0 | 157
FORT WORTH | 0008-15-059 | TARRANT | IH 820 | 2024-05-07 | 365571.75 | 65209.09 | 0 | 436553.77 | 70982.02 | 58 | 84 | 35 | 0 | 26
FORT WORTH | 0249-07-079 | JACK | US 281 | 2024-05-07 | 1303125.13 | 9946.75 | 0 | 1230416.35 | -72708.78 | 107 | 93 | 0 | 0 | -14
AMARILLO | 0030-06-066 | HEMPHILL | US 60 | 2024-05-08 | 21819571.04 | 732828.03 | 0 | 21144277.04 | -675294 | 97 | 78 | 0 | 0 | -19
HOUSTON | 0114-12-015 | HARRIS | US 290 | 2024-05-08 | 425417.8 | 78764.78 | 0 | 480069.77 | 54651.97 | 60 | 51 | 0 | 0 | -9
HOUSTON | 0500-03-634 | HARRIS | IH 45 | 2024-05-08 | 830884.84 | 729794.08 | 0 | 2023167.3 | 1192282.46 | 30 | 42 | 12 | 0 | 12
AUSTIN | 0015-09-194 | WILLIAMSON | IH 35 | 2024-05-09 | 9323423.18 | -281018.5 | 0 | 9152758.85 | -170664.33 | 253 | 317 | 64 | 0 | 64
WICHITA FALLS | 0312-01-076 | COOKE | FM 51 | 2024-05-09 | 4761917.35 | 53023.22 | 0 | 4943741.53 | 181824.18 | 285 | 256 | 0 | 0 | -29
ODESSA | 0354-04-040 | WINKLER | SH 115 | 2024-05-13 | 8225180.16 | -593703.76 | 0 | 7940347.88 | -284832.28 | 112 | 90 | 0 | 0 | -22
AUSTIN | 0683-02-070 | TRAVIS | RM 620 | 2024-05-15 | 1229140.8 | 19139.15 | 0 | 1209194.23 | -19946.57 | 140 | 113 | 0 | 0 | -27
EL PASO | 0002-06-062 | HUDSPETH | IH 10 | 2024-05-15 | 4777419.05 | -31102.74 | 0 | 4959100.67 | 181681.62 | 60 | 50 | 1 | 0 | -10
HOUSTON | 0912-72-075 | HARRIS | CS | 2024-05-15 | 24159580.68 | 2072197.83 | 1933254.14 | 25732690.29 | -360144.53 | 475 | 539 | 72 | 72 | -8
DALLAS | 1391-01-021 | COLLIN | FM 1377 | 2024-05-16 | 7597592.9 | 51849.12 | 0 | 6974511.71 | -623081.19 | 236 | 233 | 0 | 0 | -3
AUSTIN | 0914-22-071 | CALDWELL | CR | 2024-05-17 | 742959.7 | -61389.44 | 0 | 663704.96 | -79254.74 | 40 | 35 | 0 | 0 | -5
BRYAN | 0049-15-014 | ROBERTSON | SH 14 | 2024-05-17 | 14704110.35 | 654749.52 | 0 | 13955738.48 | -748371.87 | 122 | 101 | 0 | 0 | -21
EL PASO | 3451-01-033 | EL PASO | FM 1281 | 2024-05-17 | 9420480.5 | 1897490.16 | 0 | 11722161.01 | 2301680.51 | 320 | 89 | 0 | 0 | -231
PHARR | 2831-01-016 | HIDALGO | FM 2812 | 2024-05-17 | 1133775.94 | 0 | 0 | 1150290.79 | 16514.85 | 89 | 56 | 0 | 0 | -33
WACO | 0909-37-065 | HILL | CR | 2024-05-17 | 558558 | 0 | 0 | 554586.46 | -3971.54 | 75 | 69 | 0 | 0 | -6
ABILENE | 0006-18-064 | TAYLOR | BI 20R | 2024-05-20 | 879467.94 | 5968.15 | 0 | 897510.83 | 18042.89 | 58 | 57 | 0 | 0 | -1
BEAUMONT | 0920-38-280 | JEFFERSON | CS | 2024-05-20 | 850170 | -14564.34 | 0 | 836221.66 | -13948.34 | 127 | 70 | 0 | 0 | -57
EL PASO | 0020-01-022 | CULBERSON | US 90 | 2024-05-20 | 6496447.39 | 1128532.91 | 0 | 7841112.9 | 1344665.51 | 110 | 117 | 24 | 0 | 7
HOUSTON | 0027-12-158 | FORT BEND | IH 69 | 2024-05-20 | 5893966.5 | -472765.35 | 0 | 5463983.35 | -429983.15 | 367 | 330 | 0 | 0 | -37
SAN ANTONIO | 0073-08-200 | BEXAR | IH 37 | 2024-05-20 | 164889.06 | 0 | 0 | 164139 | -750.06 | 35 | 23 | 0 | 0 | -12
BRYAN | 0049-09-076 | BRAZOS | BS 6R | 2024-05-21 | 5236845.06 | -19174.67 | 0 | 5108337.83 | -128507.23 | 119 | 161 | 65 | 0 | 42
DALLAS | 0173-04-057 | KAUFMAN | SH 34 | 2024-05-21 | 5861108.95 | 116841.46 | 0 | 5723389.28 | -137719.67 | 134 | 149 | 10 | 0 | 15
DALLAS | 0197-04-084 | KAUFMAN | US 175 | 2024-05-21 | 2469855.37 | 282200 | 0 | 2779832.55 | 309977.18 | 113 | 101 | 0 | 0 | -12
HOUSTON | 0050-04-027 | WALLER | SH 6 | 2024-05-21 | 5294013.77 | -71304.53 | 0 | 5867979.6 | 573965.83 | 138 | 195 | 0 | 0 | 57
WICHITA FALLS | 0903-29-027 | ARCHER | CR | 2024-05-21 | 824216 | 0 | 0 | 795758.23 | -28457.77 | 102 | 95 | 0 | 0 | -7
ABILENE | 0908-00-116 | TAYLOR | Various | 2024-05-22 | 316290 | -6700 | 0 | 327294 | 11004 | 34 | 42 | 25 | 0 | 8
AUSTIN | 1902-01-031 | TRAVIS | FM 1825 | 2024-05-22 | 2118243.18 | 35869.62 | 0 | 2297381.63 | 179138.45 | 90 | 46 | 0 | 0 | -44
LUFKIN | 0176-05-199 | POLK | US 59 | 2024-05-22 | 5599219.46 | 1000 | 0 | 5898423.48 | 299204.02 | 69 | 74 | 0 | 0 | 5
PHARR | 0528-01-121 | HIDALGO | SH 107 | 2024-05-22 | 5739476.01 | 163049.98 | 0 | 6310667.48 | 571191.47 | 60 | 80 | 20 | 0 | 20
BRYAN | 0109-09-066 | WALKER | SH 19 | 2024-05-23 | 23496228.97 | -2530788.48 | 0 | 20598203.55 | -2898025.42 | 135 | 114 | 0 | 0 | -21
CHILDRESS | 1514-01-013 | FOARD | FM 1594 | 2024-05-23 | 156553.6 | 37507.05 | 0 | 194277.79 | 37724.19 | 35 | 28 | 0 | 0 | -7
AUSTIN | 1200-03-064 | TRAVIS | FM 973 | 2024-05-24 | 348675.07 | 11563.91 | 0 | 351835.86 | 3160.79 | 42 | 42 | 0 | 0 | 0
DALLAS | 0353-09-002 | DENTON | SH 114 | 2024-05-24 | 32367838.16 | 494862.23 | 0 | 33369974.46 | 1002136.3 | 436 | 386 | 10 | 0 | -50
FORT WORTH | 0172-01-056 | TARRANT | BU 287P | 2024-05-24 | 5671661.16 | 1294928.92 | 0 | 6863292.5 | 1191631.34 | 260 | 626 | 366 | 0 | 366
ATLANTA | 1895-02-013 | HARRISON | FM 726 | 2024-05-28 | 1697965.52 | 333025 | 0 | 1994092.34 | 296126.82 | 150 | 74 | 0 | 0 | -76
BROWNWOOD | 0923-00-075 | BROWN | VA | 2024-05-28 | 160464 | 108543.78 | 0 | 300644.46 | 140180.46 | 41 | 94 | 54 | 0 | 53
HOUSTON | 0976-03-104 | GALVESTON | FM 518 | 2024-05-28 | 2146673.65 | 183028.89 | 0 | 2188559.68 | 41886.03 | 120 | 121 | 0 | 0 | 1
LAREDO | 1937-02-032 | ZAVALA | FM 393 | 2024-05-28 | 8978775.55 | 159558.13 | 0 | 9037745.89 | 58970.34 | 275 | 421 | 146 | 0 | 146
PARIS | 0316-03-010 | GRAYSON | FM 1753 | 2024-05-29 | 6464805.44 | -22823.76 | 0 | 6770104.7 | 305299.26 | 151 | 151 | 0 | 0 | 0
WACO | 0162-01-097 | MCLENNAN | SH 31 | 2024-05-29 | 11321680 | 428480.09 | 0 | 11186581.95 | -135098.05 | 345 | 366 | 21 | 0 | 21
PHARR | 3098-01-016 | HIDALGO | FM 3072 | 2024-05-30 | 6196267.7 | 11199.22 | 0 | 5964633.86 | -231633.84 | 196 | 299 | 4 | 0 | 103
BEAUMONT | 1300-03-003 | NEWTON | SS 135 | 2024-05-31 | 626273.5 | -40396.83 | 0 | 588969.37 | -37304.13 | 36 | 60 | 0 | 0 | 24
DALLAS | 0574-02-021 | NAVARRO | FM 636 | 2024-05-31 | 7986235.47 | 69501.36 | 0 | 8073938.32 | 87702.85 | 374 | 372 | 0 | 0 | -2
EL PASO | 0924-06-635 | EL PASO | VA | 2024-05-31 | 797515.85 | 96823.99 | 0 | 860246.35 | 62730.5 | 80 | 150 | 65 | 0 | 70
LUFKIN | 0911-00-124 | ANGELINA | Various | 2024-06-03 | 899492.37 | 96646.86 | 0 | 949334.88 | 49842.51 | 141 | 140 | 0 | 0 | -1
AMARILLO | 0904-00-199 | POTTER | VA | 2024-06-04 | 843650 | 84144.75 | 0 | 994274.25 | 150624.25 | 129 | 185 | 8 | 0 | 56
AUSTIN | 0151-05-120 | WILLIAMSON | US 183 | 2024-06-04 | 995253.33 | 0 | 0 | 1035108.53 | 39855.2 | 28 | 27 | 0 | 0 | -1
BEAUMONT | 0028-13-143 | JEFFERSON | IH 10 | 2024-06-04 | 969969 | 144784.12 | 0 | 975499.38 | 5530.38 | 45 | 28 | 5 | 0 | -17
EL PASO | 3451-01-035 | EL PASO | FM 1281 | 2024-06-04 | 5171354.49 | 328204.3 | 0 | 5560404.31 | 389049.82 | 252 | 285 | 37 | 0 | 33
SAN ANTONIO | 0025-09-083 | BEXAR | FM 78 | 2024-06-04 | 962216.73 | 49662.95 | 0 | 1117249.08 | 155032.35 | 40 | 40 | 0 | 0 | 0
YOAKUM | 0515-05-016 | JACKSON | FM 822 | 2024-06-04 | 3029884.42 | 379090.92 | 0 | 3427579.23 | 397694.81 | 135 | 135 | 0 | 0 | 0
LAREDO | 0022-10-073 | VAL VERDE | US 90 | 2024-06-05 | 2280943.5 | 6840.5 | 0 | 2189538.07 | -91405.43 | 238 | 247 | 20 | 0 | 9
LUFKIN | 1409-03-020 | SHELBY | FM 2261 | 2024-06-05 | 1320204.74 | 44685.4 | 0 | 1489856 | 169651.26 | 191 | 198 | 7 | 0 | 7
PARIS | 0081-08-011 | GRAYSON | BU 377B | 2024-06-05 | 4193223.2 | 61457.1 | 0 | 4186964.44 | -6258.76 | 63 | 142 | 30 | 0 | 79
BROWNWOOD | 0007-03-108 | EASTLAND | IH 20 | 2024-06-06 | 2010120 | 30688.69 | 0 | 2041004.86 | 30884.86 | 55 | 48 | 0 | 0 | -7
FORT WORTH | 0094-02-145 | TARRANT | SH 183 | 2024-06-06 | 857399.06 | 208985.16 | 0 | 1093756.95 | 236357.89 | 56 | 65 | 12 | 0 | 9
LUBBOCK | 2740-02-016 | LUBBOCK | FM 2641 | 2024-06-06 | 7222200 | 92271.93 | 0 | 7215744.21 | -6455.79 | 302 | 323 | 53 | 0 | 21
ABILENE | 0908-12-027 | HOWARD | Various | 2024-06-07 | 424109 | -22385 | 0 | 381321 | -42788 | 37 | 37 | 0 | 0 | 0
AUSTIN | 3136-01-194 | TRAVIS | SL 1 | 2024-06-07 | 1369463.75 | 63820.5 | 0 | 1421745.32 | 52281.57 | 172 | 120 | 0 | 0 | -52
EL PASO | 2552-04-046 | EL PASO | SL 375 | 2024-06-07 | 3878272.32 | 0 | 0 | 440999.33 | -3437272.99 | 108 | 322 | 0 | 0 | 214
SAN ANTONIO | 0253-03-073 | COMAL | US 281 | 2024-06-07 | 1299000 | 51697 | 0 | 1339103.01 | 40103.01 | 178 | 86 | 0 | 0 | -92
ABILENE | 0908-33-102 | TAYLOR | CS | 2024-06-10 | 200053 | 0 | 0 | 184053 | -16000 | 38 | 11 | 0 | 0 | -27
AUSTIN | 0683-03-044 | HAYS | RM 12 | 2024-06-10 | 5424333.45 | 231685.48 | 0 | 5347781.55 | -76551.9 | 96 | 85 | 0 | 0 | -11
HOUSTON | 1414-01-022 | GALVESTON | FM 528 | 2024-06-10 | 614813.73 | 93618.32 | 0 | 741986.01 | 127172.28 | 101 | 98 | 0 | 0 | -3
LUFKIN | 0200-02-039 | ANGELINA | US 69 | 2024-06-10 | 71614966.82 | 5494618.5 | 0 | 75242514.88 | 3627548.06 | 571 | 779 | 255 | 0 | 208
SAN ANTONIO | 0915-17-072 | COMAL | CS | 2024-06-10 | 1934816.63 | 41053.95 | 8028.83 | 2002190.81 | 59345.35 | 91 | 90 | 0 | 0 | -1
PHARR | 0038-07-083 | STARR | US 83 | 2024-06-11 | 301664.6 | 5074.1 | 0 | 305287.73 | 3623.13 | 60 | 33 | 0 | 0 | -27
AUSTIN | 0151-09-150 | TRAVIS | US 183 | 2024-06-12 | 1477600.5 | 11400 | 0 | 1485317.33 | 7716.83 | 90 | 104 | 0 | 0 | 14
AUSTIN | 0914-05-209 | WILLIAMSON | VA | 2024-06-12 | 288957 | 23383.32 | 0 | 307715.32 | 18758.32 | 32 | 29 | 0 | 0 | -3
CHILDRESS | 0925-00-080 | CHILDRESS | Various | 2024-06-12 | 1414599.81 | 0 | 0 | 1442142.46 | 27542.65 | 49 | 29 | 0 | 0 | -20
FORT WORTH | 0134-06-053 | WISE | SH 101 | 2024-06-12 | 4701956.7 | -166357.63 | 0 | 4578431.27 | -123525.43 | 320 | 315 | 0 | 0 | -5
SAN ANGELO | 0141-08-050 | KIMBLE | IH 10 | 2024-06-12 | 9718660 | -63523.29 | 0 | 9765669.72 | 47009.72 | 154 | 149 | 0 | 0 | -5
AMARILLO | 0557-02-019 | HUTCHINSON | SH 152 | 2024-06-14 | 7081620.08 | -105033.95 | 0 | 7452200.59 | 370580.51 | 91 | 135 | 45 | 0 | 44
AMARILLO | 1245-02-050 | POTTER | RM 1061 | 2024-06-14 | 7909237.48 | 887048.41 | 0 | 9101665.23 | 1192427.75 | 79 | 108 | 20 | 0 | 29
AMARILLO | 2635-04-042 | POTTER | SL 335 | 2024-06-14 | 2622116.83 | 50969.86 | 0 | 2688558.83 | 66442 | 88 | 119 | 45 | 0 | 31
BRYAN | 0050-01-087 | BRAZOS | BS 6-R | 2024-06-14 | 1136623.6 | 81342.8 | 0 | 1228237.95 | 91614.35 | 158 | 168 | 0 | 0 | 10
CHILDRESS | 0032-01-034 | CHILDRESS | US 62 | 2024-06-14 | 7466259.69 | 282560.88 | 0 | 8045069.91 | 578810.22 | 101 | 115 | 20 | 0 | 14
DALLAS | 0281-02-075 | COLLIN | SH 78 | 2024-06-14 | 1531622.2 | 0 | 0 | 1571493.49 | 39871.29 | 128 | 182 | 0 | 0 | 54
DALLAS | 1047-03-074 | DALLAS | FM 1382 | 2024-06-14 | 2499926.46 | 249985 | 0 | 2789792.38 | 289865.92 | 101 | 101 | 0 | 0 | 0
AUSTIN | 0015-11-073 | TRAVIS | SL 275 | 2024-06-17 | 1029125.18 | 1908.92 | 0 | 1229118.83 | 199993.65 | 20 | 8 | 0 | 0 | -12
BEAUMONT | 0065-08-169 | JEFFERSON | SS 380 | 2024-06-17 | 1948711.68 | -81552.18 | 0 | 1870632.58 | -78079.1 | 57 | 90 | 6 | 0 | 33
BEAUMONT | 0786-01-090 | JEFFERSON | FM 364 | 2024-06-17 | 871505.39 | 95822.87 | 0 | 956652.15 | 85146.76 | 112 | 110 | 0 | 0 | -2
BEAUMONT | 0920-00-143 | JEFFERSON | VA | 2024-06-17 | 1652630 | 3722.36 | 0 | 1643116 | -9514 | 120 | 141 | 22 | 0 | 21
CORPUS CHRISTI | 0359-04-005 | KARNES | SH 119 | 2024-06-17 | 20496430.47 | 114541.59 | 0 | 20339641.82 | -156788.65 | 465 | 478 | 16 | 0 | 13
CORPUS CHRISTI | 1069-01-035 | NUECES | SH 357 | 2024-06-17 | 3511807.35 | 64005.27 | 0 | 3672280.12 | 160472.77 | 275 | 380 | 96 | 0 | 105
CORPUS CHRISTI | 1558-02-039 | NUECES | FM 70 | 2024-06-17 | 89495 | 0 | 0 | 90815 | 1320 | 27 | 22 | 0 | 0 | -5
FORT WORTH | 0172-06-104 | TARRANT | US 287 | 2024-06-17 | 769999.99 | 98082.76 | 0 | 888893.23 | 118893.24 | 120 | 106 | 0 | 0 | -14
AUSTIN | 0015-08-413 | WILLIAMSON | IH 35 | 2024-06-18 | 1659187.06 | 0 | 0 | 1634120.81 | -25066.25 | 160 | 137 | 0 | 0 | -23
BRYAN | 0675-03-067 | LEON | IH 45 | 2024-06-18 | 1382171.2 | -22038.97 | 0 | 1394016.32 | 11845.12 | 45 | 56 | 11 | 0 | 11
CORPUS CHRISTI | 0100-05-187 | KARNES | US 181 | 2024-06-18 | 642568.81 | 1600.02 | 0 | 689591.61 | 47022.8 | 88 | 63 | 0 | 0 | -25
LAREDO | 0086-02-030 | WEBB | SH 359 | 2024-06-18 | 5168084.93 | 295028.05 | 0 | 5638738.68 | 470653.75 | 280 | 275 | 0 | 0 | -5
WACO | 0120-01-022 | HAMILTON | SH 22 | 2024-06-19 | 2190515.25 | 414614.59 | 0 | 2684112.09 | 493596.84 | 150 | 125 | 0 | 0 | -25
AMARILLO | 0067-17-036 | RANDALL | IH 27 | 2024-06-20 | 4296749.45 | 9272.74 | 0 | 4417078.87 | 120329.42 | 145 | 127 | 0 | 0 | -18
EL PASO | 0104-11-008 | PRESIDIO | US67 | 2024-06-20 | 3445494.35 | 7149.15 | 0 | 3476622.46 | 31128.11 | 120 | 76 | 0 | 0 | -44
ODESSA | 1189-01-020 | WINKLER | FM 874 | 2024-06-20 | 14858747.28 | -835066.86 | 0 | 15591973.89 | 733226.61 | 279 | 247 | 0 | 0 | -32
CHILDRESS | 0275-12-083 | WHEELER | IH 40 | 2024-06-24 | 3733819 | 3040 | 0 | 3720788.53 | -13030.47 | 172 | 86 | 0 | 0 | -86
HOUSTON | 1685-05-123 | HARRIS | SH 6 | 2024-06-24 | 207829.21 | 30180.86 | 0 | 248625.32 | 40796.11 | 35 | 31 | 0 | 0 | -4
HOUSTON | 2523-02-071 | BRAZORIA | FM 2004 | 2024-06-24 | 4976855.49 | 7377 | 0 | 4138395.96 | -838459.53 | 111 | 109 | 0 | 0 | -2
LAREDO | 0922-33-204 | WEBB | VA | 2024-06-24 | 548397.72 | 102101.42 | 0 | 651940.23 | 103542.51 | 79 | 74 | 0 | 0 | -5
SAN ANTONIO | 0025-02-225 | BEXAR | IH 10 | 2024-06-24 | 1631615 | 0 | 0 | 1634329.4 | 2714.4 | 96 | 63 | 0 | 0 | -33
SAN ANTONIO | 0915-12-574 | BEXAR | Various | 2024-06-24 | 2791621.98 | 49652.63 | 0 | 2671795.16 | -119826.82 | 204 | 174 | 0 | 0 | -30
CORPUS CHRISTI | 0100-13-027 | BEE | BU 181J | 2024-06-25 | 841761.6 | 23444 | 0 | 758083.98 | -83677.62 | 195 | 163 | 0 | 0 | -32
HOUSTON | 0508-01-381 | HARRIS | IH 10 | 2024-06-25 | 655025 | 0 | 0 | 762210 | 107185 | 45 | 44 | 0 | 0 | -1
AMARILLO | 0904-02-047 | POTTER | Various | 2024-06-26 | 1974345.8 | 0 | 0 | 2262530.38 | 288184.58 | 194 | 205 | 0 | 0 | 11
SAN ANTONIO | 0915-12-664 | BEXAR | VA | 2024-06-26 | 5046004.49 | 224378.84 | 0 | 5492827.21 | 446822.72 | 160 | 237 | 77 | 0 | 77
DALLAS | 0918-47-215 | DALLAS | CS | 2024-06-27 | 1886400 | 0 | 0 | 1837593.96 | -48806.04 | 367 | 507 | 0 | 0 | 140
ODESSA | 3571-02-008 | MIDLAND | SS 588 | 2024-06-27 | 5214762.69 | 46407.35 | 0 | 5271413.32 | 56650.63 | 108 | 135 | 59 | 0 | 27
WACO | 0048-09-029 | HILL | IH 35E | 2024-06-27 | 117517085.98 | -3399090.83 | 0 | 114461646.89 | -3055439.09 | 1090 | 1089 | 0 | 0 | -1
DALLAS | 0092-07-061 | DALLAS | SH 356 | 2024-06-28 | 599968 | 0 | 0 | 589370.65 | -10597.35 | 60 | 53 | 0 | 0 | -7
DALLAS | 0430-01-065 | DALLAS | SH 352 | 2024-06-28 | 3443569.1 | 214058.17 | 0 | 3774579.46 | 331010.36 | 113 | 120 | 10 | 0 | 7
DALLAS | 1391-01-022 | COLLIN | FM 1377 | 2024-06-28 | 8279604.06 | 81513.47 | 0 | 7857681.54 | -421922.52 | 255 | 256 | 0 | 0 | 1
PARIS | 0399-03-038 | DELTA | FM 64 | 2024-07-01 | 4061048.66 | 478621.5 | 0 | 4667501.42 | 606452.76 | 224 | 256 | 32 | 0 | 32
WACO | 0015-01-243 | MCLENNAN | IH 35 | 2024-07-01 | 341215000 | 28741566.54 | 0 | 385784049.82 | 44569049.82 | 1150 | 1150 | 0 | 0 | 0
WACO | 0162-01-102 | MCLENNAN | SH 31 | 2024-07-01 | 993388.75 | -68419.17 | 0 | 898494.83 | -94893.92 | 45 | 37 | 0 | 0 | -8
HOUSTON | 0177-14-037 | MONTGOMERY | SL 494 | 2024-07-02 | 1321754.75 | 144777.18 | 0 | 1813869.7 | 492114.95 | 92 | 86 | 0 | 0 | -6
LUFKIN | 0911-00-109 | ANGELINA | VA | 2024-07-02 | 4639696.67 | 5379 | 0 | 4344272.06 | -295424.61 | 193 | 210 | 25 | 0 | 17
YOAKUM | 0025-05-024 | GONZALES | UA 90 | 2024-07-02 | 18739124.79 | 1270659.64 | 0 | 17982565.82 | -756558.97 | 75 | 90 | 19 | 0 | 15
YOAKUM | 0089-19-011 | VICTORIA | BU 59-T | 2024-07-02 | 3807959.04 | -61702.39 | 0 | 3665002.88 | -142956.16 | 90 | 50 | 0 | 0 | -40
YOAKUM | 0370-04-033 | VICTORIA | US 77 | 2024-07-02 | 9370793.24 | -93957.33 | 0 | 9933300.13 | 562506.89 | 120 | 91 | 0 | 0 | -29
YOAKUM | 0913-09-116 | WHARTON | Various | 2024-07-02 | 664041.5 | 0 | 0 | 590707.7 | -73333.8 | 120 | 115 | 0 | 0 | -5
AUSTIN | 0700-04-051 | LLANO | SH 71 | 2024-07-03 | 2134103.64 | 0 | 0 | 2147166.29 | 13062.65 | 75 | 23 | 0 | 0 | -52
AUSTIN | 3545-01-005 | HAYS | FM 110 | 2024-07-03 | 36556399.89 | 2670314.1 | 2618867.2 | 39654079.39 | 478812.3 | 475 | 440 | 0 | 0 | -35
EL PASO | 0358-01-030 | JEFF DAVIS | SH 118 | 2024-07-03 | 249571.5 | 62336 | 0 | 311906.5 | 62335 | 73 | 58 | 0 | 0 | -15
EL PASO | 2451-02-013 | CULBERSON | RM 652 | 2024-07-03 | 49745889.15 | 496754.43 | 0 | 50386799.81 | 640910.66 | 480 | 544 | 59 | 0 | 64
AUSTIN | 1200-02-035 | TRAVIS | FM 973 | 2024-07-08 | 2000249.03 | -90002.73 | 0 | 2014195.52 | 13946.49 | 39 | 17 | 0 | 0 | -22
BRYAN | 0186-01-025 | MILAM | SH 36 | 2024-07-09 | 557417.55 | 0 | 0 | 533350.96 | -24066.59 | 55 | 81 | 21 | 0 | 26
TYLER | 0910-16-122 | SMITH | PW | 2024-07-09 | 855380.51 | -19552.35 | 0 | 808880.65 | -46499.86 | 88 | 34 | 0 | 0 | -54
AUSTIN | 0396-02-029 | MASON | US 377 | 2024-07-10 | 6087039.57 | -37593.08 | 0 | 6064256.22 | -22783.35 | 83 | 83 | 0 | 0 | 0
CORPUS CHRISTI | 0100-06-065 | KARNES | US 181 | 2024-07-10 | 15738942.46 | 2425771.91 | 0 | 19014529.31 | 3275586.85 | 204 | 390 | 186 | 0 | 186
CORPUS CHRISTI | 0155-04-055 | GOLIAD | US 183 | 2024-07-10 | 31126365.1 | 323936.86 | 0 | 31939558.93 | 813193.83 | 461 | 466 | 6 | 0 | 5
LAREDO | 1545-02-023 | LA SALLE | FM 468 | 2024-07-11 | 15239642.92 | 379798.46 | 0 | 16120332.45 | 880689.53 | 497 | 450 | -21 | 0 | -47
LAREDO | 2660-01-011 | DIMMIT | FM 2688 | 2024-07-11 | 10393728.82 | 17865.32 | 0 | 10537271.05 | 143542.23 | 305 | 305 | 0 | 0 | 0
LUBBOCK | 0227-06-032 | HOCKLEY | US 385 | 2024-07-11 | 120496 | 0 | 0 | 143515.75 | 23019.75 | 73 | 32 | 0 | 0 | -41
ODESSA | 0139-04-045 | REEVES | US 285 | 2024-07-11 | 31638493.38 | 7439794.81 | 0 | 39021363.9 | 7382870.52 | 480 | 1124 | 149 | 0 | 644
SAN ANTONIO | 0915-00-198 | BEXAR | VA | 2024-07-11 | 1588564.78 | 156247.25 | 0 | 1579032.09 | -9532.69 | 320 | 258 | 0 | 0 | -62
PARIS | 0045-18-044 | GRAYSON | US 82 | 2024-07-12 | 1851966.7 | 18715.45 | 0 | 2026267.45 | 174300.75 | 78 | 78 | 0 | 0 | 0
PARIS | 0901-19-214 | GRAYSON | CR | 2024-07-12 | 999795.82 | 16856 | 0 | 1003938.52 | 4142.7 | 128 | 105 | 0 | 0 | -23
YOAKUM | 0913-27-091 | VICTORIA | CS | 2024-07-12 | 50135.5 | -2065 | 0 | 47920.5 | -2215 | 15 | 13 | 0 | 0 | -2
AUSTIN | 0265-02-045 | TRAVIS | SH 71 | 2024-07-14 | 2068353.64 | 10501.72 | 0 | 2373430.33 | 305076.69 | 54 | 18 | 0 | 0 | -36
EL PASO | 0233-04-016 | CULBERSON | SH 54 | 2024-07-15 | 5340874.6 | 249820.5 | 0 | 5487919.45 | 147044.85 | 200 | 168 | 0 | 0 | -32
LUFKIN | 0176-04-087 | POLK | US 59 | 2024-07-15 | 6239710.19 | 21838.32 | 0 | 6258574.75 | 18864.56 | 174 | 229 | 18 | 0 | 55
WICHITA FALLS | 0137-10-026 | CLAY | FM 174 | 2024-07-15 | 4557308.85 | 628311.42 | 0 | 5226168.12 | 668859.27 | 187 | 103 | 0 | 0 | -84
CHILDRESS | 0098-05-034 | KNOX | SH 6 | 2024-07-16 | 4247603.88 | 31158.92 | 0 | 4391953.8 | 144349.92 | 143 | 159 | 1 | 0 | 16
HOUSTON | 0912-73-223 | GALVESTON | Various | 2024-07-16 | 4496853.15 | -154014.68 | 0 | 3693060.63 | -803792.52 | 296 | 201 | 0 | 0 | -95
ODESSA | 0003-08-064 | REEVES | BI 20B | 2024-07-16 | 1033761.5 | -11934.5 | 0 | 1041058 | 7296.5 | 102 | 102 | 0 | 0 | 0
ODESSA | 0906-00-217 | ECTOR | Various | 2024-07-16 | 3409957.44 | 831474.08 | 0 | 4171893.2 | 761935.76 | 134 | 108 | 0 | 0 | -26
DALLAS | 0260-02-051 | ELLIS | US 67 | 2024-07-17 | 1035719.22 | 0 | 0 | 1078112.09 | 42392.87 | 119 | 91 | 0 | 0 | -28
FORT WORTH | 0008-02-073 | PARKER | US 180 | 2024-07-17 | 2139284.22 | -27793.59 | 0 | 2085092.46 | -54191.76 | 216 | 558 | 37 | 0 | 342
AUSTIN | 0289-07-021 | LLANO | SH 16 | 2024-07-18 | 5354596.06 | 25792 | 0 | 5188912.06 | -165684 | 104 | 96 | 0 | 0 | -8
DALLAS | 0092-01-057 | DALLAS | SH 310 | 2024-07-18 | 13814473.34 | 912078.87 | 0 | 15969533.19 | 2155059.85 | 593 | 689 | 77 | 0 | 96
DALLAS | 0092-03-057 | ELLIS | IH 45 | 2024-07-18 | 2668749.3 | 232152.24 | 0 | 2783397.64 | 114648.34 | 180 | 195 | 15 | 0 | 15
EL PASO | 0674-01-071 | EL PASO | FM 76 | 2024-07-18 | 2492425.85 | 80624.22 | 0 | 2341584.87 | -150840.98 | 120 | 120 | 0 | 0 | 0
WICHITA FALLS | 0903-06-022 | CLAY | Various | 2024-07-18 | 2547006.8 | 385199.57 | 0 | 2917467.72 | 370460.92 | 85 | 98 | 30 | 0 | 13
CORPUS CHRISTI | 0180-02-041 | REFUGIO | SH 35 | 2024-07-19 | 4992797.8 | 68148.71 | 0 | 5036999.87 | 44202.07 | 129 | 245 | 116 | 0 | 116
DALLAS | 1013-01-038 | COLLIN | FM 546 | 2024-07-19 | 3312753.83 | 119224.35 | 0 | 3453258.54 | 140504.71 | 90 | 134 | 46 | 0 | 44
DALLAS | 2374-03-091 | DALLAS | IH 20 | 2024-07-19 | 15308302.66 | 892753.04 | 0 | 15998176.72 | 689874.06 | 226 | 309 | 50 | 0 | 83
YOAKUM | 0089-19-014 | VICTORIA | BU 59-T | 2024-07-19 | 3461134.5 | -109152 | 0 | 3348852.78 | -112281.72 | 285 | 312 | 30 | 0 | 27
YOAKUM | 0265-14-008 | FAYETTE | BS 71-E | 2024-07-19 | 13635356.23 | 80943.1 | 0 | 13448782.29 | -186573.94 | 450 | 450 | 0 | 0 | 0
AUSTIN | 0015-09-202 | WILLIAMSON | IH 35 | 2024-07-22 | 1348346.67 | 0 | 0 | 1433000.53 | 84653.86 | 46 | 46 | 0 | 0 | 0
FORT WORTH | 0008-14-119 | TARRANT | IH 820 | 2024-07-22 | 10558103.16 | 794207.37 | 0 | 10733779.21 | 175676.05 | 278 | 341 | 83 | 0 | 63
EL PASO | 0233-05-038 | CULBERSON | SH 54 | 2024-07-23 | 6330873.7 | 620387.7 | 0 | 6783031.53 | 452157.83 | 211 | 182 | 0 | 0 | -29
FORT WORTH | 0747-04-078 | TARRANT | FM 157 | 2024-07-23 | 407983 | 65260.14 | 0 | 473115.54 | 65132.54 | 43 | 46 | 0 | 0 | 3
HOUSTON | 0110-05-126 | HARRIS | IH 45 | 2024-07-23 | 6683533.8 | 4971667.96 | 0 | 11512793.58 | 4829259.78 | 591 | 591 | 0 | 0 | 0
PARIS | 2003-03-007 | DELTA | FM 2675 | 2024-07-23 | 1592112.64 | 104937.31 | 0 | 1826866.31 | 234753.67 | 140 | 159 | 19 | 0 | 19
ABILENE | 0005-06-121 | HOWARD | IH 20 | 2024-07-24 | 8336656.83 | 0 | 0 | 8951275.97 | 614619.14 | 106 | 106 | 0 | 0 | 0
AMARILLO | 0275-01-221 | POTTER | IH 40 | 2024-07-24 | 13120890.35 | -492215.32 | 0 | 12984680.1 | -136210.25 | 145 | 157 | 0 | 0 | 12
AUSTIN | 0287-01-017 | CALDWELL | SH 80 | 2024-07-24 | 1012428.69 | 66931 | 0 | 990909.84 | -21518.85 | 56 | 37 | 7 | 0 | -19
PARIS | 0772-01-034 | RED RIVER | FM 410 | 2024-07-24 | 1196866.8 | -111695.29 | 0 | 1159662.52 | -37204.28 | 112 | 112 | 14 | 0 | 0
AUSTIN | 0473-02-041 | LEE | SH 21 | 2024-07-25 | 1219930 | 63999.79 | 0 | 1501295.58 | 281365.58 | 300 | 288 | 2 | 0 | -12
HOUSTON | 1986-01-067 | MONTGOMERY | FM 1314 | 2024-07-25 | 4740080.6 | -502871.44 | 0 | 4786833.24 | 46752.64 | 98 | 88 | 0 | 0 | -10
BEAUMONT | 0028-15-059 | ORANGE | BU 90Y | 2024-07-26 | 2977919.3 | 105939.85 | 0 | 3000399.34 | 22480.04 | 69 | 94 | 18 | 0 | 25
FORT WORTH | 2208-01-070 | TARRANT | SS 303 | 2024-07-26 | 3172002.5 | -10380.1 | 0 | 3194375.76 | 22373.26 | 192 | 464 | 190 | 0 | 272
HOUSTON | 1006-01-080 | HARRIS | FM 529 | 2024-07-26 | 355217.2 | 7404.67 | 0 | 356925.62 | 1708.42 | 30 | 24 | 0 | 0 | -6
DALLAS | 1567-02-037 | DENTON | FM 423 | 2024-07-29 | 252000 | 0 | 0 | 230173.97 | -21826.03 | 45 | 19 | 0 | 0 | -26
HOUSTON | 0111-09-044 | BRAZORIA | BS 288B | 2024-07-29 | 3933801.94 | 229459.02 | 0 | 4557974.05 | 624172.11 | 144 | 143 | 3 | 0 | -1
TYLER | 0392-08-023 | GREGG | SS 502 | 2024-07-29 | 330073 | 0 | 0 | 350636.01 | 20563.01 | 53 | 45 | 0 | 0 | -8
WACO | 0909-00-062 | MCLENNAN | Various | 2024-07-29 | 3216348.55 | 489488.37 | 0 | 3636961.54 | 420612.99 | 105 | 124 | 19 | 0 | 19
WACO | 0909-29-046 | HAMILTON | CR | 2024-07-29 | 906655.8 | 0 | 0 | 887568.62 | -19087.18 | 75 | 118 | 43 | 0 | 43
WICHITA FALLS | 0124-02-033 | WILBARGER | US 283 | 2024-07-29 | 6216761.98 | -17429.78 | 0 | 6417254.31 | 200492.33 | 61 | 101 | 7 | 0 | 40
WICHITA FALLS | 0391-04-030 | CLAY | SH 148 | 2024-07-29 | 3432425.5 | 0 | 0 | 3357190.26 | -75235.24 | 181 | 225 | 0 | 0 | 44
AMARILLO | 0030-02-052 | OCHILTREE | US 83 | 2024-07-30 | 13814377.45 | 758279.84 | 0 | 16622316.46 | 2807939.01 | 134 | 224 | 35 | 0 | 90
AMARILLO | 0356-02-048 | CARSON | SH 207 | 2024-07-30 | 1042468 | -633.91 | 0 | 1221459.87 | 178991.87 | 129 | 131 | 1 | 0 | 2
HOUSTON | 0686-02-029 | GALVESTON | FM 1765 | 2024-07-30 | 1425058.66 | 17082.58 | 0 | 1427214.47 | 2155.81 | 60 | 59 | 0 | 0 | -1
LAREDO | 0038-01-096 | WEBB | US 83 | 2024-07-30 | 812476.55 | 51811.41 | 0 | 848978.17 | 36501.62 | 153 | 99 | 0 | 0 | -54
LUBBOCK | 0905-12-043 | HALE | CS | 2024-07-30 | 847027.77 | 8000 | 0 | 822898.35 | -24129.42 | 109 | 166 | 33 | 0 | 57
PARIS | 0009-13-183 | HUNT | IH 30 | 2024-07-30 | 1994205 | 361980.61 | 0 | 2312033.31 | 317828.31 | 335 | 91 | 0 | 0 | -244
PHARR | 0038-03-041 | ZAPATA | US 83 | 2024-07-30 | 2749448.88 | 68268.61 | 0 | 2734678.53 | -14770.35 | 320 | 332 | 16 | 0 | 12
ODESSA | 0005-01-115 | ECTOR | BI 20E | 2024-08-01 | 1351826.35 | 131571.74 | 0 | 1686682.15 | 334855.8 | 106 | 120 | 15 | 0 | 14
SAN ANTONIO | 2975-01-009 | ATASCOSA | FM 2924 | 2024-08-01 | 7308202.92 | -18712.91 | 0 | 7381755.54 | 73552.62 | 456 | 402 | 0 | 0 | -54
DALLAS | 0047-07-228 | DALLAS | US 75 | 2024-08-02 | 9295242.38 | 1887148.15 | 1012428.02 | 10935843.82 | 628173.42 | 420 | 709 | 287 | 0 | 289
HOUSTON | 0912-72-391 | HARRIS | CS | 2024-08-02 | 20384046.95 | 761729 | 655515.2 | 22327149 | 1287586.85 | 671 | 666 | 0 | 0 | -5
ABILENE | 0437-04-034 | CALLAHAN | US 283 | 2024-08-05 | 3377698.15 | -138.5 | 0 | 3334745.16 | -42952.99 | 137 | 118 | 0 | 0 | -19
YOAKUM | 0026-03-042 | FAYETTE | US 90 | 2024-08-05 | 831842.19 | 0 | 0 | 860016.03 | 28173.84 | 60 | 99 | 39 | 0 | 39
YOAKUM | 0026-06-035 | COLORADO | US 90 | 2024-08-05 | 16624783.2 | 685821.28 | 0 | 15332788.78 | -1291994.42 | 75 | 73 | 2 | 0 | -2
YOAKUM | 0089-07-146 | WHARTON | US 59 | 2024-08-05 | 34757444.76 | 1003193.15 | 0 | 36182699.04 | 1425254.28 | 450 | 479 | 29 | 0 | 29
YOAKUM | 0408-05-028 | AUSTIN | FM 331 | 2024-08-05 | 5302541.13 | 111965.83 | 0 | 5389338.17 | 86797.04 | 245 | 245 | 0 | 0 | 0
YOAKUM | 0446-03-047 | COLORADO | US 90A | 2024-08-05 | 12487777.17 | 673902.01 | 0 | 13042088.34 | 554311.17 | 396 | 396 | 0 | 0 | 0
YOAKUM | 0573-04-017 | GONZALES | FM 1116 | 2024-08-05 | 3364665.43 | 57500 | 0 | 3395275.82 | 30610.39 | 139 | 232 | 77 | 0 | 93
FORT WORTH | 0353-01-027 | WISE | SH 114 | 2024-08-06 | 919578.95 | 0 | 0 | 895554.7 | -24024.25 | 106 | 100 | 0 | 0 | -6
PARIS | 0410-02-038 | GRAYSON | SH 160 | 2024-08-06 | 7831624.15 | 522707.34 | 0 | 8706420.24 | 874796.09 | 147 | 147 | 0 | 0 | 0
TYLER | 0646-02-029 | VAN ZANDT | FM 47 | 2024-08-06 | 4537223.82 | -309118.48 | 0 | 3685466.8 | -851757.02 | 338 | 354 | 16 | 0 | 16
PHARR | 2094-01-071 | HIDALGO | FM 2220 | 2024-08-07 | 809835.4 | 34952.08 | 0 | 892780.55 | 82945.15 | 45 | 35 | 0 | 0 | -10
SAN ANTONIO | 0016-04-117 | COMAL | IH 35 | 2024-08-08 | 63795147.3 | 6776724.63 | 0 | 72147122.67 | 8351975.37 | 659 | 812 | 156 | 0 | 153
AMARILLO | 0226-02-038 | OLDHAM | US 385 | 2024-08-09 | 9766079.71 | 369600.85 | 0 | 10764678.12 | 998598.41 | 150 | 150 | 0 | 0 | 0
HOUSTON | 3510-05-045 | HARRIS | SH 99 | 2024-08-09 | 3484500 | 100000 | 0 | 3495054.55 | 10554.55 | 210 | 177 | 0 | 0 | -33
BEAUMONT | 0920-00-153 | JEFFERSON | Various | 2024-08-12 | 865128.5 | 18750 | 0 | 871381.31 | 6252.81 | 45 | 31 | 0 | 0 | -14
CORPUS CHRISTI | 0255-01-090 | JIM WELLS | US 281 | 2024-08-12 | 4570094.51 | 31346.42 | 0 | 4427068.64 | -143025.87 | 66 | 53 | 0 | 0 | -13
BRYAN | 0917-00-067 | BRAZOS | Various | 2024-08-13 | 244435 | 50364.8 | 0 | 410803.48 | 166368.48 | 30 | 38 | 8 | 0 | 8
SAN ANTONIO | 1122-04-012 | WILSON | FM 1344 | 2024-08-13 | 6200914.49 | 1013454.5 | 0 | 6822099.47 | 621184.98 | 445 | 326 | 59 | 0 | -119
AUSTIN | 0836-01-016 | WILLIAMSON | SH 195 | 2024-08-14 | 2348911.02 | 0 | 0 | 2305080.82 | -43830.2 | 254 | 54 | 0 | 0 | -200
AUSTIN | 3210-01-020 | HAYS | FM 2770 | 2024-08-14 | 294471.78 | 15880.63 | 0 | 307606.96 | 13135.18 | 13 | 10 | 0 | 0 | -3
WACO | 0015-01-253 | MCLENNAN | IH 35 | 2024-08-14 | 6126287.1 | 330849.64 | 0 | 6851287.92 | 725000.82 | 148 | 148 | 0 | 0 | 0
FORT WORTH | 2737-01-020 | PARKER | FM 2257 | 2024-08-15 | 152432.36 | 47272.92 | 0 | 187660.27 | 35227.91 | 60 | 52 | 0 | 0 | -8
SAN ANTONIO | 0017-02-080 | BEXAR | IH 35 | 2024-08-15 | 486978.82 | 51658.58 | 0 | 568803.36 | 81824.54 | 235 | 222 | 10 | 0 | -13
AUSTIN | 0683-01-056 | WILLIAMSON | RM 620 | 2024-08-16 | 27468703.67 | 1979024.43 | 24073.71 | 31979826.17 | 4487048.79 | 505 | 604 | 99 | 5 | 94
BRYAN | 0917-29-133 | BRAZOS | CS | 2024-08-16 | 1198243.6 | 43315.17 | 10248.88 | 1256800.17 | 48307.69 | 223 | 133 | 0 | 0 | -90
BRYAN | 2850-01-018 | WALKER | FM 2821 | 2024-08-16 | 2117590.12 | 578011.16 | 0 | 2606129.17 | 488539.05 | 79 | 109 | 0 | 0 | 30
DALLAS | 0081-03-048 | DENTON | US 377 | 2024-08-16 | 33684843.68 | 2049910.53 | 27234.15 | 35748267.98 | 2036190.15 | 959 | 1060 | 102 | 0 | 101
DALLAS | 0092-03-063 | ELLIS | IH 45 | 2024-08-16 | 2192848.5 | 60446.83 | 0 | 2267958.56 | 75110.06 | 137 | 134 | 0 | 0 | -3
FORT WORTH | 0314-07-080 | PARKER | IH 20 | 2024-08-16 | 365891.5 | 2787.58 | 0 | 354214.52 | -11676.98 | 85 | 75 | 0 | 0 | -10
AUSTIN | 0251-08-033 | BURNET | US 281 | 2024-08-19 | 3623788.93 | -14394.8 | 0 | 3755427.19 | 131638.26 | 66 | 66 | 0 | 0 | 0
AUSTIN | 0252-01-079 | BURNET | US 281 | 2024-08-19 | 5323845.57 | 73796.05 | 0 | 5813061.46 | 489215.89 | 96 | 96 | 0 | 0 | 0
DALLAS | 0619-01-026 | COLLIN | FM 6 | 2024-08-19 | 9710335.03 | 695677.06 | 0 | 9708143.85 | -2191.18 | 310 | 239 | 0 | 0 | -71
SAN ANTONIO | 1437-02-016 | WILSON | FM 1346 | 2024-08-19 | 853370.48 | 9051.01 | 0 | 867128.55 | 13758.07 | 59 | 59 | 0 | 0 | 0
WACO | 0909-36-190 | BELL | CS | 2024-08-19 | 236667.36 | 26282 | 0 | 263546.75 | 26879.39 | 60 | 56 | 0 | 0 | -4
AUSTIN | 0914-00-471 | TRAVIS | Various | 2024-08-20 | 549976.13 | 640478.04 | 0 | 1013511.29 | 463535.16 | 86 | 63 | 40 | 0 | -23
DALLAS | 0047-06-174 | COLLIN | US 75 | 2024-08-20 | 1497240 | 7000 | 0 | 1503830.25 | 6590.25 | 99 | 103 | 21 | 0 | 4
EL PASO | 2121-02-182 | EL PASO | IH 10 | 2024-08-20 | 722722 | 146221.37 | 0 | 878031.08 | 155309.08 | 51 | 33 | 0 | 0 | -18
WACO | 0909-00-089 | MCLENNAN | Various | 2024-08-21 | 2409825.67 | -75511.7 | 0 | 2380902.84 | -28922.83 | 30 | 30 | 0 | 0 | 0
WACO | 0909-36-165 | BELL | CS | 2024-08-21 | 881150 | 95863.81 | 0 | 1007831.15 | 126681.15 | 45 | 104 | 53 | 0 | 59
ABILENE | 0558-03-028 | BORDEN | FM 669 | 2024-08-22 | 3149253.9 | 128358.04 | 0 | 3229245.8 | 79991.9 | 67 | 81 | 16 | 0 | 14
CORPUS CHRISTI | 0073-14-009 | LIVE OAK | UA 281 | 2024-08-22 | 6776929.86 | 262410.72 | 0 | 6586059.21 | -190870.65 | 41 | 44 | 0 | 0 | 3
FORT WORTH | 0364-01-158 | TARRANT | SH 121 | 2024-08-22 | 168145.55 | 42748 | 0 | 208172.45 | 40026.9 | 43 | 38 | 0 | 0 | -5
BEAUMONT | 0028-03-109 | LIBERTY | US 90 | 2024-08-23 | 1615491.38 | -422459.06 | 0 | 1208597.93 | -406893.45 | 116 | 118 | 0 | 0 | 2
BEAUMONT | 0389-01-044 | LIBERTY | SH 146 | 2024-08-23 | 9934425.44 | -350057.56 | 0 | 10682147.68 | 747722.24 | 142 | 120 | 0 | 0 | -22
BRYAN | 0917-30-054 | BURLESON | CR | 2024-08-23 | 946424.73 | -56592 | 0 | 865954.12 | -80470.61 | 84 | 88 | 0 | 0 | 4
CHILDRESS | 0043-01-083 | CHILDRESS | US 287 | 2024-08-23 | 6175663.87 | 74624.43 | 0 | 6839238.85 | 663574.98 | 62 | 135 | 74 | 0 | 73
CHILDRESS | 0133-01-049 | KING | US 82 | 2024-08-23 | 5768975.82 | 214043.05 | 0 | 6527906.26 | 758930.44 | 141 | 184 | 3 | 0 | 43
HOUSTON | 0050-04-030 | WALLER | SH 6 | 2024-08-23 | 1561386.5 | 0 | 0 | 1542213.81 | -19172.69 | 127 | 34 | 0 | 0 | -93
HOUSTON | 0912-72-360 | HARRIS | CS | 2024-08-23 | 23186628.88 | 1390884.35 | 1390884.35 | 24477049.4 | -100463.83 | 464 | 462 | 0 | 0 | -2
AMARILLO | 0308-01-013 | HANSFORD | SH 207 | 2024-08-26 | 7907129.6 | 54656.48 | 0 | 8292669.94 | 385540.34 | 387 | 288 | 4 | 0 | -99
AUSTIN | 0286-01-062 | HAYS | SH 80 | 2024-08-26 | 1292122.8 | 70765.66 | 0 | 1396858.22 | 104735.42 | 146 | 146 | 0 | 0 | 0
DALLAS | 0172-04-048 | ELLIS | US 287 | 2024-08-26 | 3186711.85 | 55178.13 | 0 | 3050651.59 | -136060.26 | 309 | 256 | 0 | 0 | -53
DALLAS | 1014-02-043 | ROCKWALL | FM 548 | 2024-08-26 | 4090390.33 | -69260.98 | 0 | 3609530.06 | -480860.27 | 102 | 118 | 0 | 0 | 16
WICHITA FALLS | 0044-09-067 | COOKE | FM 1199 | 2024-08-27 | 5027472.98 | -9159.99 | 0 | 5007419.32 | -20053.66 | 238 | 350 | 5 | 0 | 112
ATLANTA | 0248-01-082 | TITUS | SH 49 | 2024-08-28 | 2881429.5 | 6200.4 | 0 | 2691652.66 | -189776.84 | 52 | 52 | 0 | 0 | 0
ATLANTA | 0919-00-085 | CASS | Various | 2024-08-28 | 2925770.24 | 59526.32 | 0 | 3059096.52 | 133326.28 | 102 | 66 | 0 | 0 | -36
AUSTIN | 0914-05-137 | WILLIAMSON | CR | 2024-08-28 | 125524 | 0 | 0 | 123449 | -2075 | 37 | 22 | 0 | 0 | -15
LUBBOCK | 0228-02-049 | GAINES | US 62 | 2024-08-28 | 17980800 | 355935.99 | 0 | 18014440.76 | 33640.76 | 488 | 473 | 16 | 0 | -15
PHARR | 0862-01-057 | HIDALGO | FM 492 | 2024-08-29 | 1917663.5 | 0 | 0 | 1898973.67 | -18689.83 | 159 | 197 | 0 | 0 | 38
WICHITA FALLS | 0903-00-122 | WICHITA | Various | 2024-08-29 | 1041194 | 90000 | 0 | 1173141.1 | 131947.1 | 68 | 52 | 0 | 0 | -16
AUSTIN | 0334-05-035 | LEE | FM 141 | 2024-08-30 | 3387873.98 | -417105.67 | 0 | 2949400.61 | -438473.37 | 85 | 36 | 0 | 0 | -49
AUSTIN | 1060-01-012 | CALDWELL | FM 671 | 2024-08-30 | 2089053.31 | 0 | 0 | 2049449.79 | -39603.52 | 160 | 193 | 0 | 0 | 33
BROWNWOOD | 0007-06-258 | EASTLAND | IH 20 | 2024-08-30 | 606937.92 | 5625.47 | 0 | 631317.13 | 24379.21 | 17 | 109 | 13 | 0 | 92
BROWNWOOD | 0054-04-123 | COLEMAN | US 84 | 2024-08-30 | 2976495.11 | 91277.25 | 0 | 3049686.48 | 73191.37 | 113 | 113 | 0 | 0 | 0
BROWNWOOD | 0923-06-095 | BROWN | Various | 2024-08-30 | 1054719.19 | 30535.3 | 0 | 1104858.43 | 50139.24 | 93 | 83 | 0 | 0 | -10
BRYAN | 0540-08-008 | BRAZOS | SH 40 | 2024-08-30 | 2611581.83 | 284863.58 | 0 | 2794660.48 | 183078.65 | 204 | 238 | 0 | 0 | 34
BRYAN | 2447-01-033 | WASHINGTON | FM 577 | 2024-08-30 | 1013562.49 | 24626.61 | 0 | 998922.6 | -14639.89 | 56 | 77 | 0 | 0 | 21
FORT WORTH | 0008-01-046 | PALO PINTO | US 180 | 2024-08-30 | 5673196.48 | 363543.02 | 0 | 5100668.06 | -572528.42 | 342 | 263 | 0 | 0 | -79