## OTOB
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [13 empty] | Required Reporting per Texas Transportation Code §201.812 –
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | FEBRUARY | 28 | 2025 | 2024 | [6 empty] | Highway Construction Projects Completed September 1, 2024–February 28, 2025
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | CO BY THRD PRTY | AMOUNT PAID | UNDER OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | THIRD PARTY DAYS ADDED | UNDER OVER SCHEDULE
ABILENE | 0106-07-030 | HASKELL | SH 6 | 2025-02-28 | 1729616.69 | 397361 | 0 | 1945755.07 | 216138.38 | 124 | 286 | 100 | 0 | 162
ABILENE | 0908-27-006 | KENT | CR | 2025-02-27 | 878015 | 24358.4 | 0 | 880172.15 | 2157.15 | 89 | 89 | 0 | 0 | 0
ABILENE | 1360-01-030 | JONES | FM 1226 | 2025-02-20 | 1671853.75 | 0 | 0 | 1630600.65 | -41253.1 | 104 | 126 | 0 | 0 | 22
ABILENE | 0972-06-015 | HASKELL | FM 600 | 2025-02-03 | 2844984.65 | 0 | 0 | 2983799.43 | 138814.78 | 120 | 117 | 0 | 0 | -3
ABILENE | 0983-03-030 | NOLAN | FM 419 | 2025-02-03 | 3360261.38 | -119485.48 | 0 | 3421807.76 | 61546.38 | 94 | 79 | 0 | 0 | -15
ABILENE | 0006-04-080 | TAYLOR | IH 20 | 2025-01-23 | 12105731.79 | -24.84 | 0 | 12662770.77 | 557038.98 | 142 | 156 | 14 | 0 | 14
ABILENE | 0032-07-029 | STONEWALL | US 83 | 2025-01-17 | 19299562.06 | 67476.51 | 0 | 17886005.29 | -1413556.77 | 432 | 442 | 10 | 0 | 10
ABILENE | 0053-15-067 | NOLAN | FM 608 | 2025-01-09 | 8787859.33 | -465639.5 | 0 | 8072700.59 | -715158.74 | 263 | 274 | 11 | 0 | 11
ABILENE | 0437-01-025 | SHACKELFORD | US 283 | 2024-12-30 | 12676446.45 | 238500.44 | 0 | 11901429.7 | -775016.75 | 103 | 103 | 0 | 0 | 0
ABILENE | 0006-03-145 | NOLAN | IH 20 | 2024-12-27 | 2739348.25 | 47750 | 0 | 2778375.49 | 39027.24 | 161 | 160 | 0 | 0 | -1
ABILENE | 0908-33-106 | TAYLOR | CS | 2024-12-27 | 1316532.4 | 810980 | 0 | 1361029.67 | 44497.27 | 133 | 131 | 0 | 0 | -2
ABILENE | 0668-01-021 | HOWARD | FM 700 | 2024-12-18 | 588687 | -77100 | 0 | 521917 | -66770 | 38 | 56 | 0 | 0 | 18
ABILENE | 0296-01-039 | SCURRY | US 180 | 2024-11-25 | 3120194.7 | 0 | 0 | 3281803.41 | 161608.71 | 53 | 45 | 0 | 0 | -8
ABILENE | 2638-03-012 | CALLAHAN | SH 206 | 2024-11-25 | 1595477.54 | 0 | 0 | 1611398.68 | 15921.14 | 31 | 31 | 0 | 0 | 0
ABILENE | 0007-01-062 | CALLAHAN | IH 20 | 2024-11-20 | 7267838.13 | -648453.06 | 0 | 6357347.48 | -910490.65 | 191 | 197 | 15 | 0 | 6
ABILENE | 2597-01-008 | HOWARD | FM 2599 | 2024-11-20 | 5256051.97 | 54273.5 | 0 | 5633680.64 | 377628.67 | 121 | 180 | 0 | 0 | 59
ABILENE | 0908-23-053 | FISHER | CR | 2024-10-28 | 917198 | 65883 | 0 | 961219 | 44021 | 96 | 96 | 0 | 0 | 0
ABILENE | 0007-02-057 | CALLAHAN | IH 20 | 2024-10-22 | 5593534.43 | 41475.38 | 0 | 5875233.87 | 281699.44 | 152 | 156 | 5 | 0 | 4
ABILENE | 0006-05-117 | TAYLOR | IH 20 | 2024-10-16 | 9498596.31 | 175866.4 | 0 | 10353585.12 | 854988.81 | 240 | 348 | 40 | 0 | 108
ABILENE | 0407-06-047 | TAYLOR | US 277 | 2024-09-24 | 2639408.32 | -118410.62 | 0 | 2480617.87 | -158790.45 | 106 | 64 | 0 | 0 | -42
ABILENE | 1652-01-015 | FISHER | FM 419 | 2024-09-23 | 684071 | 0 | 0 | 663485 | -20586 | 74 | 51 | 0 | 0 | -23
ABILENE | 0908-21-039 | MITCHELL | CR | 2024-09-05 | 711084 | 0 | 0 | 711462.4 | 378.4 | 84 | 84 | 0 | 0 | 0
AMARILLO | 0030-07-022 | HEMPHILL | US 83 | 2025-02-27 | 5382629.98 | -48724.82 | 0 | 5644878.75 | 262248.77 | 71 | 62 | 0 | 0 | -9
AMARILLO | 0904-00-188 | POTTER | VA | 2025-02-03 | 1274691.7 | 135764.2 | 0 | 1402847.08 | 128155.38 | 214 | 214 | 0 | 0 | 0
AMARILLO | 1245-02-049 | POTTER | RM 1061 | 2025-01-13 | 12755021.41 | 117372.76 | 0 | 13377958.53 | 622937.12 | 288 | 311 | 10 | 0 | 23
AMARILLO | 1245-01-019 | OLDHAM | RM 1061 | 2024-12-31 | 18084714.17 | -223034.59 | 0 | 18757957.09 | 673242.92 | 332 | 326 | 6 | 0 | -6
AMARILLO | 1337-02-012 | LIPSCOMB | SH 23 | 2024-12-16 | 7414243.89 | 980074.07 | 0 | 8245860.29 | 831616.4 | 257 | 265 | 8 | 0 | 8
AMARILLO | 1819-01-015 | LIPSCOMB | FM 1920 | 2024-12-13 | 16356130.41 | 1804121.1 | 0 | 18093051.17 | 1736920.76 | 441 | 450 | 10 | 0 | 9
AMARILLO | 0041-02-016 | HARTLEY | US 385 | 2024-12-02 | 9656579.22 | 1326671.9 | 0 | 11122673.72 | 1466094.5 | 327 | 469 | 165 | 0 | 142
AMARILLO | 0904-00-232 | POTTER | Various | 2024-12-02 | 1635105 | -70990 | 0 | 1553315 | -81790 | 67 | 37 | 0 | 0 | -30
AMARILLO | 0275-01-199 | POTTER | IH 40 | 2024-11-21 | 50032707.74 | 1494118.8 | 0 | 53685534.42 | 3652826.68 | 575 | 974 | 168 | 0 | 399
AMARILLO | 0904-00-181 | POTTER | Various | 2024-11-15 | 1771464.25 | 29220 | 0 | 1866000.78 | 94536.53 | 194 | 122 | 0 | 0 | -72
AMARILLO | 0030-05-073 | HEMPHILL | US 60 | 2024-10-22 | 8566511.52 | 214509 | 0 | 9179770.01 | 613258.49 | 188 | 185 | 15 | 0 | -3
AMARILLO | 0169-02-068 | POTTER | US 60 | 2024-10-22 | 2207755 | 40274.87 | 0 | 2161342.01 | -46412.99 | 106 | 130 | 15 | 0 | 24
AMARILLO | 0397-01-045 | GRAY | SH 152 | 2024-10-16 | 15464360.41 | 380420.07 | 0 | 17561815.39 | 2097454.98 | 266 | 271 | 31 | 0 | 5
AMARILLO | 0090-05-111 | POTTER | IH 40 | 2024-10-03 | 4121379.4 | 0 | 0 | 4143239.09 | 21859.69 | 107 | 100 | 0 | 0 | -7
AMARILLO | 0904-00-213 | POTTER | Various | 2024-10-03 | 576034.65 | 0 | 0 | 576030.03 | -4.62 | 43 | 25 | 0 | 0 | -18
AMARILLO | 0042-03-044 | ARMSTRONG | US 287 | 2024-09-09 | 2102432.75 | 53509.2 | 0 | 2137603.46 | 35170.71 | 104 | 147 | 0 | 0 | 43
AMARILLO | 0169-03-039 | CARSON | US 60 | 2024-09-04 | 3699105.45 | 16867.91 | 0 | 3789077.89 | 89972.44 | 91 | 83 | 0 | 0 | -8
ATLANTA | 0919-00-093 | CASS | Various | 2025-02-26 | 134759 | 0 | 0 | 134145 | -614 | 20 | 8 | 0 | 0 | -12
ATLANTA | 0063-04-068 | PANOLA | US 59 | 2025-02-11 | 1105559.41 | 7825 | 0 | 1096061.62 | -9497.79 | 71 | 66 | 0 | 0 | -5
ATLANTA | 0096-03-075 | UPSHUR | US 80 | 2025-02-11 | 6277174.34 | 403397.36 | 0 | 6966176.19 | 689001.85 | 162 | 199 | 4 | 0 | 37
ATLANTA | 0010-12-075 | BOWIE | US 67 | 2024-12-13 | 1397827.97 | 0 | 0 | 1403519.39 | 5691.42 | 172 | 186 | 0 | 0 | 14
ATLANTA | 0248-05-065 | UPSHUR | US 271 | 2024-12-13 | 4881470.75 | 127363.92 | 0 | 5183042.62 | 301571.87 | 65 | 77 | 4 | 0 | 12
ATLANTA | 0218-03-094 | CASS | US 59 | 2024-12-04 | 7806579.99 | -85064.55 | 0 | 8906767.58 | 1100187.59 | 74 | 68 | 0 | 0 | -6
ATLANTA | 1511-01-013 | UPSHUR | FM 993 | 2024-11-20 | 1523718.09 | 27520 | 0 | 1622349.71 | 98631.62 | 103 | 65 | 4 | 0 | -38
ATLANTA | 0402-03-042 | HARRISON | SH 154 | 2024-10-02 | 3492422.9 | 64108 | 0 | 3448374.25 | -44048.65 | 197 | 176 | 0 | 0 | -21
ATLANTA | 0919-13-017 | PANOLA | CR | 2024-09-26 | 968856.5 | 50000 | 0 | 990490.18 | 21633.68 | 53 | 26 | 0 | 0 | -27
AUSTIN | 0016-16-028 | HAYS | RM 967 | 2025-02-28 | 8474686.36 | 483765.55 | 0 | 9067032.49 | 592346.13 | 320 | 240 | 0 | 0 | -80
AUSTIN | 0252-02-063 | BURNET | US 281 | 2025-02-25 | 597524.87 | 19017.13 | 0 | 691648.28 | 94123.41 | 79 | 73 | 10 | 0 | -6
AUSTIN | 0914-05-214 | WILLIAMSON | RONALD REAGAN BLVD | 2025-02-25 | 2006827.14 | 13265.53 | 0 | 2071820.98 | 64993.84 | 103 | 74 | 2 | 0 | -29
AUSTIN | 0914-18-120 | BASTROP | Various | 2025-02-24 | 4210981.85 | 113436.27 | 0 | 4176501.74 | -34480.11 | 279 | 225 | 0 | 0 | -54
AUSTIN | 0252-02-064 | BURNET | US 281 | 2025-02-18 | 5701426.3 | -198606.53 | 0 | 5411914.25 | -289512.05 | 72 | 57 | 2 | 0 | -15
AUSTIN | 0700-01-045 | BURNET | SH 71 | 2025-02-18 | 8763188.97 | 2393489.04 | 1567507.59 | 11694470.81 | 1363774.25 | 193 | 280 | 103 | 78 | 9
AUSTIN | 1378-03-039 | BURNET | RM 1431 | 2025-02-11 | 6275058.13 | -74485.43 | 0 | 5717124.87 | -557933.26 | 120 | 45 | 3 | 0 | -75
AUSTIN | 0914-18-107 | BASTROP | CR | 2025-02-07 | 1478746.42 | 53001.11 | 0 | 1500023.33 | 21276.91 | 79 | 130 | 28 | 0 | 51
AUSTIN | 0114-20-014 | TRAVIS | SL 212 | 2025-02-05 | 799753.9 | 10101.99 | 0 | 830885.08 | 31131.18 | 24 | 21 | 0 | 0 | -3
AUSTIN | 0150-04-046 | LLANO | SH 29 | 2025-02-05 | 7398988.99 | 999686.56 | 0 | 8798993.62 | 1400004.63 | 369 | 384 | 15 | 0 | 15
AUSTIN | 0204-02-036 | WILLIAMSON | US 79 | 2025-02-05 | 3840828.3 | 0 | 0 | 4168320.87 | 327492.57 | 68 | 37 | 0 | 0 | -31
AUSTIN | 0366-01-081 | HAYS | SH 123 | 2025-02-01 | 2331672.3 | 111777.54 | 0 | 2587105.89 | 255433.59 | 187 | 116 | 0 | 0 | -71
AUSTIN | 0384-04-034 | CALDWELL | FM 1854 | 2025-01-29 | 8806086.7 | 690144.5 | 0 | 9887536.59 | 1081449.89 | 188 | 55 | 3 | 0 | -133
AUSTIN | 2718-01-015 | TRAVIS | RM 2769 | 2025-01-29 | 2979802.82 | -80170.12 | 0 | 3523056.66 | 543253.84 | 53 | 47 | 0 | 0 | -6
AUSTIN | 0700-04-053 | LLANO | SH 71 | 2025-01-28 | 3798987.88 | 152051.64 | 0 | 4024014.96 | 225027.08 | 52 | 51 | 2 | 0 | -1
AUSTIN | 0112-03-036 | GILLESPIE | US 290 | 2025-01-21 | 3070929.9 | -74484.79 | 0 | 3033451.36 | -37478.54 | 57 | 53 | 0 | 0 | -4
AUSTIN | 1378-04-056 | BURNET | RM 1431 | 2025-01-21 | 7574977.47 | -152911.71 | 0 | 7990182.23 | 415204.76 | 145 | 108 | 0 | 0 | -37
AUSTIN | 0112-02-036 | GILLESPIE | US 290 | 2025-01-17 | 3888100.8 | -242004.5 | 0 | 4196993.75 | 308892.95 | 158 | 100 | 0 | 0 | -58
AUSTIN | 1534-01-020 | BLANCO | RM 1623 | 2025-01-17 | 976312.12 | 22132.42 | 0 | 915159.91 | -61152.21 | 25 | 12 | 0 | 0 | -13
AUSTIN | 0016-02-170 | HAYS | IH 35 | 2025-01-05 | 4186521.77 | -588359.93 | 0 | 4432691.41 | 246169.64 | 64 | 57 | 0 | 0 | -7
AUSTIN | 0914-00-457 | TRAVIS | Various | 2025-01-04 | 2965162.9 | 62548.01 | 0 | 3207664.18 | 242501.28 | 178 | 178 | 0 | 0 | 0
AUSTIN | 1753-01-017 | MASON | RM 1871 | 2024-12-19 | 4178807.04 | 71745.07 | 0 | 3982822.91 | -195984.13 | 182 | 441 | 108 | 0 | 259
AUSTIN | 0113-13-184 | TRAVIS | US 290 | 2024-12-17 | 2026821.23 | -46170.7 | 0 | 1974464.64 | -52356.59 | 48 | 18 | 0 | 0 | -30
AUSTIN | 0914-24-025 | BURNET | Various | 2024-12-17 | 1637722.85 | 143263.43 | 0 | 1879967.51 | 242244.66 | 68 | 118 | 50 | 0 | 50
AUSTIN | 0113-07-072 | HAYS | US 290 | 2024-12-16 | 1960789.39 | 132580.06 | 11546.72 | 2195536.22 | 223200.11 | 141 | 122 | 0 | 0 | -19
AUSTIN | 3417-03-021 | TRAVIS | FM 734 | 2024-12-13 | 5597210.35 | 616545.39 | 0 | 6272016.69 | 674806.34 | 155 | 155 | 0 | 0 | 0
AUSTIN | 0253-02-033 | BLANCO | US 281 | 2024-12-10 | 1151580.5 | -92138.87 | 0 | 989591.39 | -161989.11 | 88 | 82 | 0 | 0 | -6
AUSTIN | 0320-04-029 | WILLIAMSON | US 79 | 2024-12-03 | 5596125.31 | -46368.02 | 0 | 5926314.08 | 330188.77 | 112 | 99 | 0 | 0 | -13
AUSTIN | 0016-02-169 | HAYS | IH 35 | 2024-11-22 | 915988.85 | 0 | 0 | 841231.36 | -74757.49 | 23 | 5 | 0 | 0 | -18
AUSTIN | 2293-01-032 | HAYS | FM 2439 | 2024-11-20 | 958354.16 | 146633.41 | 0 | 1037314.21 | 78960.05 | 29 | 13 | 0 | 0 | -16
AUSTIN | 0914-00-455 | TRAVIS | VA | 2024-11-14 | 1305817.91 | 122372.23 | 0 | 1511179.01 | 205361.1 | 218 | 159 | 0 | 0 | -59
AUSTIN | 0471-04-035 | CALDWELL | SH 21 | 2024-11-08 | 9312831.73 | -339.43 | 0 | 9950251.61 | 637419.88 | 109 | 86 | 4 | 0 | -23
AUSTIN | 0914-00-470 | TRAVIS | Various | 2024-10-28 | 648422.03 | -59419.35 | 0 | 612529.68 | -35892.35 | 28 | 61 | 33 | 0 | 33
AUSTIN | 1197-01-025 | HAYS | RM 150 | 2024-10-23 | 1083995.67 | -55516.88 | 0 | 1097456.99 | 13461.32 | 32 | 8 | 0 | 0 | -24
AUSTIN | 0286-01-065 | HAYS | SH 80 | 2024-10-21 | 1035073.1 | -49943.43 | 0 | 1033959.71 | -1113.39 | 32 | 26 | 0 | 0 | -6
AUSTIN | 3136-01-200 | TRAVIS | SL 1 | 2024-10-07 | 4337214.75 | -73814.62 | 0 | 4487085.66 | 149870.91 | 96 | 90 | 0 | 0 | -6
AUSTIN | 0113-05-049 | BLANCO | US 290 | 2024-09-27 | 13188475.9 | 96516.1 | 0 | 12132563.88 | -1055912.02 | 193 | 186 | 0 | 0 | -7
AUSTIN | 0113-02-062 | GILLESPIE | US 290 | 2024-09-25 | 12252579.88 | 2488329.93 | 112013 | 14837828.62 | 2473235.74 | 284 | 269 | 47 | 16 | -31
AUSTIN | 2210-01-008 | TRAVIS | RM 2322 | 2024-09-20 | 1340428.6 | 0 | 0 | 1181127.76 | -159300.84 | 23 | 16 | 0 | 0 | -7
AUSTIN | 2690-01-038 | WILLIAMSON | FM 971 | 2024-09-17 | 4469902 | 30024.34 | 0 | 4562391.73 | 92489.73 | 107 | 106 | 0 | 0 | -1
AUSTIN | 0273-04-048 | WILLIAMSON | US 183 | 2024-09-11 | 5760579.27 | -155804.07 | 0 | 5427306.05 | -333273.22 | 234 | 382 | 99 | 0 | 148
AUSTIN | 0150-04-048 | LLANO | SH 29 | 2024-09-10 | 5448731.92 | 1429767.8 | 0 | 7550747.28 | 2102015.36 | 221 | 281 | 60 | 0 | 60
AUSTIN | 2100-01-060 | TRAVIS | RM 2222 | 2024-09-09 | 15507841.22 | 2397655.87 | 114232.23 | 17475155.04 | 1853081.59 | 295 | 366 | 71 | 0 | 71
BEAUMONT | 0177-03-096 | LIBERTY | US 59 | 2025-02-25 | 102144835.19 | 3979126.19 | 0 | 109065388.94 | 6920553.75 | 736 | 1125 | 433 | 0 | 389
BEAUMONT | 0932-01-118 | JEFFERSON | FM 365 | 2025-02-25 | 320758.82 | 551.2 | 0 | 326778.1 | 6019.28 | 30 | 30 | 0 | 0 | 0
BEAUMONT | 0389-02-057 | CHAMBERS | SH 146 | 2025-02-19 | 311550.68 | 63089.69 | 0 | 376736.58 | 65185.9 | 75 | 119 | 72 | 0 | 44
BEAUMONT | 0508-02-131 | CHAMBERS | IH 10 | 2025-02-19 | 1285256.5 | 2277.38 | 0 | 1306562.98 | 21306.48 | 79 | 72 | 0 | 0 | -7
BEAUMONT | 2367-01-063 | JEFFERSON | SH 82 | 2025-02-11 | 6193763.91 | -31397.44 | 0 | 6107854.49 | -85909.42 | 88 | 88 | 0 | 0 | 0
BEAUMONT | 0388-02-069 | LIBERTY | SH 146 | 2025-02-03 | 3497274.25 | 70543.98 | 0 | 3391626.64 | -105647.61 | 69 | 52 | 0 | 0 | -17
BEAUMONT | 0920-02-090 | LIBERTY | CR | 2025-02-03 | 799669.8 | 0 | 0 | 835116.8 | 35447 | 81 | 83 | 0 | 0 | 2
BEAUMONT | 3510-10-022 | CHAMBERS | SH 99 | 2025-02-03 | 23691228.21 | 136464.96 | 0 | 23713870.76 | 22642.55 | 285 | 242 | 0 | 0 | -43
BEAUMONT | 0920-13-040 | TYLER | Various | 2024-12-19 | 262629.95 | 25684.63 | 0 | 328179.18 | 65549.23 | 22 | 9 | 0 | 0 | -13
BEAUMONT | 2782-01-013 | TYLER | FM 1632 | 2024-11-20 | 5136533.23 | 63500 | 0 | 5230237.45 | 93704.22 | 129 | 100 | 5 | 0 | -29
BROWNWOOD | 0011-07-062 | STEPHENS | US 180 | 2025-02-24 | 13778329.83 | 11370.03 | 0 | 11560613.02 | -2217716.81 | 85 | 55 | 0 | 0 | -30
BROWNWOOD | 0079-03-051 | COMANCHE | US 67 | 2024-12-16 | 850894.76 | 70500.55 | 0 | 872037.21 | 21142.45 | 75 | 153 | 48 | 0 | 78
BROWNWOOD | 0923-22-025 | STEPHENS | CS | 2024-12-16 | 1073352.2 | 67095.2 | 0 | 1161254.17 | 87901.97 | 115 | 106 | 0 | 0 | -9
BROWNWOOD | 0128-01-111 | BROWN | US 377 | 2024-11-26 | 4045900.2 | 1024102.87 | 0 | 5887682.54 | 1841782.34 | 149 | 222 | 56 | 0 | 73
BROWNWOOD | 0055-01-031 | MILLS | US 84 | 2024-11-25 | 4495363.25 | 17707.25 | 0 | 4288037.74 | -207325.51 | 53 | 51 | 0 | 0 | -2
BROWNWOOD | 0257-04-029 | EASTLAND | SH 6 | 2024-10-28 | 10587368.26 | 810758.46 | 0 | 11373705.68 | 786337.42 | 230 | 306 | 81 | 0 | 76
BRYAN | 0109-09-068 | WALKER | SH 19 | 2025-02-18 | 4204817.53 | -422452.91 | 0 | 3985459.3 | -219358.23 | 100 | 58 | 0 | 0 | -42
BRYAN | 0917-18-082 | ROBERTSON | CS | 2025-02-18 | 663959.11 | 0 | 0 | 643334.43 | -20624.68 | 71 | 65 | 0 | 0 | -6
BRYAN | 0675-04-069 | LEON | IH 45 | 2025-01-03 | 17287257.6 | -329848.03 | 0 | 17936875.62 | 649618.02 | 175 | 155 | 0 | 0 | -20
BRYAN | 0917-18-085 | ROBERTSON | CS | 2024-12-31 | 722351.41 | 0 | 0 | 746575.2 | 24223.79 | 159 | 80 | 0 | 0 | -79
BRYAN | 0917-20-046 | FREESTONE | CR | 2024-12-10 | 609028.19 | 0 | 0 | 599520.95 | -9507.24 | 74 | 98 | 0 | 0 | 24
BRYAN | 0338-01-052 | GRIMES | SH 105 | 2024-11-22 | 6022301.01 | 4034857.46 | 0 | 10087359.54 | 4065058.53 | 254 | 342 | 155 | 0 | 88
BRYAN | 0917-19-053 | WASHINGTON | CR | 2024-11-14 | 815696.28 | 0 | 0 | 818354.01 | 2657.73 | 110 | 109 | 0 | 0 | -1
BRYAN | 0116-03-066 | BURLESON | SH 21 | 2024-10-21 | 2941282.43 | 0 | 0 | 2924522.07 | -16760.36 | 133 | 133 | 0 | 0 | 0
BRYAN | 0116-03-071 | BURLESON | SH 21 | 2024-10-14 | 1020603 | 0 | 0 | 927635.66 | -92967.34 | 70 | 29 | 0 | 0 | -41
BRYAN | 1507-02-016 | BURLESON | FM 696 | 2024-10-14 | 2574156.03 | 139938 | 0 | 2812606.51 | 238450.48 | 87 | 243 | 32 | 0 | 156
BRYAN | 0049-14-014 | ROBERTSON | FM 46 | 2024-10-11 | 2552415.92 | 0 | 0 | 2575307.36 | 22891.44 | 65 | 100 | 16 | 0 | 35
BRYAN | 0917-12-084 | MILAM | CR | 2024-10-03 | 515115 | 0 | 0 | 499447 | -15668 | 89 | 256 | 0 | 0 | 167
CHILDRESS | 0042-06-076 | DONLEY | US 287 | 2025-02-04 | 6446300.55 | -166311.3 | 0 | 6627654.34 | 181353.79 | 95 | 76 | 0 | 0 | -19
CHILDRESS | 0043-04-083 | HARDEMAN | US 287 | 2025-01-23 | 8059390.88 | 269727.25 | 0 | 8740321.8 | 680930.92 | 79 | 82 | 10 | 0 | 3
CHILDRESS | 0538-01-027 | KNOX | FM 267 | 2025-01-23 | 6913833.35 | -202800.17 | 0 | 6784248.83 | -129584.52 | 177 | 143 | 0 | 0 | -34
CHILDRESS | 0105-02-023 | HALL | SH 86 | 2025-01-21 | 6639789.5 | 277903.7 | 0 | 7049215.48 | 409425.98 | 89 | 91 | 4 | 0 | 2
CHILDRESS | 0043-23-008 | HARDEMAN | SL 285 | 2025-01-13 | 1870931 | 0 | 0 | 1905511.5 | 34580.5 | 134 | 133 | 0 | 0 | -1
CHILDRESS | 0031-01-022 | WHEELER | US 83 | 2024-12-19 | 12191889.22 | -154811.43 | 0 | 12447743.55 | 255854.33 | 237 | 207 | -2 | 0 | -30
CHILDRESS | 0042-07-071 | DONLEY | US 287 | 2024-11-01 | 576583 | 0 | 0 | 586894.57 | 10311.57 | 48 | 12 | 0 | 0 | -36
CHILDRESS | 0541-01-033 | BRISCOE | SH 256 | 2024-10-29 | 7556670.11 | 10148.54 | 0 | 8264327.16 | 707657.05 | 57 | 35 | 0 | 0 | -22
CHILDRESS | 0704-02-022 | CHILDRESS | FM 268 | 2024-10-29 | 17182340.87 | 668265.84 | 0 | 18254137.33 | 1071796.46 | 443 | 335 | 41 | 0 | -108
CHILDRESS | 0042-09-124 | HALL | US 287 | 2024-10-09 | 13478722.75 | 358966.57 | 0 | 14977060.49 | 1498337.74 | 420 | 481 | 53 | 0 | 61
CORPUS CHRISTI | 0371-02-074 | REFUGIO | US 77 | 2025-02-25 | 9300599.86 | -1317703.95 | 0 | 7952741.63 | -1347858.23 | 170 | 173 | 3 | 0 | 3
CORPUS CHRISTI | 0916-38-015 | ARANSAS | VA | 2025-02-22 | 254251 | 3175 | 0 | 257281 | 3030 | 56 | 59 | 3 | 0 | 3
CORPUS CHRISTI | 0086-20-023 | NUECES | FM 665 | 2025-02-20 | 4508717.9 | 145854.1 | 0 | 4765319.56 | 256601.66 | 187 | 227 | 17 | 0 | 40
CORPUS CHRISTI | 0916-00-212 | NUECES | VA | 2025-02-13 | 1847391.5 | 0 | 0 | 1727039.46 | -120352.04 | 120 | 803 | 0 | 0 | 683
CORPUS CHRISTI | 0180-05-065 | ARANSAS | BS 35-L | 2025-02-11 | 1836179 | 54711.51 | 0 | 1858442.03 | 22263.03 | 85 | 158 | 12 | 0 | 73
CORPUS CHRISTI | 0738-01-001 | REFUGIO | FM 136 | 2025-01-24 | 1136958 | 0 | 0 | 1058863.84 | -78094.16 | 85 | 641 | 162 | 0 | 556
CORPUS CHRISTI | 0516-02-029 | GOLIAD | SH 239 | 2025-01-10 | 7455639.89 | 824137.22 | 0 | 8147758.67 | 692118.78 | 246 | 375 | 129 | 0 | 129
CORPUS CHRISTI | 0073-07-068 | LIVE OAK | IH 37 | 2024-12-17 | 1030452.14 | 91817.27 | 0 | 1314043 | 283590.86 | 85 | 225 | 140 | 0 | 140
CORPUS CHRISTI | 0617-01-206 | NUECES | SH 358 | 2024-12-16 | 7618726.75 | 434909.29 | 0 | 7831165.7 | 212438.95 | 55 | 178 | 99 | 0 | 123
CORPUS CHRISTI | 0074-01-060 | LIVE OAK | IH 37 | 2024-11-22 | 5101524.26 | -145374.59 | 0 | 4959038.4 | -142485.86 | 46 | 38 | 0 | 0 | -8
CORPUS CHRISTI | 0101-02-039 | BEE | US 181 | 2024-11-21 | 9794885.95 | 1753263.7 | 0 | 11558804.84 | 1763918.89 | 139 | 160 | 25 | 0 | 21
CORPUS CHRISTI | 0102-03-087 | NUECES | US 77 | 2024-11-20 | 7712829.03 | 413355.78 | 0 | 8271901.17 | 559072.14 | 219 | 385 | 168 | 0 | 166
CORPUS CHRISTI | 0916-35-233 | NUECES | CR | 2024-11-19 | 114728 | 3990 | 0 | 117088 | 2360 | 50 | 17 | 0 | 0 | -33
CORPUS CHRISTI | 0326-03-107 | NUECES | SH 286 | 2024-10-28 | 396817.5 | 32567.59 | 0 | 407126.32 | 10308.82 | 44 | 76 | 20 | 0 | 32
CORPUS CHRISTI | 0074-01-059 | LIVE OAK | IH 37 | 2024-10-17 | 3899642.24 | 387661.42 | 0 | 3927143.28 | 27501.04 | 37 | 53 | 0 | 0 | 16
CORPUS CHRISTI | 0100-08-095 | BEE | US 181 | 2024-10-16 | 14739738.04 | 118985.18 | 0 | 15241699.63 | 501961.59 | 184 | 365 | 181 | 0 | 181
DALLAS | 0195-02-087 | DENTON | IH 35 | 2025-02-14 | 1117242.04 | 29646.14 | 0 | 859724.51 | -257517.53 | 98 | 46 | 0 | 0 | -52
DALLAS | 1451-03-017 | NAVARRO | FM 55 | 2025-02-07 | 4964579.98 | 509878.47 | 0 | 5479022.27 | 514442.29 | 210 | 271 | 65 | 0 | 61
DALLAS | 1568-02-014 | DENTON | FM 407 | 2025-02-05 | 8970766.9 | 858224.11 | 0 | 9411709.18 | 440942.28 | 203 | 205 | 2 | 0 | 2
DALLAS | 0095-05-063 | KAUFMAN | US 80 | 2025-02-03 | 2155024 | 25100 | 0 | 2331185.46 | 176161.46 | 260 | 349 | 5 | 0 | 89
DALLAS | 0568-01-059 | ELLIS | SH 34 | 2025-01-17 | 3311895 | 117138.35 | 0 | 3287129.03 | -24765.97 | 157 | 227 | 75 | 0 | 70
DALLAS | 0009-04-075 | ROCKWALL | SH 66 | 2024-12-30 | 19193970.72 | 165692.07 | 0 | 19333501.06 | 139530.34 | 243 | 216 | 0 | 0 | -27
DALLAS | 1311-01-060 | DENTON | FM 1171 | 2024-12-16 | 845850.43 | 16392.01 | 0 | 871581.6 | 25731.17 | 81 | 73 | 0 | 0 | -8
DALLAS | 2979-01-013 | DENTON | FM 2931 | 2024-12-12 | 4665613.56 | 1373304.83 | 0 | 5829103.02 | 1163489.46 | 220 | 185 | 65 | 0 | -35
DALLAS | 0047-07-242 | DALLAS | US 75 | 2024-12-09 | 5572514.47 | 0 | 0 | 5165749.3 | -406765.17 | 204 | 176 | 0 | 0 | -28
DALLAS | 0549-03-024 | COLLIN | SH 121 | 2024-12-09 | 91386585.26 | 1398398.73 | 0 | 94387841.53 | 3001256.27 | 1092 | 762 | 0 | 0 | -330
DALLAS | 0816-03-020 | DENTON | FM 455 | 2024-12-09 | 4243947.8 | 93904.16 | 0 | 4287876.13 | 43928.33 | 323 | 497 | 0 | 0 | 174
DALLAS | 0918-47-212 | DALLAS | CS | 2024-12-03 | 2040000 | 0 | 0 | 2089849.53 | 49849.53 | 360 | 513 | 0 | 0 | 153
DALLAS | 0173-01-049 | ELLIS | SH 34 | 2024-12-02 | 6698765.23 | 2007181.59 | 0 | 8438092.45 | 1739327.22 | 172 | 168 | 10 | 0 | -4
DALLAS | 0196-01-117 | DENTON | US 77 | 2024-12-02 | 3803760.4 | 52377.78 | 0 | 4017457.22 | 213696.82 | 118 | 100 | 0 | 0 | -18
DALLAS | 2374-04-091 | DALLAS | IH 20 | 2024-11-26 | 190482.1 | 0 | 0 | 187107.34 | -3374.76 | 49 | 18 | 0 | 0 | -31
DALLAS | 3427-03-007 | COLLIN | FM 3356 | 2024-11-22 | 5796924.02 | -178064.57 | 0 | 5223395.51 | -573528.51 | 189 | 185 | 0 | 0 | -4
DALLAS | 0918-47-438 | DALLAS | Various | 2024-11-04 | 3959735.05 | -741038.04 | 0 | 3210740.89 | -748994.16 | 93 | 88 | 0 | 0 | -5
DALLAS | 0918-47-359 | DALLAS | FD | 2024-11-01 | 2217976.4 | 0 | 0 | 2080564.9 | -137411.5 | 105 | 127 | 0 | 0 | 22
DALLAS | 0281-01-037 | COLLIN | SH 78 | 2024-10-31 | 3966360.02 | 0 | 0 | 3900192.97 | -66167.05 | 142 | 50 | 0 | 0 | -92
DALLAS | 0918-11-100 | KAUFMAN | CR | 2024-10-18 | 1534309.5 | -6280 | 0 | 1500205.46 | -34104.04 | 303 | 202 | 0 | 0 | -101
DALLAS | 2678-02-008 | DENTON | FM 428 | 2024-10-18 | 6544754.19 | 366604.15 | 0 | 6231734.75 | -313019.44 | 214 | 254 | 39 | 0 | 40
DALLAS | 0135-10-057 | DENTON | US 377 | 2024-10-15 | 20616736.66 | 695263.96 | 0 | 21294967.41 | 678230.75 | 836 | 890 | 54 | 0 | 54
DALLAS | 3325-01-014 | NAVARRO | FM 3243 | 2024-10-15 | 5724413.87 | 295327.09 | 0 | 5945844.75 | 221430.88 | 241 | 281 | 10 | 0 | 40
DALLAS | 0009-02-073 | DALLAS | SH 78 | 2024-09-27 | 2754566.08 | 12308.88 | 0 | 2639074.54 | -115491.54 | 103 | 71 | 0 | 0 | -32
DALLAS | 0092-06-105 | NAVARRO | IH 45 | 2024-09-27 | 6333011.92 | 1618510.08 | 0 | 7856117.24 | 1523105.32 | 237 | 236 | 0 | 0 | -1
DALLAS | 0092-14-098 | DALLAS | IH 45 | 2024-09-23 | 5125904.79 | 57252.48 | 0 | 4375512.56 | -750392.23 | 365 | 365 | 25 | 0 | 0
DALLAS | 1047-03-076 | DALLAS | FM 1382 | 2024-09-23 | 4000858.2 | -449833.97 | 0 | 3390183.92 | -610674.28 | 97 | 162 | 0 | 0 | 65
DALLAS | 0095-04-072 | KAUFMAN | US 80 | 2024-09-20 | 2575586.68 | 255202.52 | 0 | 3159226.65 | 583639.97 | 320 | 294 | 0 | 0 | -26
DALLAS | 0172-05-124 | ELLIS | US 287 | 2024-09-20 | 1859514.08 | 108812.16 | 0 | 1983774.71 | 124260.63 | 142 | 75 | 0 | 0 | -67
DALLAS | 0581-01-156 | DALLAS | SL 12 | 2024-09-20 | 7277370.47 | 415689.5 | 0 | 7456808.48 | 179438.01 | 188 | 187 | 0 | 0 | -1
DALLAS | 1663-03-020 | NAVARRO | FM 744 | 2024-09-20 | 5714506.65 | 727434.42 | 0 | 6027970.2 | 313463.55 | 370 | 348 | 0 | 0 | -22
DALLAS | 2374-04-090 | DALLAS | IH 20 | 2024-09-19 | 4350740.31 | 293289.9 | 0 | 4732772.96 | 382032.65 | 150 | 173 | 25 | 0 | 23
EL PASO | 1046-01-032 | EL PASO | FM 659 | 2025-02-28 | 14610296.05 | 792269.45 | 0 | 15729724.12 | 1119428.07 | 283 | 373 | 92 | 0 | 90
EL PASO | 0002-02-055 | EL PASO | SH 20 | 2025-01-30 | 2606597.5 | 1148552.72 | 0 | 3775359.48 | 1168761.98 | 120 | 235 | 68 | 0 | 115
EL PASO | 0924-00-105 | EL PASO | VA | 2025-01-30 | 1053915 | 158770 | 0 | 1031483.89 | -22431.11 | 186 | 185 | 0 | 0 | -1
EL PASO | 0924-06-700 | EL PASO | Various | 2025-01-10 | 458260 | 0 | 0 | 473775.2 | 15515.2 | 83 | 25 | 0 | 0 | -58
EL PASO | 0020-01-021 | CULBERSON | US 90 | 2024-12-26 | 5952638.25 | 608732.82 | 0 | 6782347.1 | 829708.85 | 180 | 176 | 0 | 0 | -4
EL PASO | 0924-06-689 | EL PASO | Various | 2024-12-13 | 832138 | -31343.57 | 0 | 872959.51 | 40821.51 | 120 | 119 | 2 | 0 | -1
EL PASO | 0924-06-663 | EL PASO | Various | 2024-11-22 | 995591.48 | 331869.02 | 0 | 1338931.33 | 343339.85 | 80 | 231 | 153 | 0 | 151
EL PASO | 0924-00-109 | EL PASO | Various | 2024-11-13 | 2271557.75 | -134856.3 | 0 | 2267863.17 | -3694.58 | 340 | 145 | 0 | 0 | -195
EL PASO | 2121-02-178 | EL PASO | IH 10 | 2024-11-08 | 5680916.35 | -1013474.58 | 0 | 4550932.85 | -1129983.5 | 77 | 63 | 0 | 0 | -14
EL PASO | 2121-04-114 | EL PASO | IH 10 | 2024-11-08 | 18039540.88 | 1229607.66 | 0 | 19341952.98 | 1302412.1 | 330 | 447 | 148 | 0 | 117
EL PASO | 2121-04-110 | EL PASO | IH 10 | 2024-10-27 | 2756557.25 | 668639.65 | 0 | 3511031.47 | 754474.22 | 124 | 86 | 0 | 0 | -38
EL PASO | 1158-01-011 | CULBERSON | FM 2185 | 2024-10-01 | 6981728.75 | 723068.71 | 0 | 7761157.77 | 779429.02 | 120 | 93 | 0 | 0 | -27
EL PASO | 0924-06-647 | EL PASO | CR | 2024-09-27 | 730107.5 | 20648.8 | 0 | 743278.87 | 13171.37 | 137 | 104 | 0 | 0 | -33
FORT WORTH | 0008-03-134 | PARKER | US 180 | 2025-02-27 | 680358.25 | 52400.72 | 0 | 712703.35 | 32345.1 | 107 | 97 | 0 | 0 | -10
FORT WORTH | 0008-16-042 | TARRANT | IH 20 | 2025-02-26 | 20961181.94 | 7155561.14 | 0 | 28304573.46 | 7343391.52 | 371 | 731 | 360 | 0 | 360
FORT WORTH | 0902-90-184 | TARRANT | VA | 2025-02-21 | 1484096.25 | 12504 | 0 | 1478427.81 | -5668.44 | 128 | 268 | 0 | 0 | 140
FORT WORTH | 0902-90-126 | TARRANT | SS 580 | 2025-02-12 | 438635 | 4161.35 | 0 | 444649.94 | 6014.94 | 64 | 66 | 0 | 0 | 2
FORT WORTH | 0250-04-049 | ERATH | US 281 | 2025-02-11 | 11095984.14 | 216501.63 | 0 | 10729638.01 | -366346.13 | 128 | 127 | 0 | 0 | -1
FORT WORTH | 0902-90-210 | TARRANT | CS | 2025-02-10 | 734812.4 | 0 | 0 | 753595.33 | 18782.93 | 200 | 135 | 0 | 0 | -65
FORT WORTH | 0081-02-076 | TARRANT | US 377 | 2025-02-03 | 470872 | 1220 | 0 | 471477.56 | 605.56 | 64 | 68 | 4 | 0 | 4
FORT WORTH | 0171-03-077 | PARKER | SH 199 | 2025-01-30 | 734777 | -4867.5 | 0 | 647956.75 | -86820.25 | 43 | 33 | 0 | 0 | -10
FORT WORTH | 1098-02-015 | TARRANT | FM 718 | 2025-01-22 | 2852725.75 | -485.62 | 0 | 2963467.28 | 110741.53 | 128 | 135 | 12 | 0 | 7
FORT WORTH | 0902-90-125 | TARRANT | CS | 2025-01-21 | 3861246.79 | -40246.25 | 0 | 3809318.98 | -51927.81 | 217 | 216 | 0 | 0 | -1
FORT WORTH | 1330-02-049 | TARRANT | FM 1187 | 2025-01-21 | 2305368.4 | 157196.59 | 0 | 2612336.12 | 306967.72 | 160 | 196 | 0 | 0 | 36
FORT WORTH | 0312-05-031 | TARRANT | FM 730 | 2025-01-09 | 5888715.63 | 298188.8 | 0 | 6103147.13 | 214431.5 | 149 | 146 | 0 | 0 | -3
FORT WORTH | 0014-03-087 | JOHNSON | IH 35W | 2024-12-10 | 13369086.3 | 375838.28 | 0 | 13829348.29 | 460261.99 | 231 | 400 | 169 | 0 | 169
FORT WORTH | 0134-07-069 | WISE | US 380 | 2024-12-09 | 3489536.12 | 314942.67 | 0 | 3536563.14 | 47027.02 | 171 | 211 | 40 | 0 | 40
FORT WORTH | 0019-01-148 | JOHNSON | SH 174 | 2024-12-01 | 1433900.47 | 98402.93 | 0 | 1543091.63 | 109191.16 | 360 | 80 | 0 | 0 | -280
FORT WORTH | 0134-05-034 | JACK | SH 59 | 2024-11-22 | 3685479.68 | 43305.4 | 0 | 3797961.77 | 112482.09 | 234 | 349 | 108 | 0 | 115
FORT WORTH | 1600-02-019 | JOHNSON | FM 1807 | 2024-11-22 | 3153376.15 | 233893.09 | 0 | 3159646.24 | 6270.09 | 64 | 64 | 0 | 0 | 0
FORT WORTH | 0902-00-339 | TARRANT | Various | 2024-11-20 | 3471786.5 | 748884.41 | 0 | 4093607.44 | 621820.94 | 421 | 334 | 0 | 0 | -87
FORT WORTH | 0902-00-340 | TARRANT | Various | 2024-11-06 | 2414176 | 65644.42 | 0 | 2494190.49 | 80014.49 | 342 | 194 | 0 | 0 | -148
FORT WORTH | 0902-00-357 | TARRANT | Various | 2024-11-04 | 4647055 | 0 | 0 | 4655773.99 | 8718.99 | 365 | 365 | 0 | 0 | 0
FORT WORTH | 0094-02-143 | TARRANT | SH 183 | 2024-10-31 | 300690.78 | -12496 | 0 | 275976.78 | -24714 | 72 | 65 | 0 | 0 | -7
FORT WORTH | 0008-12-092 | TARRANT | SH 183 | 2024-10-29 | 4619873.98 | -210867.42 | 0 | 4311408.16 | -308465.82 | 128 | 131 | 0 | 0 | 3
FORT WORTH | 0902-39-029 | PALO PINTO | CR | 2024-10-02 | 724492 | 0 | 0 | 706661.51 | -17830.49 | 64 | 110 | 19 | 0 | 46
FORT WORTH | 0363-01-147 | TARRANT | SH 26 | 2024-09-30 | 2429784.57 | -31077.75 | 0 | 2529099.42 | 99314.85 | 85 | 50 | 0 | 0 | -35
FORT WORTH | 0008-14-124 | TARRANT | IH 820 | 2024-09-27 | 1932277.5 | -18287.44 | 0 | 1933545.43 | 1267.93 | 171 | 159 | 5 | 0 | -12
FORT WORTH | 0013-10-089 | TARRANT | BU 287P | 2024-09-13 | 406337.7 | 71788.3 | 14760 | 462398.7 | 41301 | 85 | 79 | 0 | 0 | -6
HOUSTON | 0912-37-252 | MONTGOMERY | Various | 2025-02-21 | 956940.66 | 0 | 0 | 995068.96 | 38128.3 | 100 | 89 | 0 | 0 | -11
HOUSTON | 1416-03-018 | MONTGOMERY | FM 1486 | 2025-02-19 | 4541531.81 | 250930.27 | 0 | 5290109.51 | 748577.7 | 107 | 142 | 0 | 0 | 35
HOUSTON | 1912-01-022 | MONTGOMERY | FM 2090 | 2025-02-14 | 7041940.21 | 869384.6 | 0 | 9002022.69 | 1960082.48 | 124 | 118 | 0 | 0 | -6
HOUSTON | 0367-02-082 | GALVESTON | SH 87 | 2024-12-23 | 9010882.36 | 1999617.37 | 0 | 11040074.82 | 2029192.46 | 126 | 175 | 59 | 0 | 49
HOUSTON | 0051-09-024 | GALVESTON | FM 3005 | 2024-12-20 | 35347635.33 | 433840 | 0 | 34884980.38 | -462654.95 | 450 | 539 | 89 | 0 | 89
HOUSTON | 1259-01-043 | MONTGOMERY | FM 1097 | 2024-12-05 | 14690168.28 | 1573006.85 | 0 | 16771639.93 | 2081471.65 | 334 | 394 | 124 | 0 | 60
HOUSTON | 0178-03-158 | BRAZORIA | SH 35 | 2024-10-29 | 4500659.53 | -494684.95 | 0 | 4087418.22 | -413241.31 | 101 | 114 | 0 | 0 | 13
HOUSTON | 0508-01-345 | HARRIS | IH 10 | 2024-10-25 | 14598295.77 | 5695539.68 | 0 | 19217067.76 | 4618771.99 | 398 | 582 | 185 | 0 | 184
HOUSTON | 0050-06-094 | HARRIS | BU 290H | 2024-10-22 | 78734.4 | -1353.35 | 0 | 78021.05 | -713.35 | 90 | 38 | 0 | 0 | -52
HOUSTON | 3050-02-024 | MONTGOMERY | FM 2978 | 2024-10-22 | 15788778.29 | 8646460.83 | 271903.17 | 25152892.81 | 9092211.35 | 457 | 516 | 147 | 0 | 59
HOUSTON | 0912-72-363 | HARRIS | CS | 2024-10-18 | 17999505.15 | 825689.79 | 825689.79 | 18670205.06 | -154989.88 | 436 | 675 | 123 | 0 | 239
HOUSTON | 0976-01-043 | HARRIS | FM 865 | 2024-10-16 | 3261336.96 | 549088.09 | 0 | 4287775.15 | 1026438.19 | 32 | 123 | 91 | 0 | 91
HOUSTON | 0675-08-114 | MONTGOMERY | IH 45 | 2024-10-15 | 7473853.32 | 98328.98 | 0 | 7627958.41 | 154105.09 | 252 | 251 | 0 | 0 | -1
HOUSTON | 0720-02-097 | MONTGOMERY | FM 149 | 2024-10-15 | 272609.79 | 146040.59 | 0 | 409073.71 | 136463.92 | 53 | 45 | 0 | 0 | -8
HOUSTON | 0027-12-166 | FORT BEND | IH 69 | 2024-10-02 | 800573.3 | 33526.41 | 0 | 845974.12 | 45400.82 | 90 | 58 | 0 | 0 | -32
HOUSTON | 0912-70-093 | HARRIS | CS | 2024-09-20 | 4947623.92 | 417891.26 | 311029.98 | 5318772.71 | 60118.81 | 192 | 466 | 274 | 0 | 274
HOUSTON | 1257-01-052 | FORT BEND | FM 1092 | 2024-09-07 | 4238148.2 | 201880.79 | 0 | 4839461.23 | 601313.03 | 103 | 103 | 0 | 0 | 0
LAREDO | 0542-01-102 | WEBB | BU 59Z | 2025-02-14 | 907084.3 | 103536.87 | 0 | 1053013.12 | 145928.82 | 60 | 58 | 0 | 0 | -2
LAREDO | 0038-01-097 | WEBB | US 83 | 2025-02-12 | 1040125 | 0 | 0 | 1027607.5 | -12517.5 | 108 | 50 | 0 | 0 | -58
LAREDO | 0018-02-086 | LA SALLE | IH 35 | 2025-01-27 | 11045137.85 | 359166.4 | 0 | 11602781.9 | 557644.05 | 263 | 311 | 9 | 0 | 48
LAREDO | 0922-00-084 | WEBB | Various | 2025-01-27 | 796188.5 | 18992.02 | 0 | 843502.66 | 47314.16 | 80 | 80 | 0 | 0 | 0
LAREDO | 0542-01-101 | WEBB | US 59 | 2025-01-13 | 5349601.52 | 78136.6 | 0 | 5604708.45 | 255106.93 | 120 | 108 | 0 | 0 | -12
LAREDO | 2636-01-010 | MAVERICK | FM 2644 | 2025-01-13 | 2696125.5 | -32776.1 | 0 | 2863095.48 | 166969.98 | 125 | 125 | 0 | 0 | 0
LAREDO | 2150-04-076 | WEBB | FM 1472 | 2024-12-19 | 6359706.23 | 624484.13 | 0 | 6911593.72 | 551887.49 | 374 | 443 | 20 | 0 | 69
LAREDO | 0018-04-065 | WEBB | IH 35 | 2024-11-19 | 16568075.25 | 1257149.43 | 0 | 18328090.29 | 1760015.04 | 222 | 191 | 5 | 0 | -31
LAREDO | 0922-00-074 | WEBB | VA | 2024-11-13 | 2435839.81 | 66235.27 | 0 | 2349306.74 | -86533.07 | 378 | 377 | 0 | 0 | -1
LAREDO | 0017-08-118 | LA SALLE | IH 35 | 2024-10-31 | 1863389 | 129936.3 | 0 | 2114362.44 | 250973.44 | 49 | 74 | 39 | 0 | 25
LAREDO | 0018-02-089 | LA SALLE | IH 35 | 2024-10-10 | 1081952 | -1000.8 | 0 | 1128761.19 | 46809.19 | 105 | 105 | 0 | 0 | 0
LAREDO | 0037-09-033 | WEBB | US 83 | 2024-10-10 | 48720816.8 | 213508.15 | 0 | 49672485.96 | 951669.16 | 734 | 963 | 0 | 0 | 229
LAREDO | 0018-05-104 | WEBB | IH 35 | 2024-09-13 | 14045933.92 | 1048045.63 | 0 | 14084633.62 | 38699.7 | 245 | 235 | 0 | 0 | -10
LUBBOCK | 0130-05-089 | LUBBOCK | US 62 | 2025-02-06 | 340196.25 | 0 | 0 | 337436.25 | -2760 | 32 | 27 | 0 | 0 | -5
LUBBOCK | 0905-00-120 | LUBBOCK | Various | 2025-02-06 | 1639160 | -489002.5 | 0 | 1191316.8 | -447843.2 | 68 | 68 | 0 | 0 | 0
LUBBOCK | 0905-00-130 | LUBBOCK | Various | 2025-02-06 | 1783751.6 | 0 | 0 | 2105529.2 | 321777.6 | 90 | 53 | 0 | 0 | -37
LUBBOCK | 0302-04-022 | SWISHER | SH 86 | 2025-01-31 | 2320028 | 458561.72 | 0 | 3289949.44 | 969921.44 | 320 | 318 | 73 | 0 | -2
LUBBOCK | 0052-04-053 | LAMB | US 84 | 2025-01-30 | 22788746.19 | 197274.01 | 0 | 21724655.89 | -1064090.3 | 64 | 58 | 0 | 0 | -6
LUBBOCK | 0905-06-118 | LUBBOCK | CS | 2025-01-30 | 12797068.28 | 274194.87 | 0 | 12929767.77 | 132699.49 | 256 | 379 | 123 | 0 | 123
LUBBOCK | 0052-02-037 | BAILEY | US 70 | 2024-12-20 | 1843790 | 0 | 0 | 1826121.63 | -17668.37 | 121 | 107 | 0 | 0 | -14
LUBBOCK | 0905-00-116 | LUBBOCK | Various | 2024-12-20 | 1311802.1 | 0 | 0 | 1357078.19 | 45276.09 | 85 | 107 | 22 | 0 | 22
LUBBOCK | 0068-09-012 | LYNN | SL 76 | 2024-12-19 | 23982637.33 | 160410.89 | 0 | 23785167.9 | -197469.43 | 637 | 744 | 55 | 0 | 107
LUBBOCK | 0067-05-053 | HALE | IH 27 | 2024-11-26 | 2049918.5 | -202952.25 | 0 | 1971470.9 | -78447.6 | 209 | 270 | 30 | 0 | 61
LUBBOCK | 0905-00-119 | LUBBOCK | Various | 2024-11-12 | 7117196.6 | 0 | 0 | 7504466.81 | 387270.21 | 85 | 68 | 0 | 0 | -17
LUBBOCK | 0905-00-129 | LUBBOCK | Various | 2024-10-17 | 5367023.85 | 312700.85 | 0 | 5668931.6 | 301907.75 | 80 | 126 | 0 | 0 | 46
LUFKIN | 0911-08-049 | NACOGDOCHES | CR | 2025-02-27 | 2041759.25 | 0 | 0 | 2044351.26 | 2592.01 | 644 | 156 | 0 | 0 | -488
LUFKIN | 0176-06-016 | POLK | BU 59J | 2025-02-26 | 9240613.28 | 236699.62 | 0 | 9190460.25 | -50153.03 | 121 | 158 | 8 | 0 | 37
LUFKIN | 0064-01-069 | SHELBY | SH 87 | 2025-02-07 | 15659341.69 | 332973.58 | 0 | 14768418.71 | -890922.98 | 125 | 158 | 0 | 0 | 33
LUFKIN | 0175-07-065 | NACOGDOCHES | US 59 | 2025-01-30 | 6975521.46 | 27969.52 | 0 | 7419588.94 | 444067.48 | 119 | 99 | 0 | 0 | -20
LUFKIN | 0063-07-003 | SHELBY | SL 157 | 2025-01-27 | 12827779.2 | 132034.91 | 0 | 11708879.28 | -1118899.92 | 106 | 102 | 0 | 0 | -4
LUFKIN | 0200-03-021 | ANGELINA | US 69 | 2025-01-14 | 37447954.88 | 2359974.98 | 0 | 40062516.18 | 2614561.3 | 475 | 556 | 81 | 0 | 81
LUFKIN | 0809-02-070 | SHELBY | US 96 | 2024-12-05 | 9395982.34 | 1095466.59 | 0 | 9832229.15 | 436246.81 | 320 | 320 | 0 | 0 | 0
LUFKIN | 0809-02-069 | SHELBY | US 96 | 2024-11-22 | 16435546.93 | 481457.2 | 0 | 15902457.89 | -533089.04 | 402 | 311 | 0 | 0 | -91
LUFKIN | 3264-01-010 | ANGELINA | FM 326 | 2024-10-30 | 2637474.14 | 16798.4 | 0 | 2488350.16 | -149123.98 | 171 | 218 | 32 | 0 | 47
LUFKIN | 0118-08-075 | NACOGDOCHES | SH 21 | 2024-10-17 | 2490124.75 | 13526.48 | 0 | 2537576.6 | 47451.85 | 230 | 291 | 61 | 0 | 61
LUFKIN | 0597-04-005 | SAN AUGUSTINE | FM 2923 | 2024-09-03 | 1771724.54 | 1000 | 0 | 1793350.64 | 21626.1 | 79 | 61 | 0 | 0 | -18
ODESSA | 2224-01-119 | ECTOR | SL 338 | 2025-02-20 | 7949949.69 | 156838.97 | 0 | 8176183.79 | 226234.1 | 155 | 111 | 0 | 0 | -44
ODESSA | 0292-01-034 | WINKLER | SH 18 | 2025-02-12 | 37268535.81 | 285594.57 | 0 | 42166837.42 | 4898301.61 | 265 | 444 | 179 | 0 | 179
ODESSA | 0229-04-060 | UPTON | US 385 | 2025-01-31 | 5995947.22 | -12950.22 | 0 | 5859540.37 | -136406.85 | 120 | 186 | 68 | 0 | 66
ODESSA | 0479-03-016 | LOVING | SH 302 | 2025-01-31 | 36670137.75 | -329920.36 | 0 | 39347167.05 | 2677029.3 | 510 | 465 | 0 | 0 | -45
ODESSA | 2005-02-017 | ECTOR | FM 1882 | 2025-01-24 | 10165599.43 | 362129.9 | 0 | 10721567.72 | 555968.29 | 210 | 144 | 20 | 0 | -66
ODESSA | 0005-01-116 | ECTOR | BI 20E | 2025-01-13 | 2412947.5 | 807438.4 | 0 | 3022910.89 | 609963.39 | 57 | 96 | 50 | 0 | 39
ODESSA | 0076-07-038 | UPTON | US 67 | 2025-01-13 | 18404584.67 | 42466.79 | 0 | 17726890.66 | -677694.01 | 92 | 105 | 15 | 0 | 13
ODESSA | 0292-03-032 | WARD | SH 18 | 2025-01-13 | 32902552.4 | -1658414.09 | 0 | 32065142.29 | -837410.11 | 244 | 244 | 12 | 0 | 0
ODESSA | 0005-04-082 | MARTIN | IH 20 | 2025-01-03 | 1679659 | 20000 | 0 | 1633898.3 | -45760.7 | 80 | 120 | 40 | 0 | 40
ODESSA | 0548-02-043 | MARTIN | SH 176 | 2025-01-03 | 5880107.87 | -308029.96 | 0 | 5525804.79 | -354303.08 | 142 | 127 | 0 | 0 | -15
ODESSA | 0906-32-060 | MIDLAND | CS | 2025-01-03 | 496352.87 | 6163.24 | 6163.3 | 500570 | -1946.17 | 91 | 71 | 0 | 0 | -20
ODESSA | 1188-02-118 | MIDLAND | SL 250 | 2025-01-03 | 1609466.84 | -13134.93 | 0 | 1549504.39 | -59962.45 | 64 | 60 | 3 | 0 | -4
ODESSA | 0906-00-255 | ECTOR | Various | 2024-12-11 | 3569917.5 | 0 | 0 | 3627570.5 | 57653 | 253 | 140 | 0 | 0 | -113
ODESSA | 2224-01-099 | ECTOR | SL 338 | 2024-11-22 | 15760357.9 | 4576076.03 | 0 | 21459652.4 | 5699294.5 | 400 | 648 | 250 | 0 | 248
ODESSA | 3570-01-012 | ECTOR | FM 3503 | 2024-11-15 | 5107417.37 | 199997.11 | 0 | 6260310.89 | 1152893.52 | 137 | 95 | 0 | 0 | -42
ODESSA | 0228-04-043 | ANDREWS | US 385 | 2024-11-04 | 37642802.47 | -1301884.08 | 0 | 36413663.01 | -1229139.46 | 373 | 433 | 64 | 0 | 60
ODESSA | 0140-01-081 | PECOS | IH 10 | 2024-10-21 | 14363577.76 | 0 | 0 | 13997772 | -365805.76 | 67 | 67 | 0 | 0 | 0
ODESSA | 0140-02-050 | PECOS | IH 10 | 2024-10-21 | 1938518 | 0 | 0 | 1797376.5 | -141141.5 | 124 | 63 | 0 | 0 | -61
ODESSA | 0292-04-072 | WARD | SH 18 | 2024-10-14 | 13110325.39 | 783923.8 | 0 | 12839913.06 | -270412.33 | 83 | 25 | 0 | 0 | -58
ODESSA | 0139-06-021 | REEVES | US 285 | 2024-10-03 | 58528500.77 | -3781717.37 | 0 | 55093305.03 | -3435195.74 | 805 | 744 | 0 | 0 | -61
ODESSA | 2262-01-020 | WARD | FM 1776 | 2024-09-25 | 5823543.4 | 549242.94 | 0 | 6643923.43 | 820380.03 | 120 | 163 | 21 | 0 | 43
ODESSA | 0103-01-044 | REEVES | SH 17 | 2024-09-24 | 6972496.49 | 12956.15 | 0 | 7397640.93 | 425144.44 | 155 | 155 | 0 | 0 | 0
PARIS | 0901-22-117 | HUNT | CR | 2025-02-07 | 1348336.46 | -56800.5 | 0 | 1247653.44 | -100683.02 | 229 | 221 | 0 | 0 | -8
PARIS | 0901-00-063 | LAMAR | Various | 2025-01-30 | 3141295.36 | -259349.7 | 0 | 2757597.6 | -383697.76 | 101 | 63 | 0 | 0 | -38
PARIS | 1290-07-001 | HUNT | SH 276 | 2025-01-10 | 14191646.9 | 136450.31 | 0 | 13726504.74 | -465142.16 | 384 | 583 | 0 | 0 | 199
PARIS | 0771-01-019 | RAINS | FM 2946 | 2024-12-18 | 1614607.12 | 112881.74 | 0 | 1683728.44 | 69121.32 | 103 | 119 | 16 | 0 | 16
PARIS | 0009-07-043 | HUNT | SS 302 | 2024-11-14 | 4906019.96 | -206295.27 | 0 | 4616946.55 | -289073.41 | 123 | 115 | 0 | 0 | -8
PARIS | 0901-29-102 | LAMAR | Various | 2024-10-31 | 297263 | -51920 | 0 | 265882.5 | -31380.5 | 64 | 23 | 0 | 0 | -41
PARIS | 0136-01-066 | HUNT | SH 224 | 2024-10-18 | 2620776.26 | -81357.79 | 0 | 2510214.82 | -110561.44 | 129 | 122 | 0 | 0 | -7
PARIS | 0901-27-046 | RED RIVER | CS | 2024-09-27 | 1091166.37 | -35385 | 0 | 1093703.94 | 2537.57 | 172 | 171 | 0 | 0 | -1
PARIS | 0901-19-219 | GRAYSON | Various | 2024-09-01 | 744555 | 0 | 0 | 656390 | -88165 | 138 | 138 | 0 | 0 | 0
PARIS | 1452-01-018 | LAMAR | FM 1507 | 2024-09-01 | 1480238.25 | 0 | 0 | 1447773.03 | -32465.22 | 160 | 153 | 0 | 0 | -7
PHARR | 0039-12-259 | CAMERON | BU 77X | 2025-02-14 | 6349769.9 | 57866.89 | 0 | 6698813.81 | 349043.91 | 125 | 92 | 0 | 0 | -33
PHARR | 0669-03-029 | HIDALGO | FM 2221 | 2025-02-14 | 802713.95 | 0 | 0 | 780422.31 | -22291.64 | 120 | 118 | 0 | 0 | -2
PHARR | 0921-06-363 | CAMERON | CS | 2025-02-14 | 64546 | -2583.24 | 0 | 56843.47 | -7702.53 | 7 | 6 | 0 | 0 | -1
PHARR | 1103-05-002 | STARR | FM 755 | 2025-02-14 | 763589.1 | 3150 | 0 | 769825.13 | 6236.03 | 100 | 119 | 19 | 0 | 19
PHARR | 0342-02-059 | HIDALGO | SH 107 | 2025-01-29 | 554000 | 0 | 0 | 561163.91 | 7163.91 | 104 | 22 | 0 | 0 | -82
PHARR | 0921-06-311 | CAMERON | CS | 2025-01-29 | 939378.65 | -112523.49 | 0 | 886323.15 | -53055.5 | 215 | 197 | 0 | 0 | -18
PHARR | 0861-01-068 | HIDALGO | FM 491 | 2025-01-24 | 3701235.71 | 107384.73 | 0 | 3699526.31 | -1709.4 | 180 | 236 | 26 | 0 | 56
PHARR | 1586-01-089 | HIDALGO | FM 907 | 2025-01-03 | 1313573.1 | 20400 | 0 | 1290099.87 | -23473.23 | 140 | 190 | 50 | 0 | 50
PHARR | 0255-08-111 | HIDALGO | IH 69C | 2024-11-20 | 6495030.9 | 228296.65 | 0 | 7024789.07 | 529758.17 | 120 | 87 | 0 | 0 | -33
PHARR | 0921-02-483 | HIDALGO | VA | 2024-10-22 | 1287240.2 | 7455 | 0 | 1251923.4 | -35316.8 | 239 | 175 | 0 | 0 | -64
PHARR | 0039-18-123 | HIDALGO | IH 2 | 2024-10-15 | 6490669.1 | 9450 | 0 | 6431368.33 | -59300.77 | 100 | 77 | 0 | 0 | -23
PHARR | 0684-01-073 | CAMERON | FM 511 | 2024-10-08 | 4012543.76 | 0 | 0 | 3814613.62 | -197930.14 | 100 | 66 | 0 | 0 | -34
SAN ANGELO | 0142-01-076 | KIMBLE | IH 10 | 2025-02-09 | 20144525.28 | 87075.06 | 0 | 21284986.77 | 1140461.49 | 107 | 136 | 50 | 0 | 29
SAN ANGELO | 0907-00-178 | TOM GREEN | VA | 2025-02-03 | 1264222.11 | 79417.66 | 0 | 1245863.83 | -18358.28 | 171 | 205 | 16 | 0 | 34
SAN ANGELO | 0112-01-019 | KIMBLE | US 290 | 2025-01-28 | 4234053.39 | 191520.88 | 0 | 4449126.37 | 215072.98 | 235 | 563 | 324 | 0 | 328
SAN ANGELO | 0034-03-019 | RUNNELS | US 83 | 2025-01-06 | 24497111.44 | 23500.59 | 0 | 25759058.93 | 1261947.49 | 578 | 587 | 12 | 0 | 9
SAN ANGELO | 0036-05-044 | REAL | US 83 | 2024-12-17 | 10347155.74 | 3956291.82 | 0 | 11960596.98 | 1613441.24 | 96 | 76 | 2 | 0 | -20
SAN ANGELO | 0907-00-226 | TOM GREEN | CS | 2024-11-22 | 1186200 | -21718.03 | 0 | 1167254.97 | -18945.03 | 149 | 201 | 0 | 0 | 52
SAN ANGELO | 0463-04-024 | GLASSCOCK | SH 158 | 2024-11-21 | 26934934.66 | -117385.1 | 0 | 26988805.51 | 53870.85 | 517 | 532 | 17 | 0 | 15
SAN ANGELO | 0158-01-081 | RUNNELS | US 67 | 2024-11-18 | 5693419.75 | 7333.9 | 0 | 5707561.75 | 14142 | 379 | 391 | 0 | 0 | 12
SAN ANGELO | 0333-02-013 | STERLING | SH 163 | 2024-11-04 | 2615605 | 157665.7 | 0 | 2708747.7 | 93142.7 | 187 | 213 | 24 | 0 | 26
SAN ANGELO | 0141-02-033 | SUTTON | IH 10 | 2024-10-29 | 21298153.59 | -1416598.59 | 0 | 20933481.12 | -364672.47 | 221 | 316 | 0 | 0 | 95
SAN ANGELO | 0907-00-214 | TOM GREEN | Various | 2024-09-26 | 3746246.46 | -46151.04 | 0 | 3671169.58 | -75076.88 | 79 | 59 | 10 | 0 | -20
SAN ANGELO | 0141-03-062 | SUTTON | IH 10 | 2024-09-24 | 11863753.83 | 954893.06 | 0 | 12545116.84 | 681363.01 | 130 | 146 | 10 | 0 | 16
SAN ANGELO | 0907-24-054 | TOM GREEN | Various | 2024-09-05 | 1415245.12 | 3346.71 | 0 | 1453701.56 | 38456.44 | 63 | 59 | 0 | 0 | -4
SAN ANTONIO | 0658-01-045 | BEXAR | FM 1535 | 2025-02-05 | 15523367.42 | 1476602.74 | -218287.68 | 16730801.87 | 1425722.13 | 540 | 621 | 81 | 4 | 77
SAN ANTONIO | 2708-01-033 | BEXAR | FM 2696 | 2025-02-03 | 778577 | 111847.61 | 0 | 896148.62 | 117571.62 | 89 | 78 | 0 | 0 | -11
SAN ANTONIO | 1740-03-019 | ATASCOSA | FM 1333 | 2025-01-28 | 4025335.99 | 153503.36 | 0 | 4202707.98 | 177371.99 | 109 | 152 | 45 | 0 | 43
SAN ANTONIO | 0073-09-040 | BEXAR | IH 37 | 2025-01-10 | 292836 | 0 | 0 | 292830 | -6 | 54 | 41 | 0 | 0 | -13
SAN ANTONIO | 0025-10-097 | GUADALUPE | FM 78 | 2025-01-02 | 1371678.58 | 32871.91 | 0 | 1358169.73 | -13508.85 | 86 | 82 | 0 | 0 | -4
SAN ANTONIO | 0236-04-029 | FRIO | FM 117 | 2024-12-30 | 22497898.08 | 418231.37 | 0 | 22674568.66 | 176670.58 | 588 | 583 | 1 | 0 | -5
SAN ANTONIO | 0915-12-770 | BEXAR | Various | 2024-12-19 | 491128.33 | 9495.42 | 0 | 510254.23 | 19125.9 | 78 | 64 | 0 | 0 | -14
SAN ANTONIO | 0216-01-057 | COMAL | SL 337 | 2024-12-17 | 14284639.49 | 499305.68 | 0 | 14810900.93 | 526261.44 | 350 | 436 | 86 | 0 | 86
SAN ANTONIO | 0915-14-045 | WILSON | CR | 2024-12-06 | 557521.7 | 15484 | 0 | 567979.28 | 10457.58 | 175 | 81 | 0 | 0 | -94
SAN ANTONIO | 0017-04-042 | ATASCOSA | IH 35 | 2024-11-25 | 12910717.48 | 3365790.31 | 0 | 17232769.49 | 4322052.01 | 345 | 345 | 0 | 0 | 0
SAN ANTONIO | 0915-14-048 | WILSON | CS | 2024-11-22 | 1044921 | 55316.68 | 55316.68 | 1085147.75 | -15089.93 | 55 | 69 | 21 | 21 | -7
SAN ANTONIO | 0915-12-693 | BEXAR | CR | 2024-11-12 | 1705802.68 | 62470.85 | 0 | 1779546.18 | 73743.5 | 130 | 124 | 10 | 0 | -6
SAN ANTONIO | 0142-10-028 | KENDALL | RM 473 | 2024-11-08 | 640687.25 | 0 | 0 | 665487.12 | 24799.87 | 32 | 32 | 0 | 0 | 0
SAN ANTONIO | 0366-03-068 | GUADALUPE | SH 123 | 2024-11-08 | 24608308.91 | 728174.34 | 0 | 26636326.9 | 2028017.99 | 482 | 920 | 488 | 0 | 438
SAN ANTONIO | 0348-07-018 | ATASCOSA | FM 99 | 2024-10-30 | 15357877.23 | 264607.29 | 0 | 15856763.87 | 498886.64 | 743 | 502 | 0 | 0 | -241
SAN ANTONIO | 0017-13-012 | ATASCOSA | SH 132 | 2024-10-28 | 6628642 | 304378.55 | 0 | 6641766.36 | 13124.36 | 410 | 291 | 0 | 0 | -119
SAN ANTONIO | 1433-01-029 | BEXAR | FM 2252 | 2024-10-01 | 6580022.65 | 677818.31 | 194928.97 | 7766645.36 | 991693.74 | 303 | 435 | 135 | 95 | 37
SAN ANTONIO | 0024-01-109 | UVALDE | US 90 | 2024-09-19 | 1194194.94 | 112.8 | 0 | 1206183.18 | 11988.24 | 60 | 59 | 0 | 0 | -1
SAN ANTONIO | 0072-05-090 | KENDALL | IH 10 | 2024-09-04 | 5699777.56 | 1330293.68 | 0 | 6282530.92 | 582753.36 | 104 | 101 | 0 | 0 | -3
TYLER | 0095-08-021 | SMITH | US 80 | 2025-02-28 | 21313599.05 | -389663.75 | 0 | 20436143.48 | -877455.57 | 170 | 164 | 0 | 0 | -6
TYLER | 0190-03-087 | WOOD | SH 37 | 2025-02-20 | 4577457.44 | 4387022.96 | 0 | 9359240.63 | 4781783.19 | 83 | 268 | 138 | 0 | 185
TYLER | 0910-16-147 | SMITH | CS | 2025-02-18 | 1258293.7 | 2000 | 0 | 1382619.37 | 124325.67 | 180 | 147 | 0 | 0 | -33
TYLER | 0910-00-131 | SMITH | Various | 2025-02-14 | 2538364 | -373716.13 | 0 | 2213436.68 | -324927.32 | 196 | 163 | 1 | 0 | -33
TYLER | 0191-01-093 | SMITH | US 69 | 2025-02-03 | 444558 | 18659 | 0 | 468710.5 | 24152.5 | 34 | 29 | 0 | 0 | -5
TYLER | 0910-00-136 | SMITH | Various | 2025-01-17 | 932150 | 0 | 0 | 932725 | 575 | 38 | 28 | 0 | 0 | -10
TYLER | 0245-06-087 | SMITH | SH 64 | 2024-12-16 | 2208247.24 | 16023.29 | 0 | 2185109.63 | -23137.61 | 115 | 107 | 0 | 0 | -8
TYLER | 1171-01-022 | VAN ZANDT | FM 859 | 2024-12-06 | 3629409.25 | 281395.76 | 0 | 3969899.22 | 340489.97 | 166 | 179 | 13 | 0 | 13
TYLER | 0910-34-037 | HENDERSON | Various | 2024-11-12 | 173162 | 8500 | 0 | 174709.34 | 1547.34 | 64 | 31 | 0 | 0 | -33
TYLER | 0378-06-022 | CHEROKEE | SH 135 | 2024-10-11 | 4193458.94 | -146013.19 | 0 | 4106229.88 | -87229.06 | 153 | 150 | 0 | 0 | -3
TYLER | 0443-01-034 | VAN ZANDT | SH 198 | 2024-10-03 | 234450 | 0 | 0 | 239400 | 4950 | 16 | 10 | 0 | 0 | -6
TYLER | 0910-07-084 | GREGG | Various | 2024-09-27 | 224591.52 | 19400 | 0 | 245400.52 | 20809 | 17 | 11 | 0 | 0 | -6
TYLER | 0910-08-081 | ANDERSON | VA | 2024-09-27 | 757095 | 0 | 0 | 772371 | 15276 | 47 | 45 | 0 | 0 | -2
TYLER | 0910-16-169 | SMITH | VA | 2024-09-27 | 157495 | 0 | 0 | 159155.64 | 1660.64 | 86 | 81 | 0 | 0 | -5
TYLER | 0108-02-033 | VAN ZANDT | SH 19 | 2024-09-26 | 12108565.85 | -342423 | 0 | 12285353.8 | 176787.95 | 434 | 335 | 4 | 0 | -99
TYLER | 0634-01-014 | CHEROKEE | FM 22 | 2024-09-25 | 5533705.84 | -4395.13 | 0 | 5247508.68 | -286197.16 | 249 | 383 | 0 | 0 | 134
TYLER | 0198-01-032 | HENDERSON | BU 175G | 2024-09-24 | 695973.8 | 120282.22 | 0 | 895991.03 | 200017.23 | 71 | 71 | 0 | 0 | 0
TYLER | 0910-07-078 | GREGG | CS | 2024-09-19 | 638112.63 | 69403.25 | 0 | 732238.84 | 94126.21 | 58 | 97 | 39 | 0 | 39
WACO | 2311-01-042 | MCLENNAN | SL 340 | 2025-02-24 | 3759444.64 | 35828.05 | 0 | 3816287.97 | 56843.33 | 75 | 78 | 0 | 0 | 3
WACO | 3448-02-007 | MCLENNAN | FM 3268 | 2025-02-20 | 2735685.61 | 355133.62 | 0 | 2981185.01 | 245499.4 | 105 | 87 | 0 | 0 | -18
WACO | 0909-00-094 | MCLENNAN | Various | 2025-02-10 | 2897993.38 | 0 | 0 | 2522074.24 | -375919.14 | 60 | 37 | 0 | 0 | -23
WACO | 0833-01-009 | CORYELL | FM 217 | 2025-01-30 | 7582811.52 | -6609.71 | 0 | 6703339.31 | -879472.21 | 60 | 47 | 0 | 0 | -13
WACO | 0015-01-258 | MCLENNAN | IH 35 | 2025-01-27 | 787764.5 | 0 | 0 | 759616.26 | -28148.24 | 60 | 58 | 0 | 0 | -2
WACO | 0909-22-190 | MCLENNAN | CS | 2025-01-03 | 648860 | 37382.05 | 0 | 869725.76 | 220865.76 | 45 | 58 | 10 | 0 | 13
WACO | 0909-36-182 | BELL | CS | 2024-12-18 | 461858.81 | 35772 | 0 | 496236.53 | 34377.72 | 45 | 40 | 0 | 0 | -5
WACO | 1054-02-023 | BOSQUE | FM 219 | 2024-12-18 | 10387524.22 | 161324.36 | 0 | 10026263.91 | -361260.31 | 300 | 324 | 25 | 0 | 24
WACO | 0055-15-081 | MCLENNAN | US 84 | 2024-12-12 | 299986.38 | 0 | 0 | 293120.63 | -6865.75 | 45 | 23 | 0 | 0 | -22
WACO | 0049-01-101 | MCLENNAN | SL 484 | 2024-12-04 | 850998.1 | -171413 | 0 | 696888.77 | -154109.33 | 60 | 60 | 0 | 0 | 0
WACO | 3534-02-007 | BELL | SH 201 | 2024-11-26 | 5861341.86 | 9285.43 | 0 | 5608743 | -252598.86 | 120 | 103 | 0 | 0 | -17
WACO | 0184-01-068 | CORYELL | SH 36 | 2024-11-19 | 291325 | 524 | 0 | 291849 | 524 | 75 | 58 | 0 | 0 | -17
WACO | 0231-04-060 | BELL | IH 14 | 2024-11-19 | 39466124 | 3682657.34 | 0 | 44795767.17 | 5329643.17 | 360 | 525 | 165 | 0 | 165
WACO | 0231-03-145 | BELL | US 190 | 2024-11-14 | 44733665.59 | 766643.4 | 0 | 48205163.22 | 3471497.63 | 375 | 605 | 255 | 0 | 230
WACO | 0867-01-017 | HAMILTON | FM 932 | 2024-11-14 | 13587882.83 | -323157.03 | 0 | 13379432.69 | -208450.14 | 405 | 399 | 0 | 0 | -6
WACO | 0120-03-031 | BOSQUE | SH 22 | 2024-11-08 | 9797442.66 | 2091696.91 | 0 | 11972697.88 | 2175255.22 | 210 | 308 | 70 | 0 | 98
WACO | 0774-03-015 | HAMILTON | FM 1602 | 2024-11-08 | 127891 | 850 | 0 | 123907 | -3984 | 30 | 22 | 0 | 0 | -8
WACO | 0909-00-052 | MCLENNAN | Various | 2024-11-01 | 436915 | 0 | 0 | 414510 | -22405 | 45 | 25 | 0 | 0 | -20
WACO | 0833-02-020 | BOSQUE | FM 217 | 2024-10-31 | 12983870.35 | -489446.09 | 0 | 12586655.19 | -397215.16 | 315 | 317 | 16 | 0 | 2
WACO | 0019-03-028 | HILL | SH 171 | 2024-10-30 | 5859952.5 | 243970 | 0 | 6394099.02 | 534146.52 | 270 | 258 | 0 | 0 | -12
WACO | 0909-22-188 | MCLENNAN | CS | 2024-10-15 | 448310 | -353.44 | 0 | 427156.24 | -21153.76 | 45 | 34 | 0 | 0 | -11
WACO | 0386-02-026 | BOSQUE | SH 144 | 2024-09-26 | 4557803.14 | -439335 | 0 | 4071307.47 | -486495.67 | 90 | 82 | 0 | 0 | -8
WACO | 0015-01-256 | MCLENNAN | IH 35 | 2024-09-24 | 341697 | 0 | 0 | 336766.59 | -4930.41 | 45 | 47 | 0 | 0 | 2
WACO | 0231-03-154 | BELL | IH 14 | 2024-09-23 | 4494840 | -39536.35 | 0 | 4608112.02 | 113272.02 | 234 | 200 | 0 | 0 | -34
WACO | 0209-01-071 | MCLENNAN | US 77 | 2024-09-20 | 796944.5 | 25043 | 0 | 835148.07 | 38203.57 | 75 | 71 | 0 | 0 | -4
WACO | 0014-06-045 | HILL | SH 81 | 2024-09-09 | 1619000 | 179258.15 | 0 | 1733204.28 | 114204.28 | 134 | 169 | 36 | 0 | 35
WACO | 0055-15-072 | MCLENNAN | US 84 | 2024-09-04 | 9930693.78 | 316574.78 | 0 | 10889532.96 | 958839.18 | 240 | 303 | 63 | 0 | 63
WICHITA FALLS | 0282-02-031 | CLAY | SH 79 | 2025-02-24 | 3246126.19 | 272.58 | 0 | 3153288.81 | -92837.38 | 60 | 137 | 2 | 0 | 77
WICHITA FALLS | 0903-00-120 | WICHITA | VA | 2025-02-20 | 833158.86 | 0 | 0 | 807264.96 | -25893.9 | 78 | 103 | 0 | 0 | 25
WICHITA FALLS | 0903-00-119 | WICHITA | VA | 2025-02-14 | 689012.1 | 0 | 0 | 694186.09 | 5173.99 | 70 | 74 | 0 | 0 | 4
WICHITA FALLS | 0013-05-065 | MONTAGUE | US 81 | 2025-02-06 | 2243728.59 | 0 | 0 | 2039673.03 | -204055.56 | 193 | 130 | 0 | 0 | -63
WICHITA FALLS | 0282-03-031 | CLAY | SH 79 | 2024-12-19 | 4472468.24 | 269903.58 | 0 | 4702841.5 | 230373.26 | 127 | 186 | 9 | 0 | 59
WICHITA FALLS | 0146-07-033 | WILBARGER | US 70 | 2024-12-12 | 2143240 | 509332.34 | 0 | 2673976.28 | 530736.28 | 122 | 225 | 114 | 0 | 103
WICHITA FALLS | 0043-05-112 | WILBARGER | US 287 | 2024-11-20 | 3882921.05 | 28486.8 | 0 | 3755218.91 | -127702.14 | 210 | 205 | 8 | 0 | -5
WICHITA FALLS | 1609-01-029 | COOKE | FM 1630 | 2024-11-01 | 4611140.62 | -127243.59 | 0 | 4565170.85 | -45969.77 | 170 | 144 | 0 | 0 | -26
WICHITA FALLS | 0124-04-038 | WILBARGER | US 183 | 2024-10-01 | 15116541.73 | 1411392.53 | 0 | 15220263.64 | 103721.91 | 359 | 582 | 11 | 0 | 223
WICHITA FALLS | 0823-01-038 | COOKE | FM 373 | 2024-09-19 | 903763.84 | -152701.96 | 0 | 703937.21 | -199826.63 | 34 | 33 | 0 | 0 | -1
YOAKUM | 0535-07-050 | FAYETTE | IH 10 | 2025-02-28 | 10399532.44 | -527095.35 | 0 | 9967394.07 | -432138.37 | 225 | 194 | 0 | 0 | -31
YOAKUM | 0715-03-014 | DEWITT | FM 108 | 2025-02-28 | 10571632.45 | -88996.04 | 0 | 10249109.68 | -322522.77 | 270 | 308 | 38 | 0 | 38
YOAKUM | 0535-08-089 | COLORADO | IH 10 | 2025-02-05 | 4831460.04 | -194250 | 0 | 4301678.99 | -529781.05 | 75 | 67 | 0 | 0 | -8
YOAKUM | 0179-04-102 | MATAGORDA | SH 35 | 2025-02-04 | 327710 | -9546.7 | 0 | 308254.04 | -19455.96 | 30 | 20 | 0 | 0 | -10
YOAKUM | 0913-00-114 | DEWITT | VA | 2025-01-22 | 1652900 | 0 | 0 | 1649500 | -3400 | 120 | 64 | 0 | 0 | -56
YOAKUM | 0535-06-046 | FAYETTE | IH 10 | 2025-01-06 | 1588806.6 | 12293.32 | 0 | 1800499.2 | 211692.6 | 158 | 139 | 0 | 0 | -19
YOAKUM | 0143-08-098 | DEWITT | US 87 | 2024-12-16 | 6692309 | 1667476.08 | 0 | 8550631.49 | 1858322.49 | 125 | 147 | 22 | 0 | 22
YOAKUM | 0408-01-043 | FAYETTE | SH 159 | 2024-12-03 | 5331593.91 | 125891.05 | 0 | 5464571.69 | 132977.78 | 294 | 293 | 0 | 0 | -1
YOAKUM | 0913-28-088 | FAYETTE | CR | 2024-12-03 | 1728303.93 | 25044.54 | 0 | 1757900.51 | 29596.58 | 195 | 185 | 0 | 0 | -10
YOAKUM | 0315-09-011 | AUSTIN | FM 2502 | 2024-11-25 | 1284265 | 76593.4 | 0 | 1430603.65 | 146338.65 | 105 | 123 | 12 | 0 | 18
YOAKUM | 0913-28-075 | FAYETTE | CR | 2024-11-22 | 805990.58 | 0 | 0 | 787929.1 | -18061.48 | 103 | 101 | 0 | 0 | -2
YOAKUM | 0913-09-106 | WHARTON | CR | 2024-11-05 | 958659 | -95810 | 0 | 829123.35 | -129535.65 | 120 | 126 | 0 | 0 | 6
YOAKUM | 0089-06-093 | WHARTON | US 59 | 2024-10-03 | 2182905.02 | 0 | 0 | 2182996.49 | 91.47 | 72 | 51 | 0 | 0 | -21
YOAKUM | 0913-09-102 | WHARTON | CR | 2024-10-03 | 1244083.83 | 0 | 0 | 1237442.91 | -6640.92 | 238 | 138 | 0 | 0 | -100
YOAKUM | 0913-09-109 | WHARTON | CR | 2024-10-03 | 1626862.5 | 0 | 0 | 1595307.1 | -31555.4 | 184 | 140 | 0 | 0 | -44
YOAKUM | 0913-09-117 | WHARTON | CR | 2024-10-03 | 535853.15 | 0 | 0 | 530542.04 | -5311.11 | 59 | 51 | 0 | 0 | -8
YOAKUM | 0913-17-044 | DEWITT | Various | 2024-09-30 | 151104 | 2500 | 0 | 151109 | 5 | 59 | 50 | 0 | 0 | -9
YOAKUM | 0913-28-093 | FAYETTE | Various | 2024-09-30 | 286575.5 | 4072.2 | 0 | 279161.2 | -7414.3 | 62 | 44 | 0 | 0 | -18
YOAKUM | 3173-01-004 | WHARTON | FM 3086 | 2024-09-09 | 3597289.16 | -117688 | 0 | 3447687.98 | -149601.18 | 120 | 156 | 16 | 0 | 36
YOAKUM | 0446-02-037 | COLORADO | UA 90 | 2024-09-05 | 3351389.94 | 23531.19 | 0 | 3364858.2 | 13468.26 | 191 | 202 | 0 | 0 | 11
YOAKUM | 0913-20-093 | AUSTIN | CR | 2024-09-05 | 1258243.84 | 16329 | 0 | 1267589.34 | 9345.5 | 172 | 156 | 0 | 0 | -16
YOAKUM | 0913-28-082 | FAYETTE | CR | 2024-09-05 | 1338296.75 | 0 | 0 | 1335409.45 | -2887.3 | 135 | 115 | 0 | 0 | -20
YOAKUM | 1302-02-013 | WHARTON | FM 647 | 2024-09-05 | 1267616.62 | 0 | 0 | 756731.62 | -510885 | 97 | 411 | 70 | 0 | 314