## Instructions
For all Projects (revised 8/25/2025)
Start in Kickoff Team Selection
1. Fill out header information (it will propogate all subsequent tabs)
2. Identify all Project Team Supervisors & Point of Contacts
Determine Project Acceleration Requirements
1. Develop Project Recommendations prior to KO meeting
2. During Kickoff Meeting propose and discuss project needs
3. Document Project Team approval of selected Acceleration Method
Kickoff Checklist
1. Kickoff Checklist is not mandatory.
2. Intent is to offer an option of project elements to either accomplish before Kickoff or to explore the implications of prior to the Kickoff Meeting to maximize the meeting as well as begin coordination efforts.
Acceleration Determination
1. Acceleration Checklist is Mandatory. To be completed as early as possible
2. Intent is to document discussion of what acceleration method (if any) are to be applied to project. Recommend either Kickoff Meeting or Initial Plan Review be used to document discussion and elements to be incorporated
Pavement Design Request Guide
1. Pavement Design Request Guide is Mandatory. To be completed as early as possible
2. Preliminary pavement designs should be completed by the 30% PS&E review. Final pavement report with typical sections, materials, and structural analysis should be completed by 60% PS&E review.
System Safety Checklist
1. System Safety Checklist is Mandatory. To be completed as early as possible
2. Intent is to be used for all District projects to discuss what Safety Elements are to be applied to project. Recommend either Kickoff Meeting or Initial Plan Review be used to document discussion and elements to be incorporated
3. Checklist is updated based on coordination with District Maintenance efforts. Initial Version based on District System Safety Checklist 07-21-20
4. District System Safety Checklist revised 03-13-21
5. District System Safety Checklist revised 07-29-21
6. District System Safety Checklist revised 07-14-22
7. District System Safety Checklist revised 12-12-22
8. District System Safety Checklist revised 06-21-23
9. District System Safety Checklist revised 01-26-24
For all Bridge and/or Bridge Class Culvert
1. Prelim Bridge Checklist is Mandatory. (Acromyn PBLR - Preliminary Bridge Layout Review introduced)
2. Checklist is intended to be used per structure in each project. It is acceptable to use single spreadsheet for entire project for documentation purposes make note in comment box for each section that this has been verified for each bridge structure.
Railroad Coordination
1. Railroad Coordination Checklist is Mandatory. To be completed as early as possible
2. Intent is to be used for all District projects that require Railroad Coordination. Recommend either Kickoff Meeting or Initial Plan Review be used to document discussion and coordination efforts. Checklist added to Development Manual 04-20-21
3. Removed DDGN Point of Contact Box 06-22-21
Bicycle and Pedestrian Facilities
1. Bicycle and Pedestrian Facilities Checklist is Mandatory. To be completed as early as possible
IDF Checklist
1. IDF Checklist is Mandatory. *** To be completed and updated in line with Milestone Reviews
*** For projects similar to Preventive Maintenance discuss with DDGN staff if IDF checklist is necessary for project.
1. Intent of Checklist is to document all project coordination necessary. Emails, meeting summaries, etc documenting effort to be stored in ProjectWise accordingly
2. Select Yes / No / Not Applicable based on current project progression at the time of milestone development.
3. Subsequent milestone submittal to revisit previous IDF stage with the intent of updating the understanding to either Yes / Not Applicable
4. Final submission (Signed and Sealed) to include completed updated of IDF spreadsheets such that there are no longer a "No" response.
Complete PS&E Submittal checklist
1. To be filled out by District PS&E Submittal Coordinator and District Plan Reviewer
2. Information documented on Spreadsheet to identify all necessary files to be provided for the purpose of processing
Project Resolution
1. To be filled out by District Plan Reviewer
2. Information documented on Spreadsheet to document close out of all Subject Matter Expert comments provided during Milestone review
QUICK AND EASY SUBMITTAL STATE LET GUIDELINES BY % MILESTONE
1. To be used as reference of expectations of deliverables and Naming Convention for Review & Submittal.
QUICK AND EASY SUBMITTAL LOCAL LET GUIDELINES BY % MILESTONE
1. To be used as reference of expectations of deliverables and Naming Convention for Review & Submittal.

## Kickoff Team Selection
Kickoff Team Selection
|  | CSJ |  |  |  | Page 1 of 1
County
Highway/Location
Project |  | From
Limits |  | To
Type of Work
Laymans Desc
| Area Office Staff |  |  | Point of Contact
|  | Area Engineer | Area Engineer | AO Super POC | Area Engineer POC
|  | Asst Area Engineer | Asst Area Engineer | AO POC | Person C (AO rep)
|  | Maint. Supervisor | Maintenance Supervisor
| District Design Staff |  |  | Point of Contact
|  | District Design Eng | District Design Eng | TL (DDGN) | Team Leader (DDGN)
|  |  |  | Reviewer | Person A (DDGN PR rep)
|  |  |  | Dist Railroad POC | Dist Railroad POC
Design Staff
|  | Office Lead | Team Leader (PPG) or Office Lead
Project Manager
| District Structures Team |  |  | Point of Contact
|  | TL (Structures) | Team Leader (Str) | Str Super POC | Team Leader (Str)
|  |  |  | Bridge | Person D (Str rep)
|  |  |  | H&H | Person B (HH rep)
| District Transportation Operations |  |  | Point of Contact
|  | Dir of Trf Ops | Dir of Trf Ops | Ops Super POC | Dir of Trf Ops
|  |  |  | Trf POC | Person E (TRF rep)
| Transp Planning & Development |  |  | Point of Contact
|  | Dir of TPD | Dir of TPD | TPD Super POC | TPD Supervisor POC
|  | Asst Dir of TPD | Assist Dir of TPD | TPD POC | Person D (TPD rep)
|  | Dist Env Supervisor | Dist Env Supervisor | Env Super POC | Dist Env Supervisor
|  | Dist ROW Supervisor | ROW Supervisor | Env POC | Person G (Dist Env)
|  |  |  | Utilities POC | Person H (Util rep)
|  |  |  | ROW POC | Person I (ROW rep)
| District Construction |  |  | Point of Contact
|  | Dir of Construction | Dir of Construction | Constr Super POC | Dir of Construction
|  | District Pave Eng | District Pave Eng | Dist Pave POC | Person J (Lab rep)
|  |  |  | Constr POC | Person F (Constr rep)
District Maintenace
|  | Dir of Maintenance | Dir of Maintenance | Maint Super POC | Dir of Maintenance
|  | District Maint Eng | District Maint Eng | Dist Maint POC | Person K (Maint rep)

## Kickoff Checklist
Project Kickoff Checklist
|  | CSJ | 0 |  |  |  | Page 1 of 1
|  | County | 0
|  | Highway/Location | 0
Project |  | From | 0
Limits |  | To | 0
|  | Type of Work | 0
|  | Laymans Desc | 0
| Y | N | N/A | Determine if necessary; "Y", "N","N/A"
Submit CSJ request (if Necessary)
Field Visit
Drive Project(w/Maintenance Section Supervisor, A/O Staff)
Obtain Existing Plans, Determine Existing Stationing
Identify Imagery
Begin Survey Coordination
Request Traffic Data & Accident Data
Review TxDOT Connect screens
|  |  |  | Determine Preliminary Design Criteria |  | Start 1002 | Start DSR
Determine R.O.W. Needs
|  |  |  | Prelim Typical Sections | Determine Curb & Gutter Design |  | Mailbox Turnouts
Determine Side Slopes steeper than 3:1
Submit Attachment 4-Pavement Submittal Checklist to District Lab
Request Initial Pavement Design
Prepare a Preliminary Estimate
|  |  |  | Hydrology Completed | Hydraulic Coordination Initiated
Any FEMA crossings, Zones ____________________
|  |  |  | Identify Hydraulic Staff and level of effort for Hydraulics Design |  |  | WPAP Needed
Identify Structures Staff and level of effort
Environmental Questionnaire Completed
Start APD & PS&E Stage Gate Checklist (John Barton Memo 07/07/11)
Edwards Aquifer Zone
TSS Calculations (Aquifer), coordination for WPAP requirements
Drainage Easements Defined
Preliminary Traffic Control Plan and Sequence of Work (Conceptual)
|  |  |  | Illumination Type | Safety | High Mast | Continuous
Identify Preliminary Retaining Walls (Locations Defined)
Identify Utility in the area / Determine SUE Survey Needs
|  |  |  | Utility Coordination | Utility Coordinator Requested
|  |  |  | Bridge Cores Ordered | Bridge Condition Report Requested
Request Asbestos testing if bridge widening or removal
Preliminary Cross Sections Reviewed
ITS Elemens
Toll Elements
Will a Road Closure be required?
Provide copy of plans to utility companies
|  |  |  | Pedestrian Facilaties | Sidewalks | SUP | Ped Bridge
|  |  |  | Bicycle Facilities | Wide Shldr | Bike Lanes | SUP
Develop a P6 Schedule
Set up meeting with District Railroad Coordinator (if necessary) to scope work
Develop Acceleration Determination Checklist
Develop System Safety Checklist
Determine if Value Engineering Study (VE) is required; Total Project Cost > 50 Million

## Acceleration Determination
Project Acceleration Selection | [9 empty] | Project Acceleration Selection (continued)
|  | CSJ | 0 | [5 empty] | Page 1 of 2 | [9 empty] | Page 2 of 2
|  | County | 0 | [7 empty] | Y | N | Strategies for Public Information |  | Y | N
|  | Highway/Location | 0 | [9 empty] | Coordinate with District PIO |  |  |  | Coordination with emergency services
Project |  | From | 0 | [9 empty] | Press releases/media alerts |  |  |  | Rideshare promotions
Limits |  | To | 0 | [9 empty] | Public information centers |  |  |  | Changeable/dynamic message signs
|  | Type of Work | 0 | [9 empty] | Planned lane closure web site |  |  |  | Contracted public information services
|  | Laymans Desc | 0 | [9 empty] | Coordination with schools, businesses |  |  |  | Paid advertisement
Accelerated Construction Program | [12 empty] | Work zone education/safety campaigns |  |  |  | Telephone hotline
[8 empty] | Concurrence by: |  |  |  |  | Traffic radio |  |  |  | Public meetings/hearings
| Y | N | N/A | Project Selection |  |  |  | AO |  |  |  |  | Highway advisory radio |  |  |  | Brochures/mailers
|  |  |  | Controlled Access highways with lane closures |  |  |  | DDGN |  |  |  |  | Transportation Management Center |  |  |  | Temporary motorist information signs
|  |  |  | Bridge Closures |  |  |  | Dist-Bridge |  |  |  |  | Social media
|  |  |  | Road Closures |  |  |  | Const |  |  |  | Notes
|  |  |  | Added Capacity Projects |  |  |  | Dist-Util
|  |  |  | Access to nearby schools or emergency service facilities |  |  |  | PM
Affect adjacent businesses
|  |  |  | Adding lanes to facilities | [6 empty] | Y | N | Contracting Methods |  | Y | N
|  |  |  | Roadway widening | [8 empty] | Incentives/disincentives |  |  |  | Lane rental disincentive
|  |  |  | Intersections | [8 empty] | Milestones with incentives/disincentives |  |  |  | Cost-Plus-Time bidding (A + B)
|  |  |  | Small cities | [8 empty] | Substantial completion inc/disincentive |  |  |  | No excuse incentive
|  |  |  | Urban streets | [8 empty] | Non Standard Work Week
|  |  |  | Ramps | [9 empty] | 5 Day |  |  | 7 Day
[14 empty] | 6 Day |  |  | Calendar
| Y | N | Strategies for Traffic Control |  | Y | N | [5 empty] | Notes
|  |  | Construction phasing/staging |  |  |  | Full road closures
|  |  | Business access improv/coord |  |  |  | One-lane two-way operations
|  |  | 2-way traffic on 1 side of divided hwy |  |  |  | Reversible lanes
|  |  | Ramp closures/relocations |  |  |  | Night/weekend work |  |  |  | Y | N | Design |  | Y | N
|  |  | Off-site detours/alternative routes |  |  |  | Lane shifts or closures | [5 empty] | Accelerated Bridge Construction |  |  |  | Full Depth Hotmix
|  |  | Innovative construction techniques |  |  |  | Accelerated construction strategies | [6 empty] | Precast Elements |  |  | Detour Pavement
|  | Notes | [11 empty] | Phased Construction
Self Propelled Mobile Transport
Slide In Bridge
Contractor input in design process
| Y | N | Strategies for Transportation Operations |  | Y | N | [6 empty] | Full Depth Hotmix
|  |  | Signal timing/coordination improvements |  |  |  | Truck/heavy vehicle restrictions | [5 empty] | Detour Pavement
|  |  | Street/intersection improvements |  |  |  | Reversible lanes | [5 empty] | Lane Closures
|  |  | Turn/parking restrictions |  |  |  | Railroad crossing controls | [6 empty] | Day Time |  | Short Term |  | 1 lane open
|  |  | Truck lanes |  |  |  | Construction speed zone | [6 empty] | Night Time |  | Long Term |  | 2 lane open
|  |  | Ramp closures |  |  |  | Shadow vehicles with TMA | [10 empty] | Bridge Closure
|  |  | Coordination with adjacent construction |  |  |  | Temporary rumble strips |  |  |  |  | Notes
|  |  | Temporary or moveable traffic barriers |  |  |  | Warning lights
|  |  | Crash cushions |  |  |  | ITS for traffic monitoring/management
|  |  | Intrusion alarms |  |  |  | Surveillance for incidents
|  |  | Review by District Safety Review Team |  |  |  | Incident/emergency response plan
|  |  | Safety award incentives |  |  |  | Local detour routes | [5 empty] | Misc
|  |  | Transportation management center |  |  |  | Traffic fines double
|  |  | Towing/service patrol |  |  |  | Speed trailers or fixed radar units
|  |  | Police presence/enforcement |  |  |  | Bus turnouts
Notes

## Pavement Design Request Guide
Pavement Design Request Guide
|  | CSJ | 0 |  | if CCSJ, include all individual CSJ’s that need a pavement design |  | Page 1 of 1
|  | County | 0
|  | Highway/Location | 0
Project |  | From | 0
Limits |  | To | 0
Type of Work |  |  | 0
Laymans Desc |  |  | 0
Estimated Let Date
30% PS&E Review Date
60% PS&E Review Date
Email this form to the District Pavement Engineer and AUS_Pavements@txdot.gov; cc Area Office when applicable. Include CSJ, Highway, and County in the email subject header (example: CSJ 0015-09-194, IH35 Williamson Co., Pavement Design Request).
Include this information in the email if available.
| Y | N | N/A | Determine if necessary; "Y", "N","N/A"
Map with project limits
Project's schematics
Existing typical sections or as-builts plans from previous projects
TPP traffic report
| Date |  |  | If TPP traffic report request was submitted, when is it expected?
Geotechnical report
| Date |  |  | If geotechnical investigation will be performed, when is the report expected?
Roadway cores available
Additional Project information
| Y | N | N/A | Determine if necessary; "Y", "N","N/A"
Is this a Maintenance (PM) project?
Is this an overlay project to restore skid or ride?
Is milling expected?
Is the project in a floodplain zone? (Milling is required prior to an overlay to avoid raising roadway elevation.)
Does existing pavement have edge restrictions such as curb & gutter?
Safety widening (<= 4')?
Additional pavement (> 4')?
Does the widening include a full-width overlay (HMA or Seal coat)?
Is there nearby project(s) with same/similar project description?
| CSJ |  |  | If yes, list the CSJ(s) of the project(s)
Temporary pavement section needed?
| XX months |  |  | If yes, how long will the temporary pavement be used for?
Full depth repair thickness needed?
Pavement sections for cross streets needed?
Pavement section for frontage roads needed?
Is a Value Engineering Study (VE) required?
Additional project information:
Checklist for DPE
| Y | N | N/A | Determine if necessary; "Y", "N","N/A"
|  |  |  | Folder created for project |  | Folder Address:
|  |  |  | GPR data available |  | File Name:
|  |  |  | FWD data available |  | File Name:
PMIS data
Soils (PI, Sulfates, Organics)
Traffic
PVR needed?
Concrete Design needed?
SAC-A
| XX |  |  | Surface Mix

## System Safety Checklist-Constr
System Safety Checklist - Major Improvement and Construction Projects
| CSJ | 0 |  |  | Page 1 of 1
| County | 0
| Highway/Location | 0
Project | From | 0
Limits | To | 0
| Type of Work | 0
| Laymans Desc | 0
System Safety Checklist - Major Improvement and Construction Projects
System Safety Item |  | Roadways | Check if Applicable | Criteria | Conditions
Pavement Surface |  | All Roadways |  | High Friction Surface Treatment | Install surfacing that meets criteria across entire pavement width. Use of high friction surface mixes: seal coat, PFC, SMA and TOM. See the Austin District Pavement Design SOP for surface mixture map.
Pavement Repairs/Level Up |  | All Roadways |  | 2"-6" repairs 1"-1.5" level up | Include as needed. Refer to PM estimate template and flexible pavement detail, anything over 6" repairs or 1.5" level up will require pavement evaluation.
WZ Striping |  | All Roadways |  | Profile Striping | If an existing roadway has profile striping, use Type Y and W buttons as WZ striping at 18" spacing for centerline and edge lines for the duration of construction to improve safety in WZ. Refer to Item 662 Austin District Designers Guide.
Lane RPM Spacings |  | All Roadways |  | 40 foot | As warranted for safety countermeasure by the Engineer such as but not limited to rural, roadway with high side swipe crashes or undivided roadways.
Center Line RPM Spacing |  | All Roadways |  | 40 foot/20 foot | 40 foot for two lane two way and four lane two way roads. 20 foot for curves with high number of Head-On/Run-off-Road crashes.
Edge Line Striping |  | All Roadways |  | Profile Striping | Use profile striping in lieu of milled-in rumble strips per high friction surface treatment policy and milled-in rumble strip standards. Refer to Item 666 and 6056 in Austin District Designers Guide for additional information.
Center Line Striping |  | All Undivided Roadways |  | Profile Striping | Use profile striping.
|  | Undivided Roadway with Shoulder ≥ 4 ft. |  | 30/36 inch center to center-only for continuous stripe | Reduce shoulder width on each side. Standards: clb2-23 (state.tx.us) clb1-23 (state.tx.us)
|  | Undivided Roadway with Shoulder < 4 ft. |  | Max of 18 inch center to center | Refer to pavement marking standard for two lane two way and four lane two way roads. Standard: PM(1)-22 (state.tx.us)
Centerline Rumble Strip |  | All Undivided Roadways |  | Prefabricated strips | Refer to standard and Item 666 and 6056 in Austin District Designers Gude for additional information.
Metal Beam Guardfence |  | All Roadways |  | Upgrade to latest standard | Ensure that TAS are upgraded to new standard, upgrade MBGF to new standard to meet height requirements. Refer to Item 540 & 544 in Austin District Designers Guide for additional information.
Center Median |  | 5-lane, undivided roadways |  | Raised center median | Consider installation of raised center median where ADT exceeds 20,000 vehicles per day and/or where there are operations concerns for mid-block turns.
Median Barrier |  | Divided highways |  | Width of median | Cable barrier use if median is greater than 25'. Concrete barrier if median is less than or equal to 25'. For median barrier consider ped barrier where pedestrian fatalities exist. See Mark Marek Memo dated June 21, 2006 and standard for further guidance. Refer to Item 514 and 543 in Austin District Designers Guide for additional information.
Continuous Barrier & Bridge Rail Delineations |  | All Roadways |  | Reflector at max. 100 feet | Refer to D&OM(1)-20 for reflector type - CTB tab. Refer to D&OM(5)-20 and D&OM(6)-20 for spacing and place in reflector in accordance to D&OM (2)-20 on the side of the CTB. Refer to Item 658 in Austin District Designers Guide for additional information.
Curve Warning Devices |  | Roadways with Substandard with D&OM(3) -20 |  | Upgrade | Identify any curves without chevrons on shape curves meeting the latest criterion on D&OM(3) -20.
Intersection Studies |  | All Roadways |  | New signal/flashing beacon/stop condition/Upgrade Signals + Ped | If warranted install new signal, flashing beacon or stop condition. Consider sight distance and advance warning signs that may also be warranted. Upgrade based on age and existing equipment. Include pedestrian accommodations. For stop condition on minor roadway include use of Install Cross Traffic Does Not Stop (CW4-4P).
Grade Separation |  | As required if feasible |  | Grade separate intersection | Install grade separation for railroad or other intersecting road as warranted.
Railroad Crossings |  | All Roadways |  | All crossings-all projects | Replank as necessary, based on condition. Correct vertical profile issues to avoid humped intersections. Coordinate with District Railroad coordinator.
Pedestrian Elements |  | All Roadways |  | Pedestrian Elements | Include shared used path, curb ramps and ped signals.
ITS |  | All Roadways |  | New installation | Place in Phase 1 construction sequence, design alignment for proper placement, if not possible specify to maintain existing ITS infrastructure throughout construction.
Intersection Safety Lighting |  | All Roadways |  | Lighting | Install lighting at an intersection where either none existed previously or major improvements are proposed. Consider high mast at interchanges/intersections. Install lighting with all traffic signal installation. Review crash history light conditions.
Segment Safety Lighting |  | All Roadways |  | High Mast Illumination/Continuous/ Safety Iighting | Install high mast as default, consider continuous or partial lighting if high mast is not warranted. Install lighting in first phase of the construction sequence if possible to improve safety during construction.
Prep ROW |  | All Roadways |  | Clear zone | Remove all obstructions from the clear zone including trees. Avoid added elements within the clear zone. Verify if tree(s) have significance that would warrant preservation. Design to desirable.
Tree and Brush Trimming and Removal |  | All Roadways with Tree or Brush with clearance height less than 20 feet or within clear zone |  | Clearance of a minimum of 20 feet/Clear Zone | Identify any tree or brush within the limits with less than 20 foot clearence. Eliminate obstruction/tree or protect. Include district tree trim standard and prep ROW bid item.
Mowing |  | All Roadways |  | Greater than 12 month duration | Refer to Item 730, 734, & 738 in Austin District Designers Guide for additional information.
Litter Pick-Up |  | All Roadways |  | Greater than 12 month duration | Refer to Item 730, 734, & 738 in Austin District Designers Guide for additional information.
Sweeping |  | All Roadways |  | Greater than 12 month duration | Refer to Item 730, 734, & 738 in Austin District Designers Guide for additional information.
Corrugated Metal Pipe |  | All Roadways |  | Replace all existing CMP | Use appropriate concrete pipe.
Eliminate Low Water Crossings |  | As required if feasible |  | Raise roadway profile to clear event- On-System | Span crossing or install larger culverts to eliminate low water crossing. If not feasible, install a high water detection system.
Eliminate Narrow Bridges and Approaches |  | As required if feasible |  | Widen roadway, widen/replace bridge - On-System | Widen aproaches and bridges to eliminate narrow sections.
Bridge Vertical Clearance |  | All Roadways |  | Mill depth of overlay | Refer to Austin District Flex Pave standards for milling detail under bridges.

## System Safety Checklist-PM
System Safety Checklist - Preventative Maintenance Projects
| CSJ | 0 |  |  | Page 1 of 1
| County | 0
| Highway/Location | 0
Project | From | 0
Limits | To | 0
| Type of Work | 0
| Laymans Desc | 0
System Safety Checklist - Preventative Maintenance Projects
System Safety Item |  | Roadways | Check if Applicable | Criteria | Conditions
Pavement Surface |  | All Roadways |  | High Friction Surface Treatment | Install surfacing that meets criteria across entire pavement width. Use of high friction surface mixes: seal coat, PFC, SMA and TOM. See the Austin District Pavement Design SOP for surface mixture map.
Pavement Repairs/Level Up |  | All Roadways |  | 2"-6" repairs 1"-1.5" level up | Include as needed. Refer to PM estimate template and flexible pavement detail, anything over 6" repairs or 1.5" level up will require pavement evaluation.
Pavement Edge Drop-offs |  | All Roadways |  | 2" or greater | Refer to standard detail.
Lane RPM Spacings |  | All Roadways |  | 40 foot | As warranted for safety countermeasure by the Engineer such as but not limited to rural, roadway with high side swipe crashes or undivided roadways.
Center Line RPM Spacing |  | All Roadways |  | 40 foot/20 foot | 40 foot for two lane two way and four lane two way roads. 20 foot for curves with high number of Head-On/Run-off-Road crashes.
Edge Line Striping |  | All Roadways |  | Profile Striping | Use profile striping in lieu of milled-in rumble strips per high friction surface treatment policy and milled-in rumble strip standards. Refer to Item 666 and 6056 in Austin District Designers Guide for additional information.
Center Line Striping |  | All Undivided Roadways |  | Profile Striping | Use profile striping.
|  | Undivided Roadway with Shoulder ≥ 4 ft. |  | 30/36 inch center to center-only for continuous stripe | Reduce shoulder width on each side. Standards: clb2-23 (state.tx.us) clb1-23 (state.tx.us)
|  | Undivided Roadway with Shoulder < 4 ft. |  | 18 inch center to center | Refer to pavement marking standard for two lane two way and four lane two way roads. Standard: PM(1)-22 (state.tx.us)
Centerline Rumble Strip |  | All Undivided Roadways |  | Prefabricated strips | Refer to standard and Item 666 and 6056 in Austin District Designers Guide for additional information.
Metal Beam Guardfence |  | All Roadways |  | Upgrade to latest standard | Upgrade all MBGF and GET to latest MASH complaint standards. Quanitfy and estimate the amount of upgraded required for the limits of a PM project. Specify post delineator for all MBGF; no buttterflies. SUBMIT THIS ESTIMATE AND LOCATIONS SEPARATE FROM THE PM ESTIMATE FOR RMC FUNDING APPROVAL.
Continuous Barrier & Bridge Rail Delineations |  | All Roadways |  | Reflector at max. 100 feet | Refer to D&OM(1)-20 for reflector type - CTB tab. Refer to D&OM(5)-20 and D&OM(6)-20 for spacing and place in reflector in accordance to D&OM (2)-20 on the side of the CTB. Refer to Item 658 in Austin District Designers Guide for additional information.
Curve Warning Devices |  | Roadways with Substandard with D&OM(3) -20 |  | Upgrade | Identify any curves without chevrons on shape curves meeting the latest criterion D&OM(3) -20. SUBMIT THE CURVES LOCATIONS WITH THE PM ESTIMATE.
Railroad Crossings |  | All Roadways |  | All crossings - all projects | Include striping and approach pavement. Replace signs as needed. Coordinate with District Railroad coordinator. SUBMIT RR CROSSING LOCATIONS WITH THE PM ESTIMATE.
Pedestrian Elements |  | All Roadways |  | Pedestrian Elements | Include curb ramps as needed/communicate need to ADA coordinator for improvements.
Tree and Brush Trimming and Removal |  | All Roadways with Tree or Brush with clearance height less than 20 feet or within clear zone |  | Clearance of a minimum of 20 feet/Clear Zone | Identify any tree or brush within the limits with less than 20 foot clearence. Eliminate obstruction/tree or protect. Submit these locations to Austin District Maintenance to schedule tree and brush trimming and removal PRIOR to the PM project.
Bridge Vertical Clearance |  | All Roadways |  | Mill depth of overlay | Refer to Austin District Flex Pave standards for milling detail under bridges.

## Preliminary Bridge Layout
Preliminary Bridge Layout
|  | CSJ | 0 |  | Page 1 of 5
|  | County | 0
|  | Highway/Location | 0
Project | From |  | 0
Limits | To |  | 0
|  | Type of Work | 0
Laymans Desc |  |  | 0
Submittal Documents
| Y | N | N/A
1 |  |  |  | Title Sheet
2 |  |  |  | Typical
3 |  |  |  | Bridge Layout
4 |  |  |  | Hydraulic Data
5 |  |  |  | Retaining Wall Layout(s)
6 |  |  |  | Soil Bore Log
Comments
General Information
| Y | N | N/A
1 |  |  |  | Confirm Bridge Replacement (BR) or Bridge Widening and Rehabilitation (BWR) matches TxDOT Connect; Both Type of Work and Project Classification (if applicable)
2 |  |  |  | Confirm Scour Analysis has been completed and details included
3 |  |  |  | Plan View - normally shown in ascending stations from left to right.
4 |  |  |  | Elevation View - normally shown as a section through the profile grade line or control line, and should be visually aligned with the plan view.
5 |  |  |  | Typical Transverse Section - showing only the superstructure. Not required when a Staged or Phase Construction sheet is included.
6 |  |  |  | Scale 1"=20' or either 1"=40' for both vertical or horizontal. Do not mix horizontal scales and vertical scales. Show Scale Bar at the title block.
7 |  |  |  | Show proposed structure in bold, heavy weight outline to make it stand out on the plan view.
8 |  |  |  | Show only neccesary of the support informations with the light weight. Show Existing Structure in shade and in light gray color.
9 |  |  |  | Structure dimensions - bridge and rail lengths on elevation view in decimal feet to the nearest 0.01'. Widths on plan and transverse section views in feet and inches to the nearest 1/4 " (all acceptable, and preferred, on complex structures).
10 |  |  |  | Drilled Shafts - in feet rounded up to the next whole foot for lengths and in inches for drilled shaft sizes.
11 |  |  |  | Columns - in feet rounded up to the next whole foot.
12 |  |  |  | Elevation - in decimal feet to the nearest 0.001'.
General Information |  |  |  |  | Page 2 of 5
13 |  |  |  | Bearings and Angles - in degrees, minutes, and seconds to the nearest whole second.
14 |  |  |  | Stations - in decimal feet to the nearest 0.01'.
Comments
Typical Transverse Section
| Y | N | N/A
1 |  |  |  | Show widths (overall, roadway, shoulders, sidewalks, etc.).
2 |  |  |  | Local profile grade line and/or horizontal control line.
3 |  |  |  | Show cross slope.
4 |  |  |  | Dimension to stage construction joints for widening or stage construction projects. See Miscellaneous Slab Information in Appendix A.
5 |  |  |  | Show railing.
6 |  |  |  | Identify beam type and numbers (if required).
Comments
Plan View
| Y | N | N/A
1 |  |  |  | Locate reference line, centerline, or profile grade line (bearing, location, and station) and horizontal curve data. Show the railroad station (RR Sta) at intersection of railroad and roadway control lines on railroad overpass and railroad underpass bridges.
2 |  |  |  | Use the same scale horizontally and vertically (either 1:20 or 1:40 at half-scale size).
3 |  |  |  | Begin and end bridge stations and elevations.
4 |  |  |  | Show all bent numbers, stations, and bearings.
5 |  |  |  | Show deck joint type, locations, and size of seal (if used). If a sealed expansion joint (SEJ) is used, give SEJ size.
6 |  |  |  | Show overall deck width.
7 |  |  |  | Show roadway width.
8 |  |  |  | Show lane, shoulder, and sidewalk widths.
9 |  |  |  | Show approach pavement and crown width.
10 |  |  |  | Show the amount and method of varying superelevation and/or crown.
11 |  |  |  | Show traffic direction.
12 |  |  |  | Show stream flow.
13 |  |  |  | Include North Arrow.
14 |  |  |  | Include soil exploration data (test holes, identifications, locations, etc.)
Plan View (cont) |  |  |  |  | Page 3 of 5
15 |  |  |  | Include dimensions to features that control vertical and horizontal clearances (indicate points of minimum clearances as required, for structures, utilities, railroad tracks, etc.).
16 |  |  |  | Show approach slab and curb returns.
17 |  |  |  | Show right-of-way (if required).
18 |  |  |  | Show horizontal curve data.
19 |  |  |  | Show contours at crossing (when applicable).
20 |  |  |  | Show cross slope.
21 |  |  |  | Include type and limits of riprap (and blockouts, if required).
22 |  |  |  | Skew angle.
23 |  |  |  | Show the railing type.
24 |  |  |  | Include outside beam line numbers (consistent with span details).
25 |  |  |  | Include approach pavement and dimensions.
26 |  |  |  | Show vertical clearance signs (if needed).
27 |  |  |  | Show foundation type and location. See Appendix A, Foundation Parameters and Calculations, for orientation of batter for outside piling groups on abutments.
28 |  |  |  | Locate bridge drain and/or bridge lighting bracket stations on plan view, when applicable.
29 |  |  |  | Show the new structure National Bridge Inventory (NBI) number, design speed, Average Daily Traffic (ADT) and year (existing and/or proposed), and functional class of roadway for a typical bridge or overpass. For a railroad overpass, NBI and railroad milepost also are required. For a railroad underpass, Department of Transportation (DOT) number and railroad underpass, Department of Transportation (DOT) number and railroad milepost also required.
30 |  |  |  | Show existing structure (dashed) on plan view, with existing National Bridge Inventory (NBI) number shown for bridge replacements or railroad milepost for a railroad underpass.
31 |  |  |  | For widenings, show existing structure on plan view, existing NBI number, and make sure the overall and roadway widths of existing and new structures are shown.
32 |  |  |  | For staged (or phased) construction information, show dimension to stage construction joints.
33 |  |  |  | For roadways passing below or above a structure, show their horizontal, vertical and template information, as well as a station point to tie the alignments together.
34 |  |  |  | Railroad overpasses and underpasses: Because individual railroad requirements may differ, contact the particular railroad involved regarding any additional requirements. Coordinate this effort through TxDOT personnel knowledgeable in railroad issues.
Comments
Elevation View |  |  |  |  | Page 4 of 5
| Y | N | N/A
1 |  |  |  | Show overall length of structure.
2 |  |  |  | Include lengths and types of units/spans.
3 |  |  |  | Include overall length and type of railing for each side (and, if required, median barrier) “End of Bridge Rail for Payment” note at both ends (for Type T6 rail, follow instructions on standard).
4 |  |  |  | Show critical horizontal clearances (locations of railroad tracks, utilities, culverts, and nearby structures).
5 |  |  |  | Show the profile of crossing and estimated vertical clearances to all lower roadways and railroad tracks.
6 |  |  |  | Show vertical curve data and grade.
7 |  |  |  | Begin and end bridge stations (at face of abutment backwall) and elevations.
8 |  |  |  | Show doweled beam locations (if needed).
9 |  |  |  | Show minimum calculated vertical clearances to all lower roadways and railroad tracks (and other clearances as required, such as utilities and nearby structures). Railroad overpass: show minimum horizontal clearance from centerline track to face of interior bent columns, crash wall, retaining wall, or other obstructions.
10 |  |  |  | Show the control or profile grade line.
11 |  |  |  | Show existing and proposed ground lines.
12 |  |  |  | Include hydraulics data (100-year and design flood elevations and velocities).
13 |  |  |  | Show grid elevations and stations.
14 |  |  |  | Show “H” heights.
15 |  |  |  | Show header bank slope and approach fill.
16 |  |  |  | Include types, number, sizes, lengths (to scale), and/or tip elevations of foundations (and, if required, direction of pile batter and orientation of footings on elevation and plan views).
17 |  |  |  | Include test hole elevation views and data.
18 |  |  |  | Show bent numbers (inside a circle, or hexagon if encircled note numbers are used).
19 |  |  |  | Include special foundation notes (if required by geotechnical engineers).
20 |  |  |  | Show riprap type.
Comments
Final Checks |  |  |  |  | Page 5 of 5
| Y | N | N/A
1 |  |  |  | Include standards layout title with National Bridge Inventory (NBI) number (and Department of Transportation number for railroad overpass), design speed, Average Daily Traffic (ADT) and year (existing and/or proposed), and functional class of roadway.
2 |  |  |  | Included dimensions and scales conform to grid (and elevations).
3 |  |  |  | Compare layout detail views against all bridge structural details for compatibility.
4 |  |  |  | Check foundations against structural details.
5 |  |  |  | Include Engineer’s seal.
Comments

## Railroad Coordination
Railroad Coordination - Union Pacific Railroad | [11 empty] | Railroad Coordination - Capital Metro Railroad
|  | CSJ | 0 | [7 empty] | Page 1 of 1 |  |  | CSJ | 0 | [7 empty] | Page 1 of 1
|  | County | 0 |  |  |  | This form to be filled out by Project Manager | [6 empty] | County | 0 |  |  |  | This form to be filled out by Project Manager
|  | Highway/Location | 0 |  |  |  | Signed PDF form to be archive in ProjectWise | [6 empty] | Highway/Location | 0 |  |  |  | Signed PDF form to be archive in ProjectWise
Project |  | From | 0 | [8 empty] | Project |  | From | 0
Limits |  | To | 0 | [8 empty] | Limits |  | To | 0
|  | Type of Work | 0 | [10 empty] | Type of Work | 0
|  | Laymans Desc | 0 | [10 empty] | Laymans Desc | 0
Coordination Expectations | [11 empty] | Coordination Expectations
| SCOPE |  |  | Office of | [8 empty] | SCOPE |  |  | Office of
| 1 | 2 | 3 | Resp | Activities |  |  | Expected |  |  | Actual |  | 1 | 2 | 3 | Resp |  |  |  | Expected |  |  | Actual
(go-by 1) | X | X | X | PM | Pre Coordination with District RR Coord |  |  |  |  | / |  | (go-by 1) | X | X | X | PM | Pre Coordination with District RR Coord |  |  |  |  | /
| X | X | X | PM | PS&E Development (30%) |  |  |  |  | / |  |  | X | X | X | PM | PS&E Development (30%) |  |  |  |  | /
(go-by 2) |  |  | X | PM | Initial Submittal (Exhibit A) |  |  |  |  | / |  | (go-by 2) |  |  | X | PM | Initial Submittal (Exhibit A) |  |  |  |  | /
(go-by 3) | X | X |  | Dist RR Coord | Scope of Work Developed by Dist RR Coord (*) |  |  |  |  | / |  | (go-by 3) | X | X |  | Dist RR Coord | Scope of Work Developed by Dist RR Coord (*) |  |  |  |  | /
|  |  | X | Dist RR Coord | Prelim Review by Dist RR Coord (**) |  |  |  |  | / |  |  |  |  | X | Dist RR Coord | Prelim Review by Dist RR Coord (**) |  |  |  |  | /
|  |  | X | PM | Address Comments |  |  |  |  | / |  |  |  |  | X | PM | Address Comments |  |  |  |  | /
(go-by 4) |  |  | X | Dist RR Coord | Submittal to Railroad Division (Round 1) |  |  |  |  | / |  | (go-by 4) |  |  | X | Dist RR Coord | Submittal to Railroad Division (Round 1) |  |  |  |  | /
|  |  | X | DIV RR | Division Review |  |  |  |  | / |  |  |  |  | X | DIV RR | Division Review |  |  |  |  | /
|  |  | X | PM | Address Comments |  |  |  |  | / |  |  |  |  | X | PM | Address Comments |  |  |  |  | /
|  |  | X | Dist RR Coord | Submittal to Railroad Division (Round 2) |  |  |  |  | / |  |  |  |  | X | Dist RR Coord | Submittal to Railroad Division (Round 2) |  |  |  |  | /
|  |  | X | DIV RR | Coord with Railroad Agency |  |  |  |  | / |  |  |  |  | X | DIV RR | Coord with Railroad Agency |  |  |  |  | /
|  |  | X | PM | Address Comments |  |  |  |  | / |  |  |  |  | X | PM | Address Comments |  |  |  |  | /
(go-by 5) | X | X | X | PM | Project Certification (***) |  |  |  |  | / |  | (go-by 5) | X | X | X | PM | Project Certification (***) |  |  |  |  | /
| X | X | X | PM | Files to DDGN for Processing |  |  |  |  | / |  |  | X | X | X | PM | Files to DDGN for Processing |  |  |  |  | /
Proposed Scope | [11 empty] | Proposed Scope
RR Review |  | Insurance |  | Flagging |  | Notification | Right of Entry |  | Exhibit |  |  | RR Review |  | Insurance |  | Flagging |  | Notification | Right of Entry |  | Exhibit
(500ft from |  | (50ft from |  | (25ft from |  | Letter | Agreement |  | Approval |  |  | (500ft from |  | (50ft from |  | (25ft from |  | Letter | Agreement |  | Approval
RR ROW) |  | RR ROW) |  | rail) |  |  | (TxDOT)*** |  | by UPRR | Expected Deliverable |  | RR ROW) |  | RR ROW) |  | rail) |  |  | (Contractor)*** |  | by UPRR | Expected Deliverable
SCOPE 1 | Pavement Markings, Crack Seal, Seal Coat | [8 empty] | Scope of Work |  | SCOPE 1 | Pavement Markings, Crack Seal, Seal Coat | [8 empty] | Scope of Work
YES |  | YES |  | YES |  | YES | NO |  | NO |  |  | YES |  | YES |  | YES |  | YES | YES |  | NO
SCOPE 2 | Mill & Overlay | [8 empty] | Scope of Work |  | SCOPE 2 | Mill & Overlay | [8 empty] | Scope of Work
YES |  | YES |  | YES |  | YES | YES |  | NO |  |  | YES |  | YES |  | YES |  | YES | YES |  | NO
SCOPE 3 | Add shoulders, Replanking, RR Signal Work | [8 empty] | Exhibit A |  | SCOPE 3 | Add shoulders, Replanking, RR Signal Work | [8 empty] | Exhibit A
YES |  | YES |  | YES |  | YES | YES |  | YES |  |  | YES |  | YES |  | YES |  | YES | YES |  | YES
|  | Dates to be coordinated with DDGN POC for Portfolio tracking of District projects | [11 empty] | Dates to be coordinated with DDGN POC for Portfolio tracking of District projects
| * | Scope of work to be developed but not submitted until Project Certification | [10 empty] | * | Scope of work to be developed but not submitted until Project Certification
| ** | PELOA request made by Dist RR Coord to Division | [10 empty] | ** | PELOA request made by Dist RR Coord to Division
| *** | TxDOT (Division) to process ROE documents at the time of Project Certification | [10 empty] | *** | Contractor to acquire ROE documents at the time of Construction; documentation to Area Office to confirm expectations relayed
| Note: Working documents and signed coordination sheets to be stored in ProjectWise under \Design Projects\CCCCSSJJJ\4 - Design\Supporting Documents\Railroad Coordination\ | [11 empty] | Note: Working documents and signed coordination sheets to be stored in ProjectWise under \Design Projects\CCCCSSJJJ\4 - Design\Supporting Documents\Railroad Coordination\
Roles & Point of Contact | [11 empty] | Roles & Point of Contact
| Project Manager | [7 empty] | PM |  |  |  | Project Manager | [7 empty] | PM
| District Railroad Coordinator | [7 empty] | Dist RR Coord |  |  |  | District Railroad Coordinator | [7 empty] | Dist RR Coord
| Railroad Division POC | [7 empty] | DIV (RR) |  |  |  | Railroad Division POC | [7 empty] | DIV (RR)

## Bike & Ped
Bicycle and Pedestrian Facilities
CSJ | 0
County | 0
Highway/Location | 0
Project From | 0
Limits To | 0
Type of Work | 0
Laymans Desc | 0
Land Use Context |  | Does the project include full reconstruction, new construction, or pavement widening?
Design Speed |  | Is the facility part of a locally adopted sidewalk planning document? | speed | 0
Posted Speed |  | Is the project or a portion of the project on the Texas Bicycle Tourism Trails Example Network?
ADT (VPD) |  | Are there existing pedestrian features? | completion check | 8 | 8 | Incomplete
Is right-of-way acquisition proposed for the project? |  | Does the environmental documentation indicate a need for bicycle accommodations?
Does the project include bridge replacement, bridge deck replacement, or bridge rehabilitation? |  | Is there evidence of pedestrian traffic, including observed pedestrians or beaten paths?
Is the project an off-system bridge with an ADT less than 400 VPD? |  | Is there a significant potential for pedestrians to walk in the roadway if sidewalks are not provided?
Is the project on a route to school? |  | Are there transit stops within the project limits?
Are pedestrian facilities required? |  | Are pedestrian facilities being provided?
Does the project include new construction or alteration through a pedestrian crossing as defined by RDM 19.4.6? |  | Are curb ramps being added or updated where required?
Does the project include new construction or alteration of signals that include a pedestrian signal head? |  | Are Accessible Pedestrian Signals included?
Are there any other existing pedestrian elements within the project limits that are not ADA-compliant? |  | Are non-compliant pedestrian elements being modified or replaced?
If pedestrian facilities or improvements to existing facilities are required but are not provided or are only partially provided, please explain why they are not being fully included with the project: |  |  |  |  | FALSE | No
|  |  | Bridge | Rural | Urbanized
Are bicycle facilities required? |  | Are bicycle facilities being provided? | No | No | No | No
If bike facilities are required but not provided or are only partially provided, please select the applicable exemption(s). Please note that projects on the Texas Bicycle Tourism Example Network cannot be exempt from including bike facilities, and on-system bridges cannot be exempt from meeting bicycle clear space requirements. |  |  | 5' Minimum Bicycle Clear Space on Bridge | Shared Lane | Shared Lane
The project is on a roadway where bicycle travel is specifically prohibited by law or Texas Transportation Commission Minute Order.
The project is located outside of a respective MPO Boundary; AND is also located outside of any respective city limits with a population of 2,500 or greater.
The project is in an urbanized setting (defined as a city, town, or Census designated place with a population of 2,500 or greater) where a locally preferred alternative route has been adopted or implemented and bikeways are deemed impractical within the scope of the project.
The project is in an urbanized setting with limited roadway improvements, such as 3R and 2R projects, and there is already a future project programmed (e.g., MPO Active Transportation Plan) where the bicycle updates would make more sense in the context of overall transportation improvements.
The cost to provide features exclusively for bikeways is excessively disproportionate to the need or likely uses.
The source of funding specifically precludes improvements other than those for which the funding is intended.
The type of work is limited in scope such that major roadway elements are not being constructed or reconstructed.
Recommended Bike Facility |  | Bike Facility Provided:
If bike facilities are required, but the provided bike facility is different from the recommended facility, please explain:
|  |  |  | Land Use Context | Yes/No | Speed
|  |  |  | Rural | Yes | 5 | Separated Bike Path or Shared Used Path
|  |  |  | Rural Town | No | 10 | Bike Lane
|  |  |  | Suburban |  | 15 | Shared Lane
|  |  |  | Urban |  | 20 | 5' Shoulder
|  |  |  | Urban Core |  | 25 | 8' Shoulder
[6 empty] | 30 | 10'+ Shoulder
[6 empty] | 35 | 5' Minimum Bicycle Clear Space on Bridge
[6 empty] | 40 | Separated Bike Path
[6 empty] | 45 | Shared Used Path
[6 empty] | 50 | None
55
60
65
70
75
80
85
90
95
100

## IDF-Initial
Initial Review | [10 empty] | Initial Review (continued)
|  | CSJ | 0 | [6 empty] | Page 1 of 2 | [9 empty] | Page 2 of 2
|  | County | 0 | [13 empty] | Coordinator(Constr): | 0
|  | Highway/Location | 0 | [8 empty] | Y | N | N/A | Traffic Control |  | Coordinator(AO): | Person C (AO rep)
Project |  | From | 0 | [11 empty] | Preliminary Traffic Control Plan and Sequence of Work (Conceptual)
Limits |  | To | 0 | [12 empty] | Roll Plots
|  | Type of Work | 0 | [12 empty] | Typical Sections
|  | Laymans Desc | 0 | [11 empty] | Hold traffic control meeting with AO and Construction Office
| Y | N | N/A | [12 empty] | Approved |  |  | Date
|  |  |  | Review/Address Kick-off meeting comments & Action Items | [10 empty] | Road Closures & Detour Identified
|  |  |  | Review Austin District Designer's Guide |  |  |  |  | Date | [5 empty] | Accelerated Construction Methods Identified
|  | Comments | [12 empty] | Confirm Comments from Area Office Maintenance Section resolved
| Y | N | N/A | Design |  |  | Coordinator: | Person A (DDGN PR rep) |  |  |  |  | Comments
Design Summary Report Submitted
|  |  |  | Typical Sections & Design Criteria Approved |  |  |  |  | Date |  |  | Y | N | N/A | Drainage |  | Coordinator: | Person B (HH rep)
|  |  |  | Bicycle & Pedestrian Accomodations Coordinated with DDGN | [10 empty] | Drainage Easements Defined
|  |  |  | TxDOT Bicycle Accomodation Design Guidance Implemented | [10 empty] | Hydrology Completed
|  |  |  | Design Exceptions/Waivers Submitted to District |  |  |  |  | Date | [5 empty] | Hydraulic Coordination Initiated
|  |  |  | Determine existing / future CAP Metro Routes within Project Limits | [10 empty] | Other Agreements
|  |  |  | Schematic Submitted to District | [8 empty] | Comments
[5 empty] | Approved |  | District |  | DES | FHWA
Misc Details
|  |  |  | Preliminary Cross Sections Reviewed | [7 empty] | Y | N | N/A | Bridge |  | Coordinator: | Person D (Str rep)
|  |  |  | Value Eng Study (VE); Total Project cost > $50 million, Complete/Sign Form 2502 | [10 empty] | Bridge Cores Ordered
|  |  |  | System Safety Elements & ICE Process Evaluation | [10 empty] | Preliminary Bridge Layouts (PBLR Submitted) |  |  |  | Date
|  | Comments | [12 empty] | Preliminary Retaining Walls |  |  |  | Date
[15 empty] | Env. Hazards Requested (Asbestos, Lead, etc) |  |  |  | Date
Bridge Condition Survey Requested
| Y | N | N/A | District Lab |  |  | Coordinator: | Person J (Lab rep) | [6 empty] | Bridge Inspection Follow Up Actions Requested
|  |  |  | Confirm Approval of Pavement Design | [8 empty] | Comments
| Y | N | N/A | District Traffic |  |  | Coordinator: | Person E (TRF rep)
|  |  |  | Request Accident Data from District Traffic Office | [7 empty] | Y | N | N/A | Environmental |  | Coordinator: | Person G (Dist Env)
|  |  |  | Coordinate for Traffic Impact Analysis (if needed) | [10 empty] | Environmental Questionnaire Completed |  |  |  | Date
|  |  |  | Identify expected Driveway Closures (Temporary/Permanent) | [10 empty] | Compare Schematic to Environmental Document
|  |  |  | Illumination |  |  | Safety |  | High Mast | Continuous |  |  |  |  | Project within Edwards Aquifer begin coordination with Shane Rotter for WPAP
|  |  |  | ITS Elements | [10 empty] | Stage Gate Checklist (John Barton Memo 07/07/11).
|  |  |  | Toll Elements | [11 empty] | Complete APD Checklist
|  |  |  | FAA Clearance Needed | [11 empty] | Start PS&E Checklist
|  |  |  | Railroad Agreement |  |  |  |  | Exhibit A Submitted |  |  |  | Comments
|  |  |  | Coordinated Signal Plans |  |  |  |  | COA Interest
Comments
[12 empty] | Y | N | N/A | Utility |  | Coordinator: | Person H (Util rep)
| Y | N | N/A | Project Controls |  |  | Coordinator: | Person D (TPD rep) | [6 empty] | Utility Impacts Defined |  |  |  | Joint Bidding - AFA
|  |  |  | Request Traffic Projection | [10 empty] | Provide copy of plans to utility companies
|  |  |  | Advanced Funding Agreement Needed? | [10 empty] | Utility Kick off Meeting |  | Expected Date:
|  |  |  | TIP Approval |  | TIP YEAR |  |  | Group Project | [5 empty] | ROW CSJ Needed? |  | Date Requested
|  |  |  | Other Agreements | [8 empty] | Comments
|  |  |  | Verify Project is State or Federal |  |  | State |  | Federal
Estimate
[8 empty] | Authorized |  |  |  | Y | N | N/A | ROW |  | Coordinator: | Person I (ROW rep)
[8 empty] | Preliminary w/15% Contingency | [6 empty] | ROW needs Identified |  |  |  | ROW CSJ Needed?
|  | Comments | [10 empty] | Comments

## IDF-Detail
Detailed Review | [9 empty] | Detailed Review (continued)
|  | CSJ | 0 | [5 empty] | Page 1 of 2 | [10 empty] | Page 2 of 2
|  | County | 0 | [13 empty] | Coordinator(Constr): | 0
|  | Highway/Location | 0 | [7 empty] | Y | N | N/A | Traffic Control |  |  | Coordinator: | Person C (AO rep)
Project |  | From | 0 | [10 empty] | Traffic Control Plan and Sequence of Work
Limits |  | To | 0 | [10 empty] | Hold traffic control meeting with AO and Construction Office
|  | Type of Work | 0 | [12 empty] | Approved |  |  | Date
|  | Laymans Desc | 0 | [10 empty] | Road Closures Letter Sent
| Y | N | N/A | [10 empty] | Ensure access maintained to all adjacent properties
|  |  |  | Review/Address Initial Review meeting comments & Action Items | [8 empty] | Contract Time |  | Standard Wk |  | 5 day |  | 6 day | 7 day
|  | Comments | [11 empty] | Acceleration Methods Incorporated
Discuss Construction Schedule (Magnitude/LOE/Activities) with AO & Dist Constr
Comments
| Y | N | N/A | Design |  | Coordinator: | Person A (DDGN PR rep) |  |  |  | Y | N | N/A | Drainage |  |  | Coordinator: | Person B (HH rep)
|  |  |  | Received Signed 1002 |  |  |  | Date | [5 empty] | Hydraulic Design Complete
|  |  |  | Design Exceptions/Waivers Received |  |  |  | Date | [7 empty] | Approved by Dist Hyd |  |  | Date
|  |  |  | Schematic Approved |  |  |  | Date |  |  |  | Comments
Culvert Layouts/Cross Sections
|  |  |  | Storm Sewer Layouts | [6 empty] | Y | N | N/A | Bridge |  |  | Coordinator: | Person D (Str rep)
|  |  |  | Storm Water Pollution Prevention Plan | [9 empty] | Bridge Layouts Approved |  |  |  |  | Date
|  |  |  | Landscaping/Aesthetics/CSD Coordination Initiated | [9 empty] | Retaining Walls Approved |  |  |  |  | Date
|  |  |  | Misc Details | [9 empty] | Identify Temporary Shoring Needs
|  |  |  | Cross Section Status | [9 empty] | Scour Analysis required? |  |  |  | Completed by
[5 empty] | Include Utilities |  |  | AO Review | [5 empty] | Bridge Details Needed |  |  |  | Completed by
[5 empty] | Check for flat spots |  |  | TSS BMP design | [5 empty] | Structures Asbestos Inspection Completed |  |  |  |  | Date
|  |  |  | Asset Maintenance Sheet | [9 empty] | Bridge Inspection Follow Up Action Details Included
|  |  |  | Value Engineering Study (Close out of 2nd Signature) | [7 empty] | Comments
Comments
| Y | N | N/A | District Lab |  | Coordinator: | Person J (Lab rep) |  |  |  | Y | N | N/A | Environmental |  |  | Coordinator: | Person G (Dist Env)
|  |  |  | Submit TPP Traffic Count Analysis to District Lab | [9 empty] | Environmental Document and Activities |  |  |  |  | Date
|  |  |  | Submit Geotech Report to District Lab | [9 empty] | Check Environmental Document vs. Design
Edwards Aquifer coordination with Dist Env for WPAP
| Y | N | N/A | District Traffic |  | Coordinator: | Person E (TRF rep) | [6 empty] | Stage Gate Checklist (John Barton Memo 07/07/11).
|  |  |  | Receive Accident Data |  |  |  | Date | [7 empty] | Complete 60% PS&E Checklist
|  |  |  | Railroad Agreement |  |  |  | Exhibit A Submitted | [5 empty] | Submit SW3P to District Construction for review
|  |  |  | Confirm Signal Plans are w/ Dist Traffic Rep | [7 empty] | Comments
Comments
[11 empty] | Y | N | N/A | Utility |  |  | Coordinator: | Person H (Util rep)
| Y | N | N/A | Project Controls |  | Coordinator: | Person D (TPD rep) | [6 empty] | UAR exception Required |  |  |  |  | ROW CSJ Needed?
|  |  |  | Received Traffic Projection |  |  |  | Date | [5 empty] | Utility Adjustment/Relocation Details
|  |  |  | Received Advanced Funding Agreement |  |  |  | Date | [5 empty] | Date for Utility Meeting
|  |  |  | TxDOT Connect Updated | [9 empty] | Provide copy of plans to utility companies
|  |  |  | Estimate | [9 empty] | Management Plan Needed
[7 empty] | Authorized |  |  |  |  | Comments
Detailed w/10% Contingency
|  | Comments | [8 empty] | Y | N | N/A | ROW |  |  | Coordinator: | Person I (ROW rep)
[14 empty] | Maps/Docs/Field Notes Started |  |  |  |  | ROW CSJ Needed?
[15 empty] | Checked |  |  | Expected Completion Date
|  |  |  | Field Visit, drive project and confirm plans are accurate. | [10 empty] | Outside Participation |  |  | Encroachments
|  | Comments | [9 empty] | Comments

## IDF-Final
Final Review | [10 empty] | Final Review (cont) | [9 empty] | Final Review (cont)
|  | CSJ | 0 | [6 empty] | Page 1 of 3 | [9 empty] | Page 2 of 3 | [7 empty] | Page 3 of 3
|  | County | 0 | [13 empty] | Coordinator(Constr): | 0 |  |  | ACCELERATED CONSTRUCTION STRATEGIES
|  | Highway/Location | 0 | [8 empty] | Y | N | N/A | Traffic Control |  | Coordinator: | Person C (AO rep)
Project |  | From | 0 | [11 empty] | Hold safety review meeting (lighting, signs, delineator, rumble strips, tcp). | [5 empty] | A.) | Check any conditions 1-5 listed below which apply to this project and then check the recommended monetary Accelerated Construction Strategies (ACS) for the use in this contract:
Limits |  | To | 0 | [12 empty] | Approved |  |  | Date
|  | Type of Work | 0 | [11 empty] | Road Closures Memo Signed |  |  |  | Date
|  | Laymans Desc | 0 | [11 empty] | Ensure access maintained to all adjacent properties
| Y | N | N/A | [11 empty] | Speed Zone Reduction request approved |  |  |  | Date
|  |  |  | Review/Address Initial & Detailed Review meeting comments & Action Items | [10 empty] | Temporary Drainage verified | [5 empty] | 1.) |  | All project with Lane closures on all types of facilities with a medium volume or higher (5,000 ADT/lane)
|  | Comments | [12 empty] | Construction Schedule
[16 empty] | Incentives |  |  | Accelerated |  | 2.) |  | All added capacity project without lane closures on high volume facilities (12,500 ADT/Lane)
Milestones
[13 empty] | Comments | [7 empty] | 3.) |  | Projects where the calculated road-user cost (RUC) equals or exceeds the contract administrative liquidated damages (CALD)
| Y | N | N/A | Design |  |  | Coordinator: | Person A (DDGN PR rep)
|  |  |  | Final Index of Sheets | [7 empty] | Y | N | N/A | Drainage |  | Coordinator: | Person B (HH rep) |  |  | 4.) |  | Projects which impact access to businesses, schools, hospitals or public facilities
|  |  |  | Form 1002 (copy of approved), latest rev of 07/2013 | [10 empty] | Hydraulic Design Comments Resolved |  |  |  | Date
|  |  |  | Design Exceptions/Waivers Approved |  |  |  |  | Date | [5 empty] | Copy of plans to drainage contact/Floodplain Administrator (if necessary) | [5 empty] | 5.) |  | Project with bridge or road closures
|  |  |  | Corresponding Quantity Summary Sheets | [8 empty] | Comments
|  |  |  | Corresponding Standard Detail Sheets for all Items of Work in this submittal | [17 empty] | Exceptions to above criteria: Justify the request for exception below, if the project is characterized by one or more of the above conditions 1 - 5 and no monetary ACS are used
Newly Created Special Specifications/Provisions
|  |  |  | General Notes |  | Reviewed by Dist. Constr. & Area Office | [5 empty] | Y | N | N/A | Bridge |  | Coordinator: | Person D (Str rep)
|  |  |  | Misc Details | [10 empty] | Bridge Layouts Approved |  |  |  | Date
|  |  |  | Certifications (copy included in Review documents) | [10 empty] | Retaining Walls Approved |  |  |  | Date |  |  | Justification:
|  |  |  | Cross Section Status | [10 empty] | Form 2605 Scour Summary Sheet for Known Foundations completed
[5 empty] | Include Utilities |  |  |  | AO Review | [5 empty] | Bridge Inspection Follow Up Action Details Completed
[5 empty] | Check for flat spots |  |  |  | LandXML File |  |  |  | Comments
Asset Maintenance Sheet - Signed
Complete Significant Project Procedures Form 2229
|  |  |  | Railroad Scope of work in PS&E |  |  |  |  | Coordination Complete |  |  | Y | N | N/A | Environmental |  | Coordinator: | Person G (Dist Env)
|  |  |  | System Safety Tool & Score Documented | [10 empty] | Environmental Clearance Memo |  |  |  | Date
|  | Comments | [13 empty] | Provide SWP3/EPIC/Erosion Control/StageGate
| Y | N | N/A | District Traffic |  |  | Coordinator: | Person E (TRF rep) | [6 empty] | Check Environmental Document vs. Design
|  |  |  | Pavement Marking Layout/Details |  |  |  |  | Coordination Complete | [5 empty] | Stage Gate Checklist (John Barton Memo 07/07/11). | [5 empty] | B.) |  | Check if none of the above conditions 1-5 apply to this project (Monetary ACS are not required).
|  |  |  | Signalization (existing and proposed) |  |  |  |  | Coordination Complete | [6 empty] | Complete 90% PS&E Checklist
|  |  |  | Traffic Management Items | [10 empty] | Submit SW3P to Dist Construction for review
|  | Comments | [12 empty] | TSS Calcs (Aquifer) Complete, given to Dist Env for WPAP |  |  |  | Date
[15 empty] | WPAP Submitted |  |  |  | Date |  | C.) | Check the appropriate monetary ACS included on this project. (* Use of 5, 6, 7 day workweek or calendar day definitions are required when these monetary ACS provision are being utilized.)
Comments
| Y | N | N/A | Project Controls |  |  | Coordinator: | Person D (TPD rep)
TxDOT Connect Updated
|  |  |  | Overrun Justification | [7 empty] | Y | N | N/A | Utility |  | Coordinator: | Person H (Util rep)
|  |  |  | Letting Acknowledgment Certification | [10 empty] | UAR exception Received |  |  |  | Date |  |  | NOTE If any Accelerated Construction Strategies are used on this project, please use the required provision, listed on TxDOT's list of required specifications.
|  |  |  | Financial Plan (Total Project cost > $100 M) | [10 empty] | Utility Relocations Complete
|  |  |  | Major Project Critiera completed | [10 empty] | Utility Relocation Status to file
|  |  |  | Estimate | [10 empty] | Provide copy of plans to utility companies
[8 empty] | Authorized |  |  |  |  | Comments | [8 empty] | TIME DETERMINATION
[8 empty] | Final w/Force Acct & 5% Contingency | [12 empty] | A.) | Number of Working Days for Project: |  |  | XX Days
Comments
[12 empty] | Y | N | N/A | ROW |  | Coordinator: | Person I (ROW rep) |  |  | B.) | Type of Working Days: Check the appropriate box or boxes.
Possession and Use Complete
|  |  |  | Field Visit, drive project and confirm plans are accurate. | [10 empty] | Eminent Domain | [8 empty] | Calendar Day |  | 5 day | 6 day | 7 day
|  | Comments | [10 empty] | Comments | [10 empty] | Standard Workweek
Other:

## Complete PS_E Submital
Complete ePS&E Submittal
|  | CCSJ | 0 | [7 empty] | Date
|  | County | 0 | [8 empty] | Letting
|  | Highway/Location | 0
|  | Project PM | 0 | [8 empty] | Date Plans were received on
| File location (Projectwise): | [10 empty] | Plan Reviewer Recommendation
|  | Final Plans | 14 - AUS\Design Projects\CCCCSSJJJ\4 - Design\Plan Review\5. ePS&E Submittal\ | [6 empty] | Team Leader Concurrence
|  | Add'l Doc's | 14 - AUS\Design Projects\CCCCSSJJJ\4 - Design\Plan Review\5. ePS&E Submittal\
|  | Form 1814 | 14 - AUS\Design Projects\CCCCSSJJJ\4 - Design\Supporting Documents\Special Specs_Provisions
Expected Date of PR comments
| Final Plans: Plans | [5 empty] | Expected Date of Comment Close out
| Y | N | N/A |  |  | Naming Methodology:
|  |  |  | Portfolio (1) Plan set provided |  |  | Portfolio: AABB CCCC-SS-JJJ County.pdf
|  |  |  | Naming Methodology correctly used |  |  |  | ex. | 0916 0914-18-108 BASTROP.pdf
Plan Sheets signed and sealed
Title Sheet signed by Local Govt (if required)
Comments
Final Plans: Supporting Doc
| Y | N | N/A | [6 empty] | Local Government Documents
|  |  |  | Portfolio (2) Support Documentation provided | [5 empty] | Y | N | N/A
|  |  |  | Naming Methodology correctly used | [8 empty] | Project Manual
|  |  |  | Includes: |  | Naming Methodology:
[5 empty] | 1002 Page 3 (Initialed by DDGN) |  | Portfolio: AABB CCCC-SS-JJJ County(Supporting Docs).pdf
[5 empty] | 1002 (entire document) |  |  | ex. | 0916 0914-18-108 BASTROP(Supporting Docs).pdf
[5 empty] | List of Special Specifications and Provisions |  | Included files
[5 empty] | General Notes ("Accepted" & watermark removed; RTF Format) |  |  | ex. | 001 FORM 1002
[5 empty] | Estimate |  |  |  | 002 SPEC LIST
[5 empty] | Contract Time Schedule (Signed & Dated) |  |  |  | 003 GENERAL NOTES (**Plan Reviewer will create PDF)
[5 empty] | Form 2229 Significant Procedures |  |  |  | 004 ESTIMATE
[5 empty] | Certifications (signed) |  |  |  | 005 CONTRACT SCHEDULE
[5 empty] | Form 2699 - Specific Liquidated Damages |  |  |  | 006 FORM 2229 SIGNIFICANT PROCEDURES
[5 empty] | Form 2502 - Exec Decision Summary/Value Engineering (if required) |  |  |  | 007 CERTIFICATIONS
[5 empty] | Management Plan (if required) |  |  |  | 008 FORM 2699 SPECIFIC LIQUIDATED DAMAGES
009 FORM 2502 VALUE ENG RECOMMENDATIONS
|  | Comments | [6 empty] | 010 MANAGEMENT PLAN
Additional Documents for District Submittal
| Y | N | N/A | [6 empty] | Local Government Documents
|  |  |  | Form 1814 & SS_SP Word Documents | [5 empty] | Y | N | N/A
|  |  |  | Signed AP&D Stagegate Checklist (100%) Form 2442 | [8 empty] | LGPDP Checklist
|  |  |  | Signed PS&E Stagegate Checklist (100%) Form 2443 | [8 empty] | Summary Est Form
PDF copy of Cross Sections (if required)
Letting Acknowledge Form (signed)
Railroad Agreement (if required)
Funding Agreement (if required)
Airway-Highway Clearance (if required)
Safety Score Tool (if required)
Comments
Other Items
| Y | N | N/A |  |  | Y | N | N/A
|  |  |  | TxC RTL Checklist Completed |  |  |  |  | Working Days Match (1002, Schedule, TxC)
TxC Pre Bid Resources Identified
TxC Estimate Sealed

## Project Resolution
Project Resolution Certification | [9 empty] | Project Resolution Certification
|  | CCSJ | 0 |  |  |  |  | Date |  |  |  | CCSJ | 0 | [6 empty] | Page 2
|  | County | 0 | [8 empty] | County | 0
|  | Highway/Location | 0 |  |  |  |  | (to be completed by DDGN Plan Reviewer) |  |  |  | Highway/Location | 0 |  |  |  |  | (to be completed by DDGN Plan Reviewer)
| District Design Comments |  |  |  |  | Reviewed by: | Person A (DDGN PR rep) |  |  |  | District Utilities Comments |  |  |  |  | Reviewed by: | Person H (Util rep)
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time | [9 empty] | Have all comments been addressed at this time |  |  | Yes | No | CDGN Coord Required
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
| Drainage Comments |  |  |  |  | Reviewed by: | Person B (HH rep) |  |  |  | District ROW Comments |  |  |  |  | Reviewed by: | Person I (ROW rep)
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time |  |  | Yes | No | In FEMA Flood Plain |  |  |  |  | Have all comments been addressed at this time
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
| Area Office Comments |  |  |  |  | Reviewed by: | Person C (AO rep) |  |  |  | District Lab Comments |  |  |  |  | Reviewed by: | Person J (Lab rep)
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time |  |  | Yes | No | A.O Maint concurs |  |  |  |  | Have all comments been addressed at this time
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
| Structural Comments |  |  |  |  | Reviewed by: | Person D (Str rep) |  |  |  | District Maintenance Comments |  |  |  |  | Reviewed by: | Person K (Maint rep)
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time |  |  | Yes | No | Form 2605 Needed |  |  |  |  | Have all comments been addressed at this time
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
| Traffic Comments |  |  |  |  | Reviewed by: | Person E (TRF rep) |  |  |  | Railroad Confirmation |  |  |  |  | Reviewed by: | Dist Railroad POC
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time |  |  | Yes | No | Railroad Coord Required |  |  |  |  | Have all comments been addressed at this time
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
| District Construction Comments |  |  |  |  | Reviewed by: | Person F (Constr rep) |  |  |  | Ped, Bike & Landscape Comments |  |  |  |  | Reviewed by:
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time | [9 empty] | Have all comments been addressed at this time
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
| District Env Comments |  |  |  |  | Reviewed by: | Person G (Dist Env) |  |  |  | Safety Score Tool Comments |  |  |  |  | Reviewed by:
| Y | N | N/A | [7 empty] | Y | N | N/A
|  |  |  | Have all comments been addressed at this time | [9 empty] | Have all comments been addressed at this time
| Confirmed via: |  |  |  | Comments | [5 empty] | Confirmed via: |  |  |  | Comments
|  | Phone Call |  |  | [Round 1] | [6 empty] | Phone Call |  |  | [Round 1]
|  | Email | [9 empty] | Email
|  | In person |  |  | [Round 2 - Close out] | [6 empty] | In person |  |  | [Round 2 - Close out]
(archive location of completed form: 14 ‐ AUS\Design Projects\CCCCSSJJJ\4 ‐ Design\Plan Review\5. ePS&E Submittal) | [9 empty] | (archive location of completed form: 14 ‐ AUS\Design Projects\CCCCSSJJJ\4 ‐ Design\Plan Review\5. ePS&E Submittal)

## State Let Guidelines
QUICK AND EASY SUBMITTAL GUIDELINES BY % MILESTONE
30% MILESTONE SUBMISSION: ProjectWise Plan Review 30% Folder. | PREPARATION GUIDANCE FOR SUBMITTING PLANS FOR REVIEW.
01) READ ME FIRST MEMO | A) If it is a consultant submittal. Create a subfolder under the
02) AUSTIN DISTRICT PROJECT DEVELOPMENT MANUAL.xlsx (IDF-Initial & System Safety) | 30 Percent folder in Projectwise (30% SUBMITTAL FROM TBD).
03) 1234-56-789 HW1234 30% FORM 1002 | B) All files submitted for review SHALL be Non-Editable .pdf format.
04) 1234-56-789 HW1234 30% PRELIMINARY ESTIMATE | C) If sending files through SharePoint or BlueBeam substitute % for
05) 1234-56-789 HW1234 30% PLANS (TITLE SHEET, TYPICAL SECTIONS) | (pct) to avoid errors during file transfer.
06) 1234-56-789 HW1234 30% PRELIMINARY BRIDGE LAYOUT(S) | D) Any new Bid Items added during Project Development will
07) 1234-56-789 HW1234 30% PRELIMINARY RETAINING WALL LAYOUT(S) | trigger additional review of Designer's Guide.
08) 1234-56-789 HW1234 30% CROSS SECTIONS
09) 1234-56-789 HW1234 30% SAFETY SCORE TOOL (If Applicable)
10) 1234-56-789 HW1234 (SIGNED) AP&D STAGE GATE CHECKLIST (Advance to PS&E line)
11) 1234-56-789 HW1234 (SIGNED) PS&E STAGE GATE CHECKLIST (30% Review line)
Submit 1814 forms for Special Specs/Provisions and/or Bid Codes that have been Identified.
60% MILESTONE SUBMISSION: ProjectWise Plan Review 60% Folder.
01) READ ME FIRST MEMO (Updated to 60%)
02) AUSTIN DISTRICT PROJECT DEVELOPMENT MANUAL.xlsx (IDF-Initial + Detail)
03) 1234-56-789 HW1234 60% FORM 1002 (updated)
04) 1234-56-789 HW1234 60% ESTIMATE (In TxDOTCONNECT Format)
05) 1234-56-789 HW1234 60% CERTIFICATIONS
06) 1234-56-789 HW1234 60% PLANS (detailed design)
07) 1234-56-789 HW1234 60% CROSS SECTIONS (with utilities included)
08) 1234-56-789 HW1234 60% SAFETY SCORE TOOL (If Applicable)
09) 1234-56-789 HW1234 60% CONSTRUCTION MANAGEMENT PLAN (If Certs are unclear)
10) 1234-56-789 HW1234 (SIGNED) PS&E STAGE GATE CHECKLIST (60% Review line)
Submit 1814 forms for Special Specs/Provisions and/or Bid Codes that have been Identified.
90% MILESTONE SUBMISSION: ProjectWise Plan Review 90_95% Folder.
01) READ ME FIRST MEMO (Updated to 90%)
02) AUSTIN DISTRICT PROJECT DEVELOPMENT MANUAL.xlsx (IDF-Initial + Detail + Final)
03) 1234-56-789 HW1234 90% FORM 1002 (updated)
04) 1234-56-789 HW1234 90% GENERAL NOTES
05) 1234-56-789 HW1234 90% ESTIMATE (In TxDOTCONNECT Format)
06) 1234-56-789 HW1234 90% SPEC LIST
07) 1234-56-789 HW1234 90% CONTRACT SCHEDULE
08) 1234-56-789 HW1234 90% CERTIFICATIONS (updated)
09) 1234-56-789 HW1234 90% FORM 2229
10) 1234-56-789 HW1234 90% FORM 2699
11) 1234-56-789 HW1234 90% PLANS (final design)
12) 1234-56-789 HW1234 90% CROSS SECTIONS (final)
13) 1234-56-789 HW1234 90% SAFETY SCORE TOOL (If Applicable)
14) 1234-56-789 HW1234 90% CONSTRUCTION MANAGEMENT PLAN (If Certs are unclear)
15) 1234-56-789 HW1234 (SIGNED) PS&E STAGE GATE CHECKLIST (90% Review line)
Submit 1814 forms for Special Specs/Provisions and/or Bid Codes that have been Identified.
100% ePS&E COMPLETE SUBMISSION: ProjectWise Plan Review ePS&E Folder.
01) 0120(Letting Date) 1234-56-789(CSJ) TRAVIS(County).pdf | {THIS IS YOUR PLANS PORTFOLIO}
02) 0120(Letting Date) 1234-56-789(CSJ) TRAVIS(County)(SUPPORTING DOCS).pdf | {THIS IS YOUR SUPPORTING DOCS PORTFOLIO}
03) 1234-56-789 HW1234 FINAL ELECTRONIC GENERAL NOTES (.RTF format)
04) 1234-56-789 HW1234 FINAL CROSS SECTIONS (Native Format)
05) 1234-56-789 HW1234 FINAL SAFETY SCORE TOOL (If Applicable)
06) 1234-56-789 HW1234 (SIGNED) PROJECT LETTING CERTIFICATION ACKNOWLEDGEMENT FORM
07) 1234-56-789 HW1234 (SIGNED) AP&D STAGE GATE CHECKLIST (Advance to PS&E line)
08) 1234-56-789 HW1234 (SIGNED) PS&E STAGE GATE CHECKLIST (Advance to Letting line)
Submit 1814 forms for Special Specs/Provisions and/or Bid Codes that have NOT been previously identified.
The naming convention of files included in the PLANS PORTFOLIO.pdf SHALL match the names as they appear on the Index of Sheets.
The files to be included in the SUPPORTING DOCUMENTS PORTFOLIO SHALL BE NAMED, AND ARE, AS FOLLOWS.
001 FORM 1002 (editable)
002 SPEC LIST
Leave the General Notes out of the Docs Portfolio. DDGN will insert the .pdf here from the .RTF file provided above.
004 ESTIMATE
005 CONTRACT SCHEDULE (signed and dated with anticipated construction completion date noted)
006 FORM 2229 SIGNIFICANT PROCEDURES (editable)
007 CERTIFICATIONS (signed and dated)
008 FORM 2699 SPECIFIC LIQUIDATED DAMAGES (editable)
009 FORM 2502 VALUE ENGINEERING RECOMMENDATIONS
010 CONSTRUCTION MANAGEMENT PLAN
fin.

## Local Let Guidelines
Local Let Guidelines |  | Comments | 30% | 60% | 90% | 100%
1 | TxDOT LGP-Project Development Checklist (completed by the LG with all items that apply up through the Bid Document Checklist section and verified by the Area Office) |  |  |  | X | X
2 | LG Bid Document/Project Manual (including General Notes, Engineer's Seal and Specifications approved by the AO) |  |  |  | X | X
3 | Plans (with title sheet signed by the LG or their representative and the AO) |  | X | X | X | X
4 | Pdf of Cross Sections (if applicable) |  |  | X | X | X
5 | Geotechnical/Pavement Design (if applicable) |  | X | X
6 | Engineer’s Estimate of Probable Construction Phase Cost Summary Sheet (required for Federal/State Funded or On-System) | not required for 100% local funds |  |  | X | X
7 | Estimate (final estimated construction cost prior to letting) |  | X | X | X | X
8 | TxDOT Form 1002 |  | X | X | X | X
9 | Construction Schedule (signed and dated) |  |  |  | X | X
10 | TxDOT Form 2229 Significant Procedures (required for Federal/State Funded or On-System) |  |  |  | X | X
11 | Certifications (signed by the City or County Official, as applicable) If the project has Fed Funds, we use the FED Template, otherwise we use the State Template. |  |  | X | X | X
12 | TxDOT Form 2699 - Specific Liquidate Damages (required for Federal/State Funded or On-System, if applicable 3R / 4R) |  |  |  | X | X
13 | TxDOT - Austin District Project Development Manual IDF-Checklists (spreadsheet) |  | X | X | X | X
Note: FORMS 2442 & 2443 are not required for Local Let Projects.