## Project Info
TxDOT Highway: |  |  | Project Limits:
CCSJ: |  | Construction Project ID: |  |  |  |  | Let Date:
Station Project Limits |  |  | Station FROM: |  |  |  | Station TO:
ROW CSJ: |  | ROW Project ID: |  |  |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT:
Conflict Analysis Complete: |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Project Specific Information - used to set duration calculations
What type of project is this (see instructions for definition of project types)?
How long is this project ( mainlanes from beginning to end)? | [6 empty] | miles | 0 |  | LF
Project Size: |  | PS&E QA/QC duration (days): |  |  | #N/A | Conflict Analysis duration (days): |  |  |  | #N/A
Will ROW acquisition be required for this project? |  |  |  |  | NO | ROW is being acquired by: |  |  | N/A
Responsible for Design of project: | [5 empty] | Letting Type:
Utility ID Summary (no data entry below this point, all data referenced by formula)
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U0000001
Last Milestone Completed: |  | Send NOPC letter signed by TxDOT PM | [5 empty] | Date: | 2025-02-18
Next Milestone: | Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Estimated Date: |  | 2025-03-17
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000002
Last Milestone Completed: |  | Existing Utility Layout complete, provided to TxDOT | [5 empty] | Date: | 2025-01-31
Next Milestone: | Existing Utility Layout provided to utility to verify | [5 empty] | Estimated Date: |  | 2025-02-10
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000003
Last Milestone Completed: |  | Existing Utility Layout provided to utility to verify | [5 empty] | Date: | 2025-02-15
Next Milestone: | Send NOPC letter signed by TxDOT PM | [5 empty] | Estimated Date: |  | 2025-03-02
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000004
Last Milestone Completed: |  | Utility Relocation Design Begins | [5 empty] | Date: | 2025-05-25
Next Milestone: | FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | Estimated Date: |  | #N/A
Last Milestone on Schedule: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000005
Last Milestone Completed: |  | Utility Relocation Design Complete | [5 empty] | Date: | 2026-05-01
Next Milestone: | Utility Design approved by project team | [5 empty] | Estimated Date: |  | 2026-05-15
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000006
Last Milestone Completed: |  | NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | Date: | 2026-07-23
Next Milestone: | Utility Permit submitted to TxDOT | [5 empty] | Estimated Date: |  | 2026-07-30
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000007
Last Milestone Completed: |  | Existing Utility Layout complete, provided to TxDOT | [5 empty] | Date: | 2025-01-29
Next Milestone: | Existing Utility Layout provided to utility to verify | [5 empty] | Estimated Date: |  | 2025-02-08
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000008
Last Milestone Completed: |  | Existing Utility Layout complete, provided to TxDOT | [5 empty] | Date: | 2025-01-29
Next Milestone: | Existing Utility Layout provided to utility to verify | [5 empty] | Estimated Date: |  | 2025-02-08
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000009
Last Milestone Completed: |  | Existing Utility Layout complete, provided to TxDOT | [5 empty] | Date: | 2025-01-29
Next Milestone: | Existing Utility Layout provided to utility to verify | [5 empty] | Estimated Date: |  | 2025-02-08
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A
Utility Name | Utility Name HERE | [5 empty] | Utility ID: | U00000010
Last Milestone Completed: |  | Existing Utility Layout complete, provided to TxDOT | [5 empty] | Date: | 2025-01-29
Next Milestone: | Existing Utility Layout provided to utility to verify | [5 empty] | Estimated Date: |  | 2025-02-08
Last Scheduled Milestone: |  | #N/A | [5 empty] | Date: | #N/A

## U_0001
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U0000001
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-31
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-10 | 2025-02-05
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-20 | 2025-02-18
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 27 | 2025-03-17
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U0000001 = IF(ISBLANK([Project INFO Sheet, row above]),[U0000001, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0002
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000002
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-31
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-10
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-25
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-22
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000002 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000002, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0003
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000003
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-31
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-10 | 2025-02-15
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-03-02
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-27
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000003 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000003, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0004
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000004
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-20
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-01-30 | 2025-02-02
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-17 | 2025-02-14
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-11 | 2025-03-14
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-04-25
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | 2025-05-02 | 2025-05-25
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000004 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000004, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0005
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000005
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-02-14
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-24 | 2025-02-28
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-03-15 | 2025-03-10
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-04-04 | 2025-08-25
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-09-30
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | 2025-10-07 | 2025-10-20
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A | 2025-11-15
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | 2025-12-15 | 2026-05-01
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | 2026-05-15
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | 2026-05-22
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | 2026-05-29
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 31 | 2026-06-29
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | 2026-07-06
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | 2026-07-13
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | 2026-08-12
Construction Start | [5 empty] | Construction |  | Contractor | 30 | 2026-09-11
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | 2026-09-26
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | 2027-03-25
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | 2027-04-08
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | 2027-04-22
Formulas:
U00000005 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000005, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0006
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000006
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-02-14
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-24 | 2025-02-28
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-03-15 | 2025-03-10
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-04-04 | 2025-08-25
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-09-30
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | 2025-10-07 | 2025-10-20
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A | 2025-11-15
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | 2025-12-15 | 2026-05-02
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | 2026-05-16 | 2026-06-15
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | 2026-06-22 | 2026-07-23
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | 2026-07-30
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | 2026-08-29
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | 2026-09-05
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | 2026-09-12
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | 2026-10-12
Construction Start | [5 empty] | Construction |  | Contractor | 30 | 2026-11-11
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | 2026-11-26
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | 2027-05-25
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | 2027-06-08
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | 2027-06-22
Formulas:
U00000006 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000006, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0007
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000007
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-29
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-08
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-23
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-20
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000007 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000007, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0008
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000008
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-29
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-08
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-23
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-20
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000008 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000008, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0009
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000009
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-29
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-08
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-23
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-20
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000009 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000009, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## U_0010
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information (data entry below this point, all data above is from project info sheet by formula)
Utility Name |  | Utility Name HERE | [6 empty] | Utility ID: | U00000010
Utility Type: |  | Telecommunications Attachment to Poles |  |  | Utility Status: |  | Utility Identified |  |  |  | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2025-01-29
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2025-02-08
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2025-02-23
Utility ID FORM submitted to TxDOT {30% PS&E} | [5 empty] | Coordination |  | Project Team | 25 | 2025-03-20
Preliminary Utility Conflicts Identified (NOC letter) {60% PS&E} | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) {90% PS&E} | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 14 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
U00000010 = IF(ISBLANK([Project INFO Sheet, row above]),[U00000010, row above]+[Utility ID:],[Project INFO Sheet, row above]+[Utility ID:])

## USR (reimbursable) {R} (hidden)
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information
Utility Name | [8 empty] | Utility ID:
Utility Type: |  |  |  |  | Utility Status: | [5 empty] | Project INFO Sheet
Utility Process: |  | NO | Non-Reimbursable |  | YES | Reimbursable by: |  | TxDOT |  | NO | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A | 2026-01-29
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | 2026-02-08
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | 2026-02-23
Utility ID FORM submitted to TxDOT - Including Eligibility Calculations | [5 empty] | Coordination |  | Project Team | 25 | 2026-03-20
Preliminary Utility Conflicts Identified (NOC letter) | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
Advanced Approval - Proof of Property Interest Submitted | [5 empty] | Agreement |  | Project Team | 30 | #N/A
Advanced Approval - Forced Betterment Submitted | [5 empty] | Agreement |  | Project Team | 45 | #N/A
Advanced Approval - Proof of Property Approved | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
Advanced Approval - Easement Value Submitted | [5 empty] | Agreement |  | Project Team | 7 | #N/A
Advanced Approval - Forced Betterment Approved | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
Advanced Approval - Easement Value Approved | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Advanced Approval - UAR Exception Submitted | [5 empty] | Coordination |  | Project Team | 7 | #N/A
Advanced Approval - UAR Exception Approved | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 15 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Agreement draft prepared for TxDOT review | [5 empty] | Agreement |  | Project Team | 30 | #N/A
Utility Agreement draft submitted to TxDOT | [5 empty] | Agreement |  | Project Team | 7 | #N/A
TxDOT review Agreement and provide comments | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Agreement revisions to address all comments | [5 empty] | Agreement |  | Project Team | 30 | #N/A
TxDOT final review (ROW Courtesy Review optional) | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Agreement final sent to Utility for Signature | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Agreement signed by Utility, returned to TxDOT | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Agreement Executed by TxDOT, NTP sent to Utility | [5 empty] | TxDOT Action |  | AUS_Utilities | 15 | #N/A
Materials Ordered by Utility Company | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Utility to advertise project for bidding | [5 empty] | Utility Action |  | Utility | 7 | #N/A
Review bids and award contract | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Construction Start | [5 empty] | Construction |  | Contractor | 30 | #N/A
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | #N/A
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | #N/A
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | #N/A
Formulas:
NO = IF(ISBLANK([Project INFO Sheet, row above]),[NO, row above]+[Phone:],[Project INFO Sheet, row above]+[Phone:])

## USR {R} joint-bid (hidden)
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information
Utility Name | [8 empty] | Utility ID:
Utility Type: |  |  |  |  | Utility Status: | [5 empty] | Project INFO Sheet
Utility Process: |  | NO | Non-Reimbursable |  | YES | Reimbursable by: |  | TxDOT |  | YES | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | #N/A
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | #N/A
Utility ID FORM submitted to TxDOT - Including Eligibility Calculations | [5 empty] | Engineering |  | Project Team | 25 | #N/A
Preliminary Utility Conflicts Identified (NOC letter) | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
Advanced Approval - Proof of Property Interest Submitted | [5 empty] | Agreement |  | Project Team | 30 | #N/A
Advanced Approval - Forced Betterment Submitted | [5 empty] | Agreement |  | Project Team | 45 | #N/A
Advanced Approval - Proof of Property Approved | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
Advanced Approval - Easement Value Submitted | [5 empty] | Agreement |  | Project Team | 7 | #N/A
Advanced Approval - Forced Betterment Approved | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
Advanced Approval - Easement Value Approved | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Advanced Approval - UAR Exception Submitted | [5 empty] | Coordination |  | Project Team | 7 | #N/A
Advanced Approval - UAR Exception Approved | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 15 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Agreement draft prepared for TxDOT review | [5 empty] | Agreement |  | Project Team | 30 | #N/A
Utility Agreement draft submitted to TxDOT | [5 empty] | Agreement |  | Project Team | 7 | #N/A
TxDOT review Agreement and provide comments | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Agreement revisions to address all comments | [5 empty] | Agreement |  | Project Team | 30 | #N/A
TxDOT final review (ROW Courtesy Review optional) | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Agreement final sent to Utility for Signature | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Agreement signed by Utility, returned to TxDOT | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Agreement Executed by TxDOT, NTP sent to Utility | [5 empty] | TxDOT Action |  | AUS_Utilities | 15 | #N/A
TxDOT Project Let Date | [5 empty] | Joint-bid |  | Contractor |  | 0
Construction Start | [5 empty] | Construction |  | Contractor | 30 | 1900-01-29
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | 1900-07-28
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | 1900-08-11
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | 1900-08-25
Formulas:
YES = IF(ISBLANK([Project INFO Sheet, row above]),[YES, row above]+[Phone:],[Project INFO Sheet, row above]+[Phone:])

## USR {NR} Joint-Bid (AFA needed) (hidden)
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information
Utility Name | [8 empty] | Utility ID:
Utility Type: |  |  |  |  | Utility Status: | [5 empty] | Project INFO Sheet
Utility Process: |  | YES | Non-Reimbursable |  | NO | Reimbursable by: |  |  |  | YES | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | #N/A
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | #N/A
Utility ID FORM submitted to TxDOT | [5 empty] | Coordination |  | Project Team | 25 | #N/A
Preliminary Utility Conflicts Identified (NOC letter) | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 15 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Submit plans and verified cost estimate to TxDOT | [5 empty] | Coordination |  | Project Team | 7 | #N/A
Draft Advanced Funding Agreement (AFA) | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
AFA reviewed and presented to City Council or Board | [5 empty] | Agreement |  | Utility | 60 | #N/A
AFA to Contract Services Division (CSD) | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
AFA approved by CSD, sent for signatures via DocuSign | [5 empty] | Agreement |  | AUS_Utilities | 20 | #N/A
AFA Executed, request for payment letter sent to utility | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Payment received from Utility | [5 empty] | Utility Action |  | Utility | 45 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
TxDOT Project Let Date | [5 empty] | Joint-bid |  | Contractor |  | 0
Construction Start | [5 empty] | Construction |  | Contractor | 90 | 1900-03-30
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | 1900-09-26
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | 1900-10-10
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | 1900-10-24
Formulas:
YES = IF(ISBLANK([Project INFO Sheet, row above]),[YES, row above]+[Phone:],[Project INFO Sheet, row above]+[Phone:])

## USR {R} joint-bid (AFA needed) (hidden)
TxDOT Highway: |  | 0 |  | Project Limits: |  | 0
CCSJ: | 0 |  | Construction Project ID: |  |  | 0 |  | Let Date: | 0
| 0 |  |  |  |  | 0
Station Project Limits |  |  |  | Station FROM: |  | 0 |  | Station TO: |  | 0
ROW CSJ: | 0 |  | ROW Project ID: |  | 0 |  | Full Authority Date (ROW): |  |  | N/A
Project Design Schedule
|  |  | 30% PS%E |  | 60% PS&E |  | 90% PS&E |  | 100% PS&E
Design Complete Date: |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Design Submitted to TxDOT: |  |  | 0 |  | 0 |  | 0 |  | 0
Conflict Analysis Complete: |  |  | #N/A |  | #N/A |  | #N/A
Utility Notified of Conflicts: |  |  | #N/A |  | #N/A |  | #N/A
Project Specific Information
How long is this project ( mainlanes from beginning to end)? | [5 empty] | 0 |  | miles | 0 |  | LF
Project Size: |  | 0 | Project Type: |  | 0 |  | Will ROW be acquired for this project? |  |  |  | NO
Utility Specific Information
Utility Name | [8 empty] | Utility ID:
Utility Type: |  |  |  |  | Utility Status: | [5 empty] | Project INFO Sheet
Utility Process: |  | NO | Non-Reimbursable |  | YES | Reimbursable by: |  | TxDOT |  | YES | Joint-Bid
Brief Notes:
Utility Contact Name: |  |  |  |  | Email: |  |  |  | Phone:
Description of Milestone | [5 empty] | Milestone Type |  | Assigned | Duration (DAYS) | Estimated Date | Date Complete | Comments
Existing Utility Layout complete, provided to TxDOT | [5 empty] | Engineering |  | Project Team |  | #N/A
Existing Utility Layout provided to utility to verify | [5 empty] | Engineering |  | Project Team | 10 | #N/A
Send NOPC letter signed by TxDOT PM | [5 empty] | TxDOT Action |  | Project Team | 15 | #N/A
Utility ID FORM submitted to TxDOT - Including Eligibility Calculations | [5 empty] | Coordination |  | Project Team | 25 | #N/A
Preliminary Utility Conflicts Identified (NOC letter) | [5 empty] | Engineering |  | Project Team |  | #N/A
Utility Relocation Design Begins | [5 empty] | Utility Design |  | Utility | 7 | #N/A
Advanced Approval - Proof of Property Interest Submitted | [5 empty] | Agreement |  | Project Team | 30 | #N/A
Advanced Approval - Forced Betterment Submitted | [5 empty] | Agreement |  | Project Team | 45 | #N/A
Advanced Approval - Proof of Property Approved | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
Advanced Approval - Easement Value Submitted | [5 empty] | Agreement |  | Project Team | 7 | #N/A
Advanced Approval - Forced Betterment Approved | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
Advanced Approval - Easement Value Approved | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
FINAL Utility Conflicts Identified (NOC letter 03-03) | [5 empty] | TxDOT Action |  | Project Team |  | #N/A
Advanced Approval - UAR Exception Submitted | [5 empty] | Coordination |  | Project Team | 7 | #N/A
Advanced Approval - UAR Exception Approved | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Utility Relocation Design Complete | [5 empty] | Utility Design |  | Utility | 30 | #N/A
Utility Design approved by project team | [5 empty] | Engineering |  | Project Team | 15 | #N/A
NORA letter signed by TxDOT PM and sent to Utility | [5 empty] | TxDOT Action |  | Project Team | 7 | #N/A
Utility Agreement draft prepared for TxDOT review | [5 empty] | Agreement |  | Project Team | 30 | #N/A
Utility Agreement draft submitted to TxDOT | [5 empty] | Agreement |  | Project Team | 7 | #N/A
TxDOT review Agreement and provide comments | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Draft Advanced Funding Agreement (AFA) | [5 empty] | Agreement |  | AUS_Utilities | 30 | #N/A
Agreement revisions to address all comments | [5 empty] | Agreement |  | Project Team | 30 | #N/A
AFA reviewed and presented to City Council or Board | [5 empty] | Agreement |  | Utility | 60 | #N/A
AFA to Contract Services Division (CSD) | [5 empty] | Agreement |  | AUS_Utilities | 45 | #N/A
AFA approved by CSD, sent for signatures via DocuSign | [5 empty] | Agreement |  | AUS_Utilities | 20 | #N/A
AFA Executed, request for payment letter sent to utility | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Payment received from Utility | [5 empty] | Utility Action |  | Utility | 45 | #N/A
Agreement final sent to Utility for Signature | [5 empty] | Agreement |  | AUS_Utilities | 15 | #N/A
Utility Permit submitted to TxDOT | [5 empty] | Utility Action |  | Utility | 15 | #N/A
Utility Permit approved by TxDOT | [5 empty] | TxDOT Action |  | AUS_Utilities | 30 | #N/A
Agreement signed by Utility, returned to TxDOT | [5 empty] | Utility Action |  | Utility | 30 | #N/A
Agreement Executed by TxDOT, NTP sent to Utility | [5 empty] | TxDOT Action |  | AUS_Utilities | 15 | #N/A
TxDOT Project Let Date | [5 empty] | Joint-bid |  | Contractor |  | 0
Construction Start | [5 empty] | Construction |  | Contractor | 90 | 1900-03-30
Materials Received by Utility Company | [5 empty] | Utility Action |  | Utility | 15 | 1900-04-14
Construction Complete - Adjustment still in Progress | [5 empty] | Construction |  | Contractor | 180 | 1900-10-11
Splicing, pressure testing, other utility specific actions | [5 empty] | Construction |  | Utility | 14 | 1900-10-25
Existing facility removed/abandoned - Adjustment Complete | [5 empty] | Construction |  | Utility | 14 | 1900-11-08

## Durations Table
Utility Type | Project Type | Utility Design Duration based on project size |  |  | Utility Construction Duration based on project size
|  | Small (days) | Medium (days) | Large (days) | Small (days) | Medium (days) | Large (days)
Water/Wastewater | Rural | 30 | 45 | 90 | 30 | 90 | 120
| Urban | 30 | 60 | 120 | 45 | 120 | 180
| Metro | 45 | 90 | 180 | 90 | 180 | 360
Electric (Distribution) aerial on poles | Rural | 30 | 45 | 60 | 30 | 45 | 45
| Urban | 30 | 45 | 60 | 45 | 60 | 90
| Metro | 45 | 60 | 90 | 45 | 90 | 120
Electric (Distribution) underground | Rural | 30 | 45 | 60 | 30 | 60 | 90
| Urban | 45 | 45 | 60 | 45 | 90 | 120
| Metro | 45 | 60 | 90 | 45 | 120 | 180
Electric (Transmission) | Rural | 45 | 60 | 90 | 90 | 120 | 180
| Urban | 45 | 60 | 120 | 120 | 180 | 270
| Metro | 60 | 90 | 180 | 120 | 270 | 365
Gas (Distribution) | Rural | 30 | 45 | 60 | 30 | 45 | 90
| Urban | 45 | 45 | 60 | 45 | 60 | 120
| Metro | 45 | 60 | 90 | 60 | 90 | 180
Gas (Transmission) | Rural | 45 | 45 | 90 | 45 | 60 | 90
| Urban | 60 | 60 | 120 | 60 | 90 | 120
| Metro | 90 | 90 | 180 | 90 | 120 | 180
Telecommunications Attachment to Poles | Rural | 30 | 45 | 60 | 30 | 45 | 60
| Urban | 30 | 45 | 60 | 45 | 60 | 90
| Metro | 45 | 60 | 90 | 45 | 90 | 120
Telecommunications Underground | Rural | 30 | 30 | 45 | 30 | 45 | 90
| Urban | 45 | 45 | 60 | 45 | 60 | 120
| Metro | 60 | 60 | 90 | 60 | 90 | 180
TxDOT Project Types | Descriptions based on what is located in the ground for these projects
Rural | roadways with open ditches in less populated areas.
Urban | roadways in more populated area with open ditches, but may have storm sewer at intersections.
Metro | roadways in highly populated area with complex storm sewer and shared use paths.
Project Size | Descriptions based on LF of TxDOT roadway project or units of anticipated utility adjustment
Small | intersection or bridge projects typically <1,000 feet,<10 poles (distribution) 4 (transmission)
Medium | >1,000 feet <1 mile (5,280 feet), >10 poles <20 poles (distribution) 10 (transmission)
Large | >1 mile (5,280 feet), >20 poles (distribution) 11 (transmission)

## Lists (hidden)
Utility Status (non-reimbursable)
Utility Identified
Utility Owner Notified of Conflict
Utility Design in Progress
Utility Design Complete
Utility Permit Submitted to TxDOT
Utility Permit Approved by TxDOT
Adjustment in Progress
Adjustment Completed - Close OUT
No Utility Adjustment Needed - Close OUT
Check box
YES
NO
Project Size | Duration (days)
Small | 15
Medium | 30
Large | 45
Project Types | Duration (days)
Rural | 20
Urban | 30
Metro | 45
YES
NO
Designed by | ROW acquired by
TxDOT | TxDOT
Local Government | Local Government
N/A
Letting Type
Statewide Let
Local Let
Utility Status for Agreements
Utility Identified
Utility Owner Notified of Conflict
Utility Design in Progress
Utility Design Complete
Utility Permit Submitted to TxDOT
Utility Permit Approved by TxDOT
Utility Agreement Drafted
Utility Agreement Executed
Adjustment in Progress
Adjustment Completed - Close OUT
No Utility Adjustment Needed - Close OUT
Assigned To
Project Team
AUS_Utilities
Utility
Contractor
Other
Milestone Type
Coordination
Engineering
Agreement
Utility Design
Utility Action
Construction
Joint-bid
TxDOT Action