## Schematic Submittal Checklist
Schematic Project Submittal Checklist
CSJ
County
Area Office(s)
Highway/Location
Project Limits | From
To
Type of Work
Layman's Desc
| Draft Schematic | Final Schematic | Tasks
Select "Y" (yes), "N" (no), or "N/A" (not applicable).
Project Controls | [6 empty] | SME: | District APD/ATP/LG
CSJ request (TxDOT PM)
CSJ request to make Chargeable (TxDOT PM)
P6/TxDOTCONNECT Milestones Tracking (TxDOT PM)
LG coordination-Advance Funding Agreement (TxDOT PM)
Project Management | [5 empty] | SME: |  | District APD PM
Project Management Plan
Quality Assurance/Quality Control Plan
Project Schedule
Project Files & Data/Electronic Management Tool (EMT)
Kick off and monthly progress meeting
Monthly Progress Report along with invoice
Environmental / Public Involvement | [6 empty] | SME: | District ENV PM
Env. Scope kick off meeting
APD Stage Gate Checklist
Environmental constraints mapping
Define ENV Clearance type (CE/EA/EIS)
Develop project website content/fact sheet
Develop stakeholder database
PI Strategy Conference
Public Involvement Plan
Right-of-entry letters
Purpose and Need statement
Meeting with affected property owners (MAPOs)
Stakeholder workshop
Public meeting (the number and type of the meeting will depends on the type of project
Meeting #1: Get feedback on the existing issue
Meeting #2: Present different alternatives
Meeting #3: Present the final alternatives
Public Meeting/Hearing summary report/comment response matrix
Environmental Documentation including Tech reports
Survey | [6 empty] | SME: | District Surveyor
SME one-on-one meeting
Design survey (DGN/DTM/TIN)
Existing ROW Verification
Aerial/Mobile/UAS LiDAR
Aerial/Mobile/UAS photography
Horizontal and vertical control
Design | [6 empty] | SME: | District Engineering Services
Kickoff Meeting
Design Conference Meeting
Design Summary Report (DSR): Form 2440
Form 1002
Stick flow diagrams (functional classification/design speed)
Design Exceptions/Waivers/Variance Request
Typical Sections
Frontage Road Briefing Document (FRBD)
Texas Highway Freight Network (THFN) Design Deviation Request
FHWA requirements
Major Project (Total Project Cost of $500 million or more)
Cost Estimates Review (CER)
Project Management Plan (PMP)
Initial Financial Plan (IFP)
Other project (Total Project Cost between $100 million to $500 million)
Initial Financial Plan (IFP)
Value engineering study -Form 2502: Executive Decision Summary
Interstate Access Justification Report
Geometric Schematic
Cross-Sections
Identify preliminary retaining walls
Identify bicycle & pedestrian accommodations
Cost estimate
Safety Score Tool (Safer By Design)
ORD 3D model of schematic design
KMZ/KML of schematic design
Engineering Summary Report
Schematic Final Acceptance/Lessons-Learned
[6 empty] | District |  | DES | FHWA
Traffic | [6 empty] | SME: | District Traffic SME
SME one-on-one meeting
TSAP Scoping Form
Data collection (Field Data Collection Memo)
Traffic Impact Analysis Review Memo
Traffic volume and forecasting
Submit Traffic Data Request Forms
Traffic projections methodology memo
[6 empty] | District |  | TPP
Traffic Forecast/Projection Memo
[6 empty] | District |  | TPP
Traffic and Operational Analysis Report
Operational analysis
Safety analysis
Intersection Control Evaluation (ICE) Memo
Traffic Guide Sign Schematic
Traffic renderings/simulation for public outreach
Drainage | [6 empty] | SME: | District Drainage/Hydraulic SME
Drainage Research: FEMA, eBLE, contact local FPA(s) for other studies, TxDOT projects
SME one-on-one meeting on research and analysis approach
H&H Modeling Criteria and Guidelines Tech Memo
Hydrologic studies, refer District H&H Guidance Document
Preliminary hydraulic analyses/design
Determine detention/water quality needs
Define drainage easements (for outfall, ditch, ponds)
Define drainage types (closed vs open system)
Water quality BMP analyses and grading
Drainage report
Bridge | [6 empty] | SME: | District Bridge SME
SME one-on-one meeting
Preliminary planning (bridge limits, span length, bent locations)
Identify boring locations (If only request by District Bridge SME)
Perform geotechnical investigations (If only request by District Bridge SME)
Geotechnical report (If only request by District Bridge SME)
Pavement | [6 empty] | SME: | District Pavement Engineer
Identify boring locations
Perform geotechnical investigations
|  |  | Pavement design recommendation |  |  |  |  | Provided by District
Pavement/Geotechnical report
Right-of-Way | [6 empty] | SME: | District ROW and Survey SME
ROW workshop
Perform preliminary ROW research
Prepare ROW/property base map
Prepare required ROW acquisition documentation
Property Descriptions (parcel metes and bounds; deeds)
ROW GIS files
Traditional ROW Map document
Request ROW Resource in TxDOTConnect (ROW CSJ)
Utilities | [6 empty] | SME: | Schematic Project Manager
Utility SME one-on-one meeting (as needed)
SUE investigations (both in existing and proposed ROW)
QLD - Existing Records
QLC - Surface visible feature survey
QLB - Designate {if needed for advanced relocation or early conflict analysis}
QLA - Locate (test hole) {if needed for advanced relocation}
Utility Conflict Matrix including utility contact list (district template recommended)
Existing Utility Layout (.kmz, .dgn, and .pdf)
Identify long lead time utility conflicts (materials, outages, new easements, etc.)
Proposed Utility Layout (.kmz, .dgn, and .pdf)
Railroad | [6 empty] | SME: | District RR Coordinator
SME one-on-one meeting
Initiate RR coordination
Exhibit A
Traffic Control | [6 empty] | SME: | AO / CST
SME one-on-one meeting (30%)
Conceptual traffic control plan layouts
Constructability review

## Feasibility Study Checklist
Feasibility Study Project Submittal Checklist
CSJ/Project ID
County
Area Office(s)
Highway/Location
Project Limits | From
To
Type of Work
Layman's Desc
| Draft | Final | Tasks
Select "Y" (yes), "N" (no), or "N/A" (not applicable).
Project Controls (For TxDOT-PM) | [5 empty] | SME: | District APD/ATP
CSJ request / Feasibility Study Job Aid Request Form (TxDOT PM)
CSJ request to make Chargeable (TxDOT PM)
P6/TxDOTCONNECT Milestones Tracking (TxDOT PM)
LG coordination-Advance Funding Agreement (TxDOT PM)
Project Management
|  |  | Project Management Plan |  |  | SME: | District APD PM
Quality Assurance/Quality Control Plan
Project Schedule
Project Files & Data/Electronic Management Tool (EMT)
Kick off and monthly progress meeting
Monthly Progress Report along with invoice
Environmental / Public Involvement | [5 empty] | SME: | District ENV PM
PI Strategy Conference
Environmental Constraints Mapping
Public Involvement Plan
Develop Project Website content/fact sheet
Stakeholder Workshop
Public meeting (the number and type of the meeting will depends on the type of project
Meeting #1: Get feedback on the existing issue
Meeting #2: Present different alternatives
Meeting #3: Present the final alternatives
Public Meeting/Hearing summary report/comment response matrix
Meeting with affected property owners (MAPOs)-If needed
Survey | [5 empty] | SME: | District Surveyor
SME one-on-one meeting
Aerial photography
Signed/Sealed Date:
Design | [5 empty] | SME: | APD/District Engineering Service
SME one-on-one meeting
Preliminary Design Values-Design Criteria and Typical Section
Bicycle and Pedestrian Accommodations
Location Studies
Alternatives analysis Memo
Conceptual layouts for short, mid, long term build conceptual alternative
Improvement concept screening matrix
Cost Estimate
Economic Analysis
Feasibility study Report
Traffic | [5 empty] | SME: | District Traffic SME
SME one-on-one meeting
TSAP Scoping Form
Data collection-Field Data Collection memo
Traffic Impact Analysis Review Memo
Submit Traffic Data Request Forms
Traffic projections methodology memo
[5 empty] | District |  | TPP
Traffic Forecast/Projection Memo
[5 empty] | District |  | TPP
Traffic and Operational Analysis Report
Operational analysis (existing, no build and build)
Safety analysis
Drainage | [5 empty] | SME: | District Drainage/Hydraulic SME
Drainage Research: FEMA, eBLE, contact local FPA(s) for other studies, TxDOT projects
Drainage Research Summary & Recommendations: Flood levels to set bridge or roadway profiles,
known local flooding areas, qualitative assessment of need for detention, WQ
SME one-on-one meeting on findings
Provide feedback on alternative analysis
Flood Prone areas within the Study Limits Map
Bridge | [5 empty] | SME: | District Bridge Engineer
SME one-on-one meeting
Preliminary planning (bridge limits, span length, bent locations)
Geotechnical | [5 empty] | SME: | District Pavement Engineer
None
Right-of-Way | [5 empty] | SME: | District ROW SME
Preliminary right-of -way requirements-Preliminary ROW Maps
Utilities | [5 empty] | SME: | Schematic Project Manager
Utility SME one-on-one meeting (as needed)
SUE investigations
QLD - Existing Records(In existing ROW)
Utility Conflict Matrix including utility contact list (district template recommended)
Existing Utility Layout (.kmz, .dgn, and .pdf)
Identify long lead time utility conflicts (materials, outages, new easements, etc.)
Railroad | [5 empty] | SME: | District RR Coordinator
SME one-on-one meeting
Initiate RR coordination

## Sheet1 (hidden)
Y
N
N/A

## 2 (hidden)
Y
N
N/A