## Sheet1
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED
DISTRICT | COUNTY | HIGHWAY | C C S J | DATE FINAL ESTIMATE PAID | CONTRACT AWARD | CHANGE ORDERS | AMOUNT PAID | UNDER/OVER BUDGET | CONTRACT DAYS | DAYS ADDED | DAYS USED | UNDER/OVER SCHEDULE
ABILENE | CALLAHAN | SH 36 | 18102029 | 2017-08-02 | 5388974.28 | 411912.32 | 6048340.61 | 247454.01 | 129 | 20 | 149 | 0
ABILENE | FISHER | FM 2832 | 285701005 | 2017-07-26 | 678682.96 | 24994.33 | 685660.51 | -18016.78 | 72 | 0 | 108 | 36
ABILENE | HOWARD | IH 20 | 505102 | 2017-08-03 | 18434933.56 | 455691.25 | 18626251.8 | -264373.01 | 470 | 59 | 542 | 13
ABILENE | HOWARD | VA | 90812019 | 2017-04-10 | 44837998.95 | 1045985.76 | 47492406.76 | 1608422.05 | 679 | 0 | 538 | -141
ABILENE | MITCHELL | SH 208 | 45403041 | 2017-08-21 | 2654056.79 | 184486.34 | 2794235.89 | -44307.24 | 56 | 22 | 77 | -1
ABILENE | MITCHELL | FM 2836 | 233101014 | 2017-08-25 | 1445914.79 | 21534.54 | 1295805.67 | -171643.66 | 82 | 8 | 148 | 58
ABILENE | NOLAN | IH 20 | 602112 | 2017-05-25 | 3498754.25 | 14859.84 | 3494140.24 | -19473.85 | 48 | 0 | 100 | 52
ABILENE | SCURRY | FM 1606 | 152602009 | 2017-03-03 | 6584662.31 | 50870 | 6592132.73 | -43399.58 | 194 | 19 | 215 | 2
ABILENE | TAYLOR | BU 83-D | 3308038 | 2017-05-22 | 9806711.43 | -467085.05 | 9276972.49 | -62653.89 | 67 | 2 | 69 | 0
ABILENE | TAYLOR | US 84 | 5401031 | 2017-04-11 | 7380051.17 | 53592 | 7536274.34 | 102631.17 | 72 | 10 | 110 | 28
ABILENE | TAYLOR | VA | 90800080 | 2017-03-06 | 448260.5 | 14190.4 | 472197.4 | 9746.5 | 75 | 0 | 67 | -8
AMARILLO | GRAY | IH 40 | 27511077 | 2017-08-03 | 3565812.59 | -176195.5 | 3487286.09 | 97669 | 76 | 0 | 69 | -7
AMARILLO | GRAY | SH 152 | 39701043 | 2017-06-20 | 6779225.7 | 0 | 6932565.86 | 153340.16 | 52 | 0 | 79 | 27
AMARILLO | HARTLEY | US 87 | 4101045 | 2017-03-28 | 9173359.64 | 37359.68 | 9914154.76 | 703435.44 | 120 | 0 | 116 | -4
AMARILLO | HEMPHILL | US 83 | 3005063 | 2017-03-03 | 7498932.21 | -415347.11 | 7337566.02 | 253980.92 | 125 | 3 | 121 | -7
AMARILLO | HEMPHILL | US 60 | 3006056 | 2017-08-15 | 19606573.39 | 26480.14 | 19219408.67 | -413644.86 | 170 | 45 | 209 | -6
AMARILLO | HEMPHILL | PW | 90403017 | 2017-06-27 | 938346.79 | -616.18 | 852506.37 | -85224.24 | 57 | 0 | 49 | -8
AMARILLO | OCHILTREE | US 83 | 3001032 | 2017-07-12 | 7967738.81 | 172922.12 | 7746312.75 | -394348.18 | 94 | 0 | 93 | -1
AMARILLO | POTTER | VA | 90400161 | 2017-04-28 | 1946236.07 | 10000 | 1721416.37 | -234819.7 | 210 | 3 | 127 | -86
AMARILLO | POTTER | VA | 90400162 | 2017-05-30 | 369998.68 | 7479.6 | 377478.28 | 3.4561e-11 | 74 | 0 | 13 | -61
AMARILLO | ROBERTS | US 60 | 16908022 | 2017-05-15 | 996579.09 | -12658.43 | 788116.42 | -195804.24 | 76 | 0 | 76 | 0
AMARILLO | SHERMAN | US 54 | 23806029 | 2017-06-02 | 7825684.43 | -2752 | 8125791.39 | 302858.96 | 57 | 0 | 55 | -2
ATLANTA | BOWIE | US 67 | 1012067 | 2017-06-20 | 1829345.43 | -806106.53 | 782795.38 | -240443.52 | 195 | 7 | 193 | -9
ATLANTA | BOWIE | SL 14 | 4608016 | 2017-07-26 | 381220 | 0 | 381220 | 0 | 120 | 0 | 27 | -93
ATLANTA | BOWIE | IH 30 | 61007098 | 2017-04-27 | 3821270.5 | 31452.04 | 4044069.59 | 191347.05 | 290 | 0 | 277 | -13
ATLANTA | CASS | FM 1399 | 54608011 | 2017-05-19 | 1162910.4 | 78796.8 | 1242252.87 | 545.67 | 150 | 15 | 178 | 13
ATLANTA | HARRISON | IH 20 | 49508095 | 2017-05-19 | 7872292.12 | 470421.77 | 8730188.57 | 387474.68 | 110 | 0 | 100 | -10
ATLANTA | HARRISON | IH 20 | 49508096 | 2017-04-20 | 1038536.77 | 0 | 1045544.42 | 7007.65 | 245 | 0 | 200 | -45
ATLANTA | MARION | US 59 | 6206053 | 2017-05-25 | 2050585.72 | 101411.74 | 2268977.72 | 116980.26 | 50 | 0 | 52 | 2
ATLANTA | MARION | SH 43 | 56903021 | 2017-07-14 | 1204182.24 | 88060.28 | 1303620.59 | 11378.07 | 63 | 0 | 61 | -2
ATLANTA | TITUS | US 271 | 22105088 | 2017-03-29 | 2995056.85 | 327626.83 | 3453628.7 | 130945.02 | 55 | 0 | 75 | 20
AUSTIN | BASTROP | US 290 | 11406030 | 2017-04-28 | 19049776.57 | 945623.78 | 20453629.55 | 458229.2 | 301 | 90 | 390 | -1
AUSTIN | BASTROP | SH 71 | 26503048 | 2017-07-07 | 286525.3 | 11611.21 | 312888.74 | 14752.23 | 32 | 0 | 20 | -12
AUSTIN | BASTROP | SH 71 | 26505071 | 2017-04-25 | 13669975.32 | 8765.8 | 13468670.8 | -210070.32 | 346 | 0 | 307 | -39
AUSTIN | BASTROP | SH 21 | 47201041 | 2017-03-13 | 423190.77 | 20043.38 | 431830.73 | -11403.42 | 15 | 0 | 11 | -4
AUSTIN | BASTROP | CS | 91418091 | 2017-08-25 | 529317.55 | 0 | 518173.55 | -11144 | 95 | 0 | 90 | -5
AUSTIN | BASTROP | CR | 91418108 | 2017-06-12 | 431059.21 | 2484 | 420652.11 | -12891.1 | 75 | 0 | 65 | -10
AUSTIN | BASTROP | FM 2571 | 268601011 | 2017-03-23 | 1212626.25 | 151057.01 | 1372413.63 | 8730.37 | 115 | 85 | 200 | 0
AUSTIN | BLANCO | US 281 | 11305047 | 2017-03-24 | 1397340.04 | 63856.9 | 1549889.08 | 88692.14 | 55 | 0 | 41 | -14
AUSTIN | BLANCO | RM 3232 | 335102005 | 2017-04-12 | 3490778.45 | -110886.15 | 3367320.34 | -12571.96 | 225 | 34 | 253 | -6
AUSTIN | BURNET | US 281 | 25201074 | 2017-03-21 | 2392271.35 | 79352.46 | 2552279.57 | 80655.76 | 62 | 0 | 54 | -8
AUSTIN | BURNET | SH 71 | 70001040 | 2017-06-29 | 113531 | 0 | 115302 | 1771 | 64 | 0 | 64 | 0
AUSTIN | CALDWELL | SH 80 | 28701015 | 2017-04-27 | 2205029.54 | 58435.25 | 2520761.55 | 257296.76 | 40 | 1 | 40 | -1
AUSTIN | GILLESPIE | CR | 91419022 | 2017-08-23 | 2659843.08 | 28423.14 | 2735756.21 | 47489.99 | 623 | 0 | 584 | -39
AUSTIN | GILLESPIE | RM 2721 | 271901008 | 2017-03-13 | 2899581.31 | -58265.4 | 2710899.58 | -130416.33 | 159 | 82 | 510 | 269
AUSTIN | HAYS | IH 35 | 1603096 | 2017-03-14 | 1166528.52 | 14395.94 | 1288079.87 | 107155.41 | 36 | 0 | 33 | -3
AUSTIN | HAYS | IH 35 | 1603101 | 2017-05-18 | 386404.3 | -48520.13 | 328419.14 | -9465.03 | 14 | 0 | 16 | 2
AUSTIN | HAYS | US 290 | 11307067 | 2017-05-18 | 816443 | 6185 | 850118.86 | 27490.86 | 29 | 0 | 17 | -12
AUSTIN | HAYS | RM 12 | 28503053 | 2017-07-26 | 1923900.41 | 6127.92 | 1884965.75 | -45062.58 | 126 | 0 | 165 | 39
AUSTIN | HAYS | SH 80 | 28601055 | 2017-03-28 | 295843 | 0 | 285988.1 | -9854.9 | 60 | 0 | 80 | 20
AUSTIN | HAYS | RM 1826 | 175402019 | 2017-07-14 | 746842.8 | 0 | 778356.57 | 31513.77 | 129 | 0 | 116 | -13
AUSTIN | HAYS | RM 1826 | 175402024 | 2017-08-23 | 605145.34 | 48970.61 | 682603.45 | 28487.5 | 40 | 12 | 75 | 23
AUSTIN | HAYS | RM 967 | 177601032 | 2017-07-19 | 4408237.86 | 126398.79 | 4510489.23 | -24147.42 | 227 | 104 | 328 | -3
AUSTIN | HAYS | FM 2439 | 229301024 | 2017-03-10 | 6950845.23 | -212279.94 | 6516295.6 | -222269.69 | 263 | 94 | 356 | -1
AUSTIN | HAYS | FM 2439 | 229301027 | 2017-03-10 | 274000 | 0 | 306029.49 | 32029.49 | 23 | 0 | 6 | -17
AUSTIN | HAYS | FM 2770 | 321001013 | 2017-03-24 | 839994.76 | 0 | 858053.66 | 18058.9 | 40 | 0 | 24 | -16
AUSTIN | LEE | FM 180 | 311401012 | 2017-03-24 | 4218820.7 | 199874.25 | 4288501.64 | -130193.31 | 129 | 28 | 154 | -3
AUSTIN | LLANO | CR | 91425007 | 2017-03-07 | 299364.78 | 14504.93 | 266404.6 | -47465.11 | 52 | 5 | 72 | 15
AUSTIN | MASON | US 377 | 14904016 | 2017-05-19 | 765167.5 | 14850 | 773528.75 | -6488.75 | 87 | 0 | 57 | -30
AUSTIN | MASON | RM 386 | 57701028 | 2017-08-22 | 1151527.25 | 108203.32 | 1320111.13 | 60380.56 | 247 | 6 | 203 | -50
AUSTIN | TRAVIS | LP 275 | 1511062 | 2017-04-05 | 1249601.8 | 408594.34 | 1733262.12 | 75065.98 | 42 | 0 | 41 | -1
AUSTIN | TRAVIS | IH 35 | 1513352 | 2017-04-26 | 1822826.45 | 44303.16 | 2127256.05 | 260126.44 | 66 | 0 | 64 | -2
AUSTIN | TRAVIS | IH 35 | 1513360 | 2017-04-19 | 2905019.45 | 333426.65 | 3416873.43 | 178427.33 | 175 | 10 | 177 | -8
AUSTIN | TRAVIS | IH 35 | 1513405 | 2017-07-26 | 848590 | 17774.88 | 963708.74 | 97343.86 | 23 | 0 | 23 | 0
AUSTIN | TRAVIS | LP 275 | 1601109 | 2017-04-12 | 453261.1 | -27.61 | 403137.44 | -50096.05 | 32 | 0 | 72 | 40
AUSTIN | TRAVIS | IH 35 | 1601110 | 2017-06-07 | 2011905.83 | 111496.01 | 2038409.32 | -84992.52 | 54 | 5 | 39 | -20
AUSTIN | TRAVIS | SL 275 | 1601115 | 2017-05-19 | 293000 | 32507 | 348450.34 | 22943.34 | 52 | 25 | 77 | 0
AUSTIN | TRAVIS | US 290 | 11309070 | 2017-08-11 | 2906870.88 | -269610.65 | 2531490.45 | -105769.78 | 49 | 0 | 54 | 5
AUSTIN | TRAVIS | SL 360 | 11313154 | 2017-05-30 | 3188700.55 | -5129.95 | 3395653.88 | 212083.28 | 49 | 0 | 49 | 0
AUSTIN | TRAVIS | US 290 | 11403025 | 2017-03-07 | 1623285.68 | 66577.4 | 1726891.76 | 37028.68 | 107 | 0 | 102 | -5
AUSTIN | TRAVIS | RM 3238 | 68304018 | 2017-04-10 | 1504303.45 | 35403.04 | 1699602.7 | 159896.21 | 106 | 60 | 166 | 0
AUSTIN | TRAVIS | SH 71 | 70003123 | 2017-07-27 | 8246005.41 | 411667.58 | 8341862.11 | -315810.88 | 161 | 137 | 328 | 30
AUSTIN | TRAVIS | SH 71 | 70003130 | 2017-03-22 | 425202.19 | 0 | 353073.09 | -72129.1 | 20 | 0 | 8 | -12
AUSTIN | TRAVIS | VA | 91400301 | 2017-05-08 | 4204759.5 | 483450.83 | 4549610.1 | -138600.23 | 508 | 0 | 501 | -7
AUSTIN | TRAVIS | VA | 91400344 | 2017-03-23 | 1083323.5 | -13005.6 | 1363027 | 292709.1 | 300 | 0 | 239 | -61
AUSTIN | TRAVIS | VA | 91400367 | 2017-04-07 | 278620.64 | 26712.24 | 308911.43 | 3578.55 | 133 | 0 | 81 | -52
AUSTIN | TRAVIS | VA | 91400381 | 2017-03-02 | 994912 | 29620.44 | 1059612.25 | 35079.81 | 168 | 0 | 153 | -15
AUSTIN | TRAVIS | FM 969 | 118601089 | 2017-03-16 | 2067551.68 | 23498.48 | 2208651.93 | 117601.77 | 38 | 0 | 40 | 2
AUSTIN | TRAVIS | FM 973 | 120003046 | 2017-03-24 | 4060301.68 | 3500.45 | 3973672.89 | -90129.24 | 288 | 0 | 288 | 0
AUSTIN | TRAVIS | FM 973 | 120003052 | 2017-03-10 | 3332550.36 | 24307.61 | 3305884.22 | -50973.75 | 247 | 5 | 291 | 39
AUSTIN | TRAVIS | FM 1825 | 190201027 | 2017-03-13 | 406530.37 | -35335.56 | 351477.68 | -19717.13 | 32 | 0 | 9 | -23
AUSTIN | TRAVIS | FM 3177 | 327701013 | 2017-07-18 | 3616126.77 | 290559.32 | 3931149.28 | 24463.19 | 159 | 73 | 232 | 0
AUSTIN | WILLIAMSON | US 183 | 15104067 | 2017-03-08 | 867875.03 | -94409.25 | 711091.83 | -62373.95 | 33 | 0 | 39 | 6
AUSTIN | WILLIAMSON | US 183 | 15105103 | 2017-03-28 | 344399 | 4954.1 | 248108.65 | -101244.45 | 55 | 0 | 188 | 133
AUSTIN | WILLIAMSON | US 183 | 15105108 | 2017-03-24 | 1517070.86 | -414572.97 | 1133337.88 | 30839.99 | 38 | 0 | 32 | -6
AUSTIN | WILLIAMSON | US 79 | 20401061 | 2017-06-28 | 434443.61 | 27802.1 | 497143.91 | 34898.2 | 67 | 0 | 63 | -4
AUSTIN | WILLIAMSON | US 183 | 27304033 | 2017-07-14 | 1846967.1 | 14563.57 | 1879420.85 | 17890.18 | 122 | 0 | 114 | -8
AUSTIN | WILLIAMSON | US 183 | 27304035 | 2017-06-28 | 1300087.1 | 0 | 1340547.43 | 40460.33 | 101 | 0 | 98 | -3
AUSTIN | WILLIAMSON | SH 95 | 32003083 | 2017-08-17 | 2497365.8 | 62005.86 | 2700875.63 | 141503.97 | 180 | 0 | 167 | -13
AUSTIN | WILLIAMSON | SH 29 | 33701038 | 2017-03-16 | 2014970.42 | -41558.55 | 2140417.13 | 167005.26 | 60 | 0 | 73 | 13
AUSTIN | WILLIAMSON | SH 29 | 33702041 | 2017-03-16 | 1499000 | 0 | 1512381.18 | 13381.18 | 40 | 0 | 31 | -9
AUSTIN | WILLIAMSON | SH 195 | 44001039 | 2017-06-23 | 33311111 | -218238.77 | 33630210.99 | 537338.76 | 510 | 0 | 509 | -1
AUSTIN | WILLIAMSON | SH 195 | 44002010 | 2017-04-03 | 18778887.62 | 359759.29 | 18597243.04 | -541403.87 | 368 | 152 | 520 | 0
AUSTIN | WILLIAMSON | SH 45 | 68306027 | 2017-04-26 | 24729960.45 | 3376695.89 | 28136945.96 | 30289.62 | 495 | 142 | 677 | 40
AUSTIN | WILLIAMSON | VA | 91405182 | 2017-07-13 | 77034.5 | 0 | 81568.9 | 4534.4 | 18 | 0 | 11 | -7
AUSTIN | WILLIAMSON | FM 1466 | 120004011 | 2017-03-28 | 597945.34 | 0 | 590237.62 | -7707.72 | 48 | 0 | 48 | 0
AUSTIN | WILLIAMSON | FM 487 | 120102019 | 2017-05-08 | 6128687.87 | 365888.84 | 6577440.64 | 82863.93 | 287 | 8 | 290 | -5
AUSTIN | WILLIAMSON | FM 487 | 120103021 | 2017-04-24 | 6707427.52 | 1364798.6 | 7814572.96 | -257653.16 | 391 | 0 | 359 | -32
AUSTIN | WILLIAMSON | RM 1431 | 137802040 | 2017-07-10 | 6684011.94 | 313111.91 | 7481296.5 | 484172.65 | 177 | 25 | 202 | 0
AUSTIN | WILLIAMSON | FM 3406 | 137806011 | 2017-05-25 | 4776174.8 | 118803.62 | 5008793.15 | 113814.73 | 260 | 26 | 284 | -2
BEAUMONT | CHAMBERS | IH 10 | 50802111 | 2017-05-11 | 131475.45 | 0 | 129031.5 | -2443.95 | 12 | 0 | 10 | -2
BEAUMONT | CHAMBERS | IH 10 | 50802112 | 2017-07-03 | 1813849.84 | 71284.36 | 1903061.95 | 17927.75 | 90 | 58 | 172 | 24
BEAUMONT | CHAMBERS | FM 3180 | 327101014 | 2017-05-11 | 783181.36 | 54344 | 767324.4 | -70200.96 | 69 | 0 | 60 | -9
BEAUMONT | JASPER | BU 96-E | 6510017 | 2017-07-25 | 107712.98 | 0 | 107619.74 | -93.24 | 13 | 0 | 8 | -5
BEAUMONT | JASPER | US 190 | 21308089 | 2017-07-03 | 4313473.26 | 301584.8 | 4778310.32 | 163252.26 | 235 | 20 | 250 | -5
BEAUMONT | JASPER | FM 1004 | 94703029 | 2017-06-28 | 1120934.72 | 14407.73 | 1106845.56 | -28496.89 | 75 | 3 | 74 | -4
BEAUMONT | JASPER | FM 1007 | 127601020 | 2017-05-04 | 1655300.24 | 74836.34 | 1757443.74 | 27307.16 | 146 | 3 | 126 | -23
BEAUMONT | JEFFERSON | SH 87 | 30603121 | 2017-03-23 | 3158875.97 | 370461.45 | 3172799.5 | -356537.92 | 70 | 29 | 79 | -20
BEAUMONT | JEFFERSON | IH 10 | 73902155 | 2017-08-11 | 29990329.95 | 1677235.92 | 31289782.46 | -377783.41 | 484 | 0 | 412 | -72
BEAUMONT | JEFFERSON | CR | 92038217 | 2017-07-24 | 2984343.4 | 131628.26 | 3161299.39 | 45327.73 | 180 | 58 | 248 | 10
BEAUMONT | JEFFERSON | VA | 92038250 | 2017-04-03 | 4297854.65 | 349380.87 | 4719136.62 | 71901.1 | 201 | 0 | 255 | 54
BEAUMONT | JEFFERSON | FM 365 | 93202054 | 2017-04-24 | 1196548.36 | 294686.18 | 1409142.48 | -82092.06 | 68 | 55 | 142 | 19
BEAUMONT | JEFFERSON | FM 1406 | 132401020 | 2017-05-10 | 994488.34 | 197639.59 | 1158044.08 | -34083.85 | 63 | 31 | 159 | 65
BEAUMONT | LIBERTY | US 90 | 2803102 | 2017-03-14 | 235193.5 | 31058.37 | 267152.03 | 900.16 | 63 | 15 | 78 | 0
BEAUMONT | LIBERTY | US 90 | 2804073 | 2017-03-14 | 969508.6 | 7835.52 | 1016320.54 | 38976.42 | 30 | 0 | 29 | -1
BEAUMONT | LIBERTY | SH 146 | 38803078 | 2017-05-02 | 2077818.82 | -140873.25 | 1893497.65 | -43447.92 | 56 | 0 | 48 | -8
BEAUMONT | LIBERTY | FM 770 | 109602050 | 2017-05-03 | 1023264.24 | 7340 | 1000094.32 | -30509.92 | 75 | 0 | 61 | -14
BEAUMONT | LIBERTY | FM 1413 | 142101024 | 2017-05-23 | 2173548.35 | 367080.87 | 2397913.48 | -142715.74 | 120 | 28 | 173 | 25
BEAUMONT | NEWTON | SH 63 | 21403031 | 2017-06-05 | 2980474.58 | 59042.22 | 3001404.09 | -38112.71 | 73 | 12 | 85 | 0
BEAUMONT | NEWTON | FM 2460 | 194901016 | 2017-06-28 | 1301346.31 | 41876.84 | 1270743.26 | -72479.89 | 159 | 4 | 134 | -29
BEAUMONT | ORANGE | FM 1130 | 128401070 | 2017-04-11 | 2917601.83 | 25267.34 | 3108424.34 | 165555.17 | 90 | 0 | 115 | 25
BEAUMONT | TYLER | US 69 | 20007052 | 2017-03-29 | 188509.25 | -2919 | 189794.25 | 4204 | 41 | 0 | 30 | -11
BEAUMONT | TYLER | FM 92 | 70301059 | 2017-07-07 | 462723.66 | 60989.5 | 527503.13 | 3789.97 | 83 | 40 | 126 | 3
BROWNWOOD | BROWN | CR | 92306056 | 2017-08-16 | 1019914.95 | 0 | 1017266.25 | -2648.7 | 143 | 0 | 147 | 4
BROWNWOOD | BROWN | CR | 92306071 | 2017-07-27 | 1281509.97 | 49690.66 | 1354065.94 | 22865.31 | 183 | 17 | 190 | -10
BROWNWOOD | EASTLAND | IH 20 | 704113 | 2017-03-23 | 278879.6 | 24612.4 | 296278 | -7214 | 50 | 0 | 45 | -5
BROWNWOOD | EASTLAND | FM 8 | 55001026 | 2017-03-23 | 1189721.3 | 98600.14 | 1300886.32 | 12564.88 | 80 | 52 | 109 | -23
BROWNWOOD | EASTLAND | FM 2461 | 71405020 | 2017-08-18 | 2442864.61 | 32632.85 | 2598234.92 | 122737.46 | 238 | 18 | 304 | 48
BROWNWOOD | SAN SABA | CR | 92325020 | 2017-08-18 | 968110.8 | 57980.3 | 1048730.4 | 22639.3 | 102 | 10 | 155 | 43
BRYAN | BRAZOS | BS 6-R | 4909068 | 2017-05-24 | 8448979.14 | -746600.79 | 7467547.49 | -234830.86 | 51 | 0 | 60 | 9
BRYAN | FREESTONE |  | 16603031 | 2017-04-18 | 9728740 | -248404.85 | 9090977.95 | -389357.2 | 52 | 3 | 71 | 16
BRYAN | FREESTONE | CR | 91720038 | 2017-03-13 | 490735.18 | 1000 | 483015.75 | -8719.43 | 70 | 0 | 69 | -1
BRYAN | GRIMES | CR | 91717058 | 2017-08-08 | 417154.55 | 0 | 412191.68 | -4962.87 | 80 | 0 | 78 | -2
BRYAN | GRIMES | CR | 91717062 | 2017-07-28 | 553516.53 | 2309.36 | 557351.73 | 1525.84 | 111 | 0 | 109 | -2
BRYAN | LEON | CR | 91716034 | 2017-07-31 | 357813.6 | 11710.89 | 345121.21 | -24403.28 | 78 | 0 | 74 | -4
BRYAN | MADISON | IH 45 | 67505082 | 2017-05-08 | 3642170.65 | -30601.74 | 3642800.85 | 31231.94 | 126 | 0 | 124 | -2
BRYAN | WALKER | FM 1791 | 170601025 | 2017-05-08 | 3187515.87 | -176061.31 | 2978805.8 | -32648.76 | 328 | 0 | 232 | -96
CHILDRESS | CHILDRESS | US 287 | 4301078 | 2017-06-23 | 9914945.7 | 0 | 9862477.1 | -52468.6 | 218 | 0 | 218 | 0
CHILDRESS | CHILDRESS | VA | 92500065 | 2017-07-21 | 799497.5 | 123214.5 | 894303.76 | -28408.24 | 60 | 0 | 38 | -22
CHILDRESS | COLLINGSWORTH | US 83 | 3102028 | 2017-06-23 | 355317.13 | -5406.75 | 371600.78 | 21690.4 | 23 | 0 | 13 | -10
CHILDRESS | COLLINGSWORTH | FM 1547 | 79707030 | 2017-06-23 | 1184684 | 0 | 1271053.5 | 86369.5 | 85 | 0 | 96 | 11
CHILDRESS | DONLEY | US 287 | 4207068 | 2017-07-21 | 3887167.58 | 0 | 3724238.38 | -162929.2 | 72 | 0 | 44 | -28
CHILDRESS | WHEELER | FM 48 | 48901020 | 2017-08-16 | 5491233.54 | 448311.06 | 5937352.88 | -2191.72 | 108 | 33 | 157 | 16
CORPUS CHRISTI | BEE | FM 2441 | 73805013 | 2017-08-18 | 4303827.65 | 469090.22 | 4873213.18 | 100295.31 | 153 | 33 | 182 | -4
CORPUS CHRISTI | GOLIAD | SH 239 | 51602025 | 2017-07-10 | 5936471.36 | 75295.75 | 5868734.13 | -143032.98 | 135 | 21 | 156 | 0
CORPUS CHRISTI | JIM WELLS | FM 70 | 108801022 | 2017-08-18 | 4764522.78 | 125098.25 | 4825174.51 | -64446.52 | 170 | 37 | 207 | 0
CORPUS CHRISTI | KARNES | SH 72 | 27007029 | 2017-05-10 | 16740118.87 | 389358.58 | 17332793.49 | 203316.04 | 228 | 13 | 241 | 0
CORPUS CHRISTI | KLEBERG | FM 1717 | 184501022 | 2017-03-21 | 1459783.35 | 75752.41 | 1509341.13 | -26194.63 | 82 | 9 | 82 | -9
CORPUS CHRISTI | LIVE OAK | IH 37 | 7307060 | 2017-07-27 | 6295218.9 | 86906.13 | 7625495.03 | 1243370 | 136 | 27 | 163 | 0
CORPUS CHRISTI | LIVE OAK | IH 37 | 7402070 | 2017-07-17 | 7901610.43 | 427990.27 | 8696744.1 | 367143.4 | 170 | 126 | 329 | 33
CORPUS CHRISTI | NUECES | SH 44 | 10215002 | 2017-03-23 | 1821533.8 | 14000 | 1871456.34 | 35922.54 | 85 | 0 | 60 | -25
CORPUS CHRISTI | NUECES | VA | 91600079 | 2017-04-19 | 1792916.93 | 24694.59 | 1910652.72 | 93041.2 | 120 | 10 | 130 | 0
CORPUS CHRISTI | REFUGIO | US 183 | 15505039 | 2017-07-17 | 6324506.65 | 50335.74 | 6354826.28 | -20016.11 | 153 | 0 | 128 | -25
CORPUS CHRISTI | REFUGIO | SH 239 | 35001016 | 2017-03-29 | 179857.83 | 0 | 179857.84 | 0.01 | 25 | 0 | 16 | -9
CORPUS CHRISTI | SAN PATRICIO | US 181 | 10103087 | 2017-03-29 | 1972141.73 | 0 | 2076819.1 | 104677.37 | 68 | 0 | 40 | -28
CORPUS CHRISTI | SAN PATRICIO | US 181 | 10105035 | 2017-04-26 | 5293778.15 | 141287.79 | 5456264.61 | 21198.67 | 119 | 9 | 115 | -13
CORPUS CHRISTI | SAN PATRICIO | FM 1069 | 154903017 | 2017-07-24 | 5913903.69 | 394008.51 | 6472437.84 | 164525.64 | 187 | 29 | 210 | -6
DALLAS | COLLIN | US 75 | 4706157 | 2017-03-23 | 1527421.35 | 18560.5 | 1488299.15 | -57682.7 | 169 | 0 | 162 | -7
DALLAS | COLLIN | US 380 | 13502044 | 2017-06-28 | 17277016.92 | 158717.35 | 17378828.1 | -56906.17 | 380 | 80 | 460 | 0
DALLAS | COLLIN | US 380 | 13505025 | 2017-05-19 | 18186687.1 | 721408.56 | 19155692.12 | 247596.46 | 551 | 266 | 817 | 0
DALLAS | COLLIN | SH 78 | 28101030 | 2017-06-20 | 24832811.16 | 2491260.33 | 26791783.92 | -532287.57 | 630 | 227 | 857 | 0
DALLAS | COLLIN | FM 6 | 61901023 | 2017-04-14 | 3493547.4 | 37479.22 | 3466707.32 | -64319.3 | 292 | 0 | 246 | -46
DALLAS | COLLIN | FM 455 | 81604054 | 2017-06-28 | 3866001.55 | 8092.08 | 3564503.35 | -309590.28 | 188 | 0 | 179 | -9
DALLAS | COLLIN | FM 1378 | 139201035 | 2017-06-20 | 1788995.73 | 47071.71 | 1900274.71 | 64207.27 | 300 | 10 | 310 | 0
DALLAS | DALLAS | US 75 | 4707206 | 2017-04-26 | 991603.7 | 115303.61 | 1088525.51 | -18381.8 | 126 | 56 | 182 | 0
DALLAS | DALLAS | US 75 | 4707231 | 2017-08-01 | 754480.04 | 6019.78 | 789670.57 | 29170.75 | 52 | 1 | 33 | -20
DALLAS | DALLAS | SH 289 | 9106058 | 2017-03-27 | 2360163.24 | 73552.85 | 2267216.13 | -166499.96 | 105 | 46 | 146 | -5
DALLAS | DALLAS | SS 482 | 9403118 | 2017-08-21 | 1154670.5 | 120373.05 | 1302052.16 | 27008.61 | 72 | 0 | 71 | -1
DALLAS | DALLAS | VA | 91800185 | 2017-03-31 | 1297700 | 0 | 1246584.92 | -51115.08 | 346 | 0 | 343 | -3
DALLAS | DALLAS | CS | 91845791 | 2017-08-28 | 1305085 | 0 | 1245327.14 | -59757.86 | 247 | 0 | 220 | -27
DALLAS | DALLAS | CS | 91847101 | 2017-05-19 | 802955.85 | 331.71 | 780724.01 | -22563.55 | 140 | 0 | 158 | 18
DALLAS | DALLAS | IH 30 | 106804147 | 2017-08-29 | 63081770.23 | 4174895.53 | 66561742.72 | -694923.04 | 728 | 232 | 960 | 0
DALLAS | DALLAS | IH 635 | 237402124 | 2017-03-08 | 7718650.04 | 2101441.03 | 9975071.33 | 154980.26 | 459 | 255 | 714 | 0
DALLAS | DALLAS | IH 635 | 237402136 | 2017-03-27 | 6594770.84 | 12764.85 | 6673100.38 | 65564.69 | 240 | 0 | 237 | -3
DALLAS | DENTON | US 377 | 8104040 | 2017-06-20 | 323544 | 8957.54 | 318325.88 | -14175.66 | 95 | 0 | 95 | 0
DALLAS | DENTON | FM 51 | 31202016 | 2017-06-20 | 2575804.4 | 35870 | 2594461.31 | -17213.09 | 316 | 0 | 315 | -1
DALLAS | DENTON | SH 114 | 35302075 | 2017-05-10 | 693594 | -46733.83 | 499700.17 | -147160 | 87 | 0 | 11 | -76
DALLAS | DENTON | FM 455 | 81602053 | 2017-04-04 | 3335495.2 | 47063.26 | 3357283.89 | -25274.57 | 193 | 35 | 254 | 26
DALLAS | DENTON | PW | 91846269 | 2017-07-25 | 1587178.55 | 407433.32 | 2029186.66 | 34574.79 | 91 | 0 | 63 | -28
DALLAS | DENTON | FM 720 | 156701029 | 2017-05-23 | 54321262.7 | 5341376.36 | 58934113.62 | -728525.44 | 577 | 197 | 774 | 0
DALLAS | DENTON | FM 2181 | 205402016 | 2017-05-22 | 23602199.11 | 684987.56 | 23768981.58 | -518205.09 | 416 | 52 | 639 | 171
DALLAS | DENTON | LP 288 | 225002016 | 2017-04-03 | 3653118 | 44040.67 | 3689398.32 | -7760.35 | 210 | 48 | 266 | 8
DALLAS | ELLIS | CR | 91822086 | 2017-07-10 | 934144.91 | 7860.71 | 875240.76 | -66764.86 | 129 | 51 | 201 | 21
DALLAS | ELLIS | FM 55 | 145101023 | 2017-05-25 | 4975101.65 | -104505.99 | 4781801 | -88794.66 | 215 | 64 | 279 | 0
DALLAS | KAUFMAN | US 175 | 19703071 | 2017-05-19 | 1913970.3 | 847.51 | 1833355.59 | -81462.22 | 122 | 0 | 43 | -79
DALLAS | KAUFMAN | FM 741 | 109201017 | 2017-06-20 | 4550316.17 | 213918.93 | 4632051.83 | -132183.27 | 187 | 0 | 277 | 90
DALLAS | KAUFMAN | FM 1565 | 149402008 | 2017-04-14 | 1652146.22 | 69194.09 | 1601099.05 | -120241.26 | 159 | 6 | 195 | 30
DALLAS | KAUFMAN | FM 2728 | 251201011 | 2017-08-04 | 9419882.39 | 667204 | 10087586.98 | 500.59 | 246 | 57 | 303 | 0
DALLAS | KAUFMAN | FM 148 | 314601006 | 2017-06-20 | 3178556.05 | 102966.86 | 3063411.57 | -218111.34 | 192 | 13 | 215 | 10
DALLAS | NAVARRO | SH 22 | 12104026 | 2017-03-14 | 6426065.65 | 243027.27 | 6928967.02 | 259874.1 | 115 | 0 | 114 | -1
DALLAS | ROCKWALL | FM 551 | 101601027 | 2017-06-27 | 5349450.72 | -71341.11 | 5237942.04 | -40167.57 | 126 | 94 | 220 | 0
EL PASO | BREWSTER | VA | 92435022 | 2017-07-17 | 202104.08 | 0 | 194703.82 | -7400.26 | 60 | 0 | 34 | -26
EL PASO | BREWSTER | FM 1703 | 269401008 | 2017-05-31 | 1323354.8 | -41847.55 | 1273641.55 | -7865.7 | 80 | 0 | 80 | 0
EL PASO | CULBERSON | IH 10 | 302039 | 2017-08-31 | 12874699.15 | 4764407.99 | 20104811.43 | 2465704.29 | 160 | 103 | 237 | -26
EL PASO | CULBERSON | US 62 | 23301045 | 2017-06-23 | 6441134.87 | 1471791.12 | 9012190.75 | 1099264.76 | 60 | 118 | 152 | -26
EL PASO | EL PASO | SH 20 | 101058 | 2017-03-15 | 1133585.95 | -1149.5 | 1132431.2 | -5.25 | 60 | 40 | 140 | 40
EL PASO | EL PASO | BU 54-A | 16702058 | 2017-06-27 | 570813.35 | -21464.38 | 566487.67 | 17138.7 | 20 | 0 | 20 | 0
EL PASO | EL PASO | IH 10 | 212102151 | 2017-07-17 | 7584729.54 | 1318480.93 | 9063168.46 | 159957.99 | 161 | 100 | 261 | 0
EL PASO | EL PASO | IH 10 | 212104092 | 2017-03-27 | 24887784.28 | 390535.05 | 25214538.23 | -63781.1 | 360 | 60 | 420 | 0
EL PASO | EL PASO | IH 10 | 212104093 | 2017-05-31 | 31489367.95 | 1229804.24 | 33286180.84 | 567008.65 | 519 | 0 | 436 | -83
EL PASO | EL PASO | FM 2529 | 232601023 | 2017-03-15 | 1526309.97 | 254011.43 | 1824260.39 | 43938.99 | 60 | 0 | 60 | 0
EL PASO | EL PASO | LP 375 | 255201033 | 2017-07-17 | 61272749.63 | 8713885.63 | 70291092.15 | 304456.89 | 696 | 25 | 705 | -16
EL PASO | EL PASO | SL 375 | 255203057 | 2017-06-15 | 323840.1 | 10866.22 | 393543.08 | 58836.76 | 100 | 0 | 81 | -19
EL PASO | EL PASO | MH | 805624001 | 2017-05-30 | 7505306 | 3585049.21 | 11082597.66 | -7757.55 | 290 | 151 | 438 | -3
EL PASO | JEFF DAVIS | IH 10 | 304051 | 2017-08-31 | 563630 | 3975.04 | 584914.84 | 17309.8 | 80 | 0 | 75 | -5
FORT WORTH | ERATH | US 67 | 7908003 | 2017-07-19 | 12608803.66 | 27530.97 | 13097988.33 | 461653.7 | 380 | 108 | 466 | -22
FORT WORTH | ERATH | SH 108 | 34304042 | 2017-08-15 | 75144 | -8333.52 | 59205.56 | -7604.92 | 16 | 0 | 17 | 1
FORT WORTH | HOOD | US 377 | 8003054 | 2017-08-23 | 4079052.2 | 40821.55 | 4187715.48 | 67841.73 | 39 | 12 | 49 | -2
FORT WORTH | HOOD | FM 2580 | 160103014 | 2017-08-30 | 1468973.71 | -17817.65 | 1458705.18 | 7549.12 | 147 | 0 | 62 | -85
FORT WORTH | JOHNSON | IH 35W | 1404080 | 2017-05-02 | 243825 | 0 | 252921 | 9096 | 30 | 0 | 17 | -13
FORT WORTH | JOHNSON | IH 35W | 1422031 | 2017-03-13 | 1323249.06 | 119375.51 | 1623822.73 | 181198.16 | 51 | 53 | 187 | 83
FORT WORTH | JOHNSON | BU 67-M | 42203073 | 2017-03-13 | 1839574.05 | -47174.3 | 1686483.71 | -105916.04 | 107 | 0 | 29 | -78
FORT WORTH | JOHNSON | FM 917 | 118103030 | 2017-04-18 | 919633.64 | -176454.75 | 718872.86 | -24306.03 | 43 | 0 | 38 | -5
FORT WORTH | JOHNSON | FM 917 | 118104044 | 2017-07-27 | 470738.12 | -72763.02 | 438807.21 | 40832.11 | 90 | 0 | 15 | -75
FORT WORTH | PALO PINTO | US 281 | 25002039 | 2017-06-21 | 5829658.6 | 9064.24 | 5919397.33 | 80674.49 | 273 | 0 | 256 | -17
FORT WORTH | PARKER | IH 20 | 31401077 | 2017-08-09 | 1309705.35 | 99664.08 | 1327220.28 | -82149.15 | 148 | 0 | 259 | 111
FORT WORTH | PARKER | IH 20 | 31401081 | 2017-03-22 | 8460305.7 | 133740.99 | 8555370.98 | -38675.71 | 88 | 0 | 145 | 57
FORT WORTH | PARKER | CR | 90238076 | 2017-07-10 | 1379496.35 | 0 | 1428396.43 | 48900.08 | 191 | 14 | 205 | 0
FORT WORTH | PARKER | IH 30 | 106805009 | 2017-03-23 | 14593117.4 | 439540.36 | 15155018.4 | 122360.64 | 225 | 257 | 482 | 0
FORT WORTH | PARKER | FM 730 | 160101029 | 2017-05-18 | 4868689.67 | 384310.65 | 5318091.82 | 65091.5 | 108 | 20 | 118 | -10
FORT WORTH | PARKER | FM 3028 | 293002011 | 2017-08-09 | 1561559.71 | 2000 | 1586300.75 | 22741.04 | 130 | 32 | 207 | 45
FORT WORTH | TARRANT | IH 820 | 813229 | 2017-08-15 | 675364.7 | 841818.72 | 1627227.58 | 110044.16 | 76 | 18 | 94 | 0
FORT WORTH | TARRANT | BU 287P | 1310070 | 2017-04-12 | 823422.85 | 261544.79 | 1158046.73 | 73079.09 | 69 | 115 | 184 | 0
FORT WORTH | TARRANT | SH 26 | 36406011 | 2017-05-23 | 1549096.84 | -124241.87 | 1404775.19 | -20079.78 | 179 | 349 | 528 | 0
FORT WORTH | TARRANT | SH 121 | 50402022 | 2017-05-26 | 116646468.88 | -332253.94 | 113977752.8 | -2336462.14 | 896 | 187 | 1561 | 478
FORT WORTH | TARRANT | VA | 90200131 | 2017-03-22 | 1587885 | -42754.27 | 1889430.67 | 344299.94 | 365 | 140 | 505 | 0
FORT WORTH | TARRANT | VA | 90200139 | 2017-06-06 | 317349.1 | 9847.45 | 326940.6 | -255.95 | 107 | 0 | 94 | -13
FORT WORTH | TARRANT | VA | 90200151 | 2017-06-26 | 1707025 | 55861.67 | 1849787.14 | 86900.47 | 365 | 0 | 359 | -6
FORT WORTH | TARRANT | VA | 90290015 | 2017-05-04 | 507882.63 | 10272.37 | 529260.38 | 11105.38 | 62 | 5 | 65 | -2
FORT WORTH | TARRANT | RM 2871 | 285501021 | 2017-05-10 | 2072283.33 | 378188.68 | 2501318.02 | 50846.01 | 167 | 17 | 184 | 0
FORT WORTH | WISE | VA | 90220109 | 2017-05-12 | 5019768.07 | 369523.35 | 5316847.77 | -72443.65 | 196 | 59 | 255 | 0
FORT WORTH | WISE | FM 2264 | 131003025 | 2017-04-10 | 3983917.91 | 348263.8 | 4451255.98 | 119074.27 | 200 | 86 | 286 | 0
FORT WORTH | WISE | FM 730 | 229201032 | 2017-06-23 | 288012.4 | 0 | 298483.51 | 10471.11 | 43 | 0 | 43 | 0
HOUSTON | BRAZORIA | SH 288 | 11108120 | 2017-06-15 | 651061.55 | 0 | 679189.3 | 28127.75 | 90 | 0 | 75 | -15
HOUSTON | BRAZORIA | SH 35 | 17802055 | 2017-05-30 | 21717321.24 | 2777776.3 | 24330867.56 | -164229.98 | 789 | 437 | 1216 | -10
HOUSTON | BRAZORIA | SH 35 | 17802086 | 2017-04-03 | 573748.2 | 62062.37 | 600423.22 | -35387.35 | 46 | 0 | 38 | -8
HOUSTON | BRAZORIA | SH 35 | 17803152 | 2017-05-22 | 2129904.8 | 0 | 2114321.48 | -15583.32 | 80 | 0 | 74 | -6
HOUSTON | BRAZORIA | FM 521 | 84702015 | 2017-04-05 | 1597257.65 | 6261 | 1708795.15 | 105276.5 | 45 | 0 | 41 | -4
HOUSTON | BRAZORIA | CS | 91231203 | 2017-06-19 | 2748072 | 16684.93 | 2740074.3 | -24682.63 | 270 | 0 | 305 | 35
HOUSTON | BRAZORIA | CR | 91231222 | 2017-06-07 | 435258.4 | 5398.91 | 447676.92 | 7019.61 | 54 | 0 | 58 | 4
HOUSTON | BRAZORIA | CS | 91231237 | 2017-06-08 | 766156.52 | 16306.07 | 750064.91 | -32397.68 | 113 | 42 | 135 | -20
HOUSTON | BRAZORIA | CR | 91231265 | 2017-03-31 | 448817.82 | 32174.14 | 450411.85 | -30580.11 | 70 | 0 | 98 | 28
HOUSTON | BRAZORIA | CS | 91231270 | 2017-06-13 | 4837804.77 | 471140.09 | 5312902.07 | 3957.21 | 300 | 56 | 344 | -12
HOUSTON | BRAZORIA | CR | 91231282 | 2017-05-30 | 1423278.9 | 121590.84 | 1558531.54 | 13661.8 | 84 | 12 | 93 | -3
HOUSTON | BRAZORIA | CR | 91231294 | 2017-08-07 | 12154201.39 | 519364.19 | 12818674.88 | 145109.3 | 357 | 5 | 333 | -29
HOUSTON | BRAZORIA | FM 523 | 100301091 | 2017-04-25 | 7475838.93 | 336477.74 | 8083615.54 | 271298.87 | 112 | 12 | 124 | 0
HOUSTON | BRAZORIA | SH 332 | 152401078 | 2017-04-20 | 3739396.97 | 0 | 3911873.47 | 172476.5 | 140 | 0 | 129 | -11
HOUSTON | FORT BEND | US 90A | 2708172 | 2017-08-21 | 2933336.32 | -62915.86 | 3169257.02 | 298836.56 | 120 | 0 | 109 | -11
HOUSTON | FORT BEND | US 59 | 2712134 | 2017-04-07 | 696610.9 | 110909.9 | 774664.99 | -32855.81 | 375 | 90 | 457 | -8
HOUSTON | FORT BEND | SP 10 | 18705050 | 2017-08-22 | 19773719.85 | 2787893.33 | 22820444.28 | 258831.1 | 386 | 74 | 446 | -14
HOUSTON | FORT BEND | IH 10 | 27105037 | 2017-08-22 | 10742564.74 | 1114328.86 | 11982555.09 | 125661.49 | 178 | 101 | 339 | 60
HOUSTON | GALVESTON | SH 6 | 19204104 | 2017-03-07 | 3198543.72 | 318640.42 | 3722730.3 | 205546.16 | 45 | 3 | 44 | -4
HOUSTON | GALVESTON | SH 124 | 36702081 | 2017-04-26 | 1137775 | 0 | 1113593.45 | -24181.55 | 45 | 0 | 45 | 0
HOUSTON | GALVESTON | SH 146 | 38906103 | 2017-08-10 | 369995.94 | 821.99 | 366788.7 | -4029.23 | 63 | 0 | 62 | -1
HOUSTON | GALVESTON | IH 45 | 50001143 | 2017-08-24 | 259722.3 | 0 | 267730.71 | 8008.41 | 48 | 0 | 40 | -8
HOUSTON | GALVESTON | IH 45 | 50004126 | 2017-05-26 | 4689018.6 | 1233497.15 | 5805960.95 | -116554.8 | 60 | 19 | 87 | 8
HOUSTON | GALVESTON | IH 45 | 50004129 | 2017-04-28 | 4920504.92 | 1316731.02 | 6350095.82 | 112859.88 | 60 | 15 | 85 | 10
HOUSTON | GALVESTON | VA | 91273203 | 2017-07-17 | 1529400 | 621381.33 | 2150781.33 | 0 | 180 | 155 | 330 | -5
HOUSTON | GALVESTON | FM 517 | 97802076 | 2017-08-11 | 617038.32 | -51531.66 | 573037.66 | 7531 | 60 | 0 | 33 | -27
HOUSTON | HARRIS | US 90A | 2709100 | 2017-06-14 | 1190807.2 | 123948.97 | 1301878.12 | -12878.05 | 225 | 0 | 206 | -19
HOUSTON | HARRIS | US 90 | 2802089 | 2017-06-15 | 111111.11 | 0 | 116943.56 | 5832.45 | 28 | 0 | 22 | -6
HOUSTON | HARRIS | US 290 | 5008091 | 2017-08-09 | 446813.33 | 122614.29 | 581206.3 | 11778.68 | 108 | 0 | 95 | -13
HOUSTON | HARRIS | IH 45 | 11005119 | 2017-08-03 | 2603483.83 | 559789.93 | 3511862.03 | 348588.27 | 89 | 56 | 129 | -16
HOUSTON | HARRIS | IH 10 | 27107292 | 2017-08-14 | 3594471.43 | 545491.63 | 4096926.05 | -43037.01 | 156 | 0 | 156 | 0
HOUSTON | HARRIS | IH 10 | 27107304 | 2017-07-03 | 2096611.52 | 265380.34 | 2215397.93 | -146593.93 | 186 | 0 | 183 | -3
HOUSTON | HARRIS | IH 610 | 27115086 | 2017-03-14 | 4114146.51 | -632525.61 | 3635071.09 | 153450.19 | 210 | 7 | 215 | -2
HOUSTON | HARRIS | IH 45 | 50003586 | 2017-08-24 | 3918000 | 1767051.66 | 5884410.41 | 199358.75 | 336 | 0 | 243 | -93
HOUSTON | HARRIS | IH 10 | 50801350 | 2017-06-14 | 428325.12 | 82967.59 | 492962.51 | -18330.2 | 108 | 0 | 70 | -38
HOUSTON | HARRIS | VA | 91200385 | 2017-06-14 | 911168.15 | 85757.9 | 1198840.83 | 201914.78 | 270 | 0 | 182 | -88
HOUSTON | HARRIS | VA | 91200417 | 2017-04-07 | 859065.05 | 213436.97 | 1106078.81 | 33576.79 | 220 | 24 | 213 | -31
HOUSTON | HARRIS | VA | 91200440 | 2017-05-25 | 772662.59 | -21420 | 873562.59 | 122320 | 135 | 0 | 129 | -6
HOUSTON | HARRIS | VA | 91200441 | 2017-04-07 | 1210347.9 | 0 | 1196046.65 | -14301.25 | 500 | 0 | 141 | -359
HOUSTON | HARRIS | VA | 91200484 | 2017-06-14 | 557849.99 | 0 | 615497.43 | 57647.44 | 94 | 0 | 103 | 9
HOUSTON | HARRIS | CR | 91271797 | 2017-06-07 | 1424412.7 | -30696.22 | 1386274.65 | -7441.83 | 89 | 42 | 170 | 39
HOUSTON | HARRIS | CR | 91271894 | 2017-05-23 | 10341416.18 | 933530.63 | 11178954.8 | -95992.01 | 250 | 66 | 316 | 0
HOUSTON | HARRIS | CS | 91272063 | 2017-05-10 | 1096120.32 | 82376.25 | 1171585.71 | -6910.86 | 150 | 35 | 185 | 0
HOUSTON | HARRIS | CS | 91272184 | 2017-08-22 | 3942248.8 | 467464.19 | 4392489.08 | -17223.91 | 312 | 30 | 309 | -33
HOUSTON | HARRIS | CS | 91272230 | 2017-05-26 | 2825133.25 | 332030.36 | 3327317.13 | 170153.52 | 401 | 0 | 242 | -159
HOUSTON | HARRIS | VA | 91272287 | 2017-03-28 | 2475888.05 | 190510.64 | 2508038.35 | -158360.34 | 225 | 85 | 310 | 0
HOUSTON | HARRIS | VA | 91272294 | 2017-08-11 | 1678207.72 | 0 | 1781088.57 | 102880.85 | 190 | 0 | 185 | -5
HOUSTON | HARRIS | FM 529 | 100601059 | 2017-03-14 | 7690213.53 | 696173.73 | 8449345.44 | 62958.18 | 322 | 28 | 350 | 0
HOUSTON | HARRIS | FM 1960 | 168503088 | 2017-07-31 | 6636000.51 | 74383.29 | 6964968.52 | 254584.72 | 78 | 0 | 75 | -3
HOUSTON | HARRIS | FM 1960 | 168503096 | 2017-05-17 | 191207.77 | 76766.5 | 231759.66 | -36214.61 | 42 | 0 | 30 | -12
HOUSTON | HARRIS | FM 1876 | 174301009 | 2017-03-10 | 1214435.35 | -41518.01 | 1172387.24 | -530.1 | 28 | 0 | 28 | 0
HOUSTON | HARRIS | FM 1942 | 181201021 | 2017-08-03 | 948590 | 37789.68 | 1027450.93 | 41071.25 | 45 | 30 | 42 | -33
HOUSTON | HARRIS | FM 2920 | 294101021 | 2017-07-24 | 3074858.52 | 51500 | 3251142.68 | 124784.16 | 167 | 0 | 166 | -1
HOUSTON | HARRIS | SL 8 | 325601102 | 2017-04-18 | 611048.35 | 27845.93 | 661422.74 | 22528.46 | 134 | 0 | 102 | -32
HOUSTON | HARRIS | SL 8 | 325602091 | 2017-04-25 | 596804.7 | 5629.16 | 602523.32 | 89.46 | 15 | 0 | 3 | -12
HOUSTON | HARRIS | BW 8 | 325604061 | 2017-07-11 | 10329185.49 | 321875.84 | 10609141.57 | -41919.76 | 282 | 5 | 306 | 19
HOUSTON | MONTGOMERY | SH 105 | 33802042 | 2017-07-27 | 3979077.24 | -246941.88 | 3801530.44 | 69395.08 | 107 | 0 | 81 | -26
HOUSTON | MONTGOMERY | IH 45 | 67508108 | 2017-08-25 | 1009482.55 | -30112.68 | 1055335.87 | 75966 | 75 | 0 | 72 | -3
HOUSTON | MONTGOMERY | FM 149 | 72002083 | 2017-05-25 | 3762255.52 | 482986.66 | 4258454.56 | 13212.38 | 220 | 0 | 210 | -10
HOUSTON | MONTGOMERY | CR | 91237140 | 2017-03-21 | 2496548.44 | 134456.39 | 2585631.62 | -45373.21 | 78 | 59 | 179 | 42
HOUSTON | MONTGOMERY | FM 1097 | 125901041 | 2017-05-17 | 238826.4 | 0 | 223492.8 | -15333.6 | 22 | 0 | 22 | 0
HOUSTON | MONTGOMERY | FM 1375 | 140203011 | 2017-04-20 | 1297509.45 | 81574.73 | 1391580.4 | 12496.22 | 55 | 0 | 48 | -7
HOUSTON | MONTGOMERY | SH 242 | 353801041 | 2017-08-23 | 3635039.14 | -209037.07 | 3465584.07 | 39582 | 87 | 0 | 65 | -22
HOUSTON | WALLER | IH 10 | 27104091 | 2017-05-09 | 4962242.32 | 211476 | 5424995.28 | 251276.96 | 90 | 27 | 112 | -5
HOUSTON | WALLER | FM 362 | 52302046 | 2017-06-15 | 1069740 | 187500 | 1301540 | 44300 | 180 | 0 | 57 | -123
LAREDO | DIMMIT | FM 1917 | 3715009 | 2017-06-14 | 527358.79 | -41216.39 | 485904 | -238.4 | 24 | 0 | 21 | -3
LAREDO | DIMMIT | FM 1019 | 127001026 | 2017-04-25 | 3036840.44 | 120119.7 | 3065472.72 | -91487.42 | 119 | 0 | 119 | 0
LAREDO | DUVAL | SH 44 | 23704013 | 2017-08-25 | 4178905.31 | 221103.69 | 4208030.35 | -191978.65 | 180 | 0 | 142 | -38
LAREDO | LA SALLE | IH 35 | 1708079 | 2017-07-17 | 3430660.25 | 305767.42 | 3664910.96 | -71516.71 | 129 | 60 | 274 | 85
LAREDO | LA SALLE | IH 35 | 1801078 | 2017-04-25 | 2087043.78 | 643250.53 | 3204849.81 | 474555.5 | 35 | 0 | 35 | 0
LAREDO | LA SALLE | IH 35 | 1802067 | 2017-08-21 | 5671465.4 | 55222.25 | 5826070.84 | 99383.19 | 70 | 18 | 88 | 0
LAREDO | LA SALLE | SH 97 | 48301046 | 2017-07-11 | 2157787.2 | 2075.19 | 2182724.1 | 22861.71 | 141 | 0 | 134 | -7
LAREDO | VAL VERDE | US 90 | 2301087 | 2017-07-17 | 5319276.01 | 139317.54 | 5507005.28 | 48411.73 | 80 | 17 | 97 | 0
LAREDO | WEBB | CR | 92233113 | 2017-05-16 | 855593.8 | 0 | 837245.8 | -18348 | 129 | 0 | 127 | -2
LAREDO | WEBB | CR | 92233157 | 2017-07-18 | 597832 | 340 | 574350 | -23822 | 68 | 0 | 67 | -1
LAREDO | WEBB | SH 44 | 202201013 | 2017-05-16 | 580285.54 | -60727.88 | 510878.33 | -8679.33 | 94 | 0 | 64 | -30
LUBBOCK | BAILEY | FM 54 | 56302011 | 2017-08-04 | 5673 | 0 | 5673 | 0 | 7 | 0 | 2 | -5
LUBBOCK | COCHRAN | SH 125 | 96702017 | 2017-07-28 | 64990 | 0 | 81104.92 | 16114.92 | 35 | 0 | 31 | -4
LUBBOCK | HOCKLEY | FM 597 | 87407006 | 2017-04-26 | 3845414.81 | 0 | 3604436.47 | -240978.34 | 139 | 0 | 177 | 38
LUBBOCK | LUBBOCK | US 84 | 5207063 | 2017-06-28 | 8608105.16 | -2067.7 | 8357306.97 | -248730.49 | 95 | 0 | 172 | 77
LUBBOCK | LUBBOCK | SL 289 | 78302091 | 2017-08-29 | 74935 | 12020.3 | 77237.73 | -9717.57 | 30 | 5 | 12 | -23
LUBBOCK | LUBBOCK | VA | 90500083 | 2017-08-30 | 2141840 | -30603.9 | 2163577.43 | 52341.33 | 190 | 10 | 207 | 7
LUBBOCK | LUBBOCK | CS | 90506090 | 2017-08-22 | 940883.2 | 0 | 955480.99 | 14597.79 | 82 | 0 | 83 | 1
LUBBOCK | LUBBOCK | FM 400 | 104102039 | 2017-08-04 | 2349749.83 | 33430.29 | 2239781.94 | -143398.18 | 90 | 3 | 132 | 39
LUBBOCK | PARMER | US 70 | 5201040 | 2017-07-26 | 1112445 | 510833.65 | 1792984.88 | 169706.23 | 23 | 10 | 33 | 0
LUBBOCK | PARMER | US 70 | 5201041 | 2017-06-28 | 96999 | 0 | 96999 | 0 | 31 | 0 | 8 | -23
LUBBOCK | PARMER | US 60 | 16802030 | 2017-07-13 | 14851976.58 | 60352.88 | 14163218.57 | -749110.89 | 239 | 0 | 98 | -141
LUFKIN | ANGELINA | BU 59-G | 17602094 | 2017-05-18 | 11387556.46 | 49636.23 | 11315487.15 | -121705.54 | 383 | 25 | 407 | -1
LUFKIN | ANGELINA | US 69 | 20002040 | 2017-06-01 | 359054.46 | 0 | 250354.77 | -108699.69 | 44 | 0 | 40 | -4
LUFKIN | ANGELINA | CR | 91138070 | 2017-07-06 | 460227.88 | 0 | 462129.47 | 1901.59 | 59 | 0 | 58 | -1
LUFKIN | HOUSTON | US 287 | 10904029 | 2017-08-11 | 1611863 | 80850.85 | 1764385.97 | 71672.12 | 145 | 7 | 124 | -28
LUFKIN | HOUSTON | CR | 91128036 | 2017-08-28 | 763544.08 | 147.96 | 746643.69 | -17048.35 | 88 | 5 | 93 | 0
LUFKIN | NACOGDOCHES | BU 59-F | 17508044 | 2017-08-23 | 58317 | 0 | 57347.5 | -969.5 | 15 | 0 | 14 | -1
LUFKIN | NACOGDOCHES | US 59 | 17601109 | 2017-07-27 | 2458818.05 | -31301.73 | 2279314.54 | -148201.78 | 96 | 31 | 154 | 27
LUFKIN | NACOGDOCHES | FM 1638 | 140702022 | 2017-08-22 | 1142152.76 | 0 | 1232893.81 | 90741.05 | 86 | 0 | 84 | -2
LUFKIN | POLK | US 59 | 17605179 | 2017-03-22 | 89789.5 | 1960 | 91455 | -294.5 | 20 | 6 | 23 | -3
LUFKIN | POLK | US 190 | 21304046 | 2017-07-27 | 1486579 | 2487.08 | 1357290.13 | -131775.95 | 124 | 0 | 124 | 0
LUFKIN | POLK | FM 62 | 65401026 | 2017-04-24 | 495378.86 | 0 | 482202.88 | -13175.98 | 65 | 0 | 75 | 10
LUFKIN | POLK | FM 1988 | 187601030 | 2017-08-28 | 3278223.27 | 0 | 3184870.56 | -93352.71 | 188 | 10 | 217 | 19
LUFKIN | SABINE | FM 1 | 6411014 | 2017-06-29 | 3634869.32 | 92393.7 | 3479363.51 | -247899.51 | 104 | 40 | 119 | -25
LUFKIN | SABINE | SH 21 | 11902020 | 2017-06-13 | 684933.22 | 0 | 615965.01 | -68968.21 | 23 | 14 | 56 | 19
LUFKIN | SHELBY | CR | 91139051 | 2017-08-03 | 844617.77 | 474.45 | 832862.56 | -12229.66 | 150 | 0 | 92 | -58
LUFKIN | TRINITY | US 287 | 31901062 | 2017-04-13 | 4457994.94 | -64053.95 | 4474989.45 | 81048.46 | 98 | 59 | 146 | -11
ODESSA | ECTOR | VA | 90600170 | 2017-07-26 | 394378 | 79357.18 | 475448.99 | 1713.81 | 60 | 15 | 69 | -6
ODESSA | ECTOR | VA | 90600172 | 2017-08-18 | 464333 | 0 | 464279 | -54 | 91 | 0 | 24 | -67
ODESSA | MIDLAND | CS | 90632049 | 2017-03-10 | 6205048 | -128138.43 | 6212016.66 | 135107.09 | 160 | 50 | 196 | -14
ODESSA | PECOS | SH 18 | 29206030 | 2017-03-23 | 598976.15 | 0 | 608316.85 | 9340.7 | 60 | 0 | 47 | -13
ODESSA | REEVES | US 285 | 13905042 | 2017-03-23 | 974937.2 | 0 | 976251.7 | 1314.5 | 260 | 0 | 177 | -83
ODESSA | UPTON | SH 349 | 38011023 | 2017-08-23 | 9077499.08 | 204613.05 | 9443312.99 | 161200.86 | 165 | 28 | 193 | 0
ODESSA | WARD | SS 57 | 403048 | 2017-05-19 | 1972473.84 | 133561.11 | 2245190.27 | 139155.32 | 160 | 30 | 192 | 2
ODESSA | WINKLER | SH 302 | 46306027 | 2017-05-09 | 7977007.54 | 0 | 8011164.36 | 34156.82 | 80 | 30 | 103 | -7
PARIS | GRAYSON | US 377 | 8110042 | 2017-08-17 | 8437785.27 | 636840.12 | 8573997.91 | -500627.48 | 70 | 0 | 80 | 10
PARIS | HOPKINS | IH 30 | 909101 | 2017-06-05 | 2403661.81 | 11412.55 | 2404809.05 | -10265.31 | 62 | 0 | 48 | -14
PARIS | HOPKINS | SH 19 | 40002048 | 2017-04-17 | 1267814.14 | 3500 | 1366327.94 | 95013.8 | 48 | 18 | 62 | -4
PARIS | HOPKINS | SH 154 | 40101022 | 2017-05-03 | 6591501.97 | 1137206.26 | 8144084.92 | 415376.69 | 457 | 0 | 451 | -6
PARIS | HUNT | SH 34 | 17306044 | 2017-07-20 | 39179 | 2907 | 42723 | 637 | 14 | 0 | 13 | -1
PARIS | HUNT | FM 36 | 64203022 | 2017-06-29 | 2623426.36 | 312279.06 | 2970035.28 | 34329.86 | 112 | 3 | 120 | 5
PARIS | HUNT | FM 1570 | 69201017 | 2017-04-26 | 2207943.1 | -89104.48 | 2344371.61 | 225532.99 | 58 | 9 | 58 | -9
PARIS | HUNT | FM 118 | 172501011 | 2017-07-20 | 2470540.21 | 17595.28 | 2360260.22 | -127875.27 | 144 | 0 | 156 | 12
PARIS | RAINS | US 69 | 20303044 | 2017-04-18 | 4635055.95 | -27986.52 | 4424468.13 | -182601.3 | 159 | 0 | 183 | 24
PARIS | RED RIVER | US 82 | 4601062 | 2017-03-24 | 795946.99 | -6876.1 | 801638.33 | 12567.44 | 66 | 6 | 98 | 26
PARIS | RED RIVER | SH 37 | 18901007 | 2017-05-16 | 14580056.68 | -129049.12 | 14342080.04 | -108927.52 | 495 | 4 | 501 | 2
PARIS | RED RIVER | FM 3390 | 337101009 | 2017-08-30 | 298222.05 | 15597.4 | 319161.5 | 5342.05 | 50 | 0 | 51 | 1
PHARR | HIDALGO | BU 83-S | 3903102 | 2017-06-23 | 961180.6 | 0 | 929517.6 | -31663 | 260 | 0 | 248 | -12
PHARR | HIDALGO | US 281 | 22001025 | 2017-06-23 | 4739753.21 | 555407.29 | 6347768.54 | 1052608.04 | 398 | 25 | 423 | 0
PHARR | HIDALGO | SH 336 | 62101100 | 2017-03-27 | 1846323.45 | -125355.5 | 1745328.16 | 24360.21 | 160 | 0 | 113 | -47
PHARR | HIDALGO | CS | 92102258 | 2017-06-14 | 2667755.2 | 34757.72 | 2716672.87 | 14159.95 | 240 | 0 | 230 | -10
PHARR | HIDALGO | CS | 92102316 | 2017-04-10 | 2059444.63 | 6423.6 | 2079947.47 | 14079.24 | 175 | 0 | 171 | -4
PHARR | HIDALGO | VA | 92102319 | 2017-03-07 | 1475632.37 | 4730.16 | 1421414.05 | -58948.48 | 200 | 1 | 185 | -16
PHARR | HIDALGO | VA | 92102339 | 2017-08-30 | 1398543.35 | 39474.12 | 1418711.79 | -19305.68 | 199 | 0 | 199 | 0
PHARR | HIDALGO | FM 2220 | 209401059 | 2017-08-21 | 1601730.75 | 0 | 1472278.52 | -129452.23 | 120 | 0 | 42 | -78
PHARR | WILLACY | SH 186 | 43304029 | 2017-08-18 | 266493.54 | 2192.8 | 272874.82 | 4188.48 | 103 | 0 | 10 | -93
SAN ANGELO | GLASSCOCK | US 87 | 6902028 | 2017-03-30 | 15257441.66 | 152539.08 | 15984044 | 574063.26 | 111 | 26 | 164 | 27
SAN ANGELO | GLASSCOCK | SH 158 | 46304025 | 2017-08-28 | 8716678.75 | 61064.01 | 9669872.99 | 892130.23 | 71 | 0 | 128 | 57
SAN ANGELO | KIMBLE | US 83 | 3507044 | 2017-06-01 | 1487816.87 | 38284.78 | 1619323.39 | 93221.74 | 80 | 35 | 133 | 18
SAN ANGELO | STERLING | SH 158 | 40502024 | 2017-07-31 | 22606153.69 | 1082346.97 | 24092892.39 | 404391.73 | 535 | 51 | 695 | 109
SAN ANGELO | TOM GREEN | US 67 | 7706090 | 2017-06-27 | 6072493.75 | 89135 | 6108507.48 | -53121.27 | 154 | 0 | 216 | 62
SAN ANGELO | TOM GREEN | US 67 | 7706094 | 2017-05-03 | 8069634.1 | 160958.56 | 7883537.77 | -347054.89 | 127 | 0 | 163 | 36
SAN ANGELO | TOM GREEN | VA | 90700161 | 2017-06-01 | 1275751 | 0 | 1239573.5 | -36177.5 | 174 | 0 | 239 | 65
SAN ANGELO | TOM GREEN | VA | 90700166 | 2017-06-01 | 506110.53 | 85378.86 | 591489.39 | 0 | 49 | 10 | 29 | -30
SAN ANGELO | TOM GREEN | VA | 90700168 | 2017-03-30 | 646028.77 | 55075.59 | 660070.08 | -41034.28 | 113 | 0 | 82 | -31
SAN ANTONIO | ATASCOSA | FM 536 | 100903014 | 2017-04-19 | 364903.93 | 11677.58 | 389062.13 | 12480.62 | 64 | 1 | 62 | -3
SAN ANTONIO | BANDERA | FM 1283 | 173001040 | 2017-08-17 | 496196.56 | 0 | 476175.54 | -20021.02 | 60 | 0 | 60 | 0
SAN ANTONIO | BEXAR | IH 10 | 2502201 | 2017-07-31 | 2712741.64 | -154810.52 | 2593200.53 | 35269.41 | 234 | 0 | 232 | -2
SAN ANTONIO | COMAL | BS 46-C | 21502048 | 2017-08-31 | 11041649.54 | -704367.77 | 10129728.79 | -207552.98 | 361 | -24 | 366 | 29
SAN ANTONIO | COMAL | SH 46 | 21507025 | 2017-08-14 | 2086418.25 | 4162.25 | 2151051.5 | 60471 | 169 | 0 | 161 | -8
SAN ANTONIO | COMAL | US 281 | 25303068 | 2017-08-14 | 3132254.38 | 970313.54 | 3923322.52 | -179245.4 | 138 | 333 | 626 | 155
SAN ANTONIO | FRIO | FM 1582 | 150001023 | 2017-04-19 | 8831027.88 | 232883.38 | 9336983.01 | 273071.75 | 338 | 6 | 338 | -6
SAN ANTONIO | GUADALUPE | FM 78 | 2510073 | 2017-04-19 | 4136146.75 | 590719.44 | 4906260.13 | 179393.94 | 203 | 0 | 202 | -1
SAN ANTONIO | KENDALL | IH 10 | 7206073 | 2017-03-14 | 6910844.46 | 105254.69 | 7136271.59 | 120172.44 | 53 | 11 | 61 | -3
SAN ANTONIO | KENDALL | SH 46 | 21506038 | 2017-05-19 | 1279971.5 | 46781.58 | 1324698.09 | -2054.99 | 64 | 2 | 69 | 3
SAN ANTONIO | KERR | SH 16 | 29102034 | 2017-03-14 | 2985558.94 | 135162.57 | 3124721.5 | 3999.99 | 239 | 5 | 235 | -9
SAN ANTONIO | MC MULLEN | SH 72 | 48303033 | 2017-04-27 | 11949680.48 | -84399.07 | 11905878.04 | 40596.63 | 151 | 19 | 179 | 9
SAN ANTONIO | MC MULLEN | VA | 91551011 | 2017-03-29 | 454942.12 | 21049.64 | 415297.23 | -60694.53 | 77 | 0 | 142 | 65
TYLER | ANDERSON | US 287 | 12204037 | 2017-04-19 | 10343177.55 | -603947.88 | 9408896.22 | -330333.45 | 95 | 3 | 115 | 17
TYLER | ANDERSON | CR | 91008040 | 2017-08-25 | 817412.15 | 65774.74 | 841950.42 | -41236.47 | 177 | 0 | 177 | 0
TYLER | ANDERSON | PW | 91008063 | 2017-06-12 | 446429.76 | -31083.2 | 410550.23 | -4796.33 | 62 | 10 | 80 | 8
TYLER | CHEROKEE | US 69 | 19901081 | 2017-07-24 | 11063277.59 | -645418.2 | 10267769.16 | -150090.23 | 180 | 0 | 169 | -11
TYLER | CHEROKEE | FM 22 | 63401011 | 2017-07-27 | 7730087.27 | 27081.86 | 7514948.24 | -242220.89 | 138 | 1 | 191 | 52
TYLER | CHEROKEE | CR | 91036127 | 2017-05-24 | 699993.9 | -20963.75 | 679786.93 | 756.78 | 105 | 0 | 99 | -6
TYLER | GREGG | FM 449 | 64007005 | 2017-08-25 | 4436875.01 | -228721.49 | 4139418.57 | -68734.95 | 284 | 9 | 290 | -3
TYLER | GREGG | FM 2275 | 215801013 | 2017-06-13 | 12884788.32 | 273108.29 | 13233863.86 | 75967.25 | 360 | 22 | 379 | -3
TYLER | RUSK | US 259 | 13803142 | 2017-05-25 | 4277728.08 | -63025.34 | 4115477.21 | -99225.53 | 45 | 0 | 77 | 32
TYLER | RUSK | US 259 | 13804045 | 2017-03-24 | 5667818.78 | 201422.72 | 5971715.71 | 102474.21 | 110 | 14 | 76 | -48
TYLER | RUSK | SH 43 | 20702027 | 2017-05-25 | 4691110.39 | 8884.3 | 4985301.2 | 285306.51 | 57 | 0 | 100 | 43
TYLER | RUSK | VA | 91042041 | 2017-06-26 | 145279 | 1785.98 | 145238.5 | -1826.48 | 38 | 0 | 36 | -2
TYLER | SMITH | US 271 | 16501101 | 2017-06-14 | 4372572.15 | 337080.19 | 4790758.04 | 81105.7 | 55 | 10 | 108 | 43
TYLER | SMITH | SH 64 | 24506076 | 2017-07-24 | 3872443.98 | 213559.86 | 4276105.95 | 190102.11 | 125 | 81 | 206 | 0
TYLER | SMITH | VA | 91000100 | 2017-08-11 | 209929.7 | -24957.23 | 185174.99 | 202.52 | 26 | 0 | 19 | -7
TYLER | SMITH | CR | 91016131 | 2017-07-20 | 947499.8 | 1200 | 969565.11 | 20865.31 | 183 | 0 | 177 | -6
TYLER | VAN ZANDT | SH 198 | 44301028 | 2017-03-13 | 5034636.87 | 258785.3 | 5061318.63 | -232103.54 | 227 | 54 | 362 | 81
WACO | BELL | FM 436 | 23116032 | 2017-08-31 | 174160.93 | -18274.8 | 156615.38 | 729.25 | 30 | 0 | 26 | -4
WACO | BELL | SH 317 | 39804073 | 2017-03-17 | 2346791.5 | -62075.67 | 2313492 | 28776.17 | 128 | 0 | 135 | 7
WACO | BELL | FM 2670 | 119803009 | 2017-08-17 | 521758 | 62838.36 | 615012 | 30415.64 | 128 | 0 | 117 | -11
WACO | BOSQUE | SH 6 | 25804034 | 2017-03-21 | 5936805.87 | 220786.5 | 6138369.28 | -19223.09 | 60 | 0 | 104 | 44
WACO | CORYELL | US 84 | 5506031 | 2017-04-10 | 5618425.61 | 214797.43 | 5826607.04 | -6616 | 277 | 0 | 277 | 0
WACO | CORYELL | SH 36 | 18304051 | 2017-08-22 | 281200 | 0 | 283790 | 2590 | 75 | 0 | 59 | -16
WACO | CORYELL | SH 36 | 18304052 | 2017-04-24 | 67576 | 0 | 69556 | 1980 | 45 | 0 | 30 | -15
WACO | CORYELL | US 190 | 23119002 | 2017-04-10 | 43078679.02 | 3285611.58 | 47396413.04 | 1032122.44 | 712 | 143 | 1048 | 193
WACO | CORYELL | SH 9 | 362301001 | 2017-05-15 | 31901241.27 | 2238031.06 | 33930822.57 | -208449.76 | 609 | 165 | 774 | 0
WACO | FALLS | FM 1963 | 20904031 | 2017-08-03 | 859637.65 | 0 | 835761.13 | -23876.52 | 128 | 0 | 133 | 5
WACO | FALLS | CR | 90938052 | 2017-03-23 | 272958.3 | 0 | 250993.4 | -21964.9 | 85 | 0 | 63 | -22
WACO | FALLS | CR | 90938072 | 2017-04-24 | 1169676.1 | 0 | 1118319 | -51357.1 | 489 | 0 | 377 | -112
WACO | HILL | IH 35 | 1407100 | 2017-04-24 | 918011.9 | 2876.08 | 916814.83 | -4073.15 | 107 | 0 | 106 | -1
WACO | HILL | IH 35W | 1423032 | 2017-08-31 | 1948180.02 | 42391.02 | 2057235.29 | 66664.25 | 107 | 0 | 95 | -12
WACO | LIMESTONE | FM 39 | 64302025 | 2017-06-26 | 7540212.54 | 72621 | 7369396.4 | -243437.14 | 255 | 0 | 254 | -1
WACO | MC LENNAN | FM 3476 | 1521012 | 2017-08-24 | 673249.2 | -23130.79 | 625436.07 | -24682.34 | 30 | 0 | 28 | -2
WACO | MC LENNAN | CS | 90922166 | 2017-05-24 | 755454.92 | 3090.4 | 735262.58 | -23282.74 | 90 | 0 | 108 | 18
WACO | MC LENNAN | FM 3051 | 231101037 | 2017-03-15 | 432180 | 0 | 424572.3 | -7607.7 | 107 | 0 | 88 | -19
WACO | MC LENNAN | FM 3051 | 231101038 | 2017-07-12 | 195682.45 | 0 | 191572.55 | -4109.9 | 60 | 0 | 31 | -29
WACO | MC LENNAN | FM 1695 | 250601036 | 2017-08-31 | 717978.81 | -23552.7 | 682931.1 | -11495.01 | 45 | 0 | 20 | -25
WACO | MC LENNAN | FM 2837 | 352101016 | 2017-08-31 | 1787727.68 | 69290.2 | 1789312.5 | -67705.38 | 127 | 3 | 154 | 24
WICHITA FALLS | ARCHER | US 82 | 15605058 | 2017-08-22 | 1761197.18 | 139601.79 | 1964174.3 | 63375.33 | 32 | 4 | 105 | 69
WICHITA FALLS | CLAY | US 82 | 4402096 | 2017-06-28 | 419000 | 0 | 421350 | 2350 | 103 | 0 | 98 | -5
WICHITA FALLS | COOKE | US 82 | 4407068 | 2017-04-19 | 145746.35 | 62970.63 | 221085.74 | 12368.76 | 30 | 28 | 57 | -1
WICHITA FALLS | COOKE | FM 678 | 78201033 | 2017-08-01 | 3375961.86 | -64442.48 | 3648209.66 | 336690.28 | 162 | 0 | 135 | -27
WICHITA FALLS | COOKE | FM 922 | 84503056 | 2017-05-25 | 4230047.49 | 156527.27 | 4615377.03 | 228802.27 | 213 | 31 | 244 | 0
WICHITA FALLS | COOKE | FM 922 | 84503060 | 2017-03-21 | 332007.54 | 12374.17 | 363708.56 | 19326.85 | 54 | 2 | 32 | -24
WICHITA FALLS | COOKE | CR | 90315081 | 2017-03-14 | 1009366.4 | 1300 | 999673.2 | -10993.2 | 230 | 0 | 187 | -43
WICHITA FALLS | COOKE | FM 3092 | 330801012 | 2017-07-27 | 1969043.18 | 69787.56 | 2047312.37 | 8481.63 | 71 | 0 | 71 | 0
WICHITA FALLS | MONTAGUE | US 81 | 1302020 | 2017-04-05 | 535748.33 | 82996.39 | 620892.51 | 2147.79 | 30 | 10 | 29 | -11
WICHITA FALLS | MONTAGUE | CR | 90328043 | 2017-04-11 | 1149466.65 | 0 | 1118600.08 | -30866.57 | 153 | 0 | 116 | -37
WICHITA FALLS | WICHITA | BU 287J | 4317029 | 2017-03-29 | 655287.3 | 24786.62 | 624441.31 | -55632.61 | 19 | 0 | 66 | 47
WICHITA FALLS | WICHITA | US 82 | 4401103 | 2017-06-26 | 1194000 | 9413.25 | 1142243.25 | -61170 | 102 | 0 | 93 | -9
WICHITA FALLS | WICHITA | SH 258 | 54401020 | 2017-08-11 | 5823532.08 | 159343.97 | 6161988.52 | 179112.47 | 150 | 109 | 360 | 101
WICHITA FALLS | WICHITA | VA | 90300075 | 2017-03-21 | 3132333.32 | 0 | 2992357.21 | -139976.11 | 223 | 0 | 264 | 41
WICHITA FALLS | WILBARGER | US 287 | 4307108 | 2017-03-10 | 6799282.27 | 1135907.47 | 7797685.83 | -137503.91 | 72 | 5 | 77 | 0
YOAKUM | AUSTIN | IH 10 | 27102058 | 2017-07-24 | 4099769.8 | -56738.56 | 4232099.98 | 189068.74 | 120 | 0 | 120 | 0
YOAKUM | AUSTIN | FM 109 | 71601045 | 2017-04-12 | 605947.89 | 0 | 598224.11 | -7723.78 | 20 | 0 | 11 | -9
YOAKUM | CALHOUN | FM 1090 | 51503049 | 2017-06-05 | 344790.67 | 0 | 341330.13 | -3460.54 | 60 | 0 | 65 | 5
YOAKUM | CALHOUN | FM 1289 | 143801021 | 2017-05-11 | 4870061.86 | 89618.57 | 5041738.93 | 82058.5 | 130 | 26 | 156 | 0
YOAKUM | DE WITT | US 87 | 14308089 | 2017-06-15 | 2789989.26 | 635535.54 | 3330776.03 | -94748.77 | 45 | 9 | 54 | 0
YOAKUM | DE WITT | SH 119 | 35903025 | 2017-07-21 | 4573832.62 | 40717.74 | 4677483.12 | 62932.76 | 90 | 49 | 134 | -5
YOAKUM | FAYETTE | US 77 | 26901029 | 2017-07-10 | 2609953.17 | 20752.47 | 2710532.83 | 79827.19 | 75 | 27 | 102 | 0
YOAKUM | LAVACA | SH 95 | 32402022 | 2017-06-15 | 2310815.09 | -16136.44 | 2291589.05 | -3089.6 | 60 | 0 | 50 | -10
YOAKUM | MATAGORDA | FM 457 | 60501061 | 2017-04-12 | 814911 | 0 | 817918.31 | 3007.31 | 45 | 5 | 71 | 21
YOAKUM | MATAGORDA | CR | 91321045 | 2017-03-17 | 333383.92 | 0 | 332506.48 | -877.44 | 60 | 0 | 59 | -1
YOAKUM | VICTORIA | SH 185 | 43202088 | 2017-07-03 | 193412.35 | -8063.08 | 189016.97 | 3667.7 | 30 | 0 | 15 | -15
YOAKUM | VICTORIA | FM 444 | 84005021 | 2017-07-03 | 810634.54 | 165770.37 | 967392.75 | -9012.16 | 120 | 10 | 107 | -23
YOAKUM | VICTORIA | CR | 91327065 | 2017-05-22 | 296070.6 | 6453 | 294146 | -8377.6 | 60 | 7 | 52 | -15
YOAKUM | WHARTON | CR | 91309057 | 2017-03-13 | 465982 | 0 | 462545.78 | -3436.22 | 75 | 0 | 68 | -7
YOAKUM | WHARTON | CR | 91309058 | 2017-04-13 | 524660.5 | 0 | 510315.5 | -14345 | 67 | 0 | 62 | -5