## Sheet1
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED
DISTRICT | COUNTY | HIGHWAY | C C S J | DATE FINAL ESTIMATE PAID | CONTRACT AWARD | CHANGE ORDERS | AMOUNT PAID | UNDER/OVER BUDGET | CONTRACT DAYS | DAYS ADDED | DAYS USED | UNDER/OVER SCHEDULE
ABILENE | HASKELL | US 277 | 15704051 | 2018-08-23 | 708783 | 0 | 708851.25 | 68.25 | 88 | 15 | 100 | -3
ABILENE | HOWARD | FM 2230 | 214901009 | 2018-03-19 | 6178220.66 | 586699.81 | 6591136.86 | -173783.61 | 331 | 71 | 374 | -28
ABILENE | HOWARD | IH 20 | 505110 | 2018-05-25 | 5321335.32 | 343920.19 | 6006631.66 | 341376.15 | 89 | 7 | 141 | 45
ABILENE | NOLAN | US 84 | 5312064 | 2018-07-31 | 597597 | 0 | 600752.25 | 3155.25 | 65 | 0 | 26 | -39
ABILENE | SCURRY | FM 1606 | 152603015 | 2018-06-07 | 6876410.33 | 20744.99 | 6687561.91 | -209593.41 | 228 | 44 | 354 | 82
ABILENE | SCURRY | FM 1610 | 153102012 | 2018-04-19 | 5397845.79 | -13509.84 | 5330694.81 | -53641.14 | 220 | 5 | 261 | 36
ABILENE | SHACKELFORD | US 180 | 1106045 | 2018-06-21 | 467417.1 | 44791.67 | 482564.96 | -29643.81 | 87 | 30 | 135 | 18
ABILENE | TAYLOR | IH 20 | 606103 | 2018-06-21 | 2981256.75 | 0 | 3064630.3 | 83373.55 | 166 | 0 | 140 | -26
ABILENE | TAYLOR | VA | 90800083 | 2018-08-15 | 405530.81 | 18035.9 | 457074.7 | 33507.99 | 38 | 4 | 41 | -1
ABILENE | TAYLOR | VA | 90800085 | 2018-07-16 | 258870 | 0 | 258670 | -200 | 98 | 0 | 16 | -82
AMARILLO | DALLAM | FM 1727 | 79401018 | 2018-04-04 | 6170063.74 | 155822.73 | 6364223.61 | 38337.14 | 114 | 19 | 150 | 17
AMARILLO | DALLAM | US 87 | 4003059 | 2018-06-22 | 26321210 | 154597.44 | 26961006.3 | 485198.86 | 443 | 10 | 379 | -74
AMARILLO | HANSFORD | SH 15 | 30802029 | 2018-08-13 | 9135715.42 | 423077.26 | 9816523.77 | 257731.09 | 210 | 30 | 218 | -22
AMARILLO | HEMPHILL | RM 2654 | 261201011 | 2018-05-03 | 5653751.97 | 9423.64 | 5607691.91 | -55483.7 | 272 | 0 | 166 | -106
AMARILLO | HEMPHILL | US 83 | 3006059 | 2018-07-27 | 563243.5 | 9100 | 555557.69 | -16785.81 | 54 | 7 | 66 | 5
AMARILLO | MOORE | SH 152 | 55701028 | 2018-05-17 | 15561610.53 | 1556243.31 | 17559142.79 | 441288.95 | 130 | 20 | 129 | -21
AMARILLO | OCHILTREE | US 83 | 3001033 | 2018-08-20 | 810357.03 | -37466.66 | 761601.02 | -11289.35 | 74 | 0 | 83 | 9
AMARILLO | POTTER | IH 40 | 9005099 | 2018-06-18 | 1333510.55 | 38003.54 | 1528182.95 | 156668.86 | 60 | 2 | 52 | -10
AMARILLO | POTTER | RM 1061 | 124502043 | 2018-06-25 | 10138324.09 | 704408.44 | 11113533.11 | 270800.58 | 234 | 19 | 238 | -15
AMARILLO | POTTER | US 60 | 16810069 | 2018-05-04 | 2147565.3 | 75774.3 | 2208269.37 | -15070.23 | 95 | 0 | 95 | 0
AMARILLO | POTTER | VA | 90400160 | 2018-05-29 | 2895601.55 | 34918.52 | 2982204.25 | 51684.18 | 274 | 14 | 300 | 12
AMARILLO | POTTER | VA | 90400164 | 2018-05-02 | 1085462.59 | 311932.49 | 1384436.1 | -12958.98 | 72 | 33 | 104 | -1
AMARILLO | POTTER | VA | 90400169 | 2018-07-17 | 995742.4 | 0 | 996501.95 | 759.55 | 60 | 0 | 29 | -31
AMARILLO | RANDALL | SL 335 | 263502028 | 2018-06-13 | 20341481.45 | -85849.77 | 20515997.21 | 260365.53 | 460 | 10 | 468 | -2
AMARILLO | ROBERTS | SH 70 | 49004037 | 2018-03-12 | 5139086.58 | 172096.25 | 5222476.33 | -88706.5 | 197 | 40 | 341 | 104
ATLANTA | BOWIE | FM 991 | 1019010 | 2018-08-14 | 2282446.78 | 45032.46 | 2114676.62 | -212802.62 | 137 | 0 | 66 | -71
ATLANTA | BOWIE | US 67 | 1013087 | 2018-03-12 | 566437.35 | 6474.5 | 571006.35 | -1905.5 | 203 | 0 | 135 | -68
ATLANTA | BOWIE | US 82 | 4606079 | 2018-04-25 | 1824808.25 | 17358.56 | 1926641.02 | 84474.21 | 60 | 0 | 91 | 31
ATLANTA | CAMP | US 271 | 24802063 | 2018-06-18 | 599736.4 | 2586.2 | 595082.4 | -7240.2 | 134 | 0 | 122 | -12
ATLANTA | CASS | FM 125 | 54609039 | 2018-07-31 | 3490097.96 | -23593.64 | 3360618.16 | -105886.16 | 260 | 0 | 232 | -28
ATLANTA | CASS | SH 77 | 27801044 | 2018-05-01 | 8162284.82 | 285405.1 | 8731058.56 | 283368.64 | 370 | 0 | 275 | -95
ATLANTA | CASS | VA | 91900073 | 2018-03-05 | 680959.2 | 3782.5 | 567505.54 | -117236.16 | 40 | 0 | 40 | 0
ATLANTA | HARRISON | CR | 91903057 | 2018-05-21 | 444410.7 | -1484.89 | 432004.89 | -10920.92 | 55 | 0 | 51 | -4
ATLANTA | HARRISON | US 59 | 6301088 | 2018-03-15 | 5342972.79 | 14254.08 | 5381558.07 | 24331.2 | 60 | 0 | 56 | -4
ATLANTA | HARRISON | US 80 | 9607047 | 2018-08-14 | 482088.8 | 0 | 444904.65 | -37184.15 | 83 | 0 | 63 | -20
ATLANTA | TITUS | IH 30 | 61003085 | 2018-06-11 | 67255 | 0 | 60105.54 | -7149.46 | 24 | 0 | 16 | -8
ATLANTA | TITUS | IH 30 | 61003090 | 2018-03-12 | 1841758.65 | 0 | 1846304.61 | 4545.96 | 236 | 0 | 180 | -56
ATLANTA | TITUS | US 67 | 1007050 | 2018-08-20 | 1295587 | 0 | 1203397.81 | -92189.19 | 125 | 0 | 187 | 62
ATLANTA | UPSHUR | SH 300 | 138501036 | 2018-05-14 | 2285447.84 | 29656.78 | 2468425.63 | 153321.01 | 80 | 0 | 67 | -13
AUSTIN | BASTROP | SH 71 | 26505067 | 2018-08-20 | 16509208.51 | 581705.13 | 16991493.81 | -99419.83 | 350 | 60 | 410 | 0
AUSTIN | BURNET | SH 29 | 15005047 | 2018-08-21 | 1003924.5 | 15500 | 1172835.06 | 153410.56 | 97 | 0 | 92 | -5
AUSTIN | CALDWELL | FM 1854 | 38404030 | 2018-07-19 | 986625.98 | -2644.61 | 953415.81 | -30565.56 | 109 | 0 | 118 | 9
AUSTIN | CALDWELL | US 183 | 15202070 | 2018-03-02 | 11698918.94 | 2691323.88 | 14127233.64 | -263009.18 | 267 | 227 | 501 | 7
AUSTIN | HAYS | CR | 91433070 | 2018-08-17 | 149765 | -3427 | 149797 | 3459 | 38 | 0 | 38 | 0
AUSTIN | HAYS | CR | 91433072 | 2018-04-03 | 905345.35 | 0 | 886981.48 | -18363.87 | 139 | 0 | 93 | -46
AUSTIN | HAYS | FM 1626 | 153903001 | 2018-03-07 | 1037967.6 | -56681.15 | 846267.7 | -135018.75 | 40 | 0 | 20 | -20
AUSTIN | HAYS | IH 35 | 1602133 | 2018-03-02 | 11422054.31 | -245760.42 | 11600783.13 | 424489.24 | 307 | 118 | 424 | -1
AUSTIN | HAYS | IH 35 | 1602135 | 2018-04-27 | 12215171.43 | 378720.92 | 12540141.16 | -53751.19 | 420 | 145 | 578 | 13
AUSTIN | HAYS | RM 12 | 68305012 | 2018-04-20 | 1059478.79 | 241738.42 | 1327799.42 | 26582.21 | 98 | 0 | 76 | -22
AUSTIN | HAYS | RM 150 | 80504025 | 2018-08-01 | 849078.51 | 21688.62 | 754696.44 | -116070.69 | 84 | 0 | 172 | 88
AUSTIN | HAYS | RM 1826 | 175402025 | 2018-07-17 | 4013235.58 | -38623.27 | 4004434.85 | 29822.54 | 252 | 22 | 312 | 38
AUSTIN | HAYS | SH 123 | 36601066 | 2018-06-04 | 11596550.48 | 15549.21 | 11652717.43 | 40617.74 | 465 | 116 | 505 | -76
AUSTIN | HAYS | US 290 | 11307065 | 2018-06-26 | 2315707.1 | 85307.24 | 2334475.86 | -66538.48 | 38 | 0 | 36 | -2
AUSTIN | LEE | FM 2239 | 209802008 | 2018-03-06 | 2468925.07 | -19926.28 | 2355676.84 | -93321.95 | 128 | 0 | 121 | -7
AUSTIN | LEE | US 290 | 11407082 | 2018-08-21 | 1336982.72 | 9317.1 | 1330338.02 | -15961.8 | 118 | 0 | 85 | -33
AUSTIN | LLANO | SH 29 | 15002038 | 2018-08-23 | 514230.77 | 34764 | 492773.57 | -56221.2 | 53 | 0 | 66 | 13
AUSTIN | MASON | CR | 91426007 | 2018-04-02 | 264228 | -7728.2 | 278240.08 | 21740.28 | 63 | 0 | 56 | -7
AUSTIN | MASON | SH 29 | 39602026 | 2018-08-08 | 1204213.5 | 3421 | 1237629.84 | 29995.34 | 168 | 0 | 150 | -18
AUSTIN | MASON | US 87 | 7105029 | 2018-06-01 | 983038.53 | -47312 | 872456.39 | -63270.14 | 171 | 0 | 251 | 80
AUSTIN | TRAVIS | FM 734 | 341701024 | 2018-05-11 | 1497761.6 | -49899.22 | 1391383.42 | -56478.96 | 71 | 0 | 26 | -45
AUSTIN | TRAVIS | FM 734 | 341703023 | 2018-07-25 | 248444.3 | -5005 | 223481.47 | -19957.83 | 46 | 0 | 29 | -17
AUSTIN | TRAVIS | FM 969 | 118601087 | 2018-08-24 | 5894316.37 | 484073.18 | 6223982.62 | -154406.93 | 398 | 0 | 385 | -13
AUSTIN | TRAVIS | IH 35 | 1510060 | 2018-04-02 | 4749992.46 | 67413.88 | 5140395.45 | 322989.11 | 70 | 0 | 81 | 11
AUSTIN | TRAVIS | LP 1 | 313601172 | 2018-08-22 | 7773016.78 | 1519627.97 | 9394767.89 | 102123.14 | 549 | 194 | 736 | -7
AUSTIN | TRAVIS | LP 1 | 313601174 | 2018-04-13 | 2985697.49 | 114319.76 | 3196326.01 | 96308.76 | 250 | 38 | 272 | -16
AUSTIN | TRAVIS | LP 1 | 313601178 | 2018-03-27 | 740923.26 | -16306.1 | 668957.52 | -55659.64 | 30 | 0 | 30 | 0
AUSTIN | TRAVIS | RM 620 | 68302068 | 2018-07-27 | 181556.9 | -4815.04 | 179564.66 | 2822.8 | 49 | 0 | 35 | -14
AUSTIN | TRAVIS | SH 71 | 11313149 | 2018-03-05 | 34982606.55 | 2837117.27 | 40376116.11 | 2556392.29 | 581 | 72 | 653 | 0
AUSTIN | TRAVIS | SH 71 | 70003125 | 2018-04-03 | 15965613.32 | 612038.47 | 16708646.75 | 130994.96 | 289 | 151 | 440 | 0
AUSTIN | TRAVIS | SL 360 | 11313155 | 2018-05-17 | 1306470.24 | -87509.68 | 1328512.52 | 109551.96 | 67 | 0 | 37 | -30
AUSTIN | TRAVIS | SL 360 | 11313157 | 2018-04-16 | 6447812.17 | 97038.98 | 6787014.88 | 242163.73 | 200 | 11 | 211 | 0
AUSTIN | TRAVIS | SS 69 | 11401060 | 2018-06-21 | 985635.44 | -147377.18 | 839234.99 | 976.73 | 117 | 0 | 114 | -3
AUSTIN | TRAVIS | US 183 | 15109145 | 2018-08-24 | 2711157.55 | -275101.91 | 2539755.7 | 103700.06 | 54 | 0 | 74 | 20
AUSTIN | TRAVIS | US 290 | 11402103 | 2018-07-27 | 3108528.37 | 174134.01 | 3340519.94 | 57857.56 | 72 | 9 | 81 | 0
AUSTIN | TRAVIS | VA | 91400314 | 2018-03-19 | 2958819.25 | -244121.68 | 2874854.88 | 160157.31 | 508 | 0 | 320 | -188
AUSTIN | TRAVIS | VA | 91400369 | 2018-05-25 | 1104881 | -110490 | 1069967.05 | 75576.05 | 300 | 0 | 230 | -70
AUSTIN | WILLIAMSON | FM 685 | 75701020 | 2018-04-02 | 11017549.15 | -40813.21 | 11053151.31 | 76415.37 | 441 | 10 | 475 | 24
AUSTIN | WILLIAMSON | IH 35 | 1509188 | 2018-08-14 | 4091044.67 | 0 | 4265658.62 | 174613.95 | 64 | 0 | 63 | -1
AUSTIN | WILLIAMSON | RM 1431 | 137802036 | 2018-03-26 | 17353255.73 | 1444313.54 | 19824415.47 | 1026846.2 | 269 | 150 | 419 | 0
AUSTIN | WILLIAMSON | RM 2243 | 210301031 | 2018-03-30 | 677720.76 | -29797.95 | 667668.01 | 19745.2 | 30 | 0 | 15 | -15
AUSTIN | WILLIAMSON | SH 95 | 32003097 | 2018-03-28 | 893754.23 | -37279.2 | 874355.42 | 17880.39 | 35 | 0 | 26 | -9
AUSTIN | WILLIAMSON | US 79 | 20403043 | 2018-05-04 | 911970.84 | -41172.3 | 989266.07 | 118467.53 | 43 | 0 | 36 | -7
BEAUMONT | CHAMBERS | FM 1405 | 102402044 | 2018-04-03 | 10486302.45 | -125635.7 | 10270318.39 | -90348.36 | 143 | 15 | 158 | 0
BEAUMONT | CHAMBERS | FM 3180 | 327101011 | 2018-08-24 | 6439873.51 | 184036.59 | 6310770.52 | -313139.58 | 212 | 20 | 230 | -2
BEAUMONT | CHAMBERS | SH 61 | 24203075 | 2018-08-20 | 244900.27 | 0 | 233244.32 | -11655.95 | 31 | 0 | 29 | -2
BEAUMONT | HARDIN | FM 418 | 20012014 | 2018-06-11 | 1011480.75 | 0 | 1011994.65 | 513.9 | 36 | 0 | 29 | -7
BEAUMONT | HARDIN | FM 418 | 78401046 | 2018-05-03 | 1281590.79 | 4860 | 1268108.48 | -18342.31 | 183 | 4 | 99 | -88
BEAUMONT | HARDIN | SH 105 | 33904035 | 2018-06-13 | 2678096.51 | -20610.8 | 2648444.26 | -9041.45 | 60 | 0 | 33 | -27
BEAUMONT | HARDIN | US 69 | 6506065 | 2018-08-24 | 483965 | 55971 | 547740.96 | 7804.96 | 36 | 8 | 42 | -2
BEAUMONT | JASPER | SH 63 | 24402098 | 2018-03-13 | 6777550 | 249768.89 | 7164072.24 | 136753.35 | 55 | 9 | 84 | 20
BEAUMONT | JEFFERSON | CS | 92038153 | 2018-03-05 | 11284746.71 | -237043.18 | 11497251.73 | 449548.2 | 364 | 170 | 526 | -8
BEAUMONT | JEFFERSON | FM 365 | 93202053 | 2018-07-02 | 1565852.57 | 156656.42 | 1844308.31 | 121799.32 | 89 | 46 | 149 | 14
BEAUMONT | JEFFERSON | SH 73 | 30603126 | 2018-08-24 | 8246674.85 | 405013.76 | 7934937.17 | -716751.44 | 180 | 0 | 150 | -30
BEAUMONT | JEFFERSON | SS 136 | 65301014 | 2018-05-03 | 452662.8 | 83406.68 | 539367.02 | 3297.54 | 64 | 20 | 85 | 1
BEAUMONT | JEFFERSON | VA | 92000116 | 2018-04-17 | 832522.01 | 0 | 817376.24 | -15145.77 | 219 | 0 | 198 | -21
BEAUMONT | LIBERTY | SH 105 | 59301117 | 2018-05-08 | 1388679.6 | 405964.02 | 1808766.06 | 14122.44 | 117 | 19 | 120 | -16
BEAUMONT | NEWTON | SH 87 | 30504037 | 2018-04-16 | 2270328.78 | 0 | 2243425.73 | -26903.05 | 26 | 0 | 30 | 4
BEAUMONT | ORANGE | FM 2177 | 88201013 | 2018-05-01 | 328092.65 | 18328.66 | 363655.82 | 17234.51 | 35 | 2 | 37 | 0
BROWNWOOD | EASTLAND | SH 206 | 263801022 | 2018-04-13 | 397732.27 | -3962.33 | 383324.94 | -10445 | 81 | 0 | 38 | -43
BROWNWOOD | MILLS | SH 16 | 28903026 | 2018-04-13 | 1557630.87 | 39464.42 | 1545299.84 | -51795.45 | 187 | 3 | 173 | -17
BROWNWOOD | STEPHENS | US 183 | 25701047 | 2018-05-22 | 223073.5 | 0 | 204113.65 | -18959.85 | 34 | 0 | 32 | -2
BRYAN | BRAZOS | FM 2154 | 54004072 | 2018-08-23 | 2056099.02 | 151282.69 | 1988213.24 | -219168.47 | 97 | 23 | 111 | -9
BRYAN | BRAZOS | SH 21 | 11701046 | 2018-08-17 | 2625544.77 | 268248.31 | 2878915.57 | -14877.51 | 185 | 25 | 185 | -25
BRYAN | BRAZOS | VA | 91700040 | 2018-03-16 | 3503761 | -138244.8 | 3268899.8 | -96616.4 | 418 | 7 | 423 | -2
BRYAN | BURLESON | FM 2155 | 50604022 | 2018-07-26 | 1647283.55 | 59844.5 | 1745893.52 | 38765.47 | 212 | 6 | 218 | 0
BRYAN | BURLESON | FM 60 | 64803050 | 2018-06-07 | 10487720.87 | 243982.56 | 10890745.49 | 159042.06 | 227 | 34 | 280 | 19
BRYAN | GRIMES | FM 3090 | 64305027 | 2018-05-21 | 2353004.36 | 2287.95 | 2304988.37 | -50303.94 | 185 | 0 | 142 | -43
BRYAN | GRIMES | SH 90 | 31502047 | 2018-06-07 | 7051873.09 | -151101.69 | 7064786.47 | 164015.07 | 168 | 11 | 225 | 46
BRYAN | MADISON | CR | 91731022 | 2018-05-17 | 1204839.72 | 55432.74 | 1291581.27 | 31308.81 | 205 | 0 | 135 | -70
BRYAN | MADISON | SH 21 | 11704040 | 2018-08-03 | 7687430.72 | 6501.87 | 8119976.27 | 426043.68 | 199 | 5 | 203 | -1
BRYAN | MADISON | US 190 | 11704041 | 2018-08-09 | 2150935.1 | 219929 | 2346681.92 | -24182.18 | 60 | 38 | 63 | -35
BRYAN | MILAM | US 79 | 20406055 | 2018-03-30 | 5229897.85 | -409682.37 | 4975305.89 | 155090.41 | 155 | 2 | 149 | -8
BRYAN | WALKER | VA | 91727045 | 2018-04-25 | 1833580 | 253022.7 | 2248767.62 | 162164.92 | 205 | 0 | 57 | -148
CHILDRESS | CHILDRESS | VA | 92500067 | 2018-08-20 | 763578.35 | 41955.27 | 806995.21 | 1461.59 | 60 | 0 | 47 | -13
CHILDRESS | COLLINGSWORTH | FM 1547 | 84404009 | 2018-07-13 | 6114806.4 | -1530.3 | 6631925.21 | 518649.11 | 179 | 0 | 179 | 0
CHILDRESS | HALL | CR | 92509035 | 2018-06-26 | 557176.2 | -46617.01 | 508562.24 | -1996.95 | 85 | 0 | 82 | -3
CHILDRESS | HALL | US 287 | 4209126 | 2018-07-13 | 1199814.31 | 3238.18 | 1217932.17 | 14879.68 | 54 | 0 | 19 | -35
CHILDRESS | WHEELER | IH 40 | 27512072 | 2018-03-20 | 2923330.68 | -3055.9 | 2938390.43 | 18115.65 | 170 | 0 | 136 | -34
CORPUS CHRISTI | ARANSAS | PW | 91638009 | 2018-06-29 | 1003164.46 | 86909.54 | 1093499.06 | 3425.06 | 51 | 5 | 54 | -2
CORPUS CHRISTI | BEE | FM 796 | 111801019 | 2018-08-24 | 444575.5 | 3150.53 | 450262.53 | 2536.5 | 68 | 0 | 62 | -6
CORPUS CHRISTI | BEE | FM 882 | 99104011 | 2018-06-13 | 737683.48 | 11719 | 772269.22 | 22866.74 | 139 | 0 | 106 | -33
CORPUS CHRISTI | BEE | US 59 | 8801067 | 2018-04-13 | 3243062.35 | 195744.66 | 3608795.67 | 169988.66 | 88 | 5 | 48 | -45
CORPUS CHRISTI | JIM WELLS | FM 624 | 98901037 | 2018-06-06 | 4558633.8 | 257409.56 | 4854376.05 | 38332.69 | 187 | 0 | 166 | -21
CORPUS CHRISTI | JIM WELLS | FM 665 | 8619031 | 2018-06-06 | 642139.91 | 135609.92 | 758822.96 | -18926.87 | 124 | 42 | 164 | -2
CORPUS CHRISTI | JIM WELLS | SH 44 | 8611048 | 2018-06-27 | 258988.85 | 0 | 258505.63 | -483.22 | 66 | 0 | 35 | -31
CORPUS CHRISTI | KARNES | SH 80 | 34803025 | 2018-08-17 | 15028548.88 | 436177.35 | 15674618.57 | 209892.34 | 340 | 21 | 351 | -10
CORPUS CHRISTI | KARNES | SH 80 | 34803027 | 2018-06-25 | 4785955.37 | 12333.85 | 4618785 | -179504.22 | 146 | 4 | 150 | 0
CORPUS CHRISTI | KARNES | US 181 | 10005075 | 2018-07-30 | 11984426.85 | -231254.67 | 11914719.81 | 161547.63 | 284 | 16 | 294 | -6
CORPUS CHRISTI | KARNES | US 181 | 10006064 | 2018-07-09 | 2735640.96 | 174911.33 | 2900964.27 | -9588.02 | 48 | 10 | 58 | 0
CORPUS CHRISTI | LIVE OAK | CR | 91629006 | 2018-06-06 | 649190.68 | 35102.22 | 667983.86 | -16309.04 | 94 | 12 | 105 | -1
CORPUS CHRISTI | LIVE OAK | US 281 | 25401134 | 2018-03-19 | 5606795.34 | 1141351.65 | 7204047.64 | 455900.65 | 119 | 31 | 149 | -1
CORPUS CHRISTI | NUECES | FM 43 | 155701041 | 2018-05-03 | 3286683.8 | 148688.15 | 3389698.72 | -45673.23 | 131 | 4 | 138 | 3
CORPUS CHRISTI | NUECES | FM 70 | 155803035 | 2018-03-12 | 2830324.4 | 174483.1 | 2546057.75 | -458749.75 | 139 | 25 | 149 | -15
CORPUS CHRISTI | NUECES | SH 358 | 61701185 | 2018-06-15 | 935810.65 | 0 | 878202.63 | -57608.02 | 119 | 0 | 261 | 142
CORPUS CHRISTI | NUECES | SH 358 | 61701190 | 2018-07-10 | 4086049.86 | 489115.56 | 4758323.58 | 183158.16 | 51 | 83 | 124 | -10
CORPUS CHRISTI | NUECES | SH 361 | 226303029 | 2018-06-06 | 12988210.75 | 465193.33 | 13310238.03 | -143166.05 | 408 | 44 | 452 | 0
CORPUS CHRISTI | NUECES | SH 361 | 226303040 | 2018-06-25 | 8989000 | 87750 | 8980000 | -96750 | 385 | 74 | 545 | 86
CORPUS CHRISTI | NUECES | SH 44 | 37302092 | 2018-05-03 | 1730818 | 1326828.11 | 3183240.55 | 125594.44 | 102 | 21 | 66 | -57
CORPUS CHRISTI | NUECES | VA | 91600083 | 2018-05-02 | 951312.89 | 24638 | 936435.42 | -39515.47 | 62 | 0 | 68 | 6
CORPUS CHRISTI | REFUGIO | FM 774 | 44705061 | 2018-07-10 | 4223924.56 | 234296.36 | 4453253.66 | -4967.26 | 195 | 28 | 219 | -4
CORPUS CHRISTI | SAN PATRICIO | CS | 91628068 | 2018-06-26 | 119588 | 0 | 114560 | -5028 | 90 | 0 | 16 | -74
CORPUS CHRISTI | SAN PATRICIO | SH 35 | 18006101 | 2018-03-19 | 1878411.95 | 1506 | 1926093.42 | 46175.47 | 50 | 0 | 27 | -23
DALLAS | COLLIN | FM 2514 | 267903010 | 2018-08-02 | 6339339.32 | 230655.71 | 6457038.88 | -112956.15 | 220 | 21 | 284 | 43
DALLAS | COLLIN | FM 455 | 81604044 | 2018-05-08 | 12399737.45 | 694141.8 | 12634004.23 | -459875.02 | 251 | 42 | 311 | 18
DALLAS | COLLIN | US 75 | 4706159 | 2018-03-15 | 657809 | 0 | 696391.92 | 38582.92 | 74 | 0 | 73 | -1
DALLAS | COLLIN | US 75 | 4714068 | 2018-03-28 | 63579301.83 | 1221850.59 | 64510422.94 | -290729.48 | 920 | 69 | 989 | 0
DALLAS | DALLAS | CS | 91847120 | 2018-06-07 | 1300500 | 1220 | 1275422.94 | -26297.06 | 172 | 0 | 191 | 19
DALLAS | DALLAS | FM 1382 | 104703072 | 2018-06-14 | 1680355.86 | 2509.13 | 1640059.85 | -42805.14 | 100 | 0 | 84 | -16
DALLAS | DALLAS | IH 345 | 9214080 | 2018-08-24 | 30450159 | 738983.03 | 27831944.1 | -3357197.93 | 504 | 28 | 532 | 0
DALLAS | DALLAS | IH 35E | 19603256 | 2018-04-13 | 7335235.42 | 166505.64 | 6650188.72 | -851552.34 | 133 | 0 | 182 | 49
DALLAS | DALLAS | IH 35E | 19603272 | 2018-07-02 | 3349483.21 | 61103.95 | 3237177.52 | -173409.64 | 104 | 80 | 184 | 0
DALLAS | DALLAS | IH 35E | 44202157 | 2018-08-24 | 3240394.35 | 430925.44 | 3477263.43 | -194056.36 | 156 | 0 | 145 | -11
DALLAS | DALLAS | IH 35E | 44202160 | 2018-05-07 | 496357 | 250.92 | 514912.05 | 18304.13 | 64 | 0 | 69 | 5
DALLAS | DALLAS | IH 635 | 237401176 | 2018-05-07 | 6763281.39 | 1855466.79 | 8548566.16 | -70182.02 | 267 | 172 | 433 | -6
DALLAS | DALLAS | PW | 91847118 | 2018-08-10 | 1037211.25 | 21297.13 | 904037.2 | -154471.18 | 84 | 0 | 69 | -15
DALLAS | DALLAS | SH 114 | 35304095 | 2018-07-27 | 3939023.45 | 43110.48 | 4070725.32 | 88591.39 | 187 | 0 | 186 | -1
DALLAS | DALLAS | SL 12 | 35305082 | 2018-08-10 | 6736851.5 | 348492.1 | 6960547.58 | -124796.02 | 335 | 130 | 465 | 0
DALLAS | DALLAS | SL 12 | 35305088 | 2018-06-08 | 7651961.36 | 689851.63 | 8199352.1 | -142460.89 | 457 | 220 | 677 | 0
DALLAS | DALLAS | SL 12 | 58101141 | 2018-06-07 | 1625000 | 0 | 1685897.52 | 60897.52 | 286 | 0 | 277 | -9
DALLAS | DALLAS | SL 12 | 58102145 | 2018-05-15 | 1463102.55 | 3696.9 | 1430639.41 | -36160.04 | 80 | 1 | 81 | 0
DALLAS | DALLAS | VA | 91800187 | 2018-07-27 | 1276600 | 29610 | 1275062.79 | -31147.21 | 548 | 0 | 424 | -124
DALLAS | DALLAS | VA | 91847052 | 2018-08-21 | 2270944.3 | 0 | 2162311.95 | -108632.35 | 244 | 0 | 239 | -5
DALLAS | DALLAS | VA | 91847100 | 2018-04-30 | 3464886.45 | 0 | 3250839 | -214047.45 | 315 | 0 | 259 | -56
DALLAS | DENTON | FM 455 | 81602076 | 2018-08-07 | 4986228.11 | -92631.32 | 4605291.6 | -288305.19 | 236 | 0 | 236 | 0
DALLAS | DENTON | US 377 | 13510055 | 2018-06-01 | 5166236.4 | -30393.52 | 5013095.75 | -122747.13 | 244 | 0 | 246 | 2
DALLAS | DENTON | US 380 | 13409034 | 2018-04-30 | 15088445.93 | 855039.57 | 15703706.35 | -239779.15 | 420 | 25 | 633 | 188
DALLAS | DENTON | US 380 | 13409063 | 2018-08-02 | 39346679.88 | 2003182.93 | 41733495.38 | 383632.57 | 755 | 119 | 874 | 0
DALLAS | ELLIS | FM 55 | 145101024 | 2018-03-30 | 5538628.87 | 407327.54 | 5123559.38 | -822397.03 | 263 | 0 | 378 | 115
DALLAS | ELLIS | FM 664 | 105101042 | 2018-05-17 | 11142221.18 | 936556.16 | 11931750.04 | -147027.3 | 293 | 86 | 463 | 84
DALLAS | ELLIS | FM 879 | 115902032 | 2018-05-17 | 9549753.04 | 432326.32 | 9699569.76 | -282509.6 | 315 | 61 | 448 | 72
DALLAS | ELLIS | IH 45 | 9203049 | 2018-06-27 | 1185768.45 | 0 | 1184447.07 | -1321.38 | 80 | 0 | 73 | -7
DALLAS | KAUFMAN | CR | 91811091 | 2018-04-06 | 696776.52 | 7812.91 | 644508.45 | -60080.98 | 180 | 0 | 139 | -41
DALLAS | KAUFMAN | FM 2578 | 255501011 | 2018-08-23 | 6878335.7 | -10800.72 | 6163569 | -703965.98 | 247 | 0 | 312 | 65
DALLAS | KAUFMAN | FM 2728 | 251202010 | 2018-08-21 | 3813436.38 | 106864.81 | 3699496.73 | -220804.46 | 206 | 0 | 198 | -8
DALLAS | KAUFMAN | FM 3486 | 149403001 | 2018-08-23 | 4849821.37 | -327021.35 | 4330017.41 | -192782.61 | 168 | 1 | 195 | 26
DALLAS | KAUFMAN | US 175 | 19705054 | 2018-06-11 | 1419580.25 | 7566.34 | 1201650.42 | -225496.17 | 66 | 0 | 61 | -5
DALLAS | KAUFMAN | US 80 | 9503087 | 2018-06-26 | 5049368.47 | 113540.46 | 5135395.02 | -27513.91 | 279 | 4 | 276 | -7
DALLAS | NAVARRO | FM 1838 | 99702039 | 2018-06-22 | 3875212.2 | 0 | 3751009.52 | -124202.68 | 251 | 0 | 169 | -82
DALLAS | ROCKWALL | FM 3097 | 314801006 | 2018-08-21 | 9349455.02 | 224298.66 | 9257874.44 | -315879.24 | 362 | 13 | 467 | 92
DALLAS | ROCKWALL | FM 548 | 101402041 | 2018-04-18 | 13784401.34 | 530968.84 | 14048865.48 | -266504.7 | 363 | 14 | 377 | 0
DALLAS | ROCKWALL | FM 549 | 101501025 | 2018-07-30 | 7749472.52 | 1448996.62 | 8646015.32 | -552453.82 | 410 | 87 | 478 | -19
DALLAS | ROCKWALL | IH 30 | 912074 | 2018-05-17 | 19988908.62 | 6916012.05 | 28021685.34 | 1116764.67 | 503 | 122 | 625 | 0
DALLAS | ROCKWALL | IH 30 | 912078 | 2018-05-04 | 30862690.37 | 1070492.36 | 31803455.1 | -129727.63 | 505 | 20 | 525 | 0
DALLAS | ROCKWALL | IH 30 | 912212 | 2018-07-12 | 2315893.57 | 6529.3 | 2399333.14 | 76910.27 | 121 | 6 | 127 | 0
DALLAS | ROCKWALL | IH 30 | 912216 | 2018-03-19 | 1105995.62 | 0 | 1115563.39 | 9567.77 | 70 | 0 | 65 | -5
EL PASO | BREWSTER | US 90 | 2102024 | 2018-03-20 | 5614637.07 | 649111.2 | 6312130.06 | 48381.79 | 40 | 0 | 40 | 0
EL PASO | CULBERSON | IH 10 | 301057 | 2018-06-14 | 957145 | 11010.88 | 1004351.58 | 36195.7 | 80 | 0 | 62 | -18
EL PASO | EL PASO | CS | 92406154 | 2018-07-17 | 7848531.31 | 58627.71 | 8024672.47 | 117513.45 | 218 | 52 | 270 | 0
EL PASO | EL PASO | FM 76 | 67401037 | 2018-05-21 | 18794269.46 | 3864908.82 | 23230718.49 | 571540.21 | 510 | 152 | 661 | -1
EL PASO | EL PASO | IH 10 | 212102146 | 2018-05-14 | 1399520.76 | 93733.23 | 1538780.19 | 45526.2 | 80 | 0 | 45 | -35
EL PASO | EL PASO | IH 10 | 212102152 | 2018-03-20 | 8829604.33 | 3647631.93 | 12905020.49 | 427784.23 | 218 | 310 | 518 | -10
EL PASO | EL PASO | US 54 | 16701108 | 2018-05-14 | 1898217.38 | -108864.11 | 1791783.27 | 2430 | 140 | 0 | 107 | -33
EL PASO | EL PASO | US 62 | 104094 | 2018-06-29 | 682967 | 184866.68 | 860403.18 | -7430.5 | 60 | 40 | 99 | -1
EL PASO | EL PASO | VA | 92400082 | 2018-06-25 | 815945.44 | 414171.75 | 1230392.96 | 275.77 | 120 | 20 | 140 | 0
EL PASO | HUDSPETH | IH 10 | 205044 | 2018-06-25 | 3057663.63 | 64571.81 | 3122235.44 | 5.8208e-11 | 160 | 0 | 142 | -18
EL PASO | HUDSPETH | US 62 | 37405025 | 2018-03-22 | 3121216.06 | 493585.19 | 3666586.38 | 51785.13 | 110 | 0 | 110 | 0
FORT WORTH | ERATH | FM 914 | 55003024 | 2018-06-01 | 3426804.42 | 113188.14 | 3482402.8 | -57589.76 | 215 | 0 | 149 | -66
FORT WORTH | ERATH | SH 108 | 34304042 | 2018-05-15 | 75144 | -14090.19 | 58935.56 | -2118.25 | 16 | 0 | 17 | 1
FORT WORTH | ERATH | SH 6 | 25801028 | 2018-07-10 | 6192975.12 | 330771.01 | 6083423.09 | -440323.04 | 272 | 26 | 215 | -83
FORT WORTH | HOOD | FM 2580 | 160103014 | 2018-04-18 | 1468973.71 | -17817.65 | 1458644.38 | 7488.32 | 147 | 0 | 62 | -85
FORT WORTH | HOOD | US 377 | 8003054 | 2018-06-04 | 4079052.2 | 52468.3 | 4227715.48 | 96194.98 | 39 | 12 | 49 | -2
FORT WORTH | HOOD | US 377 | 8004096 | 2018-08-24 | 3213559.48 | 278870.43 | 3412603.28 | -79826.63 | 32 | 7 | 39 | 0
FORT WORTH | PALO PINTO | FM 1821 | 228801013 | 2018-06-22 | 1057227.2 | 106076.88 | 1183684.05 | 20379.97 | 64 | 0 | 61 | -3
FORT WORTH | PALO PINTO | US 281 | 24908041 | 2018-05-09 | 8069594.95 | 87595.46 | 8503630.43 | 346440.02 | 97 | 10 | 117 | 10
FORT WORTH | PARKER | FM 1886 | 160501014 | 2018-07-16 | 4834822.79 | 441249.37 | 5114715.83 | -161356.33 | 256 | 81 | 411 | 74
FORT WORTH | TARRANT | CS | 90248539 | 2018-07-12 | 10487665.24 | 1538992.59 | 12431615.18 | 404957.35 | 315 | 301 | 606 | -10
FORT WORTH | TARRANT | FM 156 | 71802068 | 2018-08-21 | 164000 | 0 | 147440 | -16560 | 40 | 0 | 65 | 25
FORT WORTH | TARRANT | IH 820 | 815049 | 2018-08-22 | 3652534.53 | 117580.97 | 3821797.44 | 51681.94 | 256 | 39 | 383 | 88
FORT WORTH | TARRANT | SH 10 | 9402123 | 2018-08-08 | 2966572.1 | 100567 | 3015925.98 | -51213.12 | 96 | 6 | 103 | 1
FORT WORTH | TARRANT | SH 10 | 9402131 | 2018-07-17 | 314980 | 2843 | 314195 | -3628 | 180 | 0 | 112 | -68
FORT WORTH | TARRANT | SH 114 | 35303095 | 2018-05-09 | 410000 | 23795.4 | 430545.4 | -3250 | 85 | 28 | 113 | 0
FORT WORTH | TARRANT | SH 121 | 36401140 | 2018-06-05 | 366150.05 | 14388.4 | 356200.04 | -24338.41 | 76 | 67 | 185 | 42
FORT WORTH | TARRANT | SH 180 | 806050 | 2018-03-12 | 4321303.01 | -573207.65 | 3420570.68 | -327524.68 | 168 | 11 | 179 | 0
FORT WORTH | TARRANT | SH 360 | 226602146 | 2018-04-11 | 281936.15 | 8119.01 | 296937.04 | 6881.88 | 24 | 10 | 34 | 0
FORT WORTH | TARRANT | US 377 | 8101046 | 2018-04-17 | 4198919.2 | 323784.52 | 4391950.02 | -130753.7 | 236 | 229 | 515 | 50
FORT WORTH | TARRANT | VA | 90200134 | 2018-05-29 | 476055.25 | 220331.33 | 1018962.77 | 322576.19 | 128 | 10 | 281 | 143
FORT WORTH | TARRANT | VA | 90290048 | 2018-07-25 | 344814.91 | 0 | 308346.13 | -36468.78 | 40 | 0 | 83 | 43
FORT WORTH | WISE | US 380 | 13407073 | 2018-08-24 | 241382.82 | 0 | 239022.82 | -2360 | 107 | 0 | 34 | -73
FORT WORTH | WISE | US 81 | 1308127 | 2018-03-07 | 12119453.03 | 1287387.98 | 14250459.66 | 843618.65 | 543 | 0 | 536 | -7
HOUSTON | BRAZORIA | BS 288B | 11107048 | 2018-07-09 | 5258450.72 | -41228.83 | 5384592.12 | 167370.23 | 151 | 0 | 150 | -1
HOUSTON | BRAZORIA | FM 521 | 84703035 | 2018-07-20 | 7645090.82 | 402439.09 | 8123462.05 | 75932.14 | 191 | 36 | 227 | 0
HOUSTON | BRAZORIA | SH 288 | 59802097 | 2018-06-06 | 6895441.61 | -227167.88 | 6328278.84 | -339994.89 | 156 | 28 | 219 | 35
HOUSTON | BRAZORIA | SH 288 | 59802106 | 2018-07-18 | 9196617.22 | 437532.33 | 9467027.61 | -167121.94 | 290 | 32 | 304 | -18
HOUSTON | BRAZORIA | SH 35 | 17802088 | 2018-07-19 | 261915.9 | 12150.88 | 276801.55 | 2734.77 | 81 | 0 | 35 | -46
HOUSTON | BRAZORIA | SH 35 | 18807005 | 2018-04-27 | 741699.95 | 97115.9 | 692474.97 | -146340.88 | 71 | 27 | 173 | 75
HOUSTON | BRAZORIA | VA | 91231279 | 2018-07-17 | 2131009.56 | -140186.04 | 1985565.19 | -5258.33 | 120 | 26 | 164 | 18
HOUSTON | FORT BEND | CS | 91234182 | 2018-05-07 | 6588849.4 | 61347.42 | 6627714.72 | -22482.1 | 245 | 0 | 178 | -67
HOUSTON | FORT BEND | FM 2234 | 210501046 | 2018-08-23 | 8068060.38 | 891299.37 | 8804425.59 | -154934.16 | 215 | 9 | 211 | -13
HOUSTON | FORT BEND | FM 360 | 52706019 | 2018-06-11 | 1482901.93 | 87410.66 | 1736282.33 | 165969.74 | 90 | 0 | 44 | -46
HOUSTON | FORT BEND | IH 10 | 27105040 | 2018-06-12 | 1897990.52 | 348896.38 | 2238854 | -8032.9 | 105 | 44 | 145 | -4
HOUSTON | FORT BEND | SH 36 | 18705060 | 2018-06-28 | 4918131.86 | 84548.1 | 5658294.65 | 655614.69 | 120 | 0 | 99 | -21
HOUSTON | FORT BEND | US 59 | 2712134 | 2018-07-27 | 696610.9 | 110909.9 | 774664.99 | -32855.81 | 375 | 90 | 457 | -8
HOUSTON | FORT BEND | US 90A | 2706057 | 2018-07-06 | 741888.35 | 82329.52 | 940730.95 | 116513.08 | 26 | 11 | 45 | 8
HOUSTON | GALVESTON | FM 2094 | 97604020 | 2018-08-24 | 213735.35 | 0 | 228615.25 | 14879.9 | 180 | 0 | 71 | -109
HOUSTON | GALVESTON | FM 519 | 62801022 | 2018-04-30 | 3878490.98 | -192652.46 | 3685579.54 | -258.98 | 165 | 0 | 83 | -82
HOUSTON | GALVESTON | FM 646 | 97802054 | 2018-06-21 | 5827858.98 | 342606.74 | 5825324.73 | -345140.99 | 135 | 70 | 205 | 0
HOUSTON | GALVESTON | SH 146 | 38906105 | 2018-04-16 | 318156.25 | -11418.24 | 290440.81 | -16297.2 | 45 | 0 | 26 | -19
HOUSTON | GALVESTON | SH 275 | 359501017 | 2018-05-04 | 985671.81 | -79611.25 | 937776.14 | 31715.58 | 75 | 0 | 46 | -29
HOUSTON | GALVESTON | SH 87 | 5104063 | 2018-05-23 | 699482.62 | 76894.59 | 880101.97 | 103724.76 | 139 | 0 | 92 | -47
HOUSTON | GALVESTON | SS 342 | 5108017 | 2018-08-10 | 1738923.02 | 383548.37 | 2222570.23 | 100098.84 | 45 | 0 | 36 | -9
HOUSTON | HARRIS | CR | 91272335 | 2018-08-24 | 1789743.3 | 69956.84 | 2007140.12 | 147439.98 | 200 | 0 | 190 | -10
HOUSTON | HARRIS | CS | 91270068 | 2018-03-09 | 499113.91 | 67438.9 | 470481.51 | -96071.3 | 60 | 25 | 167 | 82
HOUSTON | HARRIS | CS | 91270091 | 2018-08-13 | 1844818.4 | -5177.75 | 1813338.96 | -26301.69 | 254 | 0 | 254 | 0
HOUSTON | HARRIS | CS | 91271046 | 2018-08-10 | 4241559.87 | -247860.76 | 3873362.76 | -120336.35 | 300 | 0 | 263 | -37
HOUSTON | HARRIS | CS | 91272063 | 2018-04-24 | 1096120.32 | 82376.25 | 1171585.71 | -6910.86 | 150 | 35 | 185 | 0
HOUSTON | HARRIS | FM 1093 | 125804056 | 2018-07-26 | 2561914.38 | 55111.35 | 2862034.31 | 245008.58 | 154 | 0 | 151 | -3
HOUSTON | HARRIS | FM 1942 | 106205009 | 2018-07-10 | 3477178.18 | 494946.95 | 4001490.39 | 29365.26 | 157 | 0 | 139 | -18
HOUSTON | HARRIS | FM 1960 | 168502049 | 2018-08-24 | 546380.1 | 96561.32 | 516887.07 | -126054.35 | 120 | 79 | 209 | 10
HOUSTON | HARRIS | FM 1960 | 168503092 | 2018-05-18 | 732234.51 | 0 | 726021.9 | -6212.61 | 128 | 0 | 119 | -9
HOUSTON | HARRIS | FM 1960 | 168503096 | 2018-06-21 | 191207.77 | 76766.5 | 231971.76 | -36002.51 | 42 | 0 | 30 | -12
HOUSTON | HARRIS | FM 270 | 331201008 | 2018-04-26 | 3845442.26 | 59378.15 | 3979634.3 | 74813.89 | 225 | 0 | 225 | 0
HOUSTON | HARRIS | FM 2920 | 294101024 | 2018-06-22 | 3817766.77 | 63790.29 | 4198598.09 | 317041.03 | 70 | 0 | 70 | 0
HOUSTON | HARRIS | FM 2920 | 294102050 | 2018-05-25 | 2999793.89 | 11558.22 | 3081227.87 | 69875.76 | 75 | 6 | 81 | 0
HOUSTON | HARRIS | FM 529 | 100601071 | 2018-04-18 | 937479.52 | 52988.1 | 1062708.61 | 72240.99 | 44 | 0 | 33 | -11
HOUSTON | HARRIS | FM 529 | 100601072 | 2018-03-14 | 92050.2 | 0 | 95138.37 | 3088.17 | 30 | 0 | 14 | -16
HOUSTON | HARRIS | IH 10 | 27106121 | 2018-08-20 | 1856137.55 | 220685.35 | 2044276.46 | -32546.44 | 90 | 0 | 83 | -7
HOUSTON | HARRIS | IH 10 | 27107242 | 2018-06-28 | 48579333.53 | 5800447 | 58299846.45 | 3920065.92 | 777 | 184 | 917 | -44
HOUSTON | HARRIS | IH 10 | 27107292 | 2018-05-10 | 3594471.43 | 571671.63 | 4142768.61 | -23374.45 | 156 | 0 | 156 | 0
HOUSTON | HARRIS | IH 10 | 27107304 | 2018-08-21 | 2096611.52 | 265380.34 | 2215397.93 | -146593.93 | 186 | 0 | 183 | -3
HOUSTON | HARRIS | IH 10 | 50801341 | 2018-03-13 | 1482325.53 | 0 | 1511119.46 | 28793.93 | 119 | 0 | 105 | -14
HOUSTON | HARRIS | IH 45 | 11006136 | 2018-05-11 | 279667.05 | 7312.16 | 315760.18 | 28780.97 | 60 | 0 | 56 | -4
HOUSTON | HARRIS | IH 45 | 50003571 | 2018-03-26 | 3594528.4 | 2909733.01 | 6727414.71 | 223153.3 | 195 | 0 | 147 | -48
HOUSTON | HARRIS | IH 610 | 27116134 | 2018-03-20 | 699002 | 12491.84 | 735083.47 | 23589.63 | 123 | 19 | 145 | 3
HOUSTON | HARRIS | SH 146 | 38905119 | 2018-04-25 | 11747790.36 | 1628336.48 | 13276037.8 | -100089.04 | 273 | 30 | 301 | -2
HOUSTON | HARRIS | SH 225 | 50201210 | 2018-08-24 | 2602026.6 | 153276.62 | 2834757.26 | 79454.04 | 45 | 18 | 92 | 29
HOUSTON | HARRIS | SH 249 | 72003128 | 2018-05-16 | 254036.09 | 0 | 323420.8 | 69384.71 | 58 | 0 | 55 | -3
HOUSTON | HARRIS | SL 8 | 325601102 | 2018-03-15 | 611048.35 | 27845.93 | 661422.74 | 22528.46 | 134 | 0 | 102 | -32
HOUSTON | HARRIS | SS 527 | 2715026 | 2018-05-10 | 2585958.26 | 60639.33 | 3246444.65 | 599847.06 | 220 | 15 | 196 | -39
HOUSTON | HARRIS | US 59 | 2713190 | 2018-04-13 | 18777770 | 1195250.25 | 20569519.91 | 596499.66 | 478 | 2 | 480 | 0
HOUSTON | HARRIS | VA | 91200278 | 2018-04-11 | 152984.75 | 6137.2 | 199872.77 | 40750.82 | 60 | 0 | 62 | 2
HOUSTON | HARRIS | VA | 91200381 | 2018-05-25 | 1787199.58 | 16862.56 | 1941468.09 | 137405.95 | 432 | 0 | 382 | -50
HOUSTON | HARRIS | VA | 91200440 | 2018-08-10 | 772662.59 | -21420 | 873562.59 | 122320 | 135 | 0 | 129 | -6
HOUSTON | HARRIS | VA | 91200441 | 2018-05-09 | 1210347.9 | 0 | 1196045.68 | -14302.22 | 500 | 0 | 141 | -359
HOUSTON | HARRIS | VA | 91200484 | 2018-06-25 | 557849.99 | 0 | 615497.43 | 57647.44 | 94 | 0 | 103 | 9
HOUSTON | HARRIS | VA | 91200488 | 2018-05-09 | 1394256.88 | 84513.91 | 1486945.29 | 8174.5 | 180 | 0 | 151 | -29
HOUSTON | HARRIS | VA | 91270094 | 2018-07-18 | 1698653.4 | 1628671.75 | 3890808.88 | 563483.73 | 304 | 16 | 292 | -28
HOUSTON | HARRIS | VA | 91270099 | 2018-05-10 | 2767522.71 | -218768 | 2056706.76 | -492047.95 | 244 | 0 | 395 | 151
HOUSTON | HARRIS | VA | 91270100 | 2018-07-20 | 3140223.08 | -125739.12 | 2754750.42 | -259733.54 | 203 | 0 | 222 | 19
HOUSTON | HARRIS | VA | 91272294 | 2018-04-26 | 1678207.72 | 0 | 1790145.24 | 111937.52 | 190 | 0 | 185 | -5
HOUSTON | MONTGOMERY | FM 1097 | 125901036 | 2018-07-31 | 5567522.75 | 291218.38 | 5831731.09 | -27010.04 | 155 | 11 | 231 | 65
HOUSTON | MONTGOMERY | FM 149 | 72002091 | 2018-06-05 | 273413.21 | 0 | 273413.21 | 0 | 25 | 0 | 6 | -19
HOUSTON | MONTGOMERY | SH 242 | 353801044 | 2018-05-15 | 275772.88 | -173060.98 | 102734.4 | 22.5 | 38 | 0 | 28 | -10
HOUSTON | WALLER | FM 362 | 94402010 | 2018-07-09 | 569694.87 | 0 | 596907.12 | 27212.25 | 30 | 0 | 9 | -21
HOUSTON | WALLER | IH 10 | 27104091 | 2018-03-15 | 4962242.32 | 211476 | 5670759.47 | 497041.15 | 90 | 27 | 112 | -5
HOUSTON | WALLER | US 290 | 11411076 | 2018-08-01 | 181056.63 | 33925.25 | 246768.35 | 31786.47 | 23 | 0 | 16 | -7
LAREDO | DIMMIT | US 277 | 30003066 | 2018-03-13 | 9546333.92 | -811140.69 | 9226755.49 | 491562.26 | 205 | 0 | 196 | -9
LAREDO | DUVAL | SH 359 | 8610049 | 2018-04-12 | 14344014.45 | 291020.02 | 14169236.32 | -465798.15 | 263 | 0 | 258 | -5
LAREDO | LA SALLE | CS | 92220019 | 2018-04-12 | 242635.1 | 4638 | 240868.91 | -6404.19 | 90 | 0 | 90 | 0
LAREDO | LA SALLE | IH 35 | 1801076 | 2018-06-26 | 1622860.21 | 97642.21 | 1760807.45 | 40305.03 | 80 | 0 | 77 | -3
LAREDO | LA SALLE | IH 35 | 1802064 | 2018-04-12 | 6908417.36 | 443972.96 | 7342513.79 | -9876.53 | 195 | 26 | 221 | 0
LAREDO | LA SALLE | SH 97 | 32808022 | 2018-08-24 | 8315541.28 | -242507.32 | 8045978 | -27055.96 | 373 | -70 | 328 | 25
LAREDO | MAVERICK | US 277 | 29904070 | 2018-05-29 | 315267.29 | 5424.07 | 300749.17 | -19942.19 | 112 | 96 | 235 | 27
LAREDO | WEBB | SL 20 | 8614046 | 2018-08-09 | 35877887.89 | 174070.1 | 34672878.2 | -1379079.79 | 535 | 26 | 560 | -1
LAREDO | WEBB | SL 20 | 8614066 | 2018-08-09 | 21976081.15 | 317853.25 | 21696972.65 | -596961.75 | 387 | 107 | 494 | 0
LAREDO | WEBB | US 59 | 54201083 | 2018-07-16 | 1680643.3 | 69468.02 | 1754099.04 | 3987.72 | 145 | 0 | 140 | -5
LAREDO | WEBB | US 83 | 3801086 | 2018-05-29 | 7537201.74 | 218217.15 | 7905224.46 | 149805.57 | 161 | 0 | 155 | -6
LAREDO | ZAVALA | FM 1025 | 127901036 | 2018-05-21 | 7134438.21 | 357283.9 | 7219160.71 | -272561.4 | 322 | 0 | 317 | -5
LUBBOCK | LUBBOCK | FM 1730 | 134402019 | 2018-04-27 | 14189419.29 | 752311.84 | 14779035.14 | -162695.99 | 340 | 236 | 563 | -13
LUBBOCK | LUBBOCK | SL 289 | 78302096 | 2018-05-07 | 491471.2 | 32843.98 | 514743.35 | -9571.83 | 47 | 3 | 51 | 1
LUBBOCK | LUBBOCK | US 62 | 13005083 | 2018-04-10 | 2625994.43 | 367963.49 | 2976235.44 | -17722.48 | 102 | 75 | 177 | 0
LUBBOCK | LUBBOCK | US 62 | 38001078 | 2018-07-31 | 40862362.88 | 1549542.41 | 41132908.1 | -1278997.19 | 644 | 90 | 692 | -42
LUBBOCK | LUBBOCK | US 62 | 38001083 | 2018-04-10 | 14583864.95 | 69152.45 | 15638488.31 | 985470.91 | 287 | 195 | 482 | 0
LUBBOCK | LUBBOCK | US 62 | 38001085 | 2018-08-03 | 17312700 | 74492.09 | 16683221.3 | -703970.79 | 204 | 3 | 204 | -3
LUBBOCK | LUBBOCK | US 82 | 13108020 | 2018-04-19 | 6485131.99 | 351775.89 | 6503577.14 | -333330.74 | 136 | 97 | 241 | 8
LUBBOCK | LUBBOCK | US 84 | 5207061 | 2018-05-04 | 28981348.52 | 1079236.86 | 30175499.31 | 114913.93 | 459 | 70 | 449 | -80
LUBBOCK | LUBBOCK | US 84 | 5207070 | 2018-03-20 | 5963457.12 | 176501.6 | 6107296.57 | -32662.15 | 68 | 15 | 83 | 0
LUBBOCK | LUBBOCK | US 87 | 6801069 | 2018-08-03 | 7340564.16 | 1223984.28 | 8719004.32 | 154455.88 | 85 | 176 | 259 | -2
LUBBOCK | LUBBOCK | VA | 90500074 | 2018-04-10 | 3617791.56 | 10362.48 | 3396351.52 | -231802.52 | 100 | 48 | 158 | 10
LUBBOCK | LUBBOCK | VA | 90500079 | 2018-03-19 | 2988537.45 | 98848.75 | 3088247.64 | 861.44 | 213 | 25 | 358 | 120
LUBBOCK | LUBBOCK | VA | 90500082 | 2018-08-20 | 3492691.68 | 914639.89 | 4305002.45 | -102329.12 | 100 | 60 | 177 | 17
LUBBOCK | LUBBOCK | VA | 90500090 | 2018-06-05 | 691771.5 | 0 | 707472.11 | 15700.61 | 90 | 0 | 86 | -4
LUBBOCK | PARMER | SH 86 | 30201020 | 2018-08-27 | 1044122 | 0 | 1010633.68 | -33488.32 | 116 | 0 | 70 | -46
LUBBOCK | SWISHER | US 87 | 6718007 | 2018-06-22 | 2600518.07 | -325690.05 | 2727158.91 | 452330.89 | 36 | 0 | 28 | -8
LUFKIN | ANGELINA | FM 1194 | 296001012 | 2018-06-05 | 459200.62 | 0 | 462043.67 | 2843.05 | 50 | 0 | 27 | -23
LUFKIN | ANGELINA | US 59 | 17602120 | 2018-04-02 | 2865623.76 | 0 | 3153503.57 | 287879.81 | 77 | 0 | 76 | -1
LUFKIN | ANGELINA | US 59 | 255301117 | 2018-05-22 | 1891195.25 | 52969 | 1929534.55 | -14629.7 | 113 | 16 | 123 | -6
LUFKIN | ANGELINA | US 69 | 20001083 | 2018-08-16 | 1576982.23 | 6068.2 | 1505216.16 | -77834.27 | 37 | 1 | 34 | -4
LUFKIN | ANGELINA | US 69 | 20002042 | 2018-08-21 | 890456.22 | 0 | 862969.59 | -27486.63 | 109 | 0 | 133 | 24
LUFKIN | HOUSTON | CR | 91128033 | 2018-03-28 | 619443.5 | 0 | 592860.35 | -26583.15 | 62 | 0 | 50 | -12
LUFKIN | HOUSTON | FM 227 | 93703013 | 2018-05-03 | 2633662.02 | 9944.73 | 2644384.39 | 777.64 | 161 | 23 | 189 | 5
LUFKIN | HOUSTON | SH 19 | 10906041 | 2018-07-17 | 294820.39 | 0 | 248518.37 | -46302.02 | 40 | 0 | 18 | -22
LUFKIN | HOUSTON | SH 21 | 11801019 | 2018-07-31 | 2981766.6 | 0 | 2884379.82 | -97386.78 | 211 | 0 | 208 | -3
LUFKIN | NACOGDOCHES | FM 1087 | 92605008 | 2018-06-14 | 775621.06 | 0 | 880952.93 | 105331.87 | 137 | 0 | 132 | -5
LUFKIN | NACOGDOCHES | FM 1275 | 140703016 | 2018-04-02 | 272731.7 | 15410 | 295149.4 | 7007.7 | 40 | 10 | 48 | -2
LUFKIN | NACOGDOCHES | FM 1878 | 181001032 | 2018-08-02 | 1774829.45 | 102728 | 2079356.3 | 201798.85 | 115 | 33 | 158 | 10
LUFKIN | NACOGDOCHES | FM 343 | 92602011 | 2018-06-01 | 4724025.62 | 2081.34 | 4490641.83 | -235465.13 | 175 | 0 | 144 | -31
LUFKIN | NACOGDOCHES | US 59 | 17601094 | 2018-03-27 | 14030469.7 | 444641.82 | 14188491.72 | -286619.8 | 532 | 37 | 562 | -7
LUFKIN | POLK | CR | 91104034 | 2018-03-29 | 885751 | 4800 | 880350.35 | -10200.65 | 128 | 4 | 135 | 3
LUFKIN | POLK | CR | 91104067 | 2018-03-14 | 1019437.73 | 5631.3 | 1033599.05 | 8530.02 | 121 | 3 | 113 | -11
LUFKIN | POLK | CR | 91104072 | 2018-07-23 | 1452873.79 | 12682.57 | 1474968.25 | 9411.89 | 252 | 4 | 164 | -92
LUFKIN | POLK | CR | 91104080 | 2018-04-26 | 1091491.65 | 1251.4 | 1104534.08 | 11791.03 | 150 | 2 | 142 | -10
LUFKIN | POLK | CR | 91104083 | 2018-04-30 | 812182.78 | 5054 | 808472.18 | -8764.6 | 83 | 4 | 91 | 4
LUFKIN | POLK | FM 1316 | 251001016 | 2018-06-07 | 568648.5 | 2630 | 560571.2 | -10707.3 | 93 | 2 | 89 | -6
LUFKIN | POLK | US 190 | 21303097 | 2018-03-20 | 13913635.96 | 47374.19 | 13590992.57 | -370017.58 | 223 | 0 | 222 | -1
LUFKIN | POLK | US 59 | 17701102 | 2018-07-02 | 2215251.08 | 48793.52 | 2331438.31 | 67393.71 | 55 | 18 | 69 | -4
LUFKIN | SAN AUGUSTINE | FM 705 | 107901031 | 2018-08-02 | 1266570.98 | 25334.93 | 1252923.1 | -38982.81 | 336 | 0 | 325 | -11
LUFKIN | SAN AUGUSTINE | SH 21 | 6404038 | 2018-04-05 | 1848256.1 | 6704.52 | 1763208.06 | -91752.56 | 176 | 0 | 198 | 22
LUFKIN | SAN AUGUSTINE | US 96 | 80903038 | 2018-06-05 | 7319958.62 | 20801.73 | 7021873.52 | -318886.83 | 149 | 34 | 199 | 16
LUFKIN | SHELBY | US 84 | 17501005 | 2018-05-01 | 20412099.61 | 699346.51 | 20993514.31 | -117931.81 | 611 | 227 | 883 | 45
ODESSA | ECTOR | IH 20 | 407126 | 2018-06-12 | 3196509.8 | 0 | 3343307.46 | 146797.66 | 107 | 0 | 105 | -2
ODESSA | ECTOR | SL 338 | 222401087 | 2018-04-26 | 2347299 | 54216.53 | 2366716.59 | -34798.94 | 117 | 30 | 145 | -2
ODESSA | MARTIN | IH 20 | 504069 | 2018-04-04 | 759179.12 | -18672.63 | 721481.7 | -19024.79 | 260 | 0 | 286 | 26
ODESSA | MARTIN | IH 20 | 504072 | 2018-03-20 | 1987502.23 | 0 | 2016414.09 | 28911.86 | 88 | 0 | 57 | -31
ODESSA | MIDLAND | IH 20 | 514080 | 2018-06-22 | 11801426.99 | 462346.7 | 12115885.43 | -147888.26 | 210 | 131 | 333 | -8
ODESSA | MIDLAND | SH 349 | 171807042 | 2018-06-22 | 6917371.67 | 632353.5 | 7614640.66 | 64915.49 | 160 | 68 | 227 | -1
ODESSA | PECOS | US 285 | 13908037 | 2018-03-20 | 1244957 | 93678.07 | 1398058.56 | 59423.49 | 58 | 30 | 82 | -6
ODESSA | REEVES | US 285 | 13905044 | 2018-04-24 | 936605.4 | 45000 | 1004197.69 | 22592.29 | 75 | 0 | 80 | 5
ODESSA | UPTON | SH 349 | 38011025 | 2018-08-06 | 17114217.07 | 85739.09 | 17633900.19 | 433944.03 | 374 | 40 | 410 | -4
ODESSA | WARD | IH 20 | 404086 | 2018-06-12 | 14274035.01 | 46835 | 13612299.98 | -708570.03 | 327 | 0 | 271 | -56
ODESSA | WARD | IH 20 | 404087 | 2018-05-24 | 13195417.33 | 139638.5 | 13715024.37 | 379968.54 | 351 | 20 | 217 | -154
PARIS | FRANKLIN | US 67 | 1004021 | 2018-05-20 | 382000 | -2266.44 | 392758.35 | 13024.79 | 36 | 0 | 36 | 0
PARIS | GRAYSON | FM 120 | 72802029 | 2018-04-30 | 2460214.08 | -201182.46 | 2294996.72 | 35965.1 | 116 | 14 | 150 | 20
PARIS | GRAYSON | FM 121 | 72902026 | 2018-05-14 | 1590415.6 | -549 | 1563025.49 | -26841.11 | 234 | 0 | 243 | 9
PARIS | GRAYSON | SH 5 | 4703075 | 2018-08-24 | 3711917.79 | 652505.66 | 4263227.46 | -101195.99 | 107 | 36 | 191 | 48
PARIS | GRAYSON | SH 56 | 4503043 | 2018-06-26 | 1696316.58 | 0 | 1743367.61 | 47051.03 | 56 | 0 | 43 | -13
PARIS | HOPKINS | FM 900 | 68005008 | 2018-04-06 | 1570944.58 | 39123.4 | 1584187.58 | -25880.4 | 270 | 0 | 277 | 7
PARIS | HOPKINS | SH 11 | 8302048 | 2018-06-22 | 5504239.11 | -411786.25 | 5191556.73 | 99103.87 | 231 | 0 | 180 | -51
PARIS | HUNT | FM 272 | 76402011 | 2018-07-24 | 3455817.16 | 152268.99 | 3658619.39 | 50533.24 | 202 | 2 | 200 | -4
PARIS | HUNT | IH 30 | 913163 | 2018-04-16 | 8807758.17 | 5045.22 | 8241518.99 | -571284.4 | 65 | 0 | 68 | 3
PARIS | HUNT | SH 276 | 64101033 | 2018-03-02 | 47845878.71 | 1214671.48 | 49060109.82 | -440.37 | 671 | 254 | 925 | 0
PARIS | LAMAR | CR | 90129084 | 2018-06-22 | 724233.9 | 0 | 731152.2 | 6918.3 | 213 | 0 | 174 | -39
PARIS | RED RIVER | FM 44 | 42701037 | 2018-06-22 | 4617291.21 | -83474.74 | 4467997.98 | -65818.49 | 222 | 4 | 244 | 18
PHARR | CAMERON | IH 69E | 3908099 | 2018-08-14 | 6778722.86 | 820948.91 | 7827524.05 | 227852.28 | 100 | 38 | 138 | 0
PHARR | CAMERON | SH 345 | 63001051 | 2018-04-06 | 296534 | 130680 | 454138.7 | 26924.7 | 80 | 35 | 92 | -23
PHARR | CAMERON | US 281 | 22003028 | 2018-03-16 | 7709997.35 | 424911.52 | 8302738.92 | 167830.05 | 400 | 49 | 477 | 28
PHARR | HIDALGO | BU 83-S | 3904122 | 2018-07-24 | 525149.3 | 0 | 535437.6 | 10288.3 | 160 | 0 | 160 | 0
PHARR | HIDALGO | FM 1925 | 180301037 | 2018-06-29 | 8117383.1 | 7590.31 | 8560281.28 | 435307.87 | 420 | 0 | 285 | -135
PHARR | HIDALGO | FM 88 | 69802052 | 2018-08-07 | 428221.04 | 22697.18 | 453371.18 | 2452.96 | 125 | 0 | 35 | -90
PHARR | HIDALGO | IH 2 | 3918009 | 2018-05-09 | 286920 | 2525.76 | 321245.74 | 31799.98 | 60 | 0 | 30 | -30
PHARR | HIDALGO | US 281 | 25506065 | 2018-05-31 | 16896197.77 | 0 | 17284317.4 | 388119.63 | 280 | 0 | 278 | -2
PHARR | HIDALGO | US 83 | 3917176 | 2018-06-20 | 35990313.96 | 3327162.55 | 39891542.01 | 574065.5 | 626 | 179 | 805 | 0
PHARR | ZAPATA | US 83 | 3803034 | 2018-04-19 | 6674470.78 | 206461.47 | 7349987.46 | 469055.21 | 280 | 169 | 446 | -3
SAN ANGELO | CONCHO | US 87 | 7004035 | 2018-04-18 | 7317864.52 | 40197.47 | 6713718.82 | -644343.17 | 87 | 0 | 95 | 8
SAN ANGELO | IRION | RL SO | 710708004 | 2018-06-07 | 5357270.94 | 0 | 5354314.17 | -2956.77 | 199 | 15 | 214 | 0
SAN ANGELO | KIMBLE | SL 481 | 14120009 | 2018-08-13 | 1146308.58 | 44786.32 | 1100764.87 | -90330.03 | 112 | 3 | 117 | 2
SAN ANGELO | MENARD | US 83 | 3505057 | 2018-03-22 | 1881273.2 | -19048 | 1945021.81 | 82796.61 | 80 | 0 | 65 | -15
SAN ANGELO | REAL | RM 336 | 55401034 | 2018-07-19 | 1191740 | 0 | 1198940 | 7200 | 77 | 0 | 72 | -5
SAN ANGELO | REAL | US 83 | 3605033 | 2018-07-05 | 6989144.86 | 295531.64 | 7457844.94 | 173168.44 | 225 | 153 | 392 | 14
SAN ANGELO | RUNNELS | US 83 | 3405039 | 2018-06-04 | 14622336.57 | 406904.18 | 15455875.33 | 426634.58 | 304 | 208 | 536 | 24
SAN ANGELO | TOM GREEN | US 87 | 6907105 | 2018-07-06 | 5416629.76 | 791064.43 | 6613007.22 | 405313.03 | 126 | 7 | 133 | 0
SAN ANGELO | TOM GREEN | VA | 90700167 | 2018-06-18 | 689377.2 | 0 | 685987.6 | -3389.6 | 40 | 0 | 27 | -13
SAN ANTONIO | BANDERA | SH 16 | 29104024 | 2018-06-28 | 4845061.91 | -244129.88 | 4566982.07 | -33949.96 | 442 | -33 | 444 | 35
SAN ANTONIO | BEXAR | FM 1560 | 223001016 | 2018-07-09 | 1447520.48 | 38000 | 1578452.77 | 92932.29 | 181 | 0 | 173 | -8
SAN ANTONIO | BEXAR | IH 10 | 7208120 | 2018-06-28 | 35968285.3 | 4649382.86 | 41844808.28 | 1227140.12 | 698 | 312 | 1031 | 21
SAN ANTONIO | BEXAR | IH 10 | 7212197 | 2018-04-11 | 1177187.95 | 248402.58 | 1566687.38 | 141096.85 | 59 | 18 | 77 | 0
SAN ANTONIO | BEXAR | US 281 | 7308173 | 2018-06-28 | 143550 | 0 | 145767.16 | 2217.16 | 46 | 0 | 23 | -23
SAN ANTONIO | COMAL | FM 306 | 172802058 | 2018-06-21 | 7936418.82 | 96770.25 | 8444904.53 | 411715.46 | 364 | 59 | 421 | -2
SAN ANTONIO | COMAL | IH 35 | 1604111 | 2018-03-19 | 5557723.41 | 147229.62 | 5405810.4 | -299142.63 | 168 | 9 | 175 | -2
SAN ANTONIO | COMAL | IH 35 | 1605109 | 2018-03-19 | 6295132.13 | 498302.77 | 7228265.57 | 434830.67 | 159 | 0 | 126 | -33
SAN ANTONIO | COMAL | IH 35 | 1605113 | 2018-07-24 | 716940.08 | 0 | 729515.79 | 12575.71 | 240 | 0 | 233 | -7
SAN ANTONIO | COMAL | SH 46 | 21601051 | 2018-07-11 | 3011597.6 | 158105.1 | 3199447.13 | 29744.43 | 122 | 3 | 124 | -1
SAN ANTONIO | GUADALUPE | FM 3009 | 310702034 | 2018-03-16 | 3240269.5 | 129395.28 | 3361294.86 | -8369.92 | 123 | 49 | 171 | -1
SAN ANTONIO | GUADALUPE | FM 466 | 21603032 | 2018-04-23 | 1436279.68 | 269389.11 | 1714160.27 | 8491.48 | 218 | 0 | 153 | -65
SAN ANTONIO | KENDALL | CR | 91511031 | 2018-03-28 | 1522927.91 | 3606.53 | 1526534.44 | 2.774e-11 | 268 | 0 | 180 | -88
SAN ANTONIO | UVALDE | SH 127 | 36901033 | 2018-03-28 | 2838089.05 | 151970.96 | 2907635.1 | -82424.91 | 190 | 120 | 415 | 105
SAN ANTONIO | WILSON | SH 123 | 36605044 | 2018-05-21 | 611559.93 | 10070.68 | 585628.41 | -36002.2 | 33 | 5 | 37 | -1
SAN ANTONIO | WILSON | US 87 | 14305032 | 2018-06-21 | 9551891.66 | -98049.61 | 9673854.04 | 220011.99 | 138 | 0 | 138 | 0
TYLER | ANDERSON | CR | 91008067 | 2018-06-11 | 753675.6 | 8336 | 734611.41 | -27400.19 | 108 | 10 | 124 | 6
TYLER | CHEROKEE | FM 22 | 63401012 | 2018-08-21 | 1037127 | -21931.28 | 906120.38 | -109075.34 | 110 | 0 | 115 | 5
TYLER | CHEROKEE | US 69 | 19902057 | 2018-04-16 | 9380454.05 | 184507.68 | 9352465.07 | -212496.66 | 180 | 10 | 204 | 14
TYLER | CHEROKEE | US 79 | 20604039 | 2018-05-17 | 5778866.01 | -185892.02 | 5619446.03 | 26472.04 | 150 | 0 | 168 | 18
TYLER | GREGG | FM 2087 | 193101017 | 2018-03-12 | 3698176.82 | 93404.7 | 3667947.34 | -123634.18 | 174 | 26 | 215 | 15
TYLER | GREGG | FM 2275 | 215801011 | 2018-04-11 | 12423396.89 | 293355.4 | 13236844.12 | 520091.83 | 215 | 93 | 308 | 0
TYLER | GREGG | LP 281 | 176303029 | 2018-06-11 | 13235356.94 | 431042.35 | 13977725.61 | 311326.32 | 575 | 231 | 805 | -1
TYLER | GREGG | US 259 | 39203047 | 2018-05-14 | 475527.9 | -131.29 | 441822.3 | -33574.31 | 36 | 0 | 34 | -2
TYLER | HENDERSON | FM 315 | 55902034 | 2018-08-13 | 3079333.97 | 426035.21 | 3898288.24 | 392919.06 | 175 | 3 | 177 | -1
TYLER | HENDERSON | US 175 | 19802027 | 2018-08-24 | 37849155.31 | 1119445.25 | 41998403.57 | 3029803.01 | 654 | 4 | 528 | -130
TYLER | RUSK | SH 43 | 20701021 | 2018-03-12 | 4670549.69 | 27272.29 | 4935195.04 | 237373.06 | 70 | 10 | 77 | -3
TYLER | RUSK | US 79 | 20607058 | 2018-03-12 | 6661253.87 | 795582.5 | 7458597.31 | 1760.94 | 263 | 2 | 246 | -19
TYLER | SMITH | FM 1253 | 20308015 | 2018-06-25 | 7499499.38 | -360751.28 | 7146562.41 | 7814.31 | 311 | 0 | 291 | -20
TYLER | SMITH | IH 20 | 49504067 | 2018-08-15 | 2876796.84 | -71153.9 | 2889542.6 | 83899.66 | 51 | 13 | 85 | 21
TYLER | SMITH | LP 323 | 207502045 | 2018-06-22 | 11988788.88 | -284030.07 | 12546537.21 | 841778.4 | 459 | 25 | 481 | -3
TYLER | SMITH | PW | 91016121 | 2018-03-12 | 1269696 | -14241.2 | 1195096.98 | -60357.82 | 123 | 0 | 87 | -36
TYLER | SMITH | SH 155 | 52001021 | 2018-04-11 | 5534730.86 | 6912.35 | 5720796.51 | 179153.3 | 76 | 0 | 54 | -22
TYLER | SMITH | SH 31 | 42401048 | 2018-07-30 | 7802782.95 | 52400.8 | 7971832.27 | 116648.52 | 328 | 0 | 322 | -6
TYLER | SMITH | SH 31 | 42401053 | 2018-05-17 | 1795043.65 | -14886.45 | 1619348.41 | -160808.79 | 35 | 0 | 40 | 5
TYLER | SMITH | SH 64 | 24505047 | 2018-06-22 | 1789204.91 | -55375.17 | 1649411.87 | -84417.87 | 35 | 0 | 53 | 18
TYLER | SMITH | SH 64 | 24506081 | 2018-04-16 | 3624096.35 | -77234.67 | 3718378.78 | 171517.1 | 40 | 0 | 40 | 0
TYLER | SMITH | US 271 | 16501102 | 2018-07-30 | 2038396.38 | 50127.39 | 2204633.53 | 116109.76 | 45 | 14 | 85 | 26
TYLER | SMITH | VA | 91000105 | 2018-03-12 | 1419691.25 | 225463.91 | 1599896.27 | -45258.89 | 145 | 8 | 153 | 0
TYLER | SMITH | VA | 91000108 | 2018-08-13 | 224599.5 | 22483.48 | 248265.98 | 1183 | 98 | 0 | 91 | -7
TYLER | SMITH | VA | 91016143 | 2018-08-21 | 126560 | 195.29 | 131115.29 | 4360 | 48 | 0 | 18 | -30
TYLER | WOOD | US 80 | 9602049 | 2018-08-13 | 160005 | 4474.5 | 163904.5 | -575 | 49 | 0 | 27 | -22
WACO | BELL | FM 1741 | 183502054 | 2018-03-28 | 897190.43 | 1054.98 | 813303.96 | -84941.45 | 30 | 0 | 36 | 6
WACO | BELL | FM 93 | 329201014 | 2018-05-22 | 55200.91 | -3879.67 | 51321.24 | -5.457e-12 | 30 | 0 | 24 | -6
WACO | CORYELL | FM 116 | 72401044 | 2018-04-24 | 17587091.47 | -138415.5 | 17194196.1 | -254479.87 | 510 | 4 | 505 | -9
WACO | CORYELL | FM 116 | 72401049 | 2018-06-20 | 5543320.51 | -259971.12 | 5241806.92 | -41542.47 | 340 | 0 | 313 | -27
WACO | CORYELL | US 84 | 5506033 | 2018-06-18 | 277779.4 | -30834.4 | 262133.14 | 15188.14 | 64 | 0 | 50 | -14
WACO | CORYELL | VA | 90939128 | 2018-07-03 | 663079.06 | 34929.87 | 708121.86 | 10112.93 | 107 | 0 | 104 | -3
WACO | FALLS | SH 53 | 23202021 | 2018-08-13 | 1598158.58 | 15000 | 1586366.3 | -26792.28 | 128 | 0 | 126 | -2
WACO | HILL | FM 933 | 119001043 | 2018-04-24 | 9917107.31 | 388710.58 | 10394305.43 | 88487.54 | 574 | 0 | 533 | -41
WACO | HILL | FM 934 | 183101019 | 2018-06-18 | 2487232.28 | -29289.35 | 2329803.98 | -128138.95 | 170 | 0 | 158 | -12
WACO | LIMESTONE | FM 147 | 75206022 | 2018-04-24 | 4469649.31 | 114231.21 | 4522426.48 | -61454.04 | 234 | 44 | 310 | 32
WACO | LIMESTONE | FM 2838 | 286601009 | 2018-08-24 | 1299987.08 | 68437.5 | 1290689.31 | -77735.27 | 106 | 4 | 130 | 20
WACO | MC LENNAN | FM 2311 | 217401016 | 2018-03-07 | 3380323.06 | 41127.48 | 3538827.18 | 117376.64 | 213 | 0 | 240 | 27
WACO | MC LENNAN | IH 35 | 1501237 | 2018-06-20 | 4480299.62 | 252867.84 | 4608850.02 | -124317.44 | 179 | 0 | 173 | -6
WACO | MC LENNAN | SH 6 | 4901092 | 2018-05-17 | 3877223.25 | -239395.45 | 3617246.64 | -20581.16 | 45 | 48 | 118 | 25
WACO | MC LENNAN | SH 6 | 25808032 | 2018-07-23 | 4687935.11 | 42915.23 | 4931929.85 | 201079.51 | 234 | 0 | 170 | -64
WICHITA FALLS | COOKE | FM 1201 | 135601027 | 2018-07-16 | 1250025 | 29800 | 1387824.76 | 107999.76 | 82 | 48 | 142 | 12
WICHITA FALLS | COOKE | FM 678 | 135702012 | 2018-08-14 | 1677816.78 | 0 | 1699931.12 | 22114.34 | 125 | 0 | 124 | -1
WICHITA FALLS | MONTAGUE | US 82 | 4404059 | 2018-03-08 | 4894838.28 | 42170.94 | 5165571.6 | 228562.38 | 71 | 0 | 73 | 2
WICHITA FALLS | WICHITA | SL 11 | 4314024 | 2018-08-09 | 351296.4 | 0 | 372180.13 | 20883.73 | 51 | 0 | 50 | -1
WICHITA FALLS | WICHITA | US 287 | 4309126 | 2018-07-19 | 2454758.6 | 0 | 2343685.25 | -111073.35 | 185 | 0 | 182 | -3
WICHITA FALLS | WILBARGER | US 287 | 4307109 | 2018-05-31 | 2490919.29 | 56899.28 | 2514712.57 | -33106 | 102 | 10 | 95 | -17
WICHITA FALLS | YOUNG | FM 61 | 52901023 | 2018-07-05 | 4288948.68 | 65151.8 | 4367416.37 | 13315.89 | 186 | 19 | 254 | 49
YOAKUM | AUSTIN | CR | 91320073 | 2018-03-23 | 538926.26 | 0 | 537514.26 | -1412 | 75 | 0 | 67 | -8
YOAKUM | AUSTIN | CR | 91320087 | 2018-03-19 | 314926.26 | 0 | 312221.76 | -2704.5 | 60 | 0 | 27 | -33
YOAKUM | CALHOUN | CR | 91319028 | 2018-03-23 | 416186.67 | 0 | 403265.94 | -12920.73 | 60 | 0 | 62 | 2
YOAKUM | COLORADO | US 90A | 44603049 | 2018-05-18 | 6297396.25 | 108541.65 | 6806494.78 | 400556.88 | 183 | 31 | 214 | 0
YOAKUM | DE WITT | CR | 91317040 | 2018-06-04 | 449866.88 | 0 | 435444.89 | -14421.99 | 60 | 0 | 69 | 9
YOAKUM | DE WITT | US 183 | 15501038 | 2018-05-09 | 4639995.05 | -55068.96 | 4667009.61 | 82083.52 | 60 | 33 | 88 | -5
YOAKUM | DE WITT | VA | 91300088 | 2018-08-21 | 475081 | 86980.34 | 578122.17 | 16060.83 | 165 | 0 | 142 | -23
YOAKUM | GONZALES | FM 443 | 83901015 | 2018-07-20 | 1222090.6 | 16952.13 | 1220735.11 | -18307.62 | 75 | 17 | 98 | 6
YOAKUM | GONZALES | US 183 | 15302039 | 2018-08-14 | 1398785.73 | 0 | 1396488.43 | -2297.3 | 30 | 0 | 43 | 13
YOAKUM | GONZALES | US 90A | 2505022 | 2018-05-21 | 11550371.74 | 90886.22 | 12203044.14 | 561786.18 | 75 | 3 | 101 | 23
YOAKUM | LAVACA | SH 95 | 32402024 | 2018-07-20 | 3147885.71 | 0 | 3387461.75 | 239576.04 | 60 | 0 | 60 | 0
YOAKUM | LAVACA | US 90A | 44601047 | 2018-06-22 | 3321678.02 | -5426.4 | 3206830.62 | -109421 | 150 | 0 | 259 | 109
YOAKUM | MATAGORDA | SH 35 | 17906042 | 2018-08-14 | 649910.64 | 14769.99 | 687047.64 | 22367.01 | 60 | 27 | 87 | 0
YOAKUM | MATAGORDA | SH 71 | 26607021 | 2018-06-04 | 3097496.79 | 0 | 2999446.88 | -98049.91 | 120 | 0 | 104 | -16
YOAKUM | WHARTON | CR | 91309056 | 2018-08-14 | 552981.25 | 0 | 554641.07 | 1659.82 | 73 | 0 | 72 | -1
YOAKUM | WHARTON | SH 71 | 26606047 | 2018-07-13 | 1713209.17 | 0 | 1663951.01 | -49258.16 | 90 | 0 | 67 | -23