## BUDGET-SCHEDULE
Required Reporting per Texas Transportation Code §201.812 –
Highway Construction Projects Completed March 1, 2019–August 31, 2019
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED
DISTRICT | COUNTY | HIGHWAY | CCSJ | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | AMOUNT PAID | UNDER/OVER BUDGET | CONTRACT DAYS | DAYS ADDED | CHARGED DAYS | UNDER/OVER SCHEDULE
ABILENE | HOWARD | IH 20 | 0005-05-109 | 2019-06-21 | 6798902.47 | 1168455.77 | 7980514.92 | -1181612.45 | 92 | 86 | 218 | -40
ABILENE | HOWARD | IH 20 | 0005-06-116 | 2019-04-23 | 1092202.76 | 58202.62 | 1149672.2 | -57469.44 | 77 | 27 | 104 | 0
ABILENE | HOWARD | IH 20 | 0005-06-117 | 2019-05-17 | 1316919.24 | 247418.73 | 1582869.36 | -265950.12 | 99 | 41 | 183 | -43
ABILENE | NOLAN | IH 20 | 0006-03-134 | 2019-07-23 | 1487306.61 | 114043.75 | 1727556.72 | -240250.11 | 113 | 53 | 171 | -5
ABILENE | TAYLOR | US 83 | 0033-06-114 | 2019-06-03 | 412646.9 | 0 | 427995.2 | -15348.3 | 60 | 0 | 28 | 32
ABILENE | TAYLOR | FM 126 | 0733-03-054 | 2019-03-25 | 1017875.26 | 136958.01 | 1185282.37 | -167407.11 | 72 | 0 | 72 | 0
ABILENE | TAYLOR | VA | 0908-00-087 | 2019-03-18 | 1386588.15 | 963832.16 | 2412691.41 | -1026103.26 | 60 | 0 | 56 | 4
AMARILLO | POTTER | IH 40 | 0090-05-097 | 2019-05-10 | 1771160.83 | 168318.55 | 1847979.54 | -76818.71 | 57 | 0 | 58 | -1
AMARILLO | CARSON | US 60 | 0169-04-036 | 2019-08-19 | 11057967.43 | 109972.07 | 12889633.11 | -1831665.68 | 155 | 0 | 204 | -49
AMARILLO | POTTER | IH 40 | 0275-01-163 | 2019-08-05 | 6982390.1 | 275818.29 | 7390004.49 | -407614.39 | 80 | 12 | 89 | 3
AMARILLO | POTTER | IH 40 | 0275-01-166 | 2019-07-01 | 26403959.25 | 4000848.77 | 30947466.63 | -4543507.38 | 560 | 67 | 623 | 4
AMARILLO | POTTER | IH 40 | 0275-01-187 | 2019-06-18 | 7472229.76 | 507772.27 | 7747796.19 | -275566.43 | 212 | 72 | 288 | -4
AMARILLO | POTTER | VA | 0904-00-171 | 2019-03-05 | 611327.01 | 0 | 613245.41 | -1918.4 | 39 | 0 | 11 | 28
ATLANTA | BOWIE | US 67 | 0010-13-092 | 2019-08-12 | 761772.13 | -154142.38 | 633795.75 | 127976.38 | 26 | 0 | 17 | 9
ATLANTA | BOWIE | US 67 | 0010-13-094 | 2019-04-22 | 1149721.78 | 0 | 1097868.88 | 51852.9 | 50 | 0 | 40 | 10
ATLANTA | BOWIE | US 82 | 0046-05-050 | 2019-07-23 | 494828.25 | 0 | 411606.72 | 83221.53 | 20 | 0 | 19 | 1
ATLANTA | CASS | SH 8 | 0062-03-042 | 2019-06-13 | 2050901.92 | 0 | 2015247.95 | 35653.97 | 125 | 0 | 64 | 61
ATLANTA | HARRISON | US 80 | 0096-07-049 | 2019-05-23 | 951647.73 | 278349.05 | 1277243.23 | -325595.5 | 155 | 8 | 164 | -1
ATLANTA | TITUS | US 271 | 0221-05-090 | 2019-06-11 | 2501081.88 | 894341.55 | 3594666.23 | -1093584.35 | 64 | 17 | 98 | -17
ATLANTA | PANOLA | FM 699 | 0394-03-040 | 2019-07-17 | 1204986.39 | 0 | 1189251.48 | 15734.91 | 113 | 0 | 100 | 13
ATLANTA | UPSHUR | SH 155 | 0520-02-037 | 2019-03-20 | 18869886.17 | 4938808.83 | 24178790.18 | -5308904.01 | 780 | 79 | 860 | -1
ATLANTA | CASS | VA | 0919-00-078 | 2019-04-22 | 378300.3 | 0 | 333193.78 | 45106.52 | 40 | 0 | 40 | 0
ATLANTA | HARRISON | VA | 0919-03-053 | 2019-03-07 | 1404255.26 | 29602.36 | 1487738.93 | -83483.67 | 175 | 0 | 161 | 14
ATLANTA | CAMP | CS | 0919-21-029 | 2019-05-23 | 309168 | 9144.81 | 303615.31 | 11220.69 | 180 | 0 | 179 | 1
ATLANTA | TITUS | FM 3417 | 3404-01-016 | 2019-06-06 | 3193652.3 | 239003.77 | 3511334.01 | -317681.71 | 97 | 0 | 92 | 5
AUSTIN | TRAVIS | IH 35 | 0015-13-380 | 2019-07-25 | 16555013.44 | 303790.19 | 17308693.88 | -753680.44 | 370 | 59 | 413 | 16
AUSTIN | TRAVIS | IH 35 | 0015-13-385 | 2019-05-07 | 320535.2 | 7425.3 | 328810.3 | -8275.1 | 120 | 0 | 67 | 53
AUSTIN | TRAVIS | IH 35 | 0015-13-391 | 2019-08-23 | 412024.72 | 58812.63 | 467098.31 | -55073.59 | 145 | -45 | 215 | -115
AUSTIN | TRAVIS | US 290 | 0113-08-077 | 2019-03-26 | 1856165.1 | 459907.97 | 2538897.15 | -682732.05 | 87 | 64 | 149 | 2
AUSTIN | TRAVIS | SL 212 | 0114-20-011 | 2019-07-26 | 1158086 | 54020.27 | 1301335.19 | -143249.19 | 58 | 41 | 99 | 0
AUSTIN | CALDWELL | US 183 | 0153-01-013 | 2019-03-29 | 1769284.15 | 241088.01 | 1991886.85 | -222602.7 | 83 | 9 | 92 | 0
AUSTIN | WILLIAMSON | US 79 | 0204-01-070 | 2019-07-25 | 110817.6 | 12501.55 | 120229.55 | -9411.95 | 42 | 0 | 36 | 6
AUSTIN | LEE | US 77 | 0211-02-026 | 2019-03-14 | 5387885.79 | 399960 | 5516051 | -128165.21 | 86 | 5 | 102 | -11
AUSTIN | BASTROP | SH 95 | 0322-01-046 | 2019-03-22 | 158863 | 6556.77 | 173312.37 | -14449.37 | 54 | 0 | 42 | 12
AUSTIN | BASTROP | SH 304 | 0573-01-037 | 2019-06-18 | 383726.44 | 0 | 378643.57 | 5082.87 | 37 | 0 | 14 | 23
AUSTIN | WILLIAMSON | RM 620 | 0683-01-095 | 2019-08-15 | 1482655.75 | -5764.35 | 1588388.31 | -105732.56 | 62 | 0 | 61 | 1
AUSTIN | TRAVIS | VA | 0914-00-406 | 2019-06-06 | 1116909 | 12817.23 | 333185.96 | 783723.04 | 730 | 0 | 354 | 376
AUSTIN | TRAVIS | VA | 0914-00-413 | 2019-04-10 | 2193468.15 | -82223.97 | 2053573.28 | 139894.87 | 63 | 0 | 37 | 26
AUSTIN | BASTROP | CR | 0914-18-110 | 2019-07-08 | 399604.26 | 5979.46 | 420710.5 | -21106.24 | 77 | 0 | 73 | 4
AUSTIN | HAYS | FM 2439 | 2293-01-030 | 2019-08-05 | 409850.1 | 56016.3 | 486675.87 | -76825.77 | 20 | 0 | 19 | 1
BEAUMONT | LIBERTY | US 90 | 0028-05-042 | 2019-05-29 | 20677586.4 | -54134.38 | 20551406.77 | 126179.63 | 540 | 69 | 611 | -2
BEAUMONT | JEFFERSON | US 90 | 0028-06-078 | 2019-04-22 | 1139171.29 | 40785.89 | 1194126.11 | -54954.82 | 60 | 0 | 54 | 6
BEAUMONT | JEFFERSON | US 90 | 0028-07-052 | 2019-04-18 | 237658 | 3461 | 239478.22 | -1820.22 | 64 | 2 | 54 | 12
BEAUMONT | ORANGE | IH 10 | 0028-11-193 | 2019-07-16 | 13089624.73 | 194721.45 | 13418620.65 | -328995.92 | 449 | 0 | 398 | 51
BEAUMONT | HARDIN | US 96 | 0065-05-146 | 2019-08-27 | 341805.45 | 5564.03 | 349087.19 | -7281.74 | 78 | 0 | 72 | 6
BEAUMONT | JEFFERSON | US 69 | 0200-14-079 | 2019-04-22 | 4643294.5 | 192257.9 | 4910943.83 | -267649.33 | 326 | 11 | 273 | 64
BEAUMONT | JASPER | SH 62 | 0243-01-050 | 2019-03-13 | 9556276.11 | 186378.74 | 10013454.93 | -457178.82 | 200 | 81 | 329 | -48
BEAUMONT | CHAMBERS | SH 146 | 0389-02-051 | 2019-05-16 | 223068.55 | 0 | 242921.85 | -19853.3 | 38 | 27 | 72 | -7
BEAUMONT | CHAMBERS | IH 10 | 0508-02-121 | 2019-06-14 | 235049.18 | 48057.39 | 289426.06 | -54376.88 | 44 | 0 | 45 | -1
BEAUMONT | LIBERTY | SH 321 | 0593-01-114 | 2019-04-26 | 1050836.68 | 21559.15 | 1044378.51 | 6458.17 | 29 | 4 | 58 | -25
BEAUMONT | LIBERTY | SH 321 | 0593-01-123 | 2019-03-04 | 845384.55 | 15106.88 | 806882.23 | 38502.32 | 30 | 0 | 29 | 1
BEAUMONT | TYLER | FM 256 | 0877-03-025 | 2019-08-20 | 539688.9 | 26550.92 | 543952.69 | -4263.79 | 75 | 0 | 73 | 2
BEAUMONT | JEFFERSON | VA | 0920-00-117 | 2019-04-26 | 718877.79 | 0 | 702554 | 16323.79 | 186 | 0 | 100 | 86
BEAUMONT | JASPER | FM 1408 | 1419-01-009 | 2019-07-22 | 1409475.08 | 66155.7 | 1473713.85 | -64238.77 | 174 | 93 | 275 | -8
BEAUMONT | CHAMBERS | FM 1410 | 1420-02-012 | 2019-08-27 | 328471.82 | 11413.51 | 344485.2 | -16013.38 | 28 | 4 | 22 | 10
BROWNWOOD | EASTLAND | SH 206 | 0007-04-126 | 2019-06-06 | 6070587.66 | -74997 | 5190396.06 | 880191.6 | 54 | 1 | 55 | 0
BROWNWOOD | EASTLAND | IH 20 | 0007-06-070 | 2019-03-14 | 16358386.58 | 406740.15 | 16614750.62 | -256364.04 | 415 | 180 | 628 | -33
BROWNWOOD | BROWN | US 67 | 0054-06-104 | 2019-08-13 | 1059136.16 | 2768.87 | 994484.8 | 64651.36 | 46 | 0 | 29 | 17
BROWNWOOD | STEPHENS | US 183 | 0257-01-041 | 2019-03-22 | 3737969.44 | 9329.35 | 4046211.98 | -308242.54 | 238 | 21 | 231 | 28
BROWNWOOD | BROWN | SH 279 | 0480-01-039 | 2019-03-22 | 1175289 | 228487.9 | 1413075.96 | -237786.96 | 34 | 0 | 34 | 0
BROWNWOOD | COLEMAN | SH 153 | 0636-01-038 | 2019-05-23 | 1682223.99 | -13414.29 | 1506337.1 | 175886.89 | 114 | 0 | 119 | -5
BROWNWOOD | BROWN | VA | 0923-00-060 | 2019-08-28 | 978221.46 | -7491.36 | 1059457.77 | -81236.31 | 50 | 0 | 32 | 18
BROWNWOOD | COMANCHE | CR | 0923-17-077 | 2019-05-13 | 636369.2 | 97962.6 | 744559.55 | -108190.35 | 68 | 26 | 97 | -3
BROWNWOOD | SAN SABA | VA | 0923-25-025 | 2019-05-13 | 151446.5 | 37409.93 | 202058.98 | -50612.48 | 54 | 0 | 49 | 5
BROWNWOOD | COMANCHE | FM 1689 | 1033-04-021 | 2019-03-11 | 2464851.85 | 9076.65 | 2394743.35 | 70108.5 | 264 | 13 | 283 | -6
BRYAN | BRAZOS | US 190 | 0049-09-073 | 2019-04-23 | 17282629.32 | 3184.45 | 15832332.31 | 1450297.01 | 104 | 0 | 99 | 5
BRYAN | BRAZOS | SH 6 | 0049-12-087 | 2019-07-31 | 9587817.87 | 3951738.93 | 13679908.55 | -4092090.68 | 288 | 190 | 478 | 0
BRYAN | GRIMES | SH 6 | 0050-03-095 | 2019-05-29 | 5968699.79 | 182654.88 | 6232194.01 | -263494.22 | 222 | 73 | 295 | 0
BRYAN | WALKER | SH 30 | 0212-02-035 | 2019-07-22 | 16587457.25 | -110562.34 | 17080952.36 | -493495.11 | 240 | 45 | 290 | -5
BRYAN | LEON | SH 7 | 0335-03-042 | 2019-08-22 | 2256435.1 | 80962.47 | 2428948.33 | -172513.23 | 137 | 23 | 160 | 0
BRYAN | FREESTONE | IH 45 | 0675-01-072 | 2019-05-22 | 1744338.76 | -12248.41 | 1746679.79 | -2341.03 | 77 | 0 | 77 | 0
BRYAN | MILAM | FM 487 | 0858-01-033 | 2019-06-26 | 5587641.64 | 15800 | 5382088.53 | 205553.11 | 150 | 4 | 242 | -88
BRYAN | BRAZOS | VA | 0917-00-042 | 2019-03-21 | 549299.8 | 816545.95 | 1379042.79 | -829742.99 | 85 | 98 | 160 | 23
CHILDRESS | KING | US 83 | 0032-06-038 | 2019-07-15 | 3231944.54 | -845.99 | 3303129.84 | -71185.3 | 59 | -25 | 32 | 2
CHILDRESS | COLLINGSWORTH | FM 338 | 0449-01-019 | 2019-04-17 | 72769.79 | 0 | 75380.98 | -2611.19 | 25 | 0 | 7 | 18
CHILDRESS | CHILDRESS | VA | 0925-00-069 | 2019-07-22 | 804836.46 | -54373.65 | 776349.1 | 28487.36 | 62 | 0 | 40 | 22
CORPUS CHRISTI | NUECES | IH 37 | 0074-06-221 | 2019-03-19 | 4615768.33 | 0 | 4482412.33 | 133356 | 85 | 17 | 102 | 0
CORPUS CHRISTI | SAN PATRICIO | US 181 | 0101-04-115 | 2019-03-20 | 933485.52 | -296.18 | 913238.66 | 20246.86 | 68 | 4 | 71 | 1
CORPUS CHRISTI | NUECES | US 77 | 0102-02-096 | 2019-05-03 | 38721708.43 | 5289939.63 | 44922273.37 | -6200564.94 | 527 | 33 | 554 | 6
CORPUS CHRISTI | ARANSAS | BS 35-L | 0180-05-064 | 2019-08-19 | 430619.9 | 0 | 390217.45 | 40402.45 | 154 | 1 | 160 | -5
CORPUS CHRISTI | SAN PATRICIO | SH 361 | 0180-10-077 | 2019-05-15 | 3335329.15 | 19991.8 | 3323040.48 | 12288.67 | 82 | 21 | 102 | 1
CORPUS CHRISTI | LIVE OAK | US 281 | 0254-02-042 | 2019-03-21 | 8925015.09 | 222665.77 | 9567331.21 | -642316.12 | 134 | 26 | 164 | -4
CORPUS CHRISTI | NUECES | IH 69E | 0373-01-103 | 2019-03-08 | 5823754.28 | 913524.11 | 7161703.04 | -1337948.76 | 199 | 62 | 261 | 0
CORPUS CHRISTI | NUECES | VA | 0916-00-214 | 2019-06-07 | 1859510.41 | 41437.4 | 1701775.56 | 157734.85 | 104 | 7 | 104 | 7
CORPUS CHRISTI | NUECES | PW | 0916-35-164 | 2019-07-11 | 2331963.36 | 213747.83 | 2620645.05 | -288681.69 | 55 | 206 | 302 | -41
CORPUS CHRISTI | JIM WELLS | CR | 0916-37-030 | 2019-05-22 | 348040.69 | 51349.66 | 388315.24 | -40274.55 | 75 | 30 | 145 | -40
DALLAS | DALLAS | SH 66 | 0009-03-047 | 2019-07-30 | 399625.73 | 0 | 393510.18 | 6115.55 | 64 | 0 | 62 | 2
DALLAS | ROCKWALL | SH 66 | 0009-04-066 | 2019-08-22 | 2226102 | 131844.47 | 2388817.97 | -162715.97 | 146 | 47 | 206 | -13
DALLAS | COLLIN | US 75 | 0047-06-139 | 2019-06-26 | 47531666.94 | 4211923.27 | 51979898.1 | -4448231.16 | 766 | 104 | 875 | -5
DALLAS | COLLIN | US 75 | 0047-06-162 | 2019-05-03 | 1230202.68 | 138466.5 | 1286135.1 | -55932.42 | 83 | 46 | 130 | -1
DALLAS | DALLAS | US 75 | 0047-07-229 | 2019-06-26 | 834793.5 | 39002 | 608769.93 | 226023.57 | 148 | 0 | 205 | -57
DALLAS | ELLIS | US 77 | 0048-03-091 | 2019-04-16 | 829774.11 | 18148.8 | 760627.75 | 69146.36 | 81 | 0 | 80 | 1
DALLAS | ELLIS | IH 35E | 0048-08-049 | 2019-05-03 | 35775602.93 | 850132.1 | 36330650.52 | -555047.59 | 453 | 59 | 562 | -50
DALLAS | DENTON | IH 35W | 0081-13-041 | 2019-03-05 | 15427421.65 | 2681596.38 | 17989497.19 | -2430075.54 | 486 | 59 | 536 | 9
DALLAS | DENTON | IH 35W | 0081-13-063 | 2019-04-15 | 11361086.24 | -1615127.87 | 9897379.3 | 1463706.94 | 104 | 5 | 107 | 2
DALLAS | COLLIN | SH 289 | 0091-03-025 | 2019-07-31 | 1375000 | -37941.67 | 1262623.73 | 112376.27 | 265 | 0 | 204 | 61
DALLAS | ELLIS | SS 469 | 0092-15-002 | 2019-03-01 | 2889061.76 | 454954.92 | 3040524.6 | -151462.84 | 126 | 19 | 131 | 14
DALLAS | KAUFMAN | SH 34 | 0173-03-040 | 2019-03-26 | 1757483.94 | -527394.28 | 1129291.47 | 628192.47 | 103 | -21 | 135 | -53
DALLAS | DALLAS | SS 366 | 0196-07-033 | 2019-05-14 | 865310.53 | 0 | 927829.61 | -62519.08 | 180 | 0 | 179 | 1
DALLAS | KAUFMAN | US 175 | 0197-03-073 | 2019-07-02 | 2389678.4 | -138058.18 | 2260932.75 | 128745.65 | 99 | 3 | 145 | -43
DALLAS | COLLIN | SH 78 | 0281-02-039 | 2019-03-22 | 21337007.6 | 3144049.81 | 21926224.05 | -311923.58 | 630 | 186 | 876 | -60
DALLAS | KAUFMAN | IH 20 | 0495-01-074 | 2019-04-26 | 9178944.72 | 554184.16 | 9789448.02 | -610503.3 | 120 | 8 | 127 | 1
DALLAS | COLLIN | SH 121 | 0549-03-025 | 2019-03-11 | 14843626.57 | 697734.78 | 15322493.89 | -478867.32 | 415 | 0 | 414 | 1
DALLAS | ELLIS | FM 66 | 0596-02-042 | 2019-08-22 | 2085055.65 | 426373.43 | 2481566.75 | -396511.1 | 159 | 155 | 299 | 15
DALLAS | ELLIS | FM 878 | 0596-04-041 | 2019-06-03 | 6987285.33 | 11533.79 | 6062570.88 | 924714.45 | 225 | 77 | 303 | -1
DALLAS | KAUFMAN | FM 148 | 0751-03-037 | 2019-03-13 | 1359589.42 | 32092.41 | 1327691.85 | 31897.57 | 244 | 0 | 223 | 21
DALLAS | ELLIS | FM 875 | 0815-08-031 | 2019-06-28 | 8799580.97 | 339551.93 | 8885008.4 | -85427.43 | 287 | 23 | 310 | 0
DALLAS | COLLIN | FM 981 | 1012-03-018 | 2019-08-30 | 1885537.1 | 3392.16 | 1817076.22 | 68460.88 | 126 | 0 | 109 | 17
DALLAS | COLLIN | FM 546 | 1013-01-026 | 2019-04-26 | 17391616.98 | 152252.35 | 17452769.25 | -61152.27 | 411 | 0 | 395 | 16
DALLAS | ELLIS | FM 85 | 1050-01-017 | 2019-06-26 | 12874396.21 | 871804.96 | 13088339.03 | -213942.82 | 490 | 34 | 577 | -53
DALLAS | DALLAS | IH 30 | 1068-04-148 | 2019-05-22 | 7991673.3 | 913153.74 | 8804320.03 | -812646.73 | 380 | 37 | 377 | 40
DALLAS | KAUFMAN | FM 1388 | 1217-03-019 | 2019-08-22 | 22041072.58 | 322490.46 | 21983133.41 | 57939.17 | 580 | 0 | 579 | 1
DALLAS | ROCKWALL | SH 276 | 1290-03-024 | 2019-08-23 | 1258635.45 | 40665.17 | 1331540.15 | -72904.7 | 74 | 0 | 53 | 21
DALLAS | DENTON | FM 423 | 1315-02-009 | 2019-07-11 | 29826069.73 | 1634176.34 | 32109503.89 | -1934447.13 | 603 | 18 | 680 | -59
DALLAS | ELLIS | FM 55 | 1451-01-020 | 2019-08-22 | 2010620.16 | 11992.34 | 1976551.69 | 34068.47 | 340 | 0 | 627 | -287
DALLAS | COLLIN | FM 1461 | 1973-01-014 | 2019-04-08 | 2697083.13 | -54066.95 | 2701632.2 | -4549.07 | 148 | 0 | 148 | 0
DALLAS | DALLAS | IH 635 | 2374-01-187 | 2019-03-04 | 3522310.64 | 116766.71 | 3480954.15 | 41356.49 | 185 | 29 | 218 | -4
DALLAS | COLLIN | FM 2933 | 2977-01-008 | 2019-06-26 | 1562281.63 | 26159.18 | 1515479.41 | 46802.22 | 86 | 0 | 88 | -2
EL PASO | PRESIDIO | US 90 | 0020-06-017 | 2019-05-29 | 7823711.77 | -897549.51 | 6797936.62 | 1025775.15 | 80 | 0 | 17 | 63
EL PASO | EL PASO | VA | 0924-00-098 | 2019-04-23 | 783671.49 | 51889.38 | 819935.76 | -36264.27 | 80 | 10 | 90 | 0
FORT WORTH | PARKER | US 180 | 0008-03-116 | 2019-07-11 | 4502728.59 | 19051.97 | 3882879.71 | 619848.88 | 86 | 38 | 124 | 0
FORT WORTH | TARRANT | IH 820 | 0008-13-239 | 2019-08-22 | 655000 | 16253.48 | 737146.42 | -71382.38 | 39 | 11 | 43 | 7
FORT WORTH | JOHNSON | IH 35W | 0014-03-096 | 2019-03-21 | 459534.39 | 4245.46 | 457515.45 | 2018.94 | 100 | 0 | 51 | 49
FORT WORTH | TARRANT | IH 35W | 0014-16-255 | 2019-04-16 | 123285892.6 | 3881224.42 | 127462001.29 | -4176108.69 | 847 | 547 | 1540 | -146
FORT WORTH | ERATH | US 67 | 0079-05-054 | 2019-04-08 | 4655723.69 | 248120.84 | 5062118.08 | -406394.39 | 76 | 17 | 154 | -61
FORT WORTH | ERATH | US 67 | 0079-05-057 | 2019-04-18 | 8357383.92 | -847631.25 | 7815477.71 | 541906.21 | 70 | 13 | 83 | 0
FORT WORTH | PARKER | US 377 | 0080-06-030 | 2019-03-01 | 7889839.76 | 582112.87 | 8661949.36 | -772109.6 | 154 | 79 | 233 | 0
FORT WORTH | PARKER | SH 199 | 0171-03-067 | 2019-05-10 | 3096310.69 | -271804.59 | 2842858.61 | 253452.08 | 128 | 0 | 120 | 8
FORT WORTH | PARKER | SH 171 | 0365-01-046 | 2019-03-22 | 810034.93 | 36798.28 | 880159.13 | -70124.2 | 26 | 0 | 28 | -2
FORT WORTH | HOOD | FM 4 | 0385-02-029 | 2019-03-29 | 2113790.14 | -203095.59 | 1758900.4 | 354889.74 | 96 | 0 | 102 | -6
FORT WORTH | HOOD | SH 144 | 0385-04-045 | 2019-04-18 | 2899083.65 | 26153.92 | 2746341.79 | 152741.86 | 149 | 69 | 218 | 0
FORT WORTH | TARRANT | VA | 0902-00-143 | 2019-03-15 | 1734750 | 1505764.04 | 3205526.22 | -1470776.22 | 256 | 348 | 572 | 32
FORT WORTH | TARRANT | VA | 0902-00-148 | 2019-07-22 | 1240000 | 622947.09 | 1740410.44 | -18551.44 | 300 | 115 | 366 | 49
FORT WORTH | PARKER | CS | 0902-38-075 | 2019-03-14 | 7269140.69 | 463461.24 | 7809339 | -540198.31 | 299 | 183 | 482 | 0
FORT WORTH | TARRANT | CS | 0902-48-502 | 2019-05-21 | 13943404.45 | 535189.58 | 14546098.7 | -334848.33 | 533 | 141 | 706 | -32
FORT WORTH | ERATH | VA | 0902-49-068 | 2019-08-02 | 2150084.2 | 45600.45 | 2101818.81 | 83849.14 | 180 | 90 | 242 | 28
FORT WORTH | TARRANT | CS | 0902-90-067 | 2019-04-24 | 2474990.24 | 38398.84 | 2497481.47 | -22491.23 | 192 | 104 | 296 | 0
FORT WORTH | PARKER | FM 2552 | 1179-03-010 | 2019-04-24 | 1285250.03 | -34187.19 | 1267119.02 | 18131.01 | 51 | 0 | 43 | 8
FORT WORTH | TARRANT | FM 1187 | 1330-03-003 | 2019-04-17 | 540000 | 7557.68 | 525203.19 | 14796.81 | 104 | 0 | 72 | 32
FORT WORTH | HOOD | FM 167 | 1513-01-019 | 2019-03-28 | 2616562.96 | 173527.48 | 2549461.6 | 67101.36 | 187 | 14 | 168 | 33
FORT WORTH | JOHNSON | FM 916 | 1599-02-014 | 2019-05-22 | 6925133.46 | 1446450.73 | 8210768.32 | -1285634.86 | 201 | 220 | 421 | 0
FORT WORTH | PARKER | FM 1884 | 1601-02-032 | 2019-08-21 | 105020.85 | 4400 | 101679.75 | 7741.1 | 43 | 10 | 51 | 2
FORT WORTH | JOHNSON | FM 1902 | 2118-02-019 | 2019-04-16 | 6740440.33 | 394020.8 | 6971572.35 | -231132.02 | 354 | 35 | 395 | -6
FORT WORTH | TARRANT | SH 360 | 2266-02-139 | 2019-03-12 | 1297564.52 | 495724.95 | 1856957.77 | -559393.25 | 43 | 39 | 82 | 0
FORT WORTH | TARRANT | IH 20 | 2374-05-082 | 2019-04-24 | 1256871.32 | 75716.7 | 1358022.08 | -101150.76 | 92 | 39 | 131 | 0
FORT WORTH | PALO PINTO | SH 337 | 2839-01-012 | 2019-05-22 | 89999 | 0 | 89280.9 | 718.1 | 43 | 0 | 7 | 36
HOUSTON | HARRIS | US 90 | 0028-02-090 | 2019-03-19 | 1444399.84 | 2318.76 | 1442521.07 | 1878.77 | 105 | 45 | 139 | 11
HOUSTON | HARRIS | SH 3 | 0051-02-100 | 2019-04-29 | 345345.91 | 0 | 303028.98 | 42316.93 | 60 | 0 | 60 | 0
HOUSTON | HARRIS | US 290 | 0114-12-007 | 2019-08-20 | 60092663.96 | 438602.46 | 60242642.59 | 213021.37 | 536 | 168 | 704 | 0
HOUSTON | MONTGOMERY | IH 69 | 0177-05-110 | 2019-03-18 | 1838258.2 | 8978.79 | 1837438.46 | 819.74 | 90 | 3 | 91 | 2
HOUSTON | HARRIS | IH 10 | 0271-07-312 | 2019-05-17 | 12293403.13 | 1022825.43 | 14336306.63 | -2042903.5 | 170 | 47 | 317 | -100
HOUSTON | HARRIS | IH 610 | 0271-14-232 | 2019-03-19 | 828677.47 | 0 | 829927.75 | -1250.28 | 75 | 0 | 73 | 2
HOUSTON | HARRIS | IH 610 | 0271-16-144 | 2019-07-03 | 614672 | 0 | 3000 | 611672 | 45 | 0 | 0 | 45
HOUSTON | HARRIS | IH 610 | 0271-16-145 | 2019-08-22 | 356092 | -114686.39 | 273009.31 | 83082.69 | 55 | 0 | 34 | 21
HOUSTON | GALVESTON | SH 146 | 0389-06-105 | 2019-04-18 | 318156.25 | -11418.24 | 290440.81 | 27715.44 | 45 | 0 | 26 | 19
HOUSTON | GALVESTON | SH 146 | 0389-06-106 | 2019-07-12 | 7195186.6 | -283958.43 | 7537861.48 | -342674.88 | 120 | 27 | 147 | 0
HOUSTON | GALVESTON | SH 146 | 0389-06-107 | 2019-04-19 | 219473.36 | 0 | 198484.64 | 20988.72 | 36 | 0 | 16 | 20
HOUSTON | HARRIS | SH 225 | 0502-01-212 | 2019-03-04 | 992122 | -82291.64 | 965213.79 | 26908.21 | 75 | 0 | 84 | -9
HOUSTON | HARRIS | SH 249 | 0720-03-133 | 2019-05-21 | 361037.7 | 1904.07 | 333178.22 | 27859.48 | 40 | 0 | 32 | 8
HOUSTON | HARRIS | VA | 0912-00-424 | 2019-03-28 | 2697458.33 | -94765.8 | 2460523.89 | 214674.24 | 228 | 0 | 273 | -45
HOUSTON | HARRIS | VA | 0912-00-489 | 2019-04-23 | 887550.77 | 1213058.62 | 2212051.79 | -1324501.02 | 45 | 9 | 53 | 1
HOUSTON | BRAZORIA | VA | 0912-31-279 | 2019-07-26 | 2131009.8 | -140186.04 | 1999695.19 | 131314.61 | 120 | 26 | 164 | -18
HOUSTON | BRAZORIA | VA | 0912-31-301 | 2019-05-06 | 920524 | 52535.68 | 904097.23 | 16426.77 | 120 | 0 | 120 | 0
HOUSTON | FORT BEND | CS | 0912-34-143 | 2019-03-14 | 3825527.24 | 140232.2 | 3910781.55 | -43431.71 | 176 | 0 | 130 | 46
HOUSTON | HARRIS | CS | 0912-70-091 | 2019-08-28 | 1844818.4 | 42878.07 | 1855256.51 | -10438.11 | 254 | 0 | 254 | 0
HOUSTON | HARRIS | CR | 0912-70-105 | 2019-05-16 | 3061039.35 | 427290.23 | 3486505.01 | -392930.13 | 157 | 0 | 143 | 14
HOUSTON | HARRIS | CS | 0912-71-688 | 2019-06-26 | 13480682.2 | 169005.14 | 13681950.67 | -142672.1 | 404 | 0 | 402 | 2
HOUSTON | HARRIS | CR | 0912-71-894 | 2019-04-05 | 10341416.18 | 1261776.35 | 11426681.13 | 176511.4 | 250 | 66 | 316 | 0
HOUSTON | HARRIS | VA | 0912-72-319 | 2019-03-22 | 792114.5 | 53792.41 | 784254.34 | 61652.57 | 151 | 0 | 143 | 8
HOUSTON | HARRIS | VA | 0912-72-420 | 2019-05-06 | 632045.25 | 16698.97 | 726330.8 | -94285.55 | 116 | 0 | 106 | 10
HOUSTON | GALVESTON | VA | 0912-73-203 | 2019-06-05 | 1529400 | 621381.33 | 2150781.33 | -621381.33 | 180 | 155 | 330 | 5
HOUSTON | GALVESTON | FM 3436 | 0978-02-078 | 2019-05-14 | 625529.3 | 4357.28 | 676857.35 | -51328.05 | 45 | 0 | 42 | 3
HOUSTON | BRAZORIA | FM 524 | 1004-01-063 | 2019-03-15 | 438751.1 | 34948.2 | 438904.55 | -153.45 | 104 | 0 | 83 | 21
HOUSTON | HARRIS | FM 1960 | 1685-02-049 | 2019-03-05 | 546380.1 | 96561.32 | 522945.73 | 23434.37 | 120 | 79 | 209 | -10
HOUSTON | HARRIS | SL 8 | 3256-01-105 | 2019-03-12 | 3448134.33 | 230648.56 | 3984164.16 | -536029.83 | 80 | 0 | 79 | 1
HOUSTON | FORT BEND | PR 72 | 3422-01-011 | 2019-05-03 | 563996.22 | -109153.64 | 443777.54 | 120218.68 | 30 | 0 | 30 | 0
HOUSTON | HARRIS | SH 99 | 3510-05-036 | 2019-08-15 | 3069959.81 | 465386.66 | 4020884.03 | -951225.7 | 97 | 35 | 132 | 0
HOUSTON | GALVESTON | SH 275 | 3595-01-017 | 2019-03-12 | 985671.81 | -79611.25 | 937776.14 | 47895.67 | 75 | 0 | 46 | 29
LAREDO | LA SALLE | IH 35 | 0017-08-102 | 2019-04-12 | 541921.2 | 5000.25 | 518535.85 | 23385.35 | 82 | 0 | 82 | 0
LAREDO | WEBB | IH 35 | 0018-03-049 | 2019-04-16 | 1521454.71 | 20680.89 | 1475185.45 | 46269.26 | 74 | 0 | 74 | 0
LAREDO | VAL VERDE | US 90 | 0022-10-064 | 2019-03-01 | 419937.4 | -11649 | 405206.8 | 14730.6 | 110 | 8 | 116 | 2
LAREDO | KINNEY | US 90 | 0023-04-065 | 2019-03-12 | 10014131.22 | 170876.05 | 10759462.69 | -745331.47 | 300 | 0 | 233 | 67
LAREDO | DIMMIT | US 83 | 0037-05-051 | 2019-04-12 | 452670.2 | -2865.25 | 443350.65 | 9319.55 | 133 | 0 | 132 | 1
LAREDO | DIMMIT | FM 133 | 0237-07-013 | 2019-08-16 | 9690620.28 | 391950.34 | 9958315.43 | -267695.15 | 185 | 39 | 224 | 0
LAREDO | MAVERICK | US 277 | 0299-04-068 | 2019-03-01 | 6593233.7 | -177697.22 | 6289880.69 | 303353.01 | 97 | 22 | 117 | 2
LAREDO | WEBB | VA | 0922-00-062 | 2019-04-12 | 1680038.5 | -59741.6 | 1518037.35 | 162001.15 | 184 | 10 | 193 | 1
LAREDO | WEBB | VA | 0922-00-068 | 2019-08-16 | 630091.27 | 20029.08 | 649887.85 | -19796.58 | 90 | 0 | 66 | 24
LAREDO | VAL VERDE | SL 79 | 3621-01-012 | 2019-04-12 | 5023548.03 | 76145.08 | 4963966.11 | 59581.92 | 115 | 0 | 103 | 12
LUBBOCK | LAMB | US 84 | 0052-04-050 | 2019-08-19 | 14065121.25 | 287219.11 | 12944672.78 | 1120448.47 | 77 | 6 | 78 | 5
LUBBOCK | LUBBOCK | US 84 | 0053-18-043 | 2019-03-20 | 1197726.9 | 52835.97 | 1254348.94 | -56622.04 | 140 | 0 | 140 | 0
LUBBOCK | BAILEY | US 70 | 0145-01-031 | 2019-03-07 | 125595 | 0 | 113220 | 12375 | 53 | 0 | 13 | 40
LUBBOCK | SWISHER | FM 146 | 0357-04-019 | 2019-07-22 | 1899776.19 | 0 | 2395529.24 | -495753.05 | 49 | 0 | 18 | 31
LUBBOCK | LUBBOCK | VA | 0905-00-073 | 2019-07-23 | 2938105.4 | 1387142.9 | 4335491.77 | -1397386.37 | 100 | 80 | 150 | 30
LUBBOCK | LUBBOCK | VA | 0905-00-075 | 2019-04-01 | 514251.95 | 133924.9 | 604662.49 | -90410.54 | 60 | 20 | 59 | 21
LUBBOCK | LUBBOCK | VA | 0905-00-098 | 2019-04-25 | 483414.3 | 1000 | 505271.96 | -21857.66 | 120 | 0 | 138 | -18
LUBBOCK | LUBBOCK | VA | 0905-06-098 | 2019-08-29 | 1273974.55 | 0 | 1587642.9 | -313668.35 | 80 | 0 | 73 | 7
LUBBOCK | LUBBOCK | VA | 0905-06-106 | 2019-03-13 | 998393.93 | 152099.15 | 1162531.54 | -164137.61 | 187 | 0 | 181 | 6
LUFKIN | SHELBY | SH 7 | 0059-04-046 | 2019-08-19 | 2926648.23 | 7122.87 | 2502206.3 | 424441.93 | 185 | 0 | 218 | -33
LUFKIN | SHELBY | SH 87 | 0064-01-067 | 2019-08-01 | 1118355.83 | -21363 | 1104916.56 | 13439.27 | 202 | 0 | 199 | 3
LUFKIN | HOUSTON | SH 7 | 0117-07-041 | 2019-03-11 | 10385539.17 | -238222.96 | 9414619.87 | 970919.3 | 100 | 10 | 114 | -4
LUFKIN | NACOGDOCHES | US 259 | 0138-06-045 | 2019-06-28 | 574813 | 91226.8 | 687929.8 | -113116.8 | 56 | 20 | 76 | 0
LUFKIN | POLK | CR | 0911-04-046 | 2019-03-13 | 480182.55 | 0 | 488830.21 | -8647.66 | 59 | 0 | 66 | -7
LUFKIN | HOUSTON | CR | 0911-28-041 | 2019-07-31 | 584116.65 | 3011.96 | 588093.75 | -3977.1 | 60 | 2 | 59 | 3
LUFKIN | SHELBY | CR | 0911-39-050 | 2019-05-14 | 671325.95 | 30032 | 726697.23 | -55371.28 | 127 | 0 | 122 | 5
LUFKIN | ANGELINA | FM 841 | 1157-01-014 | 2019-06-28 | 1023277.64 | 21933.36 | 1018894.83 | 4382.81 | 64 | 6 | 72 | -2
LUFKIN | NACOGDOCHES | FM 1638 | 1407-02-023 | 2019-08-13 | 2498804.12 | 9439.5 | 2351800.71 | 147003.41 | 123 | 0 | 91 | 32
LUFKIN | HOUSTON | FM 2967 | 3034-01-005 | 2019-08-26 | 1499731.08 | 14486.26 | 1383621.99 | 116109.09 | 40 | 3 | 42 | 1
ODESSA | WARD | SS 57 | 0004-03-050 | 2019-04-01 | 619319.3 | 2500 | 627705.85 | -8386.55 | 143 | 0 | 124 | 19
ODESSA | MARTIN | IH 20 | 0005-04-079 | 2019-05-31 | 377596.71 | 0 | 411846.62 | -34249.91 | 26 | 0 | 25 | 1
ODESSA | MIDLAND | IH 20 | 0005-14-089 | 2019-04-10 | 944367.23 | 17124.2 | 986661.19 | -42293.96 | 46 | 11 | 46 | 11
ODESSA | PECOS | US 67 | 0076-01-028 | 2019-06-18 | 5286212 | 188842 | 5455623.4 | -169411.4 | 288 | 26 | 351 | -37
ODESSA | REEVES | US 285 | 0139-03-039 | 2019-06-12 | 15005109.23 | 2313939.3 | 17415233.13 | -2410123.9 | 380 | 0 | 321 | 59
ODESSA | REEVES | RM 652 | 0493-01-013 | 2019-04-05 | 5983269.3 | 944880.57 | 7111568.99 | -1128299.69 | 107 | 122 | 220 | 9
ODESSA | REEVES | PR 30B | 0626-01-007 | 2019-08-28 | 560740 | 39762.39 | 598182.39 | -37442.39 | 18 | 1 | 19 | 0
ODESSA | ECTOR | SH 191 | 2296-01-052 | 2019-03-08 | 62229 | 0 | 62229 | 0 | 20 | 0 | 1 | 19
PARIS | HOPKINS | BU 67-V | 0009-18-020 | 2019-05-24 | 11652174.67 | -24661.25 | 11268265.4 | 383909.27 | 68 | 0 | 68 | 0
PARIS | GRAYSON | US 82 | 0045-19-050 | 2019-08-07 | 12500127.04 | -58736.79 | 12600988.44 | -100861.4 | 350 | 10 | 437 | -77
PARIS | GRAYSON | US 75 | 0047-18-074 | 2019-07-30 | 4673413.96 | 0 | 4590708.87 | 82705.09 | 130 | 0 | 227 | -97
PARIS | RAINS | SH 19 | 0108-10-024 | 2019-07-31 | 8460153.96 | 62585.52 | 8424887.23 | 35266.73 | 255 | 3 | 258 | 0
PARIS | FANNIN | US 69 | 0202-03-041 | 2019-08-22 | 3186550 | -77525 | 3323338.28 | -136788.28 | 180 | 123 | 309 | -6
PARIS | GRAYSON | SH 289 | 0202-08-063 | 2019-08-07 | 201885.96 | 0 | 214253 | -12367.04 | 45 | 0 | 38 | 7
PARIS | RAINS | FM 275 | 0725-02-019 | 2019-03-22 | 685540.51 | 8362.33 | 736928.02 | -51387.51 | 120 | 0 | 120 | 0
PARIS | HUNT | FM 1569 | 1493-01-017 | 2019-07-31 | 3081938.39 | -65564.88 | 2918613.75 | 163324.64 | 165 | 0 | 135 | 30
PHARR | STARR | US 83 | 0038-07-068 | 2019-04-05 | 1030636.95 | -15516.8 | 994918.7 | 35718.25 | 320 | 0 | 303 | 17
PHARR | HIDALGO | FM 1016 | 0219-02-013 | 2019-08-20 | 7102463 | -163949.9 | 7265555.4 | -163092.4 | 402 | 0 | 389 | 13
PHARR | CAMERON | SH 100 | 0331-01-044 | 2019-06-07 | 6339987.25 | -39365.08 | 6644030.91 | -304043.66 | 340 | 59 | 377 | 22
PHARR | CAMERON | FM 106 | 0630-02-041 | 2019-06-07 | 12406043.3 | 501879.64 | 13473076.62 | -1067033.32 | 651 | 0 | 650 | 1
SAN ANGELO | RUNNELS | US 83 | 0035-01-033 | 2019-04-26 | 2069426.77 | 0 | 1887261.79 | 182164.98 | 164 | 0 | 144 | 20
SAN ANGELO | CONCHO | US 83 | 0035-04-035 | 2019-07-29 | 1472270.45 | 32925.55 | 1598554.83 | -126284.38 | 209 | 10 | 261 | -42
SAN ANGELO | TOM GREEN | US 87 | 0069-06-034 | 2019-07-29 | 3255516.18 | 341492.9 | 3854617.81 | -599101.63 | 83 | 26 | 119 | -10
SAN ANGELO | TOM GREEN | US 87 | 0070-02-090 | 2019-08-07 | 2731400.55 | 2839711.66 | 7986103.04 | -5254702.49 | 53 | 52 | 93 | 12
SAN ANGELO | CONCHO | US 87 | 0070-03-057 | 2019-06-17 | 1474796.26 | 71017.72 | 1625402.51 | -150606.25 | 163 | 31 | 253 | -59
SAN ANGELO | REAGAN | US 67 | 0077-01-029 | 2019-03-20 | 6531381.36 | 37307.96 | 6925991.64 | -394610.28 | 131 | 0 | 115 | 16
SAN ANGELO | TOM GREEN | US 67 | 0077-06-098 | 2019-07-17 | 3805303.54 | 1363765.43 | 5392012.11 | -1586708.57 | 174 | 121 | 295 | 0
SAN ANGELO | TOM GREEN | US 67 | 0077-06-099 | 2019-04-09 | 3463806.62 | 0 | 3475815.35 | -12008.73 | 54 | 0 | 64 | -10
SAN ANGELO | TOM GREEN | VA | 0907-00-172 | 2019-05-24 | 1285520.09 | 16102.38 | 1315952.36 | -30432.27 | 208 | 12 | 214 | 6
SAN ANGELO | TOM GREEN | VA | 0907-00-173 | 2019-07-02 | 1514294.85 | 0 | 1500584.55 | 13710.3 | 52 | 0 | 44 | 8
SAN ANGELO | KIMBLE | VA | 0907-20-006 | 2019-06-03 | 3089229.59 | 7215.9 | 3098932.06 | -9702.47 | 410 | 0 | 367 | 43
SAN ANGELO | SCHLEICHER | CS | 0907-26-004 | 2019-03-13 | 368395.8 | 4930.15 | 372620.86 | -4225.06 | 57 | 2 | 55 | 4
SAN ANGELO | CROCKETT | RL SO | 7107-04-001 | 2019-05-09 | 6591742 | 0 | 6656315.08 | -64573.08 | 195 | 0 | 186 | 9
SAN ANTONIO | BEXAR | IH 35 | 0017-09-096 | 2019-03-28 | 748708 | 35118.97 | 783826.97 | -35118.97 | 101 | 0 | 93 | 8
SAN ANTONIO | BEXAR | IH 35 | 0017-10-261 | 2019-06-27 | 61196365.25 | 10642264.53 | 80015656.14 | -18819290.89 | 916 | 385 | 1283 | 18
SAN ANTONIO | BEXAR | IH 35 | 0017-10-270 | 2019-03-19 | 5439586.71 | 542501.46 | 6283390.13 | -843803.42 | 222 | 25 | 250 | -3
SAN ANTONIO | BEXAR | IH 35 | 0017-10-272 | 2019-03-19 | 342679.48 | -122644.75 | 228168.97 | 114510.51 | 100 | 484 | 572 | 12
SAN ANTONIO | GUADALUPE | FM 78 | 0025-10-094 | 2019-04-18 | 504134.68 | -337768.59 | 176366.09 | 327768.59 | 120 | 0 | 117 | 3
SAN ANTONIO | UVALDE | US 83 | 0036-07-036 | 2019-04-24 | 1559435.35 | -11355.79 | 1550630.82 | 8804.53 | 123 | 0 | 95 | 28
SAN ANTONIO | ATASCOSA | IH 37 | 0073-05-070 | 2019-06-27 | 3919729.02 | 173259.97 | 4221967.24 | -302238.22 | 143 | -10 | 121 | 12
SAN ANTONIO | BEXAR | IH 37 | 0073-08-180 | 2019-03-28 | 973428.36 | 11322.1 | 984227.88 | -10799.52 | 130 | 0 | 111 | 19
SAN ANTONIO | WILSON | US 181 | 0100-04-038 | 2019-08-28 | 9084167.29 | 953663.15 | 10653328.05 | -1569160.76 | 289 | 116 | 404 | 1
SAN ANTONIO | KERR | IH 10 | 0142-14-061 | 2019-08-28 | 4379478.03 | 88525.95 | 4468004.07 | -88526.04 | 60 | 21 | 98 | -17
SAN ANTONIO | COMAL | SH 46 | 0215-01-043 | 2019-03-19 | 681930.3 | 15738.81 | 740660.33 | -58730.03 | 73 | 8 | 81 | 0
SAN ANTONIO | COMAL | BS 46-C | 0215-02-056 | 2019-05-23 | 852181 | 26413.53 | 887132.08 | -34951.08 | 129 | 25 | 136 | 18
SAN ANTONIO | COMAL | US 281 | 0253-03-072 | 2019-05-29 | 726396.37 | 7903.82 | 1038328.18 | -311931.81 | 57 | 0 | 57 | 0
SAN ANTONIO | WILSON | SH 97 | 0328-01-014 | 2019-05-21 | 17618829.46 | 364630.14 | 18015626.05 | -396796.59 | 455 | 30 | 423 | 62
SAN ANTONIO | WILSON | SH 97 | 0328-02-043 | 2019-05-23 | 18593935.69 | -85446.44 | 18513230.93 | 80704.76 | 586 | 0 | 430 | 156
SAN ANTONIO | GUADALUPE | SH 123 | 0366-02-090 | 2019-05-23 | 669005.33 | 273070.83 | 1035585.05 | -366579.72 | 72 | 3 | 75 | 0
SAN ANTONIO | BEXAR | VA | 0915-00-159 | 2019-03-19 | 2452827.79 | 182637.22 | 2763428.67 | -261600.88 | 360 | 0 | 304 | 56
SAN ANTONIO | BEXAR | VA | 0915-12-530 | 2019-03-28 | 2958588.16 | 6289.33 | 3051642.28 | -93054.12 | 309 | 0 | 300 | 9
SAN ANTONIO | BEXAR | VA | 0915-12-555 | 2019-03-26 | 5286690.36 | 88508.21 | 5058670.49 | 228019.87 | 309 | 29 | 329 | 9
SAN ANTONIO | MCMULLEN | FM 791 | 1739-04-010 | 2019-04-18 | 4956163.24 | 49616 | 4989662.29 | -33499.05 | 176 | 6 | 181 | 1
SAN ANTONIO | BEXAR | FM 1976 | 1890-01-048 | 2019-06-17 | 405949 | 23398.3 | 429215.37 | -23266.37 | 100 | 53 | 187 | -34
SAN ANTONIO | BEXAR | FM 1957 | 2104-02-032 | 2019-05-28 | 979020.4 | 16249.16 | 1002562.52 | -23542.12 | 101 | 0 | 105 | -4
SAN ANTONIO | BEXAR | FM 1560 | 2230-01-018 | 2019-06-30 | 3419684.6 | 42910.95 | 3673415.88 | -253731.28 | 271 | 0 | 269 | 2
SAN ANTONIO | BEXAR | SP 53 | 2230-02-004 | 2019-03-29 | 7297370.94 | 296346.22 | 7512085.65 | -214714.71 | 534 | 0 | 521 | 13
TYLER | ANDERSON | SH 19 | 0108-06-051 | 2019-06-10 | 12487715.87 | 4017911.74 | 17370149.42 | -4882433.55 | 453 | 140 | 583 | 10
TYLER | RUSK | US 259 | 0138-04-046 | 2019-06-20 | 5220900.06 | 104958.3 | 5342943.07 | -122043.01 | 71 | 1 | 78 | -6
TYLER | HENDERSON | BS 31H | 0164-01-071 | 2019-08-20 | 1161999.49 | -21527.2 | 1048076.42 | 113923.07 | 35 | 0 | 33 | 2
TYLER | HENDERSON | SH 31 | 0164-03-053 | 2019-04-15 | 2687805.15 | 50326.9 | 2926530.52 | -238725.37 | 95 | 12 | 107 | 0
TYLER | ANDERSON | US 79 | 0206-01-049 | 2019-08-26 | 1646254.33 | -23735.21 | 2038219.44 | -391965.11 | 136 | 21 | 157 | 0
TYLER | VAN ZANDT | FM 279 | 0245-04-022 | 2019-07-17 | 257510 | 0 | 246950 | 10560 | 22 | 0 | 21 | 1
TYLER | GREGG | SH 135 | 0377-01-048 | 2019-03-26 | 2405351.66 | -8552.57 | 2591679.05 | -186327.39 | 100 | 15 | 120 | -5
TYLER | GREGG | SH 149 | 0393-01-097 | 2019-07-17 | 3114797.79 | 297529.53 | 3441298.11 | -326500.32 | 145 | 0 | 170 | -25
TYLER | GREGG | SH 42 | 0545-04-051 | 2019-03-20 | 654890 | 0 | 672341.35 | -17451.35 | 64 | 0 | 64 | 0
TYLER | SMITH | VA | 0910-00-111 | 2019-08-09 | 958012.88 | -99666.48 | 870564.95 | 87447.93 | 60 | 0 | 58 | 2
TYLER | GREGG | VA | 0910-07-069 | 2019-03-18 | 1279638.81 | 3712.89 | 1253280.55 | 26358.26 | 141 | 46 | 171 | 16
TYLER | SMITH | CR | 0910-16-125 | 2019-08-26 | 833389.25 | -29663.39 | 793831.12 | 39558.13 | 151 | 0 | 119 | 32
WACO | HILL | SH 22 | 0121-03-054 | 2019-06-21 | 6520301.12 | 76036.58 | 6722678.57 | -202377.45 | 277 | 202 | 478 | 1
WACO | BELL | SL 363 | 0184-04-046 | 2019-08-30 | 13297595.81 | 2204371.3 | 15524728.76 | -2227132.95 | 383 | 53 | 436 | 0
WACO | BELL | SH 36 | 0184-04-050 | 2019-05-13 | 2282821.5 | -31720 | 2222560.21 | 60261.29 | 90 | 0 | 39 | 51
WACO | BELL | US 190 | 0231-04-056 | 2019-03-26 | 1063872.2 | 53343.26 | 1209360.75 | -145488.55 | 120 | 6 | 126 | 0
WACO | MCLENNAN | SH 6 | 0258-09-111 | 2019-08-30 | 22387388.26 | 465646.74 | 23151668.53 | -764280.27 | 701 | 10 | 706 | 5
WACO | CORYELL | FM 116 | 0724-01-050 | 2019-03-13 | 4345840.87 | 45293.6 | 4155131.83 | 190709.04 | 234 | 0 | 234 | 0
WACO | BELL | SH 195 | 0836-02-071 | 2019-04-04 | 796526.1 | 14433.26 | 831086.87 | -34560.77 | 60 | 0 | 46 | 14
WACO | HAMILTON | CR | 0909-29-040 | 2019-04-25 | 495665.2 | 0 | 474411.11 | 21254.09 | 90 | 0 | 79 | 11
WACO | FALLS | CR | 0909-38-071 | 2019-06-21 | 439500.32 | 2468.69 | 443562.29 | -4061.97 | 90 | 1 | 70 | 21
WACO | FALLS | CR | 0909-38-076 | 2019-08-21 | 1139586.13 | 3434.5 | 1166424.37 | -26838.24 | 255 | 0 | 229 | 26
WACO | FALLS | CS | 0909-38-078 | 2019-06-21 | 279403.6 | 24715.97 | 303630 | -24226.4 | 45 | 8 | 47 | 6
WACO | BELL | FM 1123 | 1308-01-024 | 2019-03-04 | 2950399.18 | -65139.96 | 2745414.07 | 204985.11 | 298 | 0 | 296 | 2
WACO | MCLENNAN | SL 340 | 2362-01-036 | 2019-08-14 | 2101671.86 | 26065.33 | 2211731.13 | -110059.27 | 60 | 7 | 64 | 3
WACO | CORYELL | SH 9 | 3623-01-003 | 2019-03-05 | 661980.04 | -25517.18 | 622025.91 | 39954.13 | 85 | 6 | 141 | -50
WICHITA FALLS | WILBARGER | US 287 | 0043-05-107 | 2019-04-23 | 1842668.48 | 128000 | 1970331.79 | -127663.31 | 102 | 4 | 136 | -30
WICHITA FALLS | WILBARGER | US 70 | 0043-06-084 | 2019-04-19 | 3149693.5 | 46006.86 | 3120703.24 | 28990.26 | 204 | 37 | 261 | -20
WICHITA FALLS | WICHITA | US 287 | 0043-08-078 | 2019-07-30 | 433433 | 0 | 424820.44 | 8612.56 | 25 | 0 | 16 | 9
WICHITA FALLS | WICHITA | US 287 | 0043-09-130 | 2019-04-12 | 2398060.27 | 0 | 2380094.4 | 17965.87 | 214 | 0 | 226 | -12
WICHITA FALLS | WICHITA | BU 287J | 0043-17-030 | 2019-08-26 | 3440613.52 | -120873.94 | 3269635.26 | 170978.26 | 51 | 0 | 253 | -202
WICHITA FALLS | WILBARGER | US 183 | 0124-04-031 | 2019-04-08 | 6688994.61 | 40577.51 | 6609412.77 | 79581.84 | 208 | 40 | 263 | -15
WICHITA FALLS | COOKE | FM 51 | 0312-01-078 | 2019-03-19 | 706189.82 | 13693.06 | 738272.48 | -32082.66 | 102 | 10 | 78 | 34
WICHITA FALLS | THROCKMORTON | US 380 | 0360-05-029 | 2019-07-30 | 3381084.97 | -22811.49 | 3816190.63 | -435105.66 | 48 | 0 | 36 | 12
WICHITA FALLS | MONTAGUE | CR | 0903-28-064 | 2019-05-24 | 376569.5 | 0 | 351357.73 | 25211.77 | 80 | 0 | 73 | 7
WICHITA FALLS | ARCHER | CR | 0903-29-026 | 2019-05-02 | 265264.9 | 2941.72 | 294565.57 | -29300.67 | 85 | 0 | 79 | 6
WICHITA FALLS | MONTAGUE | FM 455 | 1352-02-021 | 2019-03-11 | 554791.65 | 50855.49 | 669126.28 | -114334.63 | 103 | 0 | 73 | 30
WICHITA FALLS | CLAY | FM 2393 | 2405-01-012 | 2019-08-13 | 2307479.2 | 30650.6 | 2268542.07 | 38937.13 | 95 | 4 | 185 | -86
YOAKUM | GONZALES | SH 97 | 0025-07-064 | 2019-05-15 | 5889198.08 | 182056.85 | 6020596.95 | -131398.87 | 45 | 0 | 50 | -5
YOAKUM | FAYETTE | US 90 | 0026-03-043 | 2019-03-27 | 958370 | 3832.67 | 943873.47 | 14496.53 | 75 | 0 | 99 | -24
YOAKUM | VICTORIA | US 59 | 0088-05-094 | 2019-04-16 | 1983066.57 | 12347.32 | 1839606.14 | 143460.43 | 90 | 0 | 91 | -1
YOAKUM | WHARTON | BU 59-R | 0089-10-022 | 2019-06-18 | 4875271.5 | 1341194.57 | 6957613.14 | -2082341.64 | 170 | 193 | 322 | 41
YOAKUM | AUSTIN | SH 36 | 0187-02-066 | 2019-08-13 | 1151604.59 | 78667.41 | 1231254.09 | -79649.5 | 75 | 0 | 71 | 4
YOAKUM | COLORADO | FM 155 | 0211-10-042 | 2019-05-15 | 714920.82 | 0 | 687898.28 | 27022.54 | 40 | 38 | 78 | 0
YOAKUM | MATAGORDA | SH 60 | 0241-02-053 | 2019-04-12 | 306857.45 | 0 | 325224.06 | -18366.61 | 45 | 0 | 49 | -4
YOAKUM | AUSTIN | US 90 | 0271-08-012 | 2019-06-03 | 9013434.63 | 190770.72 | 9358064.15 | -344629.52 | 190 | 13 | 203 | 0
YOAKUM | JACKSON | FM 616 | 0497-03-009 | 2019-04-16 | 2063461.48 | 0 | 1995606.33 | 67855.15 | 105 | 0 | 106 | -1
YOAKUM | MATAGORDA | FM 521 | 0846-03-046 | 2019-06-18 | 1521680.37 | 0 | 1564998.07 | -43317.7 | 45 | 0 | 25 | 20
YOAKUM | DE WITT | VA | 0913-00-092 | 2019-03-19 | 3469339.75 | 401641.63 | 3721791.93 | -252452.18 | 203 | 105 | 305 | 3
YOAKUM | WHARTON | CR | 0913-09-059 | 2019-06-18 | 746501.3 | 0 | 739662.5 | 6838.8 | 120 | 0 | 72 | 48
YOAKUM | WHARTON | CR | 0913-09-065 | 2019-05-21 | 320804.3 | 22102.52 | 316550.82 | 4253.48 | 60 | 0 | 52 | 8
YOAKUM | WHARTON | CS | 0913-09-081 | 2019-03-11 | 311986 | 7002.6 | 326303.6 | -14317.6 | 45 | 0 | 45 | 0
YOAKUM | JACKSON | CR | 0913-18-029 | 2019-04-12 | 462863.85 | 1550 | 457612.85 | 5251 | 60 | 2 | 75 | -13
YOAKUM | AUSTIN | CR | 0913-20-090 | 2019-06-18 | 410493.12 | 0 | 416287.96 | -5794.84 | 75 | 0 | 55 | 20
YOAKUM | COLORADO | CR | 0913-26-058 | 2019-03-11 | 233008 | 14068 | 240605 | -7597 | 40 | 0 | 33 | 7
YOAKUM | LAVACA | CR | 0913-29-031 | 2019-05-03 | 567765.26 | 0 | 555403.84 | 12361.42 | 75 | 0 | 87 | -12
YOAKUM | LAVACA | FM 958 | 1008-02-018 | 2019-04-11 | 3498600.69 | 602.59 | 3568076.76 | -69476.07 | 135 | 20 | 169 | -14
YOAKUM | DE WITT | FM 766 | 1113-01-026 | 2019-04-12 | 4871848.95 | -21632.63 | 4886202.63 | -14353.68 | 165 | 0 | 165 | 0