## OTOB
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [11 empty] | Highway Construction Projects Completed March 1, 2020–August 31, 2020
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | AMOUNT PAID | OVER/UNDER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | OVER/UNDER SCHEDULE | MONTH | MMM_YY | QUARTER FINALED | QUARTER | CONSULTANT DESIGN | A + B PROJECT | CEI PROJECT | PROJECT SIZE | FY_CMPL
AUSTIN | 0016-02-160 | HAYS | IH 35 | 2020-03-03 | 3187981.52 | 120390.05 | 3191448.39 | 3466.87 | 98 | 89 | 0 | -9 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
LUFKIN | 0138-06-044 | NACOGDOCHES | US 259 | 2020-03-03 | 3341270 | -262066.2 | 3196128.39 | -145141.61 | 86 | 112 | 0 | 26 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 1978-01-056 | TARRANT | FM 1938 | 2020-03-04 | 2235382.79 | 349685.72 | 2589949.72 | 354566.93 | 150 | 145 | 0 | -5 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
BRYAN | 0057-02-037 | FREESTONE | BU 84-R | 2020-03-05 | 12525077 | 3831093.24 | 15772697.95 | 3247620.95 | 75 | 152 | 141 | 77 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
DALLAS | 0092-07-060 | DALLAS | SH 356 | 2020-03-05 | 2032592.95 | 204.06 | 1193084.41 | -839508.54 | 85 | 46 | 0 | -39 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
DALLAS | 0817-01-026 | DENTON | FM 428 | 2020-03-05 | 1092190.95 | -248948.27 | 846107.32 | -246083.63 | 78 | 49 | 0 | -29 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 0172-10-015 | JOHNSON | US 287 | 2020-03-05 | 709937.29 | 367209.4 | 1018377.44 | 308440.15 | 28 | 28 | 0 | 0 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0782-03-020 | COOKE | FM 1201 | 2020-03-05 | 2392784.46 | 19643.73 | 2475249.59 | 82465.13 | 68 | 67 | 1 | -1 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0508-01-034 | HARRIS | IH 10 | 2020-03-06 | 2122122.8 | 22860 | 2351860.2 | 229737.4 | 312 | 303 | 0 | -9 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0912-70-099 | HARRIS | VA | 2020-03-06 | 2767522.72 | -218768 | 2175241.76 | -592280.96 | 244 | 395 | 0 | 151 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0015-13-401 | TRAVIS | IH 35 | 2020-03-09 | 188299 | 16440 | 219853.28 | 31554.28 | 109 | 62 | 0 | -47 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0495-08-116 | HARRISON | IH 20 | 2020-03-10 | 2388393.75 | 3176.56 | 2440950.64 | 52556.89 | 55 | 66 | 0 | 11 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0044-06-075 | MONTAGUE | US 82 | 2020-03-10 | 4024790.81 | 56250.92 | 4190218.98 | 165428.17 | 55 | 60 | 20 | 5 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0015-13-402 | TRAVIS | IH 35 | 2020-03-11 | 1127245.94 | 29288.4 | 1198944.81 | 71698.87 | 286 | 212 | 0 | -74 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-08-075 | WICHITA | US 287 | 2020-03-11 | 2014723.35 | 0 | 1935326.42 | -79396.93 | 85 | 102 | 0 | 17 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0045-05-048 | FANNIN | SH 56 | 2020-03-12 | 205853 | 0 | 205865.5 | 12.5 | 50 | 30 | 0 | -20 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0108-11-019 | RAINS | SH 19 | 2020-03-12 | 6503123.07 | -169866.82 | 6253575.95 | -249547.12 | 210 | 277 | 0 | 67 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0136-04-035 | DELTA | SH 19 | 2020-03-12 | 1665295.93 | 0 | 1631825.18 | -33470.75 | 180 | 179 | 0 | -1 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0435-01-073 | LAMAR | FM 38 | 2020-03-12 | 2447924.56 | -186921.25 | 2166799.08 | -281125.48 | 128 | 82 | 0 | -46 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 2139-03-021 | FANNIN | SH 11 | 2020-03-12 | 3667040.21 | 59164.42 | 3933963.36 | 266923.15 | 64 | 64 | 0 | 0 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0909-22-176 | MCLENNAN | CR | 2020-03-12 | 863437.65 | 26800 | 894075.69 | 30638.04 | 150 | 126 | 0 | -24 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0096-07-045 | HARRISON | US 80 | 2020-03-13 | 877536.57 | 184.9 | 839833.77 | -37702.8 | 130 | 124 | 0 | -6 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 0172-09-036 | TARRANT | US 287 | 2020-03-13 | 3458299.91 | 57588.52 | 3414542.94 | -43756.97 | 128 | 121 | 0 | -7 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
LAREDO | 0086-05-018 | DUVAL | SH 359 | 2020-03-13 | 877187.66 | -262393.77 | 618066.33 | -259121.33 | 60 | 45 | 0 | -15 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0221-01-074 | LAMAR | US 271 | 2020-03-13 | 8915686.64 | -1082113.73 | 8961256.22 | 45569.58 | 197 | 169 | -23 | -28 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
PARIS | 1482-02-019 | FANNIN | FM 1550 | 2020-03-13 | 3303723.03 | 36054.28 | 3312803.72 | 9080.69 | 179 | 216 | 0 | 37 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0328-06-030 | ATASCOSA | SH 97 | 2020-03-16 | 2924983.58 | -111538.05 | 2736420.44 | -188563.14 | 185 | 198 | 33 | 13 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0915-00-178 | BEXAR | VA | 2020-03-16 | 3495290.12 | 6524.33 | 2747214.56 | -748075.56 | 335 | 335 | 0 | 0 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0320-05-015 | BELL | SL 363 | 2020-03-16 | 2938130.95 | 48217 | 3001046.09 | 62915.14 | 60 | 85 | 0 | 25 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
BEAUMONT | 0593-01-120 | LIBERTY | SH 321 | 2020-03-17 | 5234742.15 | 135180.07 | 5278152.76 | 43410.61 | 208 | 203 | 0 | -5 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
ATLANTA | 0248-01-077 | TITUS | US 271 | 2020-03-18 | 12222495.52 | 448529.77 | 12570105.88 | 347610.36 | 208 | 218 | 12 | 10 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0915-00-226 | BEXAR | VA | 2020-03-18 | 238000 | 0 | 238000 | 0 | 33 | 18 | 0 | -15 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0209-01-063 | MCLENNAN | SL 2 | 2020-03-18 | 1014136.75 | -3488.46 | 955198.92 | -58937.83 | 30 | 39 | 1 | 9 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 2452-02-115 | BEXAR | SL 1604 | 2020-03-19 | 13947909.96 | 415908.06 | 16234675.6 | 2286765.64 | 186 | 302 | 141 | 116 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
WACO | 0833-03-035 | MCLENNAN | FM 1637 | 2020-03-19 | 27836847.99 | 552295.78 | 29425580.67 | 1588732.68 | 574 | 644 | 53 | 70 | MARCH | MAR-20 | 2019-07-01 | Q3 | Y | N | Y | MEDIUM | FY20
AUSTIN | 0150-02-039 | LLANO | SH 29 | 2020-03-20 | 890245 | 48293.36 | 990385.72 | 100140.72 | 68 | 105 | 40 | 37 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 0910-08-068 | ANDERSON | CR | 2020-03-20 | 607852.4 | 34787.6 | 634522.06 | 26669.66 | 113 | 112 | 5 | -1 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 1711-01-029 | YOUNG | FM 1769 | 2020-03-20 | 3310004.48 | 0 | 3412491.93 | 102487.45 | 153 | 158 | 0 | 5 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0515-06-024 | LAVACA | FM 957 | 2020-03-20 | 1599661.93 | 4351.6 | 1525211.13 | -74450.8 | 90 | 88 | 0 | -2 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ODESSA | 0139-03-040 | REEVES | US 285 | 2020-03-23 | 12525496.02 | 9103567.31 | 22497277.82 | 9659531.8 | 332 | 582 | 250 | 250 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
SAN ANTONIO | 1066-02-017 | MEDINA | PR 37 | 2020-03-23 | 1099115.25 | 17207.27 | 1118271.6 | 19156.35 | 153 | 179 | 26 | 26 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 2654-01-022 | SMITH | FM 2661 | 2020-03-23 | 2792589.05 | -141177.22 | 2575975.74 | -216613.31 | 157 | 146 | 0 | -11 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 1202-03-014 | WILLIAMSON | FM 1063 | 2020-03-24 | 1248578.85 | -29706 | 1130635.57 | -117943.28 | 287 | 287 | 0 | 0 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
BEAUMONT | 0883-02-086 | ORANGE | FM 105 | 2020-03-24 | 1139721.42 | -145529.48 | 1030752.33 | -108969.09 | 49 | 111 | 39 | 62 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0009-08-031 | HUNT | SH 24 | 2020-03-24 | 11452320.53 | -48614.37 | 11185130.19 | -267190.34 | 60 | 45 | 0 | -15 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0915-12-551 | BEXAR | VA | 2020-03-24 | 1723801.41 | 84554.36 | 1965572.22 | 241770.81 | 221 | 250 | 26 | 29 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0055-08-119 | MCLENNAN | US 84 | 2020-03-24 | 4721563.44 | 171384 | 5264616.42 | 543052.98 | 90 | 182 | 10 | 92 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0520-05-050 | UPSHUR | SH 155 | 2020-03-25 | 3772058.91 | 229021.38 | 4222421.2 | 450362.29 | 76 | 68 | 0 | -8 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0919-03-059 | HARRISON | CR | 2020-03-25 | 398056.85 | 3830.97 | 394512.52 | -3544.33 | 80 | 43 | 0 | -37 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0009-09-081 | HOPKINS | IH 30 | 2020-03-25 | 23690539.51 | 3060189.15 | 27024837.26 | 3334297.75 | 368 | 437 | 73 | 69 | MARCH | MAR-20 | 2019-07-01 | Q3 | Y | N | Y | MEDIUM | FY20
ATLANTA | 0248-05-064 | UPSHUR | US 271 | 2020-03-26 | 5046398.13 | 27831.93 | 5461669.35 | 415271.22 | 121 | 119 | 0 | -2 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 1202-01-018 | WILLIAMSON | FM 972 | 2020-03-26 | 3320330.51 | 206445.82 | 3765544.24 | 445213.73 | 272 | 195 | 0 | -77 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
BEAUMONT | 0200-07-054 | TYLER | US 69 | 2020-03-26 | 3070400.3 | -125779.35 | 3133459.31 | 63059.01 | 64 | 47 | 3 | -17 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | Y | N | SMALL | FY20
BEAUMONT | 0200-11-100 | JEFFERSON | US 69 | 2020-03-26 | 27390861.67 | 1791296.86 | 31406007.26 | 4015145.59 | 636 | 1082 | 454 | 446 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | MEDIUM | FY20
TYLER | 0164-01-072 | HENDERSON | SH 31 | 2020-03-26 | 144985 | 3103.18 | 147709.8 | 2724.8 | 51 | 47 | 0 | -4 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 0889-04-078 | SMITH | FM 346 | 2020-03-26 | 799066.29 | 1070.18 | 654417.82 | -144648.47 | 96 | 72 | 0 | -24 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
DALLAS | 0047-06-133 | COLLIN | US 75 | 2020-03-27 | 37466722.18 | 6830365.59 | 45726585.82 | 8259863.64 | 750 | 977 | 228 | 227 | MARCH | MAR-20 | 2019-07-01 | Q3 | Y | N | Y | MEDIUM | FY20
SAN ANTONIO | 0024-08-131 | BEXAR | US 90 | 2020-03-27 | 355044 | 0 | 354650.4 | -393.6 | 58 | 43 | 0 | -15 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ODESSA | 0228-05-068 | ANDREWS | US 385 | 2020-03-30 | 598519 | 0 | 594079.25 | -4439.75 | 80 | 49 | 0 | -31 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ODESSA | 0292-02-040 | WINKLER | SH 18 | 2020-03-30 | 11998398.69 | 2987821.05 | 16151748.47 | 4153349.78 | 204 | 261 | 57 | 57 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ODESSA | 0906-00-176 | ECTOR | VA | 2020-03-30 | 395738.21 | -1405 | 382471.28 | -13266.93 | 47 | 46 | 0 | -1 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
WACO | 0320-01-072 | BELL | SH 95 | 2020-03-31 | 3571166.53 | 104599.24 | 4183032.87 | 611866.34 | 45 | 60 | 26 | 15 | MARCH | MAR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
HOUSTON | 3510-04-053 | FORT BEND | SH 99 | 2020-04-03 | 2240983.05 | 94126.43 | 2410493.13 | 169510.08 | 147 | 226 | 9 | 79 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
LUBBOCK | 0905-00-096 | LUBBOCK | VA | 2020-04-03 | 277650 | 0 | 281591 | 3941 | 75 | 70 | 0 | -5 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-07-111 | WILBARGER | US 287 | 2020-04-03 | 524560 | 0 | 585171.54 | 60611.54 | 68 | 127 | 0 | 59 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
EL PASO | 3572-01-006 | EL PASO | SS 6 | 2020-04-06 | 735009.95 | 10500 | 797860.84 | 62850.89 | 30 | 30 | 0 | 0 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 0164-04-160 | SMITH | SH 31 | 2020-04-06 | 3587845.3 | -376285.61 | 3368330.67 | -219514.63 | 58 | 45 | 0 | -13 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ODESSA | 1188-02-107 | MIDLAND | SL 250 | 2020-04-07 | 6656389.81 | 771998.6 | 7565863.71 | 909473.9 | 133 | 137 | 15 | 4 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0366-01-076 | HAYS | SL 82 | 2020-04-08 | 1025322.11 | -16500.59 | 949610.33 | -75711.78 | 26 | 26 | 0 | 0 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
DALLAS | 0596-02-037 | ELLIS | FM 66 | 2020-04-08 | 2694785.55 | -242.49 | 2646750.37 | -48035.18 | 378 | 528 | 0 | 150 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0015-04-067 | BELL | IH 35 | 2020-04-08 | 123628672.32 | 11593829.42 | 136792574.08 | 13163901.76 | 1166 | 2022 | 856 | 856 | APRIL | APR-20 | 2019-07-01 | Q3 | Y | N | N | LARGE | FY20
PARIS | 0009-13-171 | HUNT | IH 30 | 2020-04-09 | 542727.5 | -8939.5 | 556166.6 | 13439.1 | 59 | 49 | 1 | -10 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0083-03-055 | HOPKINS | SH 154 | 2020-04-09 | 5289098.26 | -37362.09 | 5297225.03 | 8126.77 | 107 | 127 | 31 | 20 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PHARR | 1429-01-033 | HIDALGO | FM 2557 | 2020-04-10 | 4427442.75 | 47231.57 | 4565243.49 | 137800.74 | 200 | 209 | 9 | 9 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0044-02-079 | CLAY | US 82 | 2020-04-10 | 5938095.15 | 2091922.28 | 7749757.48 | 1811662.33 | 197 | 346 | 54 | 149 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0113-08-090 | TRAVIS | US 290 | 2020-04-13 | 2265980.68 | 32915.47 | 2649294.99 | 383314.31 | 48 | 49 | 0 | 1 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
AUSTIN | 0113-13-165 | TRAVIS | SH 71 | 2020-04-13 | 737000 | 0 | 723286.8 | -13713.2 | 120 | 38 | 0 | -82 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 0102-01-114 | NUECES | SH 44 | 2020-04-13 | 2213165.86 | 5200.32 | 1932999.04 | -280166.82 | 102 | 78 | 0 | -24 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 0383-04-061 | KLEBERG | SH 141 | 2020-04-13 | 3087010.92 | 361788.17 | 3728054.89 | 641043.97 | 174 | 165 | 0 | -9 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 0363-01-143 | TARRANT | SH 26 | 2020-04-13 | 2116624.32 | -207557.04 | 1976403.37 | -140220.95 | 128 | 86 | 0 | -42 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
SAN ANGELO | 0035-06-032 | MENARD | US 83 | 2020-04-13 | 5814758.83 | 956842.5 | 6812948.1 | 998189.27 | 265 | 296 | 38 | 31 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0913-09-071 | WHARTON | CR | 2020-04-13 | 441100.21 | 0 | 443336.97 | 2236.76 | 75 | 75 | 0 | 0 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0027-01-040 | COLORADO | US 90 | 2020-04-14 | 7142388.4 | 1396229.2 | 1419329.2 | -5723059.2 | 350 | 0 | 0 | -350 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
SAN ANTONIO | 1042-01-032 | KENDALL | RM 474 | 2020-04-15 | 4456842.62 | 514684.97 | 5142601.26 | 685758.64 | 261 | 311 | 52 | 50 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0632-04-034 | HARRISON | FM 9 | 2020-04-16 | 2792494.9 | 7964.06 | 2852225.55 | 59730.65 | 87 | 98 | 0 | 11 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0150-01-028 | MASON | SH 29 | 2020-04-16 | 607278.53 | -5495.7 | 592189.48 | -15089.05 | 37 | 18 | 0 | -19 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 3256-02-089 | HARRIS | SL 8 | 2020-04-16 | 26822716.09 | 659004.8 | 28961474.45 | 2138758.36 | 536 | 548 | 14 | 12 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | MEDIUM | FY20
AUSTIN | 0700-03-142 | TRAVIS | SH 71 | 2020-04-17 | 4059393.25 | 624691.27 | 5102571.21 | 1043177.96 | 62 | 68 | 0 | 6 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 0008-07-035 | TARRANT | SH 180 | 2020-04-17 | 6444576.45 | -424550.67 | 5648567.33 | -796009.12 | 96 | 167 | 71 | 71 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 0014-02-051 | TARRANT | IH 35W | 2020-04-17 | 2034583.75 | 347516.76 | 2251698.01 | 217114.26 | 171 | 215 | 66 | 44 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
ODESSA | 1639-01-014 | REEVES | FM 1450 | 2020-04-17 | 10632822.07 | -60906.73 | 10302236.94 | -330585.13 | 200 | 240 | 40 | 40 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0009-13-159 | HUNT | IH 30 | 2020-04-17 | 23164560.31 | 645054.19 | 24224192.52 | 907017.83 | 493 | 514 | 27 | 21 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | Y | MEDIUM | FY20
SAN ANTONIO | 0291-11-021 | BEXAR | SS 421 | 2020-04-17 | 320840 | 7590 | 310976.9 | -9863.1 | 58 | 40 | 0 | -18 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0156-06-052 | BAYLOR | US 82 | 2020-04-17 | 3745737.67 | 55399.93 | 3420099.01 | -325638.66 | 212 | 245 | 3 | 33 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0016-07-132 | BEXAR | IH 35 | 2020-04-18 | 287874.5 | 2852.08 | 287432.07 | -442.43 | 57 | 49 | 0 | -8 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0072-07-068 | BEXAR | IH 10 | 2020-04-18 | 7586328.53 | 317180.72 | 7513352.36 | -72976.17 | 387 | 522 | 139 | 135 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0252-01-085 | BURNET | US 281 | 2020-04-20 | 562104.6 | 45448.7 | 662244.48 | 100139.88 | 17 | 6 | 0 | -11 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 0172-06-093 | TARRANT | SS 280 | 2020-04-20 | 1037381.32 | -157832.69 | 673339.75 | -364041.57 | 43 | 36 | 0 | -7 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0598-02-100 | BRAZORIA | SH 288 | 2020-04-20 | 4993779.69 | 280426.82 | 5603683.29 | 609903.6 | 183 | 198 | 15 | 15 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0301-03-026 | FRIO | SH 85 | 2020-04-20 | 1754395.66 | -107372.37 | 1595233.5 | -159162.16 | 105 | 86 | 0 | -19 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
BEAUMONT | 0065-06-063 | HARDIN | US 69 | 2020-04-21 | 10637780.19 | 85869.34 | 10746729.99 | 108949.8 | 262 | 246 | 5 | -16 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
BEAUMONT | 0920-03-034 | HARDIN | CR | 2020-04-21 | 586641.7 | 645.85 | 573985.55 | -12656.15 | 105 | 125 | 0 | 20 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
EL PASO | 0924-06-450 | EL PASO | VA | 2020-04-22 | 1766126.5 | -188800 | 1356729.83 | -409396.67 | 235 | 237 | 2 | 2 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 1414-01-019 | GALVESTON | FM 528 | 2020-04-22 | 204386.5 | 19678.99 | 222597.19 | 18210.69 | 24 | 24 | 0 | 0 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0221-02-026 | RED RIVER | US 271 | 2020-04-22 | 841028.2 | 131623.5 | 1015451.52 | 174423.32 | 93 | 125 | 32 | 32 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 1200-01-027 | WILLIAMSON | FM 973 | 2020-04-23 | 1408397.94 | -14115.96 | 1299082.73 | -109315.21 | 28 | 22 | 0 | -6 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
EL PASO | 0924-06-457 | EL PASO | CS | 2020-04-23 | 6591274.78 | 391102.31 | 6994151.99 | 381757.68 | 240 | 409 | 111 | 169 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
LAREDO | 0037-03-083 | ZAVALA | US 83 | 2020-04-23 | 687075.49 | 8305.71 | 690976.39 | 3900.9 | 60 | 40 | 0 | -20 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
LAREDO | 0086-14-061 | WEBB | SL 20 | 2020-04-23 | 25541056.4 | -682953.13 | 25497977.18 | -43079.22 | 596 | 753 | 28 | 157 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | MEDIUM | FY20
ATLANTA | 1176-02-019 | TITUS | FM 899 | 2020-04-24 | 1121133.28 | 13811.96 | 1122994.24 | 1860.96 | 115 | 117 | 0 | 2 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
FORT WORTH | 1606-01-034 | WISE | FM 1658 | 2020-04-24 | 80011 | -6080 | 71691 | -8320 | 22 | 5 | 0 | -17 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0271-07-322 | HARRIS | IH 10 | 2020-04-24 | 529715.95 | 25874.4 | 618583.47 | 88867.52 | 55 | 110 | 0 | 55 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0136-07-050 | LAMAR | BU 271B | 2020-04-24 | 1740082.17 | 8771.05 | 1774234.4 | 34152.23 | 54 | 54 | 0 | 0 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ABILENE | 0006-01-100 | MITCHELL | IH 20 | 2020-04-27 | 328277.7 | -27148.4 | 304180.6 | -24097.1 | 93 | 85 | 0 | -8 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ABILENE | 0006-15-034 | NOLAN | BI 20-M | 2020-04-27 | 4949400 | 63839.1 | 5280791.11 | 331391.11 | 139 | 146 | 8 | 7 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0392-01-073 | MORRIS | US 259 | 2020-04-27 | 7028104.55 | -81310.26 | 7097634.48 | 69529.93 | 275 | 247 | 0 | -28 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0500-01-150 | GALVESTON | IH 45 | 2020-04-27 | 3322042.95 | 201268.39 | 3448820.53 | 126777.58 | 105 | 100 | 0 | -5 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
LAREDO | 3621-01-014 | VAL VERDE | SL 79 | 2020-04-27 | 11318353.33 | 24138.32 | 10992056.19 | -326297.14 | 245 | 240 | 0 | -5 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0014-07-103 | HILL | SH 81 | 2020-04-27 | 482159.2 | 0 | 462891.7 | -19267.5 | 30 | 31 | 0 | 1 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0347-02-030 | GONZALES | SH 97 | 2020-04-27 | 2265659.38 | 0 | 2267447.11 | 1787.73 | 30 | 67 | 0 | 37 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AMARILLO | 0904-13-024 | GRAY | CR | 2020-04-28 | 1525326 | 133182.1 | 1701928.1 | 176602.1 | 185 | 244 | 63 | 59 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
EL PASO | 0002-12-023 | EL PASO | US 62 | 2020-04-28 | 3537952.65 | -199622.61 | 3408388.16 | -129564.49 | 294 | 292 | 0 | -2 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
EL PASO | 0924-06-533 | EL PASO | VA | 2020-04-28 | 1330984.07 | 183307.04 | 1358038.61 | 27054.54 | 100 | 140 | 40 | 40 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0500-04-134 | GALVESTON | IH 45 | 2020-04-28 | 960543.57 | 257709.67 | 1261394.5 | 300850.93 | 45 | 67 | 52 | 22 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AMARILLO | 0357-05-025 | ARMSTRONG | SH 207 | 2020-04-30 | 2257957 | 324422.58 | 2512173.75 | 254216.75 | 96 | 152 | 58 | 56 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PHARR | 0921-06-303 | CAMERON | VA | 2020-04-30 | 361733 | 54554.13 | 418115.49 | 56382.49 | 54 | 60 | 8 | 6 | APRIL | APR-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0190-01-021 | FRANKLIN | SH 37 | 2020-05-01 | 20387243.98 | 196746.07 | 21234077.98 | 846834 | 457 | 586 | 136 | 129 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | MEDIUM | FY20
PARIS | 0901-19-181 | GRAYSON | CR | 2020-05-01 | 1074079.5 | 0 | 1074136.95 | 57.45 | 173 | 141 | 0 | -32 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0901-29-087 | LAMAR | VA | 2020-05-01 | 679839.4 | 14209.09 | 699865.69 | 20026.29 | 344 | 195 | 0 | -149 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0143-08-091 | DE WITT | US 87 | 2020-05-01 | 10180818.7 | -205628.82 | 10140567.62 | -40251.08 | 246 | 277 | 31 | 31 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
AUSTIN | 0396-09-021 | LLANO | RM 152 | 2020-05-04 | 1011049.85 | 7003.92 | 900000.98 | -118052.79 | 161 | 148 | 0 | -13 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0088-05-092 | VICTORIA | US 59 | 2020-05-04 | 8914435.17 | 10085.45 | 8957164.76 | 42729.59 | 165 | 196 | 34 | 31 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
YOAKUM | 1090-05-015 | CALHOUN | FM 1593 | 2020-05-04 | 1354288.45 | 30619.07 | 1438294.67 | 84006.22 | 67 | 137 | 14 | 70 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0016-01-125 | TRAVIS | SL 275 | 2020-05-05 | 1030069.64 | -98832.82 | 951767.57 | -78302.07 | 26 | 30 | 4 | 4 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
AUSTIN | 0273-04-036 | WILLIAMSON | US 183 | 2020-05-05 | 3898284.65 | -8437.34 | 4037115.75 | 138831.1 | 67 | 92 | 0 | 25 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
LUFKIN | 0118-08-074 | NACOGDOCHES | SH 21 | 2020-05-05 | 1578551 | 69176.69 | 1679970.77 | 101419.77 | 205 | 232 | 30 | 27 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
YOAKUM | 0716-02-042 | COLORADO | FM 109 | 2020-05-05 | 3476586.21 | 4854.5 | 3312245.25 | -164340.96 | 169 | 137 | 0 | -32 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0222-05-048 | MARION | SH 49 | 2020-05-06 | 95254 | 0 | 90408.4 | -4845.6 | 40 | 22 | 0 | -18 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WACO | 0184-03-040 | BELL | SH 53 | 2020-05-06 | 2670992.39 | 10598.52 | 2672318.48 | 1326.09 | 45 | 60 | 0 | 15 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
ABILENE | 0437-02-014 | CALLAHAN | US 283 | 2020-05-07 | 3117046.36 | 34754.94 | 3006764.05 | -110282.31 | 179 | 301 | 0 | 122 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 0113-13-175 | TRAVIS | SH 71 | 2020-05-07 | 3958941.6 | 210350.23 | 4406290.77 | 447349.17 | 117 | 107 | 0 | -10 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
AUSTIN | 0914-00-414 | TRAVIS | VA | 2020-05-07 | 1954799.49 | 39263.07 | 1975490.73 | 20691.24 | 125 | 83 | 0 | -42 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0976-01-019 | HARRIS | FM 865 | 2020-05-07 | 13285921.44 | 1881405.88 | 15371043.06 | 2085121.62 | 305 | 317 | 8 | 12 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0823-01-029 | COOKE | FM 373 | 2020-05-07 | 2899372.26 | 2055.81 | 3007213.5 | 107841.24 | 204 | 201 | 1 | -3 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
ATLANTA | 0919-00-079 | CASS | VA | 2020-05-08 | 1112297.25 | 0 | 1126118.02 | 13820.77 | 50 | 32 | 0 | -18 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0045-08-038 | LAMAR | US 82 | 2020-05-08 | 200076.16 | 6014.58 | 207554.41 | 7478.25 | 100 | 72 | 0 | -28 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0400-02-053 | HOPKINS | SH 19 | 2020-05-08 | 837425.93 | -71707.96 | 828108.53 | -9317.4 | 48 | 48 | 0 | 0 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 0901-27-048 | RED RIVER | VA | 2020-05-08 | 519916.51 | 76833.55 | 585459.3 | 65542.79 | 133 | 147 | 14 | 14 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PARIS | 1690-01-120 | LAMAR | US 271 | 2020-05-08 | 375115.5 | -36372 | 332816.25 | -42299.25 | 29 | 32 | 0 | 3 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
EL PASO | 2552-03-054 | EL PASO | SL 375 | 2020-05-11 | 21784387.32 | -980765.67 | 20712003.74 | -1072383.58 | 452 | 544 | 85 | 92 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | MEDIUM | FY20
WACO | 1187-01-029 | CORYELL | FM 929 | 2020-05-11 | 9397775.38 | -284527.24 | 8205273.34 | -1192502.04 | 60 | 55 | 0 | -5 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-20-021 | WILBARGER | BU 287F | 2020-05-11 | 739514.5 | 0 | 662764.53 | -76749.97 | 85 | 67 | 0 | -18 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AMARILLO | 0041-07-107 | POTTER | US 87 | 2020-05-12 | 12390506.45 | -104156.8 | 13006340.69 | 615834.24 | 92 | 99 | 0 | 7 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
LUFKIN | 0200-01-091 | ANGELINA | US 69 | 2020-05-12 | 114856.5 | 0 | 112185.55 | -2670.95 | 30 | 13 | 0 | -17 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
AUSTIN | 2103-01-035 | WILLIAMSON | RM 2243 | 2020-05-13 | 1310876.26 | 0 | 1437294.47 | 126418.21 | 72 | 77 | 0 | 5 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | Y | SMALL | FY20
DALLAS | 0561-01-024 | KAUFMAN | SH 274 | 2020-05-13 | 3753154.82 | 7643.24 | 3600922.63 | -152232.19 | 96 | 96 | 0 | 0 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
PHARR | 0220-05-069 | CAMERON | SH 48 | 2020-05-13 | 5234721.77 | 226468.57 | 5524820.21 | 290098.44 | 80 | 121 | 25 | 41 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 0910-16-039 | SMITH | CS | 2020-05-13 | 469505.5 | -2619.6 | 472264.82 | 2759.32 | 45 | 43 | 0 | -2 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 0910-16-140 | SMITH | CR | 2020-05-13 | 719184.75 | -46502.2 | 678031.11 | -41153.64 | 179 | 102 | 0 | -77 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
BROWNWOOD | 0007-03-092 | EASTLAND | IH 20 | 2020-05-14 | 9089126.43 | -659046.33 | 7717965.56 | -1371160.87 | 57 | 62 | 5 | 5 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 0180-10-083 | SAN PATRICIO | SH 361 | 2020-05-14 | 3356712.65 | 143031.41 | 3583055.7 | 226343.05 | 87 | 95 | 8 | 8 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0051-09-120 | GALVESTON | FM 3005 | 2020-05-14 | 2837928.34 | -98944.5 | 2880806.6 | 42878.26 | 60 | 55 | 0 | -5 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
SAN ANTONIO | 0915-00-194 | BEXAR | VA | 2020-05-14 | 1756584.32 | 168938.06 | 2097843.52 | 341259.2 | 123 | 164 | 45 | 41 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
TYLER | 0910-12-125 | VAN ZANDT | CR | 2020-05-14 | 904834.8 | 24778.56 | 897902.3 | -6932.5 | 226 | 224 | 0 | -2 | MAY | MAY-20 | 2019-07-01 | Q3 | N | N | N | SMALL | FY20
HOUSTON | 0051-02-079 | HARRIS | SH 3 | 2020-06-09 | 1755643.65 | 733029.07 | 2583290.95 | 827647.3 | 132 | 125 | 4 | -7 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0044-11-002 | WICHITA | BU 287J | 2020-06-09 | 8903751.77 | 153921.85 | 9255551.25 | 351799.48 | 62 | 74 | 0 | 12 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0320-03-100 | WILLIAMSON | SH 95 | 2020-06-10 | 1339951.97 | 154640 | 1508922.11 | 168970.14 | 77 | 84 | 7 | 7 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BRYAN | 0116-04-100 | BRAZOS | SH 21 | 2020-06-10 | 5427954.28 | 2430727.61 | 8285714.22 | 2857759.94 | 135 | 182 | 49 | 47 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0390-03-035 | ANGELINA | SH 147 | 2020-06-10 | 776953.95 | 0 | 746606.31 | -30347.64 | 109 | 104 | 0 | -5 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 1673-01-008 | VAN ZANDT | FM 1653 | 2020-06-10 | 3972777 | -165486.08 | 3617517.75 | -355259.25 | 344 | 328 | 0 | -16 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ABILENE | 0006-18-058 | TAYLOR | BI 20-R | 2020-06-11 | 5844817.84 | -204672.54 | 5087182.49 | -757635.35 | 162 | 231 | -5 | 69 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ABILENE | 0908-19-027 | SCURRY | VA | 2020-06-11 | 1138632.89 | 65770.13 | 1488339.8 | 349706.91 | 42 | 32 | 0 | -10 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ABILENE | 1503-02-011 | HOWARD | FM 1584 | 2020-06-11 | 3443262.37 | 28421.89 | 3219018.74 | -224243.63 | 210 | 190 | 0 | -20 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ATLANTA | 0632-04-032 | HARRISON | FM 451 | 2020-06-11 | 4700001.75 | 40544.98 | 4772820.59 | 72818.84 | 105 | 93 | 0 | -12 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | Y | N | SMALL | FY20
HOUSTON | 0389-13-059 | HARRIS | SH 146 | 2020-06-11 | 1277107.8 | 0 | 1284391.69 | 7283.89 | 105 | 105 | 0 | 0 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0055-08-122 | MCLENNAN | US 84 | 2020-06-11 | 986493 | 15973.81 | 1044897.37 | 58404.37 | 60 | 48 | 0 | -12 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0137-10-025 | CLAY | FM 174 | 2020-06-11 | 656778.17 | 0 | 522420.34 | -134357.83 | 75 | 67 | 0 | -8 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AMARILLO | 0042-03-042 | ARMSTRONG | US 287 | 2020-06-12 | 6591547.92 | 45591.3 | 7102173.94 | 510626.02 | 73 | 60 | 0 | -13 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0047-09-036 | COLLIN | SH 5 | 2020-06-12 | 15172926.19 | 10134.58 | 14579529.5 | -593396.69 | 242 | 237 | 0 | -5 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
LUFKIN | 0063-06-098 | SHELBY | US 96 | 2020-06-12 | 9572121.03 | 92855.2 | 9886471.02 | 314349.99 | 120 | 169 | 29 | 49 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0117-07-040 | HOUSTON | SH 21 | 2020-06-12 | 11462865.25 | 1001327.41 | 14102286.18 | 2639420.93 | 408 | 622 | 214 | 214 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0175-02-093 | SHELBY | US 84 | 2020-06-12 | 1365031.81 | 37000 | 1446840.34 | 81808.53 | 38 | 34 | 0 | -4 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0009-04-061 | ROCKWALL | SH 66 | 2020-06-15 | 15872365.34 | 698081.94 | 14895700.29 | -976665.05 | 505 | 529 | 7 | 24 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
HOUSTON | 0271-14-231 | HARRIS | IH 610 | 2020-06-15 | 7781945.15 | 544338.52 | 9248088.02 | 1466142.87 | 330 | 323 | 0 | -7 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0382-02-036 | FALLS | SH 7 | 2020-06-15 | 6187425.2 | -84789.9 | 6324365.81 | 136940.61 | 90 | 105 | 15 | 15 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0909-38-080 | FALLS | CR | 2020-06-15 | 933888.42 | 5964.64 | 950167.74 | 16279.32 | 210 | 102 | 0 | -108 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ATLANTA | 0063-04-061 | PANOLA | US 59 | 2020-06-16 | 134765 | 9500 | 140390.1 | 5625.1 | 36 | 8 | 0 | -28 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 0086-20-022 | NUECES | FM 665 | 2020-06-16 | 7653200.28 | -945422.88 | 6756447.28 | -896753 | 81 | 73 | 0 | -8 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 1755-01-019 | WILLIAMSON | RM 1869 | 2020-06-17 | 287073.15 | -4040.85 | 282791.87 | -4281.28 | 33 | 27 | 0 | -6 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 3417-01-030 | TRAVIS | FM 734 | 2020-06-17 | 279705 | 0 | 254554.7 | -25150.3 | 22 | 9 | 0 | -13 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PHARR | 0220-03-030 | CAMERON | US 281 | 2020-06-17 | 3939634.17 | 161339.6 | 4153776.92 | 214142.75 | 320 | 325 | 6 | 5 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 0016-05-115 | COMAL | IH 35 | 2020-06-17 | 7256065.09 | 1343022.71 | 9110794.74 | 1854729.65 | 408 | 536 | 129 | 128 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
SAN ANTONIO | 0215-06-037 | KENDALL | SH 46 | 2020-06-17 | 8970343.48 | 1260530.65 | 10119457.66 | 1149114.18 | 413 | 530 | 120 | 117 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 0915-00-204 | BEXAR | VA | 2020-06-17 | 1349187 | 17345.57 | 1327910.38 | -21276.62 | 320 | 314 | 0 | -6 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CHILDRESS | 0541-01-028 | BRISCOE | SH 256 | 2020-06-18 | 113928.08 | -3600 | 109630.27 | -4297.81 | 54 | 101 | 0 | 47 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CHILDRESS | 1053-01-016 | HALL | FM 658 | 2020-06-18 | 774679.7 | 48018.66 | 984021.66 | 209341.96 | 154 | 193 | 23 | 39 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
EL PASO | 0374-08-021 | CULBERSON | US 62 | 2020-06-18 | 1434496 | -67723.35 | 1381022.5 | -53473.5 | 100 | 100 | 0 | 0 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 0174-04-033 | FANNIN | FM 100 | 2020-06-18 | 1423584.72 | 0 | 1434238.35 | 10653.63 | 68 | 54 | 0 | -14 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 0901-29-082 | LAMAR | CR | 2020-06-18 | 1097243.75 | 0 | 1071191.13 | -26052.62 | 247 | 192 | 0 | -55 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0914-00-426 | TRAVIS | VA | 2020-06-19 | 667921.72 | -7390.59 | 635046.32 | -32875.4 | 29 | 16 | 0 | -13 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BROWNWOOD | 0825-02-021 | MCCULLOCH | US 190 | 2020-06-22 | 1191745.5 | 0 | 1213681.46 | 21935.96 | 136 | 134 | 0 | -2 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 1206-01-018 | LIVE OAK | FM 1358 | 2020-06-22 | 2572494.78 | 162395.55 | 2685198.42 | 112703.64 | 202 | 200 | 8 | -2 | JUNE | JUN-20 | 2019-10-01 | Q4 | Y | N | N | SMALL | FY20
CORPUS CHRISTI | 1959-01-014 | LIVE OAK | FM 2049 | 2020-06-22 | 6025846.06 | 340292.46 | 6543265.74 | 517419.68 | 202 | 266 | 74 | 64 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUBBOCK | 0067-06-052 | HALE | IH 27 | 2020-06-22 | 2885701.5 | 55472 | 2259414.68 | -626286.82 | 246 | 228 | 0 | -18 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 2455-01-032 | GRAYSON | FM 1417 | 2020-06-23 | 19817292.16 | -9609877.9 | 10426234.37 | -9391057.79 | 424 | 265 | -141 | -159 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
TYLER | 3199-01-008 | ANDERSON | FM 2054 | 2020-06-23 | 2573741.95 | 5010.4 | 2790437.82 | 216695.87 | 125 | 152 | 30 | 27 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0015-02-048 | MCLENNAN | IH 35 | 2020-06-23 | 120722098.7 | 17131950.62 | 139762922.33 | 19040823.63 | 1210 | 1997 | 787 | 787 | JUNE | JUN-20 | 2019-10-01 | Q4 | Y | N | N | LARGE | FY20
ODESSA | 0004-02-058 | WARD | IH 20 | 2020-06-24 | 24141875.15 | -148234.68 | 24175230.82 | 33355.67 | 351 | 269 | 0 | -82 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | MEDIUM | FY20
ODESSA | 0139-02-025 | REEVES | US 285 | 2020-06-24 | 32027183.64 | 9358559.03 | 41381966.16 | 9082414.21 | 545 | 412 | 0 | -133 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | MEDIUM | FY20
ODESSA | 0906-00-177 | ECTOR | VA | 2020-06-24 | 3767757.53 | 10000 | 3548721.27 | -219036.26 | 101 | 84 | 0 | -17 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
ODESSA | 1188-02-084 | MIDLAND | SL 250 | 2020-06-24 | 12997699.17 | 2928497.45 | 15890964.98 | 2893265.81 | 306 | 330 | 35 | 24 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
AUSTIN | 0015-09-173 | WILLIAMSON | IH 35 | 2020-06-25 | 28127003.83 | 1581684.42 | 30741752.6 | 2647248.77 | 555 | 656 | 111 | 101 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
DALLAS | 0918-47-176 | DALLAS | CS | 2020-06-25 | 2950293.01 | 136205.79 | 3116370.23 | 166077.22 | 275 | 254 | 0 | -21 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
EL PASO | 0002-12-025 | EL PASO | US 62 | 2020-06-25 | 724708.7 | 0 | 674682.92 | -50025.78 | 60 | 56 | 0 | -4 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
FORT WORTH | 0008-16-046 | TARRANT | IH 20 | 2020-06-25 | 1511128.67 | 0 | 1447607.03 | -63521.64 | 171 | 66 | 0 | -105 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
FORT WORTH | 1310-03-026 | WISE | FM 2264 | 2020-06-25 | 7015561.58 | 1226887.85 | 8156063.55 | 955478.84 | 406 | 418 | 12 | 12 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 0910-00-126 | SMITH | VA | 2020-06-25 | 738213.91 | 83079.77 | 836463.36 | 98249.45 | 75 | 62 | 0 | -13 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-17-032 | WICHITA | BU 287J | 2020-06-25 | 761013.13 | 0 | 704885.34 | -56127.79 | 60 | 88 | 0 | 28 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0116-01-039 | LEE | SH 21 | 2020-06-26 | 12787554.01 | -337420.74 | 13453796.61 | 666242.6 | 130 | 154 | 0 | 24 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0914-00-442 | TRAVIS | VA | 2020-06-26 | 235560 | 0 | 235455 | -105 | 20 | 9 | 0 | -11 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0271-07-305 | HARRIS | IH 10 | 2020-06-26 | 1166377.54 | 961829.26 | 2137661.84 | 971284.3 | 67 | 75 | 31 | 8 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0909-00-049 | MCLENNAN | VA | 2020-06-26 | 1647633.4 | -1035 | 1580560.65 | -67072.75 | 198 | 321 | 0 | 123 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 1198-03-010 | BELL | FM 2670 | 2020-06-26 | 2672893.94 | -17974.74 | 2509473.85 | -163420.09 | 90 | 78 | 0 | -12 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-05-108 | WILBARGER | US 287 | 2020-06-29 | 6884724 | 9360 | 7274595.84 | 389871.84 | 50 | 71 | 0 | 21 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
EL PASO | 0002-01-055 | EL PASO | SH 20 | 2020-06-30 | 7093503.35 | 191688.92 | 7350081.87 | 207945.58 | 385 | 431 | 46 | 46 | JUNE | JUN-20 | 2019-10-01 | Q4 | Y | N | N | SMALL | FY20
PHARR | 0039-17-201 | HIDALGO | IH 2 | 2020-06-30 | 2966777.57 | 7294.3 | 2870390.44 | -96387.13 | 120 | 103 | 0 | -17 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
WACO | 0909-38-079 | FALLS | CR | 2020-06-30 | 362831.1 | 0 | 353821.71 | -9009.39 | 60 | 45 | 0 | -15 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
YOAKUM | 0025-07-065 | GONZALES | SH 97 | 2020-06-30 | 7309912.8 | 480570.32 | 8213775.43 | 903862.63 | 45 | 33 | 4 | -12 | JUNE | JUN-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AMARILLO | 0030-07-019 | HEMPHILL | US 83 | 2020-07-01 | 14437253.18 | -232936.61 | 14442306.73 | 5053.55 | 98 | 140 | 0 | 42 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0836-02-075 | BELL | SH 195 | 2020-07-01 | 288044.6 | 0 | 289525.6 | 1481 | 45 | 38 | 0 | -7 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 2311-01-041 | MCLENNAN | SL 340 | 2020-07-01 | 243475 | 4185 | 252377.5 | 8902.5 | 30 | 26 | 0 | -4 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ABILENE | 1529-02-010 | SCURRY | FM 1607 | 2020-07-02 | 197824 | 0 | 171219 | -26605 | 43 | 43 | 0 | 0 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BROWNWOOD | 0011-08-026 | STEPHENS | US 180 | 2020-07-02 | 13412991.58 | 1367534.26 | 15684475.94 | 2271484.36 | 459 | 551 | 129 | 92 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0596-01-021 | HILL | FM 66 | 2020-07-02 | 849409.1 | 23421.75 | 757817.61 | -91591.49 | 90 | 44 | 0 | -46 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 2263-02-098 | NUECES | SH 361 | 2020-07-03 | 4671605 | 334400.06 | 5005154.12 | 333549.12 | 159 | 225 | 66 | 66 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0403-02-019 | SAN JACINTO | FM 224 | 2020-07-03 | 516228.1 | 32624.72 | 509885.43 | -6342.67 | 206 | 204 | 5 | -2 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0533-01-020 | BURNET | PR 4 | 2020-07-08 | 1963009.89 | 181208.23 | 2258397.5 | 295387.61 | 55 | 46 | 0 | -9 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BEAUMONT | 0341-04-070 | TYLER | US 287 | 2020-07-08 | 5442445.86 | 633874.6 | 5572095.83 | 129649.97 | 90 | 104 | 20 | 14 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BRYAN | 0117-01-052 | BRAZOS | US 190 | 2020-07-08 | 321352.99 | 19323.68 | 343749.6 | 22396.61 | 59 | 56 | 0 | -3 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0081-05-044 | DENTON | FM 3524 | 2020-07-08 | 1667506.66 | 232579.86 | 1536480.03 | -131026.63 | 164 | 178 | 15 | 14 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0092-06-101 | NAVARRO | IH 45 | 2020-07-08 | 58762184.65 | 7050592.71 | 65571307.09 | 6809122.44 | 772 | 782 | 15 | 10 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | LARGE | FY20
DALLAS | 0197-04-080 | KAUFMAN | US 175 | 2020-07-08 | 6161838.27 | 134751.2 | 6704292.18 | 542453.91 | 142 | 152 | 10 | 10 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0177-07-114 | HARRIS | IH 69 | 2020-07-08 | 1311904.39 | 424417.6 | 1787446.32 | 475541.93 | 50 | 30 | 0 | -20 | JULY | JUL-20 | 2019-10-01 | Q4 | N | Y | N | SMALL | FY20
HOUSTON | 0912-70-100 | HARRIS | VA | 2020-07-09 | 3140223.08 | -125739.12 | 2773180.42 | -367042.66 | 203 | 222 | 0 | 19 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0176-03-135 | ANGELINA | US 59 | 2020-07-10 | 8332374.81 | 22530.65 | 8391755.73 | 59380.92 | 119 | 161 | 41 | 42 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-08-076 | WICHITA | US 287 | 2020-07-10 | 1090136.6 | 0 | 1111396.6 | 21260 | 109 | 108 | 0 | -1 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BEAUMONT | 0920-00-121 | JEFFERSON | VA | 2020-07-14 | 259711.73 | 0 | 249039.21 | -10672.52 | 45 | 39 | 0 | -6 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 3508-01-028 | BEXAR | SH 151 | 2020-07-14 | 7394842.34 | 69825.24 | 7555440.44 | 160598.1 | 202 | 202 | 0 | 0 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ATLANTA | 0247-01-057 | PANOLA | US 79 | 2020-07-15 | 8993196.63 | -416650.14 | 8719869.83 | -273326.8 | 116 | 133 | 1 | 17 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0095-02-118 | DALLAS | US 80 | 2020-07-15 | 1497828.55 | 51319.27 | 1540900.18 | 43071.63 | 130 | 141 | 13 | 11 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PHARR | 0039-01-094 | STARR | US 83 | 2020-07-15 | 1161964.96 | 0 | 1191740.87 | 29775.91 | 60 | 45 | 0 | -15 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANGELO | 0907-00-186 | TOM GREEN | VA | 2020-07-15 | 1506526.8 | 0 | 1419045.8 | -87481 | 61 | 60 | 0 | -1 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0978-01-034 | GALVESTON | FM 646 | 2020-07-16 | 12830994 | 508660.34 | 13627559.22 | 796565.22 | 310 | 342 | 37 | 32 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0176-08-024 | ANGELINA | FM 324 | 2020-07-16 | 533772.43 | 40319.02 | 574468.18 | 40695.75 | 129 | 128 | 3 | -1 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 0769-01-028 | LAMAR | FM 197 | 2020-07-16 | 2376096.44 | 47653.01 | 2274871.29 | -101225.15 | 184 | 213 | 0 | 29 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0914-00-438 | TRAVIS | VA | 2020-07-17 | 72572.5 | -10521 | 64193.51 | -8378.99 | 32 | 14 | 0 | -18 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ODESSA | 0021-06-027 | PECOS | US 90 | 2020-07-20 | 1150725.18 | 0 | 997644.66 | -153080.52 | 80 | 76 | 0 | -4 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
ODESSA | 1842-01-016 | MARTIN | FM 26 | 2020-07-20 | 935180.63 | 98350.33 | 1136464.61 | 201283.98 | 60 | 86 | 30 | 26 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ATLANTA | 0062-06-058 | MARION | US 59 | 2020-07-21 | 1452714.45 | 8559.66 | 1503589.49 | 50875.04 | 265 | 78 | 0 | -187 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
FORT WORTH | 0902-00-201 | TARRANT | VA | 2020-07-21 | 362740.08 | 0 | 352587.28 | -10152.8 | 85 | 39 | 0 | -46 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0586-01-066 | BRAZORIA | SH 332 | 2020-07-21 | 2395790.47 | 586694.2 | 3135234.32 | 739443.85 | 95 | 113 | 21 | 18 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 0910-34-031 | HENDERSON | VA | 2020-07-21 | 324000 | 11838.64 | 296363.64 | -27636.36 | 35 | 31 | 0 | -4 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0231-03-146 | BELL | US 190 | 2020-07-21 | 4549397.66 | 945902.15 | 5580057.51 | 1030659.85 | 255 | 307 | 52 | 52 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0836-02-073 | BELL | SH 195 | 2020-07-21 | 8482505.86 | 58597.32 | 8984453.08 | 501947.22 | 75 | 72 | 0 | -3 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0015-09-179 | WILLIAMSON | IH 35 | 2020-07-22 | 12362005.96 | 960773.42 | 13639081.96 | 1248315.59 | 440 | 427 | -13 | -13 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0093-01-098 | NAVARRO | IH 45 | 2020-07-22 | 71994840.25 | 4196156.39 | 76304198.89 | 4309358.64 | 776 | 760 | 0 | -16 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | LARGE | FY20
SAN ANTONIO | 0016-08-036 | BEXAR | SL 368 | 2020-07-22 | 1345680 | 131282.76 | 1485448.81 | 139768.81 | 165 | 152 | 0 | -13 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0091-04-062 | COLLIN | SH 289 | 2020-07-23 | 1750000 | 0 | 1779484.33 | 29484.33 | 320 | 318 | 0 | -2 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-09-135 | WICHITA | IH 44 | 2020-07-24 | 8831585.37 | 78258.18 | 8874287.82 | 42702.45 | 119 | 225 | 76 | 106 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
EL PASO | 0020-04-016 | JEFF DAVIS | US 90 | 2020-07-25 | 11823087.68 | 6903040.59 | 18722731.53 | 6899643.85 | 180 | 401 | 226 | 221 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
HOUSTON | 3510-05-042 | HARRIS | SH 99 | 2020-07-27 | 183439.07 | 14630.14 | 182021.75 | -1417.32 | 53 | 51 | 0 | -2 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CHILDRESS | 0042-07-067 | DONLEY | US 287 | 2020-07-28 | 7991425.56 | 202372.63 | 7998387.81 | 6962.25 | 162 | 201 | 31 | 39 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CHILDRESS | 0925-14-009 | COTTLE | CR | 2020-07-28 | 818430 | 556.96 | 810326.96 | -8103.04 | 108 | 97 | 0 | -11 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0092-14-096 | DALLAS | IH 45 | 2020-07-28 | 8251402.99 | 359738.5 | 9554158.18 | 1302755.19 | 180 | 181 | 11 | 1 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
DALLAS | 0093-02-021 | NAVARRO | SH 14 | 2020-07-29 | 3351110.26 | -299095.07 | 3147419.78 | -203690.48 | 120 | 115 | 3 | -5 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
EL PASO | 2121-04-086 | EL PASO | IH 10 | 2020-07-29 | 1988429.78 | -27272.38 | 1969778.81 | -18650.97 | 50 | 50 | 0 | 0 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0014-07-104 | HILL | IH 35 | 2020-07-29 | 1195738.3 | -1730.6 | 1143370.48 | -52367.82 | 120 | 45 | 0 | -75 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
WACO | 0015-14-091 | BELL | IH 35 | 2020-07-29 | 241296935.09 | 56266545.85 | 306265215.57 | 64943583.62 | 1200 | 1660 | 460 | 460 | JULY | JUL-20 | 2019-10-01 | Q4 | Y | N | Y | LARGE | FY20
ATLANTA | 0945-03-009 | CASS | FM 3129 | 2020-07-30 | 9147321.5 | -228835.44 | 9386139.91 | 238818.41 | 175 | 201 | 15 | 26 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0048-08-051 | ELLIS | IH 35E | 2020-07-30 | 1534350.25 | 5669.5 | 1410548.66 | -123801.59 | 227 | 200 | 0 | -27 | JULY | JUL-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ODESSA | 0075-03-021 | PECOS | US 67 | 2020-08-03 | 329700 | 46720 | 368070 | 38370 | 26 | 53 | 27 | 27 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ODESSA | 0906-00-192 | ECTOR | VA | 2020-08-03 | 951628 | 0 | 831224.62 | -120403.38 | 99 | 74 | 0 | -25 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BEAUMONT | 0028-11-179 | ORANGE | IH 10 | 2020-08-05 | 12418604.5 | 548716.13 | 12644569.98 | 225965.48 | 275 | 309 | 41 | 34 | AUGUST | AUG-20 | 2019-10-01 | Q4 | Y | N | Y | SMALL | FY20
BEAUMONT | 0200-04-024 | JASPER | US 69 | 2020-08-05 | 8845117.27 | 5400 | 9478651.81 | 633534.54 | 105 | 105 | 0 | 0 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | Y | N | SMALL | FY20
HOUSTON | 0976-01-040 | HARRIS | FM 865 | 2020-08-05 | 189822.2 | 6930 | 197198.24 | 7376.04 | 40 | 13 | 0 | -27 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
FORT WORTH | 1309-01-033 | JACK | US 380 | 2020-08-06 | 3522043.03 | 410197.05 | 3720912.64 | 198869.61 | 85 | 106 | 21 | 21 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
WACO | 0909-22-177 | MCLENNAN | CR | 2020-08-06 | 999329.68 | 0 | 1009377.3 | 10047.62 | 165 | 137 | 0 | -28 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AMARILLO | 0904-00-173 | POTTER | VA | 2020-08-07 | 1169941.34 | 0 | 1169973.34 | 32 | 60 | 38 | 0 | -22 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
FORT WORTH | 0902-00-210 | TARRANT | VA | 2020-08-07 | 965582.7 | 1114.61 | 963066.31 | -2516.39 | 107 | 74 | 0 | -33 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0028-02-091 | HARRIS | US 90 | 2020-08-07 | 1983174.98 | 39256.68 | 2020161.8 | 36986.82 | 120 | 113 | 0 | -7 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 1414-05-014 | FORT BEND | FM 1462 | 2020-08-07 | 851224 | -57393.19 | 788452.34 | -62771.66 | 30 | 49 | 0 | 19 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LAREDO | 0018-03-058 | WEBB | IH 35 | 2020-08-07 | 503366.75 | 26251 | 522567.76 | 19201.01 | 98 | 73 | 0 | -25 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LAREDO | 0922-33-163 | WEBB | CS | 2020-08-07 | 361930 | 12945 | 392185.09 | 30255.09 | 101 | 45 | 0 | -56 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 0199-03-028 | CHEROKEE | US 69 | 2020-08-07 | 17687832.87 | -346398.43 | 17366359.67 | -321473.2 | 350 | 466 | 72 | 116 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | MEDIUM | FY20
CORPUS CHRISTI | 0074-06-228 | NUECES | IH 37 | 2020-08-10 | 496446.6 | 38000 | 492897.4 | -3549.2 | 129 | 143 | 20 | 14 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 2452-02-119 | BEXAR | SL 1604 | 2020-08-10 | 6253995.31 | 540692.46 | 7142025.09 | 888029.78 | 280 | 418 | 138 | 138 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
TYLER | 0492-05-026 | SMITH | FM 346 | 2020-08-10 | 2029446.31 | 12765.1 | 2038605.69 | 9159.38 | 206 | 252 | 17 | 46 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
YOAKUM | 0604-01-043 | MATAGORDA | FM 2031 | 2020-08-10 | 594007.87 | 0 | 591477.07 | -2530.8 | 45 | 31 | 0 | -14 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BROWNWOOD | 0079-03-048 | COMANCHE | US 67 | 2020-08-11 | 759958.98 | 30000 | 845189.8 | 85230.82 | 126 | 125 | 0 | -1 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BRYAN | 0675-06-096 | WALKER | IH 45 | 2020-08-11 | 6333633.62 | 1206805.77 | 7809754.84 | 1476121.22 | 110 | 122 | 17 | 12 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 0291-10-110 | BEXAR | SH 16 | 2020-08-11 | 2107961.75 | 190049.01 | 2048952.73 | -59009.02 | 190 | 140 | 0 | -50 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 0521-06-144 | BEXAR | IH 410 | 2020-08-11 | 1310012.92 | -7113.18 | 1300274.36 | -9738.56 | 105 | 107 | 4 | 2 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
YOAKUM | 0913-09-062 | WHARTON | CR | 2020-08-11 | 324876 | 0 | 325703.08 | 827.08 | 60 | 58 | 0 | -2 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
BROWNWOOD | 0007-06-264 | EASTLAND | IH 20 | 2020-08-12 | 848830.31 | -10171.8 | 812941.94 | -35888.37 | 68 | 73 | 5 | 5 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 2374-01-180 | DALLAS | IH 635 | 2020-08-12 | 11750606.54 | 1408722.11 | 13122478.85 | 1371872.31 | 250 | 391 | 143 | 141 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AMARILLO | 0275-01-177 | POTTER | IH 40 | 2020-08-13 | 36259776.7 | 2504970.11 | 40334241.55 | 4074464.85 | 332 | 607 | 192 | 275 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
HOUSTON | 0912-00-336 | HARRIS | VA | 2020-08-13 | 439963.75 | 37144.65 | 558199.81 | 118236.06 | 187 | 187 | 0 | 0 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 0045-09-101 | LAMAR | US 82 | 2020-08-13 | 1229691.6 | 19296.84 | 1185819.67 | -43871.93 | 102 | 100 | 4 | -2 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0196-03-276 | DALLAS | IH 35E | 2020-08-14 | 6021376.81 | 832534.64 | 6920644.48 | 899267.67 | 252 | 284 | 43 | 32 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0918-00-275 | DALLAS | VA | 2020-08-14 | 2600000 | 2694 | 2561499.5 | -38500.5 | 913 | 799 | 0 | -114 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0027-12-151 | FORT BEND | IH 69 | 2020-08-14 | 1458610 | -189275.36 | 1270905.06 | -187704.94 | 90 | 117 | 5 | 27 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 0047-02-147 | GRAYSON | SH 91 | 2020-08-14 | 219910 | 0 | 226944 | 7034 | 60 | 51 | 0 | -9 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CHILDRESS | 0925-00-071 | CHILDRESS | VA | 2020-08-17 | 1225792.01 | -74477.6 | 1180057.35 | -45734.66 | 65 | 42 | 0 | -23 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUBBOCK | 2767-02-004 | GARZA | FM 3519 | 2020-08-17 | 1306629.4 | 114750 | 1617520.3 | 310890.9 | 122 | 80 | 0 | -42 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 0016-19-024 | COMAL | FM 482 | 2020-08-17 | 15797806.84 | 72464.38 | 16470450.89 | 672644.05 | 135 | 122 | 0 | -13 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
SAN ANTONIO | 0025-02-210 | BEXAR | IH 10 | 2020-08-17 | 4697952.65 | 447000.26 | 5483046.63 | 785093.98 | 304 | 289 | 0 | -15 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
ATLANTA | 0218-01-096 | BOWIE | US 59 | 2020-08-18 | 4256573.99 | 106232.68 | 4461414.66 | 204840.67 | 75 | 74 | 0 | -1 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BRYAN | 0049-09-079 | BRAZOS | US 190 | 2020-08-18 | 388060 | 272414.55 | 653635.25 | 265575.25 | 52 | 79 | 26 | 27 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
EL PASO | 2121-02-159 | EL PASO | IH 10 | 2020-08-18 | 549261.6 | 6309.31 | 566055.34 | 16793.74 | 111 | 100 | 0 | -11 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PARIS | 0045-11-038 | LAMAR | US 82 | 2020-08-18 | 1691104.69 | 0 | 1641386.43 | -49718.26 | 157 | 83 | 0 | -74 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0133-07-029 | ARCHER | SH 114 | 2020-08-18 | 7554037.74 | 51776.52 | 7977860.8 | 423823.06 | 102 | 91 | 2 | -11 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0508-01-344 | HARRIS | IH 10 | 2020-08-19 | 1351369.79 | 39818.34 | 1383570.06 | 32200.27 | 90 | 76 | 0 | -14 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
PHARR | 0921-06-286 | CAMERON | CS | 2020-08-19 | 412715 | 4756.85 | 415971.85 | 3256.85 | 93 | 95 | 0 | 2 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BEAUMONT | 0508-04-168 | JEFFERSON | SH 73 | 2020-08-20 | 2402166.15 | 27696.45 | 2244730.91 | -157435.24 | 77 | 69 | 0 | -8 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
BROWNWOOD | 0011-07-051 | STEPHENS | US 180 | 2020-08-20 | 3484144.57 | 756514.23 | 4302954.03 | 818809.46 | 199 | 320 | 122 | 121 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
SAN ANTONIO | 0521-05-145 | BEXAR | IH 410 | 2020-08-20 | 2494814.18 | 204396.92 | 2794852.06 | 300037.88 | 41 | 50 | 11 | 9 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0056-02-033 | LIMESTONE | US 84 | 2020-08-20 | 9187964.04 | -603585 | 8411574.07 | -776389.97 | 168 | 175 | 6 | 7 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BROWNWOOD | 2561-01-011 | MCCULLOCH | SH 71 | 2020-08-21 | 2449573.59 | 57892.67 | 2571493.27 | 121919.68 | 204 | 237 | 4 | 33 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUBBOCK | 0905-00-092 | LUBBOCK | VA | 2020-08-21 | 4451653.2 | 138150 | 5190845.17 | 739191.97 | 100 | 126 | 14 | 26 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0064-03-021 | SAN AUGUSTINE | SH 147 | 2020-08-21 | 2279194.21 | 0 | 2076086.79 | -203107.42 | 174 | 91 | 0 | -83 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0911-00-078 | ANGELINA | VA | 2020-08-21 | 1368036.18 | 0 | 1238814 | -129222.18 | 118 | 150 | 0 | 32 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WACO | 0231-03-143 | BELL | US 190 | 2020-08-21 | 7287694.48 | -154328.57 | 7135381.08 | -152313.4 | 276 | 308 | 12 | 32 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
EL PASO | 2121-04-098 | EL PASO | IH 10 | 2020-08-23 | 12915901.72 | 214336.31 | 13093177.4 | 177275.68 | 271 | 352 | 59 | 81 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AUSTIN | 0114-04-069 | BASTROP | US 290 | 2020-08-24 | 1549780.63 | 0 | 1557124.17 | 7343.54 | 60 | 21 | 0 | -39 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
DALLAS | 0135-03-050 | COLLIN | US 380 | 2020-08-24 | 5260480.17 | 491215.64 | 5270271.03 | -103324.27 | 208 | 325 | 117 | 117 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0197-02-126 | DALLAS | US 175 | 2020-08-24 | 3063097.8 | 46087.74 | 2947339.22 | -115758.58 | 103 | 103 | 0 | 0 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 1567-02-031 | DENTON | FM 423 | 2020-08-24 | 746680.66 | 1759.99 | 743930.65 | -2750.01 | 109 | 109 | 0 | 0 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
HOUSTON | 0586-01-067 | BRAZORIA | SH 332 | 2020-08-24 | 433600.5 | 389953.51 | 842144.12 | 408543.62 | 55 | 34 | 0 | -21 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 0206-07-062 | RUSK | US 79 | 2020-08-24 | 1940981.26 | 51608.93 | 1934938.16 | -6043.1 | 80 | 74 | 0 | -6 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 1390-03-005 | WOOD | FM 1254 | 2020-08-24 | 1518305.71 | -64847.6 | 1422084.2 | -96221.51 | 108 | 107 | 0 | -1 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
BRYAN | 0858-02-021 | MILAM | FM 908 | 2020-08-25 | 1428673.97 | 322207.18 | 1761687.84 | 333013.87 | 87 | 129 | 42 | 42 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
CORPUS CHRISTI | 0366-06-042 | KARNES | SH 123 | 2020-08-25 | 19912126.65 | 2616806.01 | 23922411.72 | 4010285.07 | 400 | 621 | 221 | 221 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
DALLAS | 0009-03-045 | DALLAS | SH 66 | 2020-08-25 | 1750000 | 273287.98 | 2061463.95 | 311463.95 | 253 | 231 | 0 | -22 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0047-14-084 | COLLIN | US 75 | 2020-08-25 | 20106927.49 | 645339.19 | 21044315.68 | 937388.19 | 416 | 416 | 0 | 0 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | Y | N | MEDIUM | FY20
FORT WORTH | 1603-03-040 | TARRANT | FM 1709 | 2020-08-25 | 2474193.46 | 15908.98 | 2509606.73 | 35413.27 | 86 | 102 | 16 | 16 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | Y | SMALL | FY20
LUBBOCK | 0905-00-095 | LUBBOCK | VA | 2020-08-25 | 1274328.5 | 0 | 1245447.41 | -28881.09 | 182 | 63 | 0 | -119 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
LUFKIN | 0937-02-030 | HOUSTON | FM 227 | 2020-08-25 | 1388285.9 | -381613.71 | 918977.73 | -469308.17 | 144 | 48 | -95 | -96 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
TYLER | 3240-01-019 | WOOD | SL 564 | 2020-08-25 | 5773806.79 | 1052001.87 | 6893473.89 | 1119667.1 | 101 | 114 | 23 | 13 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
AMARILLO | 0169-03-036 | CARSON | US 60 | 2020-08-26 | 16196034.37 | 126493.94 | 16950422.24 | 754387.87 | 162 | 152 | 26 | -10 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | MEDIUM | FY20
WACO | 0909-38-082 | FALLS | CR | 2020-08-26 | 887643.5 | 0 | 870361.5 | -17282 | 210 | 145 | 0 | -65 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
WICHITA FALLS | 0043-06-088 | WILBARGER | US 70 | 2020-08-26 | 1693704.5 | -223849.05 | 1529449.79 | -164254.71 | 102 | 102 | 9 | 0 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20
DALLAS | 0816-05-022 | COLLIN | FM 2862 | 2020-08-31 | 3291224.79 | 10738.03 | 3237723.15 | -53501.64 | 238 | 186 | 0 | -52 | AUGUST | AUG-20 | 2019-10-01 | Q4 | N | N | N | SMALL | FY20

## LINE_GRAPH_DATA (hidden)
COUNTIFS(FINL,">="&B4-DAY(B4)+1,FINL,"<="&EOMONTH(B4,0))
FY 2020 Monthly Measures | [9 empty] | YTD
Month | Total Contracts | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO
SEP-19 | 0 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
OCT-19 | 0 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
NOV-19 | 0 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
DEC-19 | 0 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
JAN-20 | 0 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
FEB-20 | 0 | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
MAR-20 | 62 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | 0 | #N/A | #REF! | #N/A
APR-20 | 64 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | 0 | #N/A | #REF! | #N/A
MAY-20 | 38 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | 0 | #N/A | #REF! | #N/A
JUN-20 | 64 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | 0 | #N/A | #REF! | #N/A
JUL-20 | 52 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | 0 | #N/A | #REF! | #N/A
AUG-20 | 72 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #N/A | 0 | #N/A | #REF! | #N/A
FY20 | 352 | #REF! | #REF! | 0 | 0% | 0 | 0% | 0 | 0% | #REF! | #REF! | 0 | 0% | 0 | 0% | 0 | 0%
|  |  | #DIV/0! |  | #DIV/0! |  | 0% |  | #DIV/0! |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!

## Summary Previous FYs (hidden)
CONSTRUCTION SUMMARY PERFORMANCE REPORT | [12 empty] | 5- YEAR AVERAGES
FY | Projects Accepted | Percent On Budget | Percent On Time | Percent On Time Previous | Projects Awarded | Awarded Amounts Billions | Estimated Amounts Billions | Amounts Over / (Under) the Estimate | Percent Over the Estimate | Dollars per Project | Awarded Amounts | Estimated Amounts | Awarded Amounts | Estimated Amounts | Percent Over the Estimate | Projects Accepted | Projects Awarded
2009 | 802 | 83.92% | 57.11% | 72.57% | 699 | 3.0857 | 3.6429 | -0.5572 | -15.3% | 4414461.6445 | 3085708689.49 | 3642907501.26
2010 | 797 | 84.69% | 65.5% | 77.42% | 1063 | 3.2459 | 3.6441 | -0.39818 | -10.93% | 3053502.9899 | 3245873678.22 | 3644056349
2011 | 872 | 88.99% | 68.17% | 77.18% | 870 | 3.497 | 3.7036 | -0.20654 | -5.577% | 4019586.1947 | 3497039989.43 | 3703575068.62
2012 | 772 | 87.95% | 67.62% | 76.55% | 685 | 2.9722 | 3.0097 | -0.037491 | -1.246% | 4338962.4606 | 2972189285.54 | 3009680367 | 3.2002 | 3.5001 | -8.567% | 810.75 | 829.25
2013 | 682 | 86.07% | 63.49% | N/A | 797 | 4.2752 | 4.2598 | 0.015356 | 0.3605% | 5364094.8547 | 4275183599.18 | 4259827109.53 | 3.4152 | 3.652 | -6.484% | 785 | 822.8
2014 | 636 | 86.48% | 68.08% | N/A | 757 | 3.8596 | 3.9509 | -0.091307 | -2.311% | 5098575.683 | 3859621792 | 3950928942.48 | 3.57 | 3.7136 | -3.868% | 751.8 | 834.4
2015 | 607 | 86.16% | 63.92% | N/A | 856 | 4.3749 | 4.3622 | 0.012684 | 0.2908% | 5110843.7065 | 4374882212.76 | 4362198207.53 | 3.7958 | 3.8572 | -1.593% | 713.8 | 793
2016 | 711 | 83.4% | 63.29% | N/A | 737 | 4.3375 | 4.4843 | -0.14682 | -3.274% | 5885376.9172 | 4337522787.99 | 4484341769.73 | 3.9639 | 4.0134 | -1.234% | 681.6 | 766.4
2017 | 864 | 80.9% | 62.73% | N/A | 779 | 4.7365 | 5.0552 | -0.31875 | -6.305% | 6080199.4759 | 4736475391.74 | 5055222420.56 | 4.3167 | 4.4225 | -2.392% | 700 | 785.2
2018 | 859 | 83.82% | 64.96% | N/A | 825 | 5.7327 | 5.8693 | -0.13661 | -2.328% | 6948682.4486 | 5732663020.12 | 5869277068.62 | 4.6082 | 4.7444 | -2.87% | 735.4 | 790.8
2019 | 718 | 94.57% | 85.79% | N/A | 895 | 6.5145 | 6.3033 | 0.21118 | 3.35% | 7278753.2179 | 6514484130 | 6303301439 | 4.9259 | 5.0042 | -1.564% | 732.5 | 808.1667
2020 | 352 | #REF! | 0% |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 5.1392 | 5.2149 | -1.451% | 685.1667 | 818.4