## OTOB
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [11 empty] | Highway Construction Projects Completed March 1, 2021–August 31, 2021
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | AUGUST | 31 | 2021
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | AMOUNT PAID | OVER/UNDER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | OVER/UNDER SCHEDULE
EL PASO | 0167-01-095 | EL PASO | US 54 | 2021-03-03 | 33676148.92 | 1023499.29 | 35216455.5 | 1540306.58 | 460 | 603 | 144 | 287
EL PASO | 0665-01-009 | EL PASO | FM 3255 | 2021-03-03 | 3220964.88 | -34123.24 | 3181060.64 | -39904.24 | 100 | 74 | 0 | -26
EL PASO | 2552-02-034 | EL PASO | SL 375 | 2021-03-03 | 777686.3 | -4577.64 | 797641.35 | 19955.05 | 26 | 24 | 0 | -2
LUFKIN | 1407-01-028 | NACOGDOCHES | FM 1275 | 2021-03-03 | 718361.99 | 115006.5 | 965018.32 | 246656.33 | 193 | 187 | 37 | 31
SAN ANTONIO | 0521-03-060 | BEXAR | SL 13 | 2021-03-03 | 3075678.77 | 219570.94 | 3347427.49 | 271748.72 | 50 | 68 | 20 | 38
ABILENE | 0908-12-022 | HOWARD | VA | 2021-03-04 | 67744816.1 | 905620.13 | 69729892.88 | 1985076.78 | 680 | 893 | 4 | 217
AUSTIN | 0914-00-399 | TRAVIS | VA | 2021-03-04 | 1784883 | 76388.46 | 1242464.88 | -542418.12 | 300 | 170 | 0 | -130
LUBBOCK | 0068-03-033 | LYNN | US 87 | 2021-03-04 | 13819500.73 | 22902.24 | 14392521.77 | 573021.04 | 215 | 203 | 7 | -5
WICHITA FALLS | 0903-00-113 | WICHITA | VA | 2021-03-04 | 743601.9 | 0 | 725077.66 | -18524.24 | 34 | 46 | 0 | 12
ABILENE | 0005-05-114 | HOWARD | IH 20 | 2021-03-05 | 5297532.08 | 0 | 4949272.12 | -348259.96 | 187 | 177 | 0 | -10
ABILENE | 0068-08-065 | HOWARD | US 87 | 2021-03-05 | 6661050.95 | 329211.8 | 7465111.53 | 804060.58 | 181 | 201 | 20 | 40
ABILENE | 0908-00-096 | TAYLOR | VA | 2021-03-05 | 1998097.41 | 45139.6 | 2211757.16 | 213659.75 | 72 | 78 | 0 | 6
AUSTIN | 0015-08-151 | WILLIAMSON | IH 35 | 2021-03-05 | 5984750.13 | 805398.94 | 7392763.07 | 1408012.94 | 78 | 97 | 0 | 19
AUSTIN | 2211-02-028 | WILLIAMSON | FM 1460 | 2021-03-05 | 2075152.53 | 30926.3 | 1986442.96 | -88709.57 | 120 | 51 | 0 | -69
BEAUMONT | 0813-01-101 | LIBERTY | FM 787 | 2021-03-05 | 539803 | 48775.1 | 609119.5 | 69316.5 | 90 | 244 | 65 | 219
BROWNWOOD | 0054-07-084 | BROWN | US 84 | 2021-03-05 | 1396322.59 | 703.8 | 1292382.25 | -103940.34 | 155 | 117 | 0 | -38
FORT WORTH | 0352-01-061 | WISE | SH 114 | 2021-03-05 | 5522922.13 | 74124.46 | 5485750.79 | -37171.34 | 85 | 128 | 34 | 77
AUSTIN | 0015-08-155 | WILLIAMSON | IH 35 | 2021-03-08 | 5739917.2 | -506236.2 | 5124211.09 | -615706.11 | 91 | 69 | 0 | -22
YOAKUM | 2350-01-057 | VICTORIA | SL 463 | 2021-03-08 | 6854284.04 | 4755.53 | 6770884.38 | -83399.66 | 135 | 125 | 0 | -10
EL PASO | 2121-06-044 | HUDSPETH | IH 10 | 2021-03-09 | 2234212 | 0 | 2371259.55 | 137047.55 | 140 | 137 | 0 | -3
HOUSTON | 0192-02-056 | BRAZORIA | SH 6 | 2021-03-09 | 537033.23 | 117952.18 | 649887.51 | 112854.28 | 60 | 53 | 0 | -7
PARIS | 2139-01-007 | GRAYSON | SH 11 | 2021-03-10 | 9962020.61 | 1994577.64 | 12142893.4 | 2180872.79 | 270 | 460 | 157 | 347
WACO | 0015-07-084 | BELL | IH 35 | 2021-03-10 | 101750 | 0 | 105384.03 | 3634.03 | 45 | 13 | 0 | -32
WICHITA FALLS | 0013-05-063 | MONTAGUE | US 81 | 2021-03-10 | 482811 | 0 | 455208.59 | -27602.41 | 55 | 20 | 0 | -35
FORT WORTH | 0172-02-076 | TARRANT | BU 287P | 2021-03-11 | 1029420.6 | 763297.26 | 1877795.79 | 848375.19 | 107 | 86 | 0 | -21
PARIS | 0901-27-053 | RED RIVER | VA | 2021-03-11 | 941217.04 | 10000 | 929592 | -11625.04 | 195 | 54 | 0 | -141
PARIS | 2247-03-008 | HUNT | FM 2194 | 2021-03-11 | 1046859.98 | 7680 | 1086604.32 | 39744.34 | 78 | 53 | 0 | -25
YOAKUM | 0941-01-024 | DE WITT | FM 237 | 2021-03-11 | 856905.05 | 41393.45 | 859843.03 | 2937.98 | 170 | 150 | 0 | -20
HOUSTON | 0912-73-204 | GALVESTON | CR | 2021-03-12 | 4488672 | 411690 | 4911103.46 | 422431.46 | 233 | 195 | 0 | -38
SAN ANTONIO | 0016-08-037 | BEXAR | SL 368 | 2021-03-15 | 3513969.16 | 23094.71 | 3618048.14 | 104078.98 | 527 | 233 | 0 | -294
SAN ANTONIO | 0915-12-531 | BEXAR | CS | 2021-03-15 | 988634.75 | 0 | 994187.88 | 5553.13 | 116 | 116 | 0 | 0
WICHITA FALLS | 0903-28-070 | MONTAGUE | CR | 2021-03-15 | 443571 | 0 | 447308.69 | 3737.69 | 60 | 49 | 0 | -11
CHILDRESS | 0486-01-032 | WHEELER | SH 152 | 2021-03-16 | 9862939.51 | 365202.13 | 10581883.79 | 718944.28 | 119 | 89 | 7 | -23
DALLAS | 0353-06-068 | DALLAS | SH 114 | 2021-03-16 | 861230.04 | 0 | 877535.93 | 16305.89 | 192 | 85 | 0 | -107
YOAKUM | 0179-10-108 | CALHOUN | SH 35 | 2021-03-16 | 3082748.5 | 125900.57 | 3111575.52 | 28827.02 | 90 | 120 | 33 | 63
CORPUS CHRISTI | 2886-02-017 | NUECES | FM 2826 | 2021-03-19 | 4689383.97 | 105334.25 | 4726996.85 | 37612.88 | 170 | 186 | 12 | 28
DALLAS | 0047-07-230 | DALLAS | US 75 | 2021-03-19 | 1655509.27 | 0 | 1729936.85 | 74427.58 | 160 | 189 | 0 | 29
DALLAS | 0549-03-027 | COLLIN | SH 121 | 2021-03-19 | 43893899.25 | 4226314.01 | 48185725.19 | 4231202.46 | 768 | 1211 | 444 | 887
FORT WORTH | 0171-04-078 | TARRANT | SH 199 | 2021-03-19 | 46273495.29 | 2130838.82 | 48335089.89 | 2061594.6 | 438 | 540 | 102 | 204
SAN ANTONIO | 0215-06-039 | KENDALL | SH 46 | 2021-03-19 | 11999321.65 | -76176.69 | 12043568.92 | 39957.45 | 229 | 445 | 216 | 432
PARIS | 2455-01-041 | GRAYSON | FM 1417 | 2021-03-21 | 1159234.84 | 88509.01 | 1218269.32 | 59034.48 | 41 | 40 | 0 | -1
ODESSA | 0380-17-005 | MARTIN | SH 349 | 2021-03-22 | 7548488.05 | 180225.86 | 7737688.46 | 189200.41 | 100 | 90 | 0 | -10
SAN ANTONIO | 0025-10-092 | GUADALUPE | FM 78 | 2021-03-22 | 7321502.7 | 338291.22 | 8218946.14 | 897443.44 | 182 | 189 | 28 | 35
SAN ANTONIO | 0517-01-043 | ATASCOSA | SH 16 | 2021-03-22 | 22041915.1 | 322581.58 | 23548270.99 | 1506355.89 | 356 | 350 | 10 | 4
AUSTIN | 0547-01-026 | LLANO | SH 261 | 2021-03-23 | 788949.05 | 31470 | 816399.68 | 27450.63 | 95 | 65 | 0 | -30
AUSTIN | 3005-02-006 | BURNET | RM 690 | 2021-03-23 | 2692128.55 | 292598.37 | 2739064.39 | 46935.84 | 160 | 193 | 35 | 68
BEAUMONT | 0177-03-103 | LIBERTY | US 59 | 2021-03-23 | 2133678.32 | 2742.21 | 2058978.59 | -74699.73 | 128 | 128 | 0 | 0
BRYAN | 0335-01-031 | LEON | SH 7 | 2021-03-23 | 25152378.87 | -123900.4 | 25866773.43 | 714394.56 | 522 | 734 | 212 | 424
HOUSTON | 0389-05-124 | HARRIS | SH 146 | 2021-03-23 | 1819178.03 | 317160.71 | 2215657.41 | 396479.38 | 75 | 83 | 21 | 29
CORPUS CHRISTI | 0180-04-130 | ARANSAS | SH 35 | 2021-03-24 | 2681504 | -33802.14 | 2628901.86 | -52602.14 | 136 | 97 | 0 | -39
DALLAS | 0095-05-059 | KAUFMAN | US 80 | 2021-03-24 | 4110939.65 | 321231.8 | 3930816.27 | -180123.38 | 179 | 179 | 0 | 0
EL PASO | 0924-00-099 | EL PASO | VA | 2021-03-24 | 2093680 | 360163.46 | 2621380.73 | 527700.73 | 168 | 194 | 21 | 47
SAN ANTONIO | 0915-00-192 | BEXAR | VA | 2021-03-24 | 817876 | 15740 | 732182 | -85694 | 100 | 92 | 0 | -8
SAN ANTONIO | 2452-04-016 | BEXAR | SL 1604 | 2021-03-24 | 19772901.99 | 21985.56 | 20083142.82 | 292285.33 | 410 | 298 | 0 | -112
YOAKUM | 0913-27-061 | VICTORIA | CR | 2021-03-24 | 1477750.04 | 27251.17 | 1490771.16 | 13021.12 | 300 | 191 | 0 | -109
CORPUS CHRISTI | 0100-12-009 | KARNES | FM 2509 | 2021-03-26 | 3244111.1 | 603530.58 | 3940851.45 | 696740.35 | 100 | 150 | 50 | 100
FORT WORTH | 0314-07-052 | PARKER | IH 20 | 2021-03-26 | 29849945.96 | 1691630.76 | 32684279.86 | 2834333.9 | 512 | 676 | 164 | 328
BROWNWOOD | 0127-02-043 | EASTLAND | US 183 | 2021-03-29 | 4526012.96 | 377339.38 | 4892937.38 | 366924.42 | 332 | 388 | 60 | 116
EL PASO | 0924-00-142 | EL PASO | VA | 2021-03-29 | 2744921.1 | 0 | 3099249.85 | 354328.75 | 100 | 100 | 0 | 0
LAREDO | 0300-01-080 | MAVERICK | US 277 | 2021-03-29 | 18990864.89 | 2045523.42 | 21164661.63 | 2173796.74 | 530 | 589 | 66 | 125
SAN ANTONIO | 0915-18-024 | FRIO | CR | 2021-03-29 | 572306.5 | 750.91 | 607929.79 | 35623.29 | 72 | 91 | 19 | 38
AMARILLO | 0030-05-067 | HEMPHILL | US 83 | 2021-03-30 | 9058028.42 | 170551.19 | 8766301.37 | -291727.05 | 92 | 140 | 31 | 79
DALLAS | 0353-04-106 | DALLAS | SS 348 | 2021-03-30 | 12971190.94 | 213025.27 | 13661976.94 | 690786 | 305 | 237 | 0 | -68
DALLAS | 0581-01-137 | DALLAS | SL 12 | 2021-03-30 | 6192206.21 | 128247 | 6398780.68 | 206574.47 | 215 | 265 | 13 | 63
FORT WORTH | 0171-05-098 | TARRANT | SH 199 | 2021-03-30 | 1243381.45 | -137602.67 | 985771.5 | -257609.95 | 107 | 68 | 0 | -39
EL PASO | 0002-07-049 | HUDSPETH | IH 10 | 2021-03-31 | 5693876.6 | 1024325.29 | 6738054.49 | 1044177.89 | 238 | 306 | 72 | 140
EL PASO | 0374-02-107 | EL PASO | US 62 | 2021-03-31 | 1033028.05 | 17706.53 | 1070223.83 | 37195.78 | 100 | 98 | 0 | -2
EL PASO | 0924-00-100 | EL PASO | VA | 2021-03-31 | 1965159.51 | 0 | 1722875.73 | -242283.78 | 98 | 281 | 0 | 183
SAN ANTONIO | 0465-02-026 | BEXAR | FM 1518 | 2021-03-31 | 2220996.91 | 539897.48 | 2803378.46 | 582381.55 | 161 | 159 | 0 | -2
BROWNWOOD | 0867-07-013 | SAN SABA | RM 501 | 2021-04-01 | 2687867.75 | 33771.1 | 3076804.65 | 388936.9 | 204 | 186 | 0 | -18
BROWNWOOD | 0923-17-087 | COMANCHE | CR | 2021-04-01 | 591668 | 0 | 589979.5 | -1688.5 | 102 | 70 | 0 | -32
EL PASO | 0001-02-060 | EL PASO | SH 20 | 2021-04-01 | 1060040.7 | -93263.57 | 968882.09 | -91158.61 | 100 | 99 | 0 | -1
ODESSA | 0229-03-035 | CRANE | US 385 | 2021-04-01 | 20285448.77 | 496374.51 | 20772395.74 | 486946.97 | 390 | 475 | 88 | 173
ODESSA | 0906-00-229 | ECTOR | VA | 2021-04-01 | 1222832.51 | -114078.1 | 1020483.41 | -202349.1 | 78 | 74 | 0 | -4
LUFKIN | 0911-00-103 | ANGELINA | VA | 2021-04-02 | 1943450.89 | 0 | 1676089.97 | -267360.92 | 91 | 44 | 0 | -47
BEAUMONT | 0920-00-125 | JEFFERSON | VA | 2021-04-05 | 2849217.25 | 11935.69 | 2877404.7 | 28187.45 | 88 | 96 | 14 | 22
LUBBOCK | 0905-00-094 | LUBBOCK | VA | 2021-04-05 | 3964416.3 | 0 | 4077012.02 | 112595.72 | 120 | 130 | 0 | 10
AUSTIN | 0115-04-054 | BASTROP | FM 20 | 2021-04-06 | 2735017.09 | -18111.58 | 2794007.64 | 58990.55 | 67 | 90 | 0 | 23
BEAUMONT | 0920-30-078 | ORANGE | CS | 2021-04-06 | 3732469.4 | 247369.36 | 4009117.06 | 276647.66 | 339 | 289 | 12 | -38
EL PASO | 0167-01-120 | EL PASO | US 54 | 2021-04-06 | 719532.16 | -4385.67 | 702792.74 | -16739.42 | 25 | 25 | 0 | 0
LUBBOCK | 0067-06-058 | HALE | IH 27 | 2021-04-06 | 117820 | 0 | 117435 | -385 | 30 | 19 | 0 | -11
YOAKUM | 0408-02-046 | AUSTIN | SH 159 | 2021-04-06 | 3793059.92 | 135013.97 | 3901300.57 | 108240.65 | 300 | 288 | 3 | -9
BRYAN | 0315-08-037 | WASHINGTON | FM 389 | 2021-04-07 | 4243520.68 | 1053635.7 | 5555121.93 | 1311601.25 | 209 | 302 | 64 | 157
FORT WORTH | 0902-00-155 | TARRANT | VA | 2021-04-07 | 2091441.77 | 135100.79 | 2238991.27 | 147549.5 | 315 | 415 | 0 | 100
FORT WORTH | 0902-00-163 | TARRANT | VA | 2021-04-07 | 3677405 | 482090.9 | 4249540.31 | 572135.31 | 365 | 380 | 15 | 30
HOUSTON | 0500-03-583 | HARRIS | IH 45 | 2021-04-07 | 2119421.76 | 381069.93 | 2802307.78 | 682886.02 | 55 | 155 | 100 | 200
WICHITA FALLS | 0903-28-058 | MONTAGUE | CR | 2021-04-07 | 1372296.6 | 0 | 1382177.96 | 9881.36 | 196 | 206 | 10 | 20
TYLER | 0910-16-151 | SMITH | VA | 2021-04-08 | 177736.4 | 2555.96 | 178163.53 | 427.13 | 28 | 27 | 0 | -1
TYLER | 0927-01-031 | SMITH | FM 344 | 2021-04-08 | 151353.24 | -23336.18 | 135956.3 | -15396.94 | 21 | 14 | 0 | -7
CHILDRESS | 0303-03-046 | BRISCOE | SH 86 | 2021-04-09 | 899401.18 | 293442 | 1202317.93 | 302916.75 | 126 | 146 | 43 | 63
DALLAS | 0081-05-046 | DENTON | FM 428 | 2021-04-09 | 14212260.27 | 70732.48 | 13106810.07 | -1105450.2 | 233 | 233 | 0 | 0
DALLAS | 0162-03-042 | NAVARRO | SH 31 | 2021-04-09 | 4889741 | 17440.16 | 3883046.05 | -1006694.95 | 376 | 350 | 0 | -26
DALLAS | 1211-02-019 | ELLIS | FM 984 | 2021-04-09 | 7140372.1 | 0 | 6696947.49 | -443424.61 | 279 | 272 | 0 | -7
DALLAS | 1290-02-017 | ROCKWALL | SH 276 | 2021-04-09 | 17676606.22 | 153482.72 | 17548656.98 | -127949.24 | 427 | 415 | 16 | 4
DALLAS | 0172-05-122 | ELLIS | US 287 | 2021-04-12 | 7983934.11 | 174146.4 | 8230489.47 | 246555.36 | 162 | 170 | 8 | 16
AUSTIN | 0914-04-309 | TRAVIS | CS | 2021-04-13 | 185709 | 0 | 185047 | -662 | 30 | 28 | 0 | -2
CORPUS CHRISTI | 0585-01-016 | ARANSAS | PR 13B | 2021-04-13 | 540816.3 | 1537.87 | 486239.14 | -54577.16 | 102 | 99 | 0 | -3
FORT WORTH | 0902-90-037 | TARRANT | CS | 2021-04-13 | 262693.66 | 0 | 255874.86 | -6818.8 | 28 | 27 | 0 | -1
FORT WORTH | 0902-90-088 | TARRANT | VA | 2021-04-13 | 370947 | -68550 | 299647 | -71300 | 171 | 144 | 0 | -27
FORT WORTH | 0902-90-097 | TARRANT | CS | 2021-04-13 | 360000 | 5735 | 351795 | -13940 | 107 | 47 | 0 | -60
SAN ANGELO | 0141-09-071 | KIMBLE | IH 10 | 2021-04-13 | 2752521 | 0 | 2798052.17 | 45531.17 | 39 | 41 | 0 | 2
DALLAS | 0048-08-052 | ELLIS | IH 35E | 2021-04-14 | 1024454.95 | 11202.44 | 1049055.5 | 24600.55 | 72 | 68 | 0 | -4
PARIS | 0202-03-042 | FANNIN | US 69 | 2021-04-14 | 133900 | 3036.04 | 136936.04 | 3036.04 | 60 | 60 | 0 | 0
AMARILLO | 0169-05-041 | CARSON | US 60 | 2021-04-15 | 16325738.33 | 276098.8 | 18869913.88 | 2544175.55 | 198 | 193 | 8 | 3
CORPUS CHRISTI | 1088-04-025 | NUECES | FM 892 | 2021-04-15 | 3732484.33 | 204762.29 | 3849141.76 | 116657.43 | 151 | 161 | 0 | 10
FORT WORTH | 0313-02-059 | PARKER | FM 51 | 2021-04-15 | 5871767.96 | 622746.15 | 6289791.46 | 418023.5 | 178 | 320 | 142 | 284
FORT WORTH | 0736-02-017 | PALO PINTO | FM 129 | 2021-04-15 | 174587.5 | 910.82 | 206503.37 | 31915.87 | 47 | 25 | 0 | -22
AUSTIN | 0015-09-177 | WILLIAMSON | IH 35 | 2021-04-16 | 939068.99 | 0 | 888479.23 | -50589.76 | 94 | 77 | 0 | -17
LUFKIN | 0064-06-055 | SABINE | US 96 | 2021-04-16 | 260935 | 16000 | 273055 | 12120 | 43 | 42 | 0 | -1
LUFKIN | 0177-02-091 | SAN JACINTO | US 59 | 2021-04-16 | 2971066.4 | 287135.95 | 3196607.6 | 225541.2 | 94 | 163 | 69 | 138
AMARILLO | 0041-08-004 | POTTER | SL 434 | 2021-04-19 | 12785668.36 | 217642.92 | 12303648.59 | -482019.77 | 91 | 91 | 0 | 0
BRYAN | 0050-02-111 | BRAZOS | SH 6 | 2021-04-19 | 4675136.43 | 195250 | 5330227.59 | 655091.16 | 40 | 46 | 0 | 6
TYLER | 0910-12-021 | VAN ZANDT | CR | 2021-04-19 | 1069893.4 | -33868.3 | 1033789.94 | -36103.46 | 92 | 87 | 0 | -5
LAREDO | 2150-04-077 | WEBB | FM 1472 | 2021-04-20 | 1135288.9 | -9561.37 | 1125875.03 | -9413.87 | 160 | 138 | 0 | -22
ODESSA | 1717-01-010 | ECTOR | FM 1787 | 2021-04-20 | 16701304.92 | 35966.28 | 17764588.57 | 1063283.65 | 407 | 379 | 0 | -28
BRYAN | 0917-20-039 | FREESTONE | CR | 2021-04-21 | 479340.5 | 0 | 451141.25 | -28199.25 | 60 | 58 | 0 | -2
AUSTIN | 0440-02-021 | WILLIAMSON | SH 195 | 2021-04-22 | 672280.41 | 16291.44 | 664829.1 | -7451.31 | 41 | 40 | 0 | -1
FORT WORTH | 1978-01-050 | TARRANT | FM 1938 | 2021-04-22 | 20575236.87 | 5263481.22 | 25583778.17 | 3698898.25 | 554 | 1113 | 559 | 1118
TYLER | 0910-35-034 | WOOD | CR | 2021-04-22 | 1332153.39 | -10490.8 | 1336484.44 | 4331.05 | 74 | 73 | 0 | -1
PHARR | 0327-08-097 | CAMERON | BU 77-X | 2021-04-23 | 1440767.43 | 0 | 1309500.48 | -131266.95 | 354 | 271 | 0 | -83
SAN ANGELO | 0235-02-047 | EDWARDS | SH 55 | 2021-04-23 | 116358 | 68040 | 183648 | 67290 | 23 | 19 | 0 | -4
TYLER | 0109-01-062 | ANDERSON | US 287 | 2021-04-23 | 6180316.71 | -311578.68 | 6221142.48 | 40825.77 | 195 | 200 | 40 | 45
BRYAN | 0114-09-080 | WASHINGTON | US 290 | 2021-04-26 | 2499110.52 | -71010.24 | 2844903.53 | 345793.01 | 96 | 94 | 0 | -2
FORT WORTH | 2266-02-151 | TARRANT | SH 360 | 2021-04-26 | 267714.08 | 73408.18 | 344647.03 | 76932.95 | 22 | 26 | 5 | 9
HOUSTON | 2941-02-055 | HARRIS | FM 2920 | 2021-04-26 | 6097569.37 | 135681.04 | 6284610.95 | 187041.58 | 148 | 144 | 0 | -4
DALLAS | 0092-06-107 | NAVARRO | IH 45 | 2021-04-28 | 1129501 | 1725 | 1154617.45 | 25116.45 | 138 | 124 | 0 | -14
FORT WORTH | 0902-00-147 | TARRANT | VA | 2021-04-28 | 1292000 | 634061.08 | 1637936.46 | 345936.46 | 300 | 287 | 0 | -13
YOAKUM | 0025-07-066 | GONZALES | SH 97 | 2021-04-28 | 15932864.26 | 71680.44 | 15972891.3 | 40027.04 | 75 | 67 | 0 | -8
AMARILLO | 0042-04-043 | ARMSTRONG | US 287 | 2021-04-29 | 8973976.41 | -3128.11 | 9308818.51 | 334842.1 | 91 | 75 | 0 | -16
FORT WORTH | 0902-48-453 | TARRANT | CS | 2021-04-29 | 24298000 | 449315.67 | 24960989.86 | 318894.92 | 427 | 525 | 137 | 235
FORT WORTH | 1606-01-035 | WISE | FM 1658 | 2021-04-29 | 1052231.64 | 30061.04 | 1120815.75 | 68584.11 | 64 | 70 | 6 | 12
DALLAS | 2250-02-017 | DENTON | SL 288 | 2021-04-30 | 3179440.57 | 261211.72 | 3464987.74 | 285547.17 | 206 | 216 | 10 | 20
SAN ANTONIO | 0017-13-010 | ATASCOSA | SH 132 | 2021-04-30 | 3207689.81 | 36314.87 | 3296018.61 | 88328.8 | 392 | 247 | 0 | -145
PHARR | 0342-04-032 | CAMERON | SH 107 | 2021-05-01 | 4313269.7 | 706238.26 | 5216068.07 | 902798.37 | 285 | 328 | 77 | 120
ATLANTA | 0247-03-032 | PANOLA | US 79 | 2021-05-03 | 4609876.4 | 20177.05 | 4771348.22 | 161444.34 | 67 | 102 | 0 | 35
EL PASO | 0002-06-054 | HUDSPETH | IH 10 | 2021-05-03 | 3670432.4 | 2693.28 | 3492811.06 | -177621.34 | 40 | 39 | 0 | -1
EL PASO | 0167-02-063 | EL PASO | BU 54-A | 2021-05-03 | 2497616.54 | -89508.06 | 2422325.68 | -75290.86 | 60 | 59 | 0 | -1
HOUSTON | 0587-01-063 | BRAZORIA | FM 1495 | 2021-05-03 | 1335803.72 | 6231 | 1233398.06 | -102405.66 | 67 | 141 | 81 | 155
SAN ANTONIO | 0366-12-026 | GUADALUPE | BS 123B | 2021-05-03 | 7088993.75 | 746333.57 | 7884337.55 | 715240.58 | 375 | 473 | 98 | 196
SAN ANTONIO | 0748-05-040 | ATASCOSA | FM 140 | 2021-05-03 | 4730331.28 | -90856.98 | 4667632.04 | -62699.24 | 358 | 296 | 12 | -50
SAN ANTONIO | 0915-13-029 | ATASCOSA | CR | 2021-05-03 | 619853.5 | 3350.38 | 629760.03 | 9906.53 | 102 | 100 | 0 | -2
ABILENE | 0548-04-021 | HOWARD | SH 176 | 2021-05-04 | 9975871.02 | -271462.93 | 10050487.73 | 74616.71 | 180 | 171 | 0 | -9
AUSTIN | 0071-03-041 | MASON | US 87 | 2021-05-04 | 1046950.51 | 3720.17 | 1020725.59 | -26224.92 | 52 | 20 | 0 | -32
HOUSTON | 0523-01-030 | WALLER | FM 1098 | 2021-05-04 | 750614.45 | 3137.59 | 751533.79 | -2218.25 | 61 | 61 | 0 | 0
WACO | 0055-05-051 | CORYELL | US 84 | 2021-05-04 | 1945672.22 | 59412.76 | 1826342.55 | -119329.67 | 150 | 64 | 0 | -86
DALLAS | 0172-08-053 | ELLIS | US 287 | 2021-05-05 | 61704500 | 2241647.73 | 64188929.48 | 2484429.48 | 715 | 730 | 74 | 89
FORT WORTH | 2079-01-043 | TARRANT | FM 1220 | 2021-05-05 | 8350775.03 | -35201.36 | 8029634.13 | -321140.9 | 278 | 697 | 268 | 687
TYLER | 0108-02-034 | VAN ZANDT | SH 19 | 2021-05-05 | 508062.5 | -1950 | 511152.28 | 3089.78 | 140 | 111 | 0 | -29
YOAKUM | 0143-06-027 | GONZALES | US 87 | 2021-05-05 | 16127476.45 | 547541.58 | 16946724.03 | 819247.58 | 329 | 411 | 82 | 164
YOAKUM | 0143-08-097 | DE WITT | US 87 | 2021-05-05 | 3015734.98 | 16292.15 | 3056631.57 | 40896.59 | 148 | 158 | 10 | 20
DALLAS | 0918-22-157 | ELLIS | VA | 2021-05-06 | 4527134.12 | 432991.85 | 4632968.56 | 105834.44 | 246 | 231 | 0 | -15
DALLAS | 2374-02-147 | DALLAS | IH 635 | 2021-05-06 | 9213869.7 | -165450.28 | 9488010.33 | 274140.63 | 208 | 205 | 0 | -3
DALLAS | 2815-01-008 | KAUFMAN | FM 2757 | 2021-05-06 | 3946271.45 | 171958.69 | 4069204.78 | 122933.33 | 192 | 192 | 0 | 0
ATLANTA | 0221-09-029 | TITUS | BU 271E | 2021-05-07 | 609994 | 0 | 597423.85 | -12570.15 | 114 | 100 | 0 | -14
TYLER | 0495-04-070 | SMITH | IH 20 | 2021-05-07 | 3079236.01 | -63036.32 | 3137926.44 | 58690.43 | 66 | 60 | 0 | -6
WICHITA FALLS | 0903-00-116 | WICHITA | VA | 2021-05-07 | 637258.66 | 0 | 617702.81 | -19555.85 | 60 | 55 | 0 | -5
HOUSTON | 0912-71-078 | HARRIS | CS | 2021-05-11 | 1687687.9 | 29229.66 | 1757561.98 | 69874.08 | 148 | 246 | 48 | 146
WACO | 0258-04-036 | BOSQUE | SH 6 | 2021-05-11 | 294193.8 | 0 | 292222.8 | -1971 | 30 | 30 | 0 | 0
YOAKUM | 0267-05-018 | FAYETTE | FM 609 | 2021-05-11 | 7416527.18 | 4585.6 | 7070836.22 | -345690.96 | 300 | 165 | 0 | -135
AUSTIN | 1186-01-098 | TRAVIS | FM 969 | 2021-05-12 | 199994.37 | 31006.26 | 224573.9 | 24579.53 | 22 | 21 | 0 | -1
DALLAS | 0095-13-043 | DALLAS | IH 20 | 2021-05-12 | 24441956.22 | 535369.33 | 24584809.2 | 142852.98 | 328 | 327 | 0 | -1
DALLAS | 0121-08-019 | NAVARRO | FM 55 | 2021-05-12 | 7343202.3 | 420791.04 | 7116851.48 | -226350.82 | 486 | 440 | 0 | -46
PARIS | 0045-15-012 | LAMAR | FM 1510 | 2021-05-12 | 2390010.19 | 0 | 2358859.8 | -31150.39 | 20 | 18 | 0 | -2
YOAKUM | 0025-05-021 | GONZALES | US 90A | 2021-05-12 | 2179041.09 | 128249.4 | 2260771.82 | 81730.73 | 192 | 235 | 43 | 86
PHARR | 0921-06-208 | CAMERON | VA | 2021-05-13 | 6949739.75 | 158042.45 | 6075625 | -874114.75 | 262 | 424 | 171 | 333
WACO | 2506-01-042 | MCLENNAN | FM 1695 | 2021-05-13 | 862612.4 | 81299.69 | 866838.84 | 4226.44 | 225 | 144 | 5 | -76
YOAKUM | 0573-04-015 | GONZALES | FM 1116 | 2021-05-13 | 4044139.16 | 14427.63 | 3895074.62 | -149064.54 | 180 | 175 | 0 | -5
ATLANTA | 0062-07-088 | HARRISON | US 59 | 2021-05-14 | 13662269.84 | 88518.49 | 14248096.56 | 585826.72 | 156 | 177 | 4 | 25
BROWNWOOD | 0274-01-035 | MILLS | US 183 | 2021-05-14 | 10810892.03 | -119455.83 | 10353359.59 | -457532.44 | 68 | 65 | 0 | -3
DALLAS | 0918-11-089 | KAUFMAN | CR | 2021-05-14 | 641516.52 | 0 | 601540.32 | -39976.2 | 231 | 239 | 0 | 8
YOAKUM | 0143-09-069 | DE WITT | US 87 | 2021-05-14 | 1812578.62 | 0 | 1842047.26 | 29468.64 | 45 | 22 | 0 | -23
AMARILLO | 0066-03-041 | SHERMAN | US 287 | 2021-05-17 | 14540198.83 | 24543.31 | 15654563.07 | 1114364.24 | 147 | 157 | 10 | 20
AUSTIN | 0113-13-178 | TRAVIS | SL 360 | 2021-05-17 | 2484393.1 | -165436.58 | 2373198.44 | -111194.66 | 162 | 177 | 16 | 31
BRYAN | 0315-03-059 | GRIMES | SH 90 | 2021-05-17 | 2078724.66 | 189542.71 | 2370932.54 | 292207.88 | 90 | 92 | 10 | 12
PHARR | 0342-01-099 | HIDALGO | SH 107 | 2021-05-17 | 325600 | 0 | 317460 | -8140 | 48 | 22 | 0 | -26
SAN ANGELO | 0463-04-026 | GLASSCOCK | SH 158 | 2021-05-17 | 20119919.32 | 6379805.67 | 28560429.2 | 8440509.88 | 217 | 359 | 106 | 248
TYLER | 0206-03-061 | CHEROKEE | US 79 | 2021-05-17 | 8257306.23 | -341451.07 | 7989367.35 | -267938.88 | 224 | 226 | 2 | 4
WICHITA FALLS | 0044-08-072 | COOKE | US 82 | 2021-05-17 | 281867.55 | 0 | 281856.92 | -10.63 | 37 | 29 | 0 | -8
DALLAS | 0122-01-043 | NAVARRO | US 287 | 2021-05-18 | 2787386.38 | 200855.77 | 2892876.88 | 105490.5 | 88 | 85 | 5 | 2
HOUSTON | 0598-02-110 | BRAZORIA | SH 288 | 2021-05-18 | 3067734.14 | 1158566.11 | 4297764.45 | 1230030.31 | 161 | 160 | 0 | -1
PARIS | 0091-01-054 | GRAYSON | SH 289 | 2021-05-18 | 2219130.09 | 6209.25 | 2243060.16 | 23930.07 | 47 | 41 | 0 | -6
TYLER | 0245-02-031 | VAN ZANDT | SH 64 | 2021-05-18 | 9587787.65 | 1893006.01 | 11400569.66 | 1812782.01 | 340 | 334 | 40 | 34
CHILDRESS | 0133-01-052 | KING | US 82 | 2021-05-19 | 1641062 | 24018.09 | 1709709.57 | 68647.57 | 95 | 109 | 12 | 26
CHILDRESS | 0133-02-025 | KNOX | US 82 | 2021-05-19 | 11182988.22 | 114020.38 | 11659687.38 | 476699.16 | 204 | 289 | 32 | 117
FORT WORTH | 0364-01-148 | TARRANT | SH 121 | 2021-05-19 | 17427949.48 | 603794.48 | 18354273.59 | 926324.11 | 368 | 370 | 20 | 22
SAN ANTONIO | 0915-12-566 | BEXAR | CS | 2021-05-19 | 1774682.65 | 23106.27 | 1837887.13 | 63204.48 | 222 | 219 | 0 | -3
FORT WORTH | 0007-08-030 | PALO PINTO | SH 16 | 2021-05-20 | 12636789.66 | -41617.29 | 12228529.74 | -408259.92 | 144 | 126 | 0 | -18
HOUSTON | 0500-03-580 | HARRIS | IH 45 | 2021-05-20 | 5562891.96 | 350358.72 | 6412975.99 | 850084.03 | 260 | 300 | 40 | 80
PHARR | 1939-01-059 | HIDALGO | FM 2061 | 2021-05-22 | 1064870.85 | 0 | 1065583.46 | 712.61 | 160 | 160 | 0 | 0
HOUSTON | 0720-02-086 | MONTGOMERY | SH 249 | 2021-05-23 | 130786.9 | -10469.33 | 106541.07 | -24245.83 | 84 | 45 | 0 | -39
HOUSTON | 0912-00-413 | HARRIS | VA | 2021-05-23 | 1456616.5 | 370676.92 | 1702150.68 | 245534.18 | 417 | 160 | 0 | -257
HOUSTON | 0912-72-313 | HARRIS | CS | 2021-05-24 | 5787450.16 | 402088.02 | 6276584.39 | 330761.27 | 205 | 254 | 52 | 101
SAN ANTONIO | 0915-12-622 | BEXAR | CS | 2021-05-24 | 1694497.85 | 85161.24 | 1841366.56 | 146868.71 | 140 | 145 | 10 | 15
ATLANTA | 0085-04-033 | BOWIE | US 259 | 2021-05-25 | 11840907.57 | 5863294.58 | 17722843.27 | 3012426.9 | 479 | 476 | 0 | -3
FORT WORTH | 0314-02-052 | PALO PINTO | IH 20 | 2021-05-25 | 3283418.88 | 1117941.67 | 3838531.17 | 555112.29 | 127 | 166 | 39 | 78
HOUSTON | 0912-72-190 | HARRIS | VA | 2021-05-25 | 1906720.28 | 83447.46 | 1832652.86 | -90756.91 | 220 | 220 | 0 | 0
HOUSTON | 0912-73-195 | GALVESTON | CR | 2021-05-25 | 1514086.65 | 0 | 1458444.94 | -55641.71 | 142 | 174 | 16 | 48
LAREDO | 0022-06-051 | VAL VERDE | US 90 | 2021-05-26 | 476631.6 | 3120.22 | 468028.29 | -8603.31 | 40 | 40 | 0 | 0
YOAKUM | 0270-10-013 | DE WITT | SH 72 | 2021-05-26 | 6117082.25 | 201490.26 | 6687348.78 | 570266.53 | 340 | 310 | 0 | -30
SAN ANTONIO | 2452-01-059 | BEXAR | SL 1604 | 2021-05-27 | 64138414.46 | 906379.57 | 68714438.79 | 4544192.7 | 986 | 800 | 0 | -186
FORT WORTH | 2374-05-086 | TARRANT | IH 20 | 2021-05-28 | 1509515.45 | -104710.89 | 1377693.6 | -131821.85 | 64 | 25 | 3 | -36
LUFKIN | 2590-02-010 | NACOGDOCHES | FM 2609 | 2021-05-28 | 3823595.55 | -15619.5 | 3460098.8 | -363496.75 | 128 | 144 | 16 | 32
PARIS | 0009-09-107 | HOPKINS | IH 30 | 2021-05-28 | 11119928.73 | 140496.41 | 10614045.05 | -505883.68 | 67 | 49 | 0 | -18
HOUSTON | 0500-03-640 | HARRIS | IH 45 | 2021-06-01 | 2587343.31 | 38090.11 | 3085546.95 | 498203.64 | 120 | 98 | 0 | -22
SAN ANTONIO | 0915-00-220 | BEXAR | VA | 2021-06-01 | 2393563.5 | -110256.55 | 2453889.46 | 60325.96 | 126 | 126 | 0 | 0
SAN ANTONIO | 0915-13-028 | ATASCOSA | CR | 2021-06-01 | 823867 | 4975.16 | 793289.5 | -30577.5 | 153 | 158 | 0 | 5
SAN ANTONIO | 3212-06-020 | BEXAR | FM 3351 | 2021-06-01 | 2608775.25 | 4604.71 | 2484441.8 | -124333.45 | 53 | 68 | 0 | 15
WICHITA FALLS | 0391-04-027 | CLAY | SH 148 | 2021-06-01 | 4202296.75 | 0 | 4317190.99 | 114894.24 | 197 | 144 | 0 | -53
SAN ANTONIO | 2021-01-013 | COMAL | FM 1044 | 2021-06-02 | 1447351.2 | -6220.33 | 1476673.14 | 29321.94 | 93 | 58 | 0 | -35
AUSTIN | 1186-01-090 | TRAVIS | FM 969 | 2021-06-03 | 6648303.62 | 1211705.31 | 7769640.23 | 445675.99 | 321 | 370 | 88 | 137
ABILENE | 0908-19-025 | SCURRY | CR | 2021-06-04 | 2153442.5 | 0 | 2150208.03 | -3234.47 | 239 | 244 | 0 | 5
EL PASO | 0002-06-055 | HUDSPETH | IH 10 | 2021-06-04 | 1232441.25 | 0 | 1250797.66 | 18356.41 | 80 | 79 | 0 | -1
FORT WORTH | 1181-04-048 | JOHNSON | FM 917 | 2021-06-04 | 208400.85 | -13012.78 | 172029.37 | -36371.48 | 60 | 38 | 0 | -22
FORT WORTH | 1601-01-033 | PARKER | FM 730 | 2021-06-04 | 552724.35 | -11413.73 | 528486.32 | -24238.03 | 92 | 81 | 0 | -11
WACO | 0258-10-047 | MCLENNAN | SL 396 | 2021-06-04 | 829994 | -590.64 | 890472.76 | 60478.76 | 75 | 65 | 0 | -10
TYLER | 0138-05-057 | RUSK | US 259 | 2021-06-07 | 7308695.21 | 27892.92 | 7405970.08 | 97274.87 | 150 | 154 | 1 | 5
TYLER | 3465-02-011 | GREGG | FM 3272 | 2021-06-07 | 3110849.34 | 160007.74 | 3156589.52 | 45740.18 | 205 | 204 | 4 | 3
DALLAS | 0751-02-026 | KAUFMAN | FM 148 | 2021-06-08 | 7818547.17 | 527257.47 | 6954177.41 | -864369.76 | 461 | 464 | 3 | 6
WACO | 0014-23-038 | HILL | IH 35W | 2021-06-08 | 2336015.94 | -232434.31 | 2058220.83 | -277795.11 | 195 | 64 | 0 | -131
AUSTIN | 1186-01-097 | TRAVIS | FM 969 | 2021-06-10 | 360089.03 | 1965.26 | 385223.49 | 25134.46 | 43 | 42 | 0 | -1
AUSTIN | 2687-01-013 | LLANO | RM 2147 | 2021-06-10 | 2394881.33 | -29835.28 | 2378425.29 | -16456.04 | 153 | 153 | 2 | 2
DALLAS | 2964-01-048 | DALLAS | SH 161 | 2021-06-14 | 20927948.34 | 619105.93 | 21819232.12 | 891283.78 | 377 | 405 | 28 | 56
SAN ANGELO | 0070-05-037 | CONCHO | US 87 | 2021-06-14 | 13599407.74 | 354711.15 | 13790957.35 | 191549.61 | 299 | 281 | 15 | -3
AUSTIN | 0113-02-065 | GILLESPIE | US 290 | 2021-06-15 | 2725725.31 | 0 | 2951172.14 | 225446.83 | 77 | 40 | 0 | -37
TYLER | 0123-04-021 | RUSK | US 84 | 2021-06-15 | 1024466.95 | -17227.56 | 987867.06 | -36599.89 | 125 | 128 | 0 | 3
FORT WORTH | 0081-02-069 | TARRANT | US 377 | 2021-06-16 | 393161.8 | 0 | 392085 | -1076.8 | 97 | 82 | 0 | -15
HOUSTON | 0523-10-034 | MONTGOMERY | FM 1488 | 2021-06-16 | 27649979.11 | 4427178.48 | 32313146.72 | 4663167.61 | 478 | 594 | 130 | 246
TYLER | 0910-00-113 | SMITH | VA | 2021-06-16 | 668550.78 | -88237.6 | 558012.65 | -110538.13 | 94 | 49 | 0 | -45
YOAKUM | 0839-01-014 | GONZALES | FM 443 | 2021-06-16 | 1655859.93 | 46948.91 | 1703847.43 | 47987.5 | 191 | 191 | 0 | 0
YOAKUM | 0913-00-104 | DE WITT | VA | 2021-06-16 | 2484164.82 | 0 | 2407663.25 | -76501.57 | 111 | 114 | 0 | 3
YOAKUM | 0913-09-066 | WHARTON | CR | 2021-06-16 | 1094298 | 0 | 1090719 | -3579 | 190 | 112 | 0 | -78
YOAKUM | 0913-22-046 | GONZALES | CR | 2021-06-16 | 399752.08 | 0 | 396211.29 | -3540.79 | 75 | 75 | 0 | 0
YOAKUM | 0913-28-066 | FAYETTE | CR | 2021-06-16 | 389284.29 | 0 | 389015.07 | -269.22 | 65 | 53 | 0 | -12
YOAKUM | 0941-02-020 | DE WITT | FM 2656 | 2021-06-16 | 4185510.72 | 7603.64 | 4150547.97 | -34962.75 | 150 | 138 | 0 | -12
FORT WORTH | 0134-15-013 | WISE | SL 373 | 2021-06-17 | 808032.39 | -38935.13 | 663942.98 | -144089.41 | 64 | 35 | 0 | -29
HOUSTON | 0976-01-039 | HARRIS | FM 865 | 2021-06-17 | 2411705.72 | -164639.73 | 2332438.01 | -79267.71 | 115 | 116 | 23 | 24
LAREDO | 0160-04-051 | VAL VERDE | US 277 | 2021-06-17 | 524312.41 | 39501.87 | 563993.87 | 39681.46 | 60 | 60 | 0 | 0
DALLAS | 1317-01-015 | ELLIS | FM 1183 | 2021-06-18 | 8149846.6 | 472975.98 | 8204884.29 | 55037.69 | 323 | 339 | 16 | 32
HOUSTON | 0271-05-042 | FORT BEND | IH 10 | 2021-06-20 | 2297994.99 | 170125.43 | 2665656.68 | 259288.45 | 151 | 149 | 0 | -2
HOUSTON | 0271-09-022 | WALLER | US 90 | 2021-06-20 | 2321743.04 | 78337.88 | 2128112.9 | -271968.02 | 163 | 211 | 0 | 48
AUSTIN | 0914-00-391 | TRAVIS | VA | 2021-06-21 | 11464497.25 | 329335.61 | 11928690.67 | 464193.42 | 360 | 424 | 64 | 128
HOUSTON | 0389-13-062 | HARRIS | SH 146 | 2021-06-21 | 350747.5 | 0 | 356905.77 | 6158.27 | 60 | 56 | 0 | -4
LUFKIN | 0177-01-112 | POLK | US 59 | 2021-06-21 | 1536274.1 | 100461.81 | 1565961.72 | 29687.62 | 120 | 108 | 5 | -7
WICHITA FALLS | 0681-08-024 | CLAY | FM 174 | 2021-06-21 | 367886.95 | 3996.72 | 367486.93 | -400.02 | 68 | 27 | 0 | -41
YOAKUM | 0114-08-035 | FAYETTE | US 290 | 2021-06-22 | 2098141.38 | 170185.07 | 2186866 | 88724.62 | 165 | 215 | 55 | 105
ABILENE | 0908-00-104 | TAYLOR | VA | 2021-06-23 | 1094531.81 | -81478.83 | 1013052.98 | -81478.83 | 54 | 8 | 0 | -46
SAN ANTONIO | 8408-15-006 | COMAL | MH | 2021-06-23 | 4518896.31 | 497901.61 | 5021058.42 | 502162.11 | 470 | 311 | 0 | -159
TYLER | 0495-03-063 | VAN ZANDT | IH 20 | 2021-06-23 | 5152008.83 | -227255.44 | 5089489.83 | -62519 | 126 | 85 | 0 | -41
YOAKUM | 0266-01-074 | FAYETTE | SH 71 | 2021-06-24 | 276120 | -10363.74 | 268325.26 | -7794.74 | 30 | 42 | 12 | 24
AMARILLO | 0041-07-106 | POTTER | US 87 | 2021-06-25 | 4976890.28 | 130000 | 5820491.46 | 843601.18 | 157 | 316 | 0 | 159
AMARILLO | 0275-04-052 | CARSON | IH 40 | 2021-06-25 | 8012745.35 | 421767.64 | 8237377.68 | 224632.33 | 119 | 119 | 0 | 0
HOUSTON | 0912-00-331 | HARRIS | VA | 2021-06-25 | 1482581.45 | 635309.07 | 1562609.17 | 80027.72 | 235 | 327 | 120 | 212
HOUSTON | 0912-34-176 | FORT BEND | CR | 2021-06-25 | 2828589.45 | 170985.09 | 2871300.11 | 42710.66 | 321 | 397 | 76 | 152
YOAKUM | 0211-10-046 | COLORADO | FM 155 | 2021-06-25 | 173450 | -3316.88 | 170133.12 | -3316.88 | 30 | 11 | 0 | -19
ABILENE | 0668-02-020 | HOWARD | FM 700 | 2021-06-28 | 4167074 | -415232.84 | 3810183.73 | -356890.27 | 110 | 94 | 0 | -16
ABILENE | 0908-20-026 | NOLAN | CR | 2021-06-28 | 830650.6 | 0 | 785026.6 | -45624 | 106 | 121 | 0 | 15
HOUSTON | 0500-03-044 | HARRIS | IH 45 | 2021-06-28 | 19637823.14 | 2777395.5 | 23286815.11 | 3648991.97 | 575 | 622 | 187 | 234
WICHITA FALLS | 0043-09-137 | WICHITA | US 287 | 2021-06-28 | 6221093.62 | 188221.28 | 6132389.78 | -88703.84 | 128 | 148 | 21 | 41
YOAKUM | 0089-06-081 | WHARTON | US 59 | 2021-06-28 | 18889263.03 | 4837.24 | 19748295.6 | 859032.57 | 324 | 361 | 45 | 82
YOAKUM | 0334-08-033 | FAYETTE | FM 154 | 2021-06-28 | 519583.1 | -12450 | 552881.94 | 33298.84 | 45 | 45 | 0 | 0
DALLAS | 2679-02-008 | COLLIN | FM 2514 | 2021-06-29 | 19081190.16 | 1271922.09 | 20521419.31 | 1145343.07 | 450 | 499 | 80 | 129
SAN ANGELO | 0558-06-016 | GLASSCOCK | RM 33 | 2021-06-29 | 6698938.52 | 3278064.32 | 9758111.33 | 3059172.81 | 124 | 207 | 55 | 138
ATLANTA | 0010-12-072 | BOWIE | US 67 | 2021-06-30 | 1089558.81 | 14953.04 | 1094690.65 | 5131.84 | 188 | 104 | 0 | -84
DALLAS | 0522-01-023 | KAUFMAN | SH 243 | 2021-07-01 | 1271679.28 | 0 | 1154975.64 | -116703.64 | 168 | 193 | 17 | 42
EL PASO | 0167-01-127 | EL PASO | US 54 | 2021-07-01 | 587855 | -1958.23 | 577491.05 | -10363.95 | 100 | 84 | 0 | -16
WACO | 0014-08-088 | MCLENNAN | IH 35 | 2021-07-01 | 323521 | 15428 | 349398.31 | 25877.31 | 30 | 26 | 0 | -4
LUBBOCK | 0461-05-011 | YOAKUM | SH 214 | 2021-07-02 | 24052607.74 | 174819.77 | 22725887.68 | -1326720.06 | 306 | 167 | 15 | -124
HOUSTON | 1685-05-110 | HARRIS | SH 6 | 2021-07-05 | 2789052.5 | 30773.95 | 2788138.78 | -913.72 | 180 | 179 | 0 | -1
AUSTIN | 0914-00-433 | TRAVIS | VA | 2021-07-06 | 601620.41 | 230.05 | 597131.95 | -4488.46 | 26 | 21 | 0 | -5
LUBBOCK | 0905-00-107 | LUBBOCK | VA | 2021-07-06 | 1385650.4 | 0 | 1279518.6 | -106131.8 | 60 | 39 | 0 | -21
LUBBOCK | 1905-01-009 | DAWSON | FM 2052 | 2021-07-06 | 4232784.05 | 64367.2 | 4325030.75 | 92246.7 | 164 | 167 | 10 | 13
BRYAN | 0205-06-032 | FREESTONE | US 79 | 2021-07-07 | 486288 | 458984.24 | 940751.91 | 454463.91 | 105 | 216 | 125 | 236
SAN ANGELO | 0907-00-171 | TOM GREEN | VA | 2021-07-07 | 682830 | 33732.39 | 832509.77 | 149679.77 | 111 | 223 | 0 | 112
TYLER | 0910-07-081 | GREGG | VA | 2021-07-07 | 415605.5 | 0 | 373396.6 | -42208.9 | 33 | 32 | 0 | -1
YOAKUM | 0913-29-036 | LAVACA | CR | 2021-07-07 | 699018.4 | 0 | 688466.1 | -10552.3 | 90 | 68 | 0 | -22
AUSTIN | 0015-13-377 | TRAVIS | IH 35 | 2021-07-08 | 5984425.71 | -249899.74 | 6836112.62 | 851686.91 | 85 | 82 | 0 | -3
HOUSTON | 0177-11-154 | HARRIS | IH 69 | 2021-07-08 | 2607139.85 | 134746.69 | 2795479.78 | 188339.93 | 110 | 113 | 3 | 6
DALLAS | 0353-05-121 | DALLAS | SL 12 | 2021-07-09 | 4663152.5 | -90847.2 | 4183278.16 | -479874.34 | 135 | 229 | 54 | 148
HOUSTON | 0543-03-072 | FORT BEND | FM 762 | 2021-07-09 | 1849419.98 | 252464.08 | 2659267.49 | 809847.51 | 75 | 96 | 5 | 26
WICHITA FALLS | 0043-09-142 | WICHITA | US 287 | 2021-07-09 | 948263.9 | 13099.64 | 948325.5 | 61.6 | 51 | 52 | 4 | 5
CORPUS CHRISTI | 0916-00-090 | NUECES | VA | 2021-07-12 | 2993801.98 | 0 | 2762820.52 | -230981.46 | 65 | 86 | 20 | 41
FORT WORTH | 1603-03-039 | TARRANT | FM 1709 | 2021-07-12 | 3540605.35 | 219875.44 | 3389813.92 | -150791.43 | 128 | 108 | 60 | 40
SAN ANTONIO | 0483-02-021 | MCMULLEN | SH 72 | 2021-07-12 | 30553964.74 | -1266096.33 | 29998636.71 | -555328.03 | 354 | 326 | -10 | -38
TYLER | 0492-04-039 | SMITH | FM 346 | 2021-07-13 | 200524.9 | -11250 | 163233.7 | -37291.2 | 90 | 68 | 0 | -22
LUBBOCK | 0168-01-029 | PARMER | US 60 | 2021-07-14 | 17450676.16 | -85323.18 | 17092089.66 | -358586.5 | 237 | 228 | 3 | -6
YOAKUM | 0913-28-067 | FAYETTE | CR | 2021-07-14 | 872849.77 | 0 | 865160.62 | -7689.15 | 120 | 119 | 0 | -1
ABILENE | 0908-00-097 | TAYLOR | VA | 2021-07-15 | 1116362.85 | 0 | 1155717.07 | 39354.22 | 98 | 40 | 0 | -58
ABILENE | 0908-00-103 | TAYLOR | VA | 2021-07-15 | 914854.2 | -38177.43 | 877251.07 | -37603.13 | 58 | 38 | 0 | -20
AUSTIN | 3545-02-007 | HAYS | FM 110 | 2021-07-15 | 14870482.38 | 618541.12 | 15342385.53 | 471903.15 | 230 | 240 | 10 | 20
DALLAS | 0081-13-064 | DENTON | IH 35W | 2021-07-15 | 1398590.15 | 279057.04 | 1733133.55 | 334543.4 | 82 | 117 | 35 | 70
DALLAS | 2374-03-094 | DALLAS | IH 20 | 2021-07-15 | 4328705.98 | 342605.68 | 4270638.53 | -58067.45 | 149 | 155 | 10 | 16
EL PASO | 0020-02-019 | CULBERSON | US 90 | 2021-07-15 | 539478.56 | 3511.51 | 542990.08 | 3511.52 | 37 | 23 | 0 | -14
HOUSTON | 0050-09-071 | HARRIS | US 290 | 2021-07-15 | 110414015.1 | 72462.14 | 112552772.77 | 2138757.67 | 1170 | 1175 | 0 | 5
PARIS | 0047-18-081 | GRAYSON | US 75 | 2021-07-15 | 1629373.4 | 7781.25 | 1741443.31 | 112069.91 | 213 | 194 | 0 | -19
PARIS | 0136-03-065 | DELTA | SH 24 | 2021-07-15 | 1347221 | 20834.69 | 1383099.06 | 35878.06 | 127 | 138 | 9 | 20
TYLER | 0495-02-066 | VAN ZANDT | IH 20 | 2021-07-15 | 285600 | 29027.77 | 304866.78 | 19266.78 | 43 | 25 | 0 | -18
AMARILLO | 0275-05-044 | GRAY | IH 40 | 2021-07-19 | 16401396.68 | -100458.4 | 16956378.42 | 554981.74 | 136 | 130 | 0 | -6
DALLAS | 0081-04-025 | DENTON | US 377 | 2021-07-19 | 34996757.47 | 1656021.99 | 36527097.51 | 1309908.33 | 603 | 661 | 66 | 124
EL PASO | 2121-02-150 | EL PASO | IH 10 | 2021-07-20 | 25376264.25 | 5703359.86 | 32005213.18 | 6628948.93 | 370 | 924 | 417 | 971
HOUSTON | 0720-03-141 | HARRIS | SH 249 | 2021-07-20 | 2241513.87 | -228374.38 | 2416180.63 | 174666.76 | 162 | 161 | 0 | -1
LUBBOCK | 0227-06-026 | HOCKLEY | US 385 | 2021-07-20 | 26651673.88 | 53025.04 | 26533164.15 | -118509.73 | 240 | 325 | 43 | 128
LUBBOCK | 0905-12-044 | HALE | CR | 2021-07-20 | 436230 | 0 | 433665 | -2565 | 90 | 90 | 0 | 0
WICHITA FALLS | 0312-01-082 | COOKE | FM 51 | 2021-07-20 | 1193935.09 | 35554.88 | 1172930.73 | -21004.36 | 102 | 93 | 0 | -9
AUSTIN | 0914-00-415 | TRAVIS | VA | 2021-07-21 | 727670.16 | -63602.23 | 739456.41 | 11786.25 | 48 | 48 | 0 | 0
FORT WORTH | 0343-03-028 | ERATH | SH 108 | 2021-07-21 | 5937214.7 | 3880593.63 | 9207993.72 | 3270779.02 | 320 | 417 | 29 | 126
LAREDO | 0237-07-015 | DIMMIT | FM 133 | 2021-07-21 | 16183209.3 | 546178.14 | 16419052.89 | 235843.59 | 540 | 552 | 51 | 63
WACO | 1664-01-019 | LIMESTONE | FM 1633 | 2021-07-21 | 7107478.07 | -349619.3 | 6600420.59 | -507057.48 | 195 | 181 | 0 | -14
AUSTIN | 0914-04-229 | TRAVIS | CS | 2021-07-22 | 571595.19 | 53840.64 | 614201.09 | -15256.76 | 99 | 94 | 5 | 0
HOUSTON | 0177-07-112 | HARRIS | IH 69 | 2021-07-23 | 598752.64 | 76923.08 | 693120.32 | 94367.68 | 60 | 58 | 0 | -2
HOUSTON | 0912-70-104 | HARRIS | CR | 2021-07-26 | 2330231.54 | 176244.18 | 2513644.49 | 42846.9 | 150 | 218 | 24 | 92
SAN ANTONIO | 1477-01-040 | BEXAR | FM 1516 | 2021-07-26 | 7388905.6 | 594478.79 | 8223049.61 | 720486.72 | 586 | 565 | 0 | -21
DALLAS | 0261-02-074 | DALLAS | US 67 | 2021-07-27 | 59011998.22 | 5236879.01 | 60275992.7 | 1263994.48 | 496 | 924 | 330 | 758
FORT WORTH | 2631-01-006 | HOOD | FM 3450 | 2021-07-27 | 5769636.53 | -752111.11 | 4993983.52 | -775653.01 | 208 | 137 | -60 | -131
TYLER | 0246-01-036 | RUSK | US 79 | 2021-07-27 | 6403500.83 | -12715.11 | 6490858.18 | 87357.35 | 145 | 143 | 0 | -2
AMARILLO | 0904-00-178 | POTTER | VA | 2021-07-28 | 1062155.82 | 0 | 1060502.48 | -1653.34 | 54 | 52 | 0 | -2
CHILDRESS | 0925-00-073 | CHILDRESS | VA | 2021-07-28 | 943646.02 | 0 | 912831.01 | -30815.01 | 61 | 42 | 0 | -19
BROWNWOOD | 0128-04-035 | MCCULLOCH | US 190 | 2021-07-29 | 8577352.87 | 420877.87 | 9335724.16 | 758371.29 | 446 | 441 | 0 | -5
HOUSTON | 0027-13-234 | HARRIS | IH 69 | 2021-07-29 | 1045020 | 13282.82 | 1166340.53 | 121320.53 | 137 | 123 | 0 | -14
SAN ANTONIO | 0366-12-030 | GUADALUPE | BS 123B | 2021-07-29 | 997498 | 115019.46 | 1111629.12 | 114131.12 | 143 | 79 | 0 | -64
DALLAS | 1567-02-035 | DENTON | FM 423 | 2021-07-30 | 958664.2 | 98435.12 | 998483.95 | 39819.75 | 229 | 204 | 21 | -4
LUFKIN | 0176-03-131 | ANGELINA | US 59 | 2021-07-30 | 1620249.39 | 47291.41 | 1785765.31 | 165515.92 | 122 | 191 | 49 | 118
AMARILLO | 0041-05-052 | POTTER | US 87 | 2021-08-02 | 1849686.2 | 846270.07 | 2879745.14 | 1030058.94 | 160 | 342 | 44 | 226
YOAKUM | 0266-03-029 | COLORADO | SH 71 | 2021-08-02 | 9120997.86 | 51992.89 | 9407259.4 | 286261.54 | 226 | 376 | 31 | 181
YOAKUM | 0346-10-021 | MATAGORDA | FM 1468 | 2021-08-02 | 1128804.52 | 7982.2 | 1059331.2 | -69473.32 | 150 | 213 | 25 | 88
BEAUMONT | 0508-04-176 | JEFFERSON | SH 73 | 2021-08-03 | 113770 | -4770 | 100550 | -13220 | 26 | 91 | 0 | 65
BEAUMONT | 0920-39-025 | CHAMBERS | VA | 2021-08-03 | 1106083.7 | 61338.88 | 1086015.54 | -20068.16 | 99 | 145 | 55 | 101
DALLAS | 0918-00-287 | DALLAS | VA | 2021-08-03 | 671750.1 | 69540 | 604407.24 | -67342.86 | 540 | 540 | 0 | 0
HOUSTON | 3256-02-098 | HARRIS | SL 8 | 2021-08-03 | 734299.1 | 66444.78 | 849037.82 | 114738.72 | 79 | 69 | 0 | -10
SAN ANGELO | 0907-00-197 | TOM GREEN | VA | 2021-08-03 | 2137529.5 | 0 | 2238320.1 | 100790.6 | 69 | 61 | 0 | -8
WACO | 0833-03-045 | MCLENNAN | FM 1637 | 2021-08-03 | 9304002.23 | 36023.21 | 9273597.38 | -30404.85 | 255 | 263 | 11 | 19
ATLANTA | 0010-12-073 | BOWIE | US 67 | 2021-08-04 | 526434.46 | 1997.1 | 518800.59 | -7633.87 | 110 | 65 | 0 | -45
BRYAN | 0117-09-002 | BRAZOS | US 190 | 2021-08-04 | 157172.4 | -8295 | 154692.4 | -2480 | 51 | 36 | 0 | -15
DALLAS | 0092-13-023 | NAVARRO | BI 45-F | 2021-08-05 | 6555440.96 | -253405.35 | 5843881.76 | -711559.2 | 169 | 307 | 128 | 266
PHARR | 0220-03-031 | CAMERON | US 281 | 2021-08-05 | 9818478.75 | 187168.21 | 10270602.43 | 452123.68 | 440 | 452 | 14 | 26
ATLANTA | 0919-00-080 | CASS | VA | 2021-08-06 | 1260630.08 | 0 | 1240681.73 | -19948.35 | 51 | 47 | 0 | -4
ATLANTA | 0046-04-065 | BOWIE | US 82 | 2021-08-09 | 1386252.75 | 6728.09 | 1404026.88 | 17774.13 | 213 | 179 | 0 | -34
FORT WORTH | 1068-02-146 | TARRANT | IH 30 | 2021-08-10 | 2498951.08 | 246418.23 | 2845083.03 | 346131.95 | 149 | 455 | 185 | 491
HOUSTON | 0110-04-195 | MONTGOMERY | IH 45 | 2021-08-10 | 3256878.26 | 52636.46 | 3429443.02 | 172564.76 | 120 | 127 | 6 | 13
HOUSTON | 3256-02-095 | HARRIS | SL 8 | 2021-08-12 | 2046085.22 | 0 | 2016882.1 | -29203.12 | 83 | 74 | 0 | -9
ODESSA | 0228-06-087 | ECTOR | US 385 | 2021-08-12 | 698267.82 | 131336.89 | 871242.69 | 172974.87 | 200 | 123 | 0 | -77
WICHITA FALLS | 1076-01-038 | THROCKMORTON | FM 209 | 2021-08-12 | 2072676.59 | -1963.15 | 1934388.62 | -138287.97 | 135 | 229 | 0 | 94
CORPUS CHRISTI | 1119-01-013 | BEE | FM 797 | 2021-08-13 | 1364407.9 | 497227.29 | 1922924.5 | 558516.6 | 102 | 146 | 44 | 88
FORT WORTH | 0902-00-205 | TARRANT | VA | 2021-08-13 | 2419003 | 25311.64 | 2306113.17 | -112889.83 | 93 | 189 | 96 | 192
FORT WORTH | 0902-38-128 | PARKER | VA | 2021-08-13 | 772789 | 0 | 764499.3 | -8289.7 | 128 | 127 | 0 | -1
HOUSTON | 0502-01-220 | HARRIS | SH 225 | 2021-08-13 | 988674.86 | 11839.09 | 1279210.03 | 290535.17 | 105 | 105 | 0 | 0
DALLAS | 0918-00-288 | DALLAS | VA | 2021-08-16 | 2286000 | 6067.9 | 2184524.89 | -101475.11 | 913 | 499 | 0 | -414
DALLAS | 1051-01-037 | ELLIS | FM 664 | 2021-08-16 | 28247126.84 | 1166163.29 | 29668580.83 | 1421453.99 | 468 | 502 | 68 | 102
FORT WORTH | 0081-01-051 | TARRANT | US 377 | 2021-08-16 | 6436651.58 | -286927.46 | 5510685.43 | -925966.15 | 278 | 194 | 0 | -84
AUSTIN | 0683-02-080 | TRAVIS | RM 620 | 2021-08-17 | 378217.6 | 66844.17 | 441564.17 | 63346.57 | 27 | 16 | 0 | -11
FORT WORTH | 3207-01-011 | JOHNSON | FM 3136 | 2021-08-17 | 5771223.24 | -524496.28 | 4943314.1 | -827909.14 | 299 | 376 | 77 | 154
BROWNWOOD | 0636-01-038 | COLEMAN | SH 153 | 2021-08-18 | 1682223.99 | -13414.29 | 1506337.1 | -175886.89 | 114 | 119 | 0 | 5
CORPUS CHRISTI | 0373-02-001 | NUECES | SH 44 | 2021-08-18 | 2419991.8 | 47352.97 | 2265942.99 | -154048.81 | 152 | 156 | 10 | 14
DALLAS | 0047-14-082 | COLLIN | US 75 | 2021-08-18 | 2750000 | 457291.5 | 3300146.35 | 555396.35 | 378 | 450 | 73 | 145
LAREDO | 0922-00-065 | WEBB | VA | 2021-08-18 | 2894261.35 | -48498.61 | 2922526 | 28264.65 | 303 | 297 | 0 | -6
LAREDO | 2150-02-009 | WEBB | FM 1472 | 2021-08-18 | 3148791.36 | -49071.07 | 2998414.74 | -150376.62 | 139 | 155 | 5 | 21
PHARR | 1586-01-076 | HIDALGO | FM 907 | 2021-08-18 | 6912455 | 126366.93 | 6670784.24 | -241670.76 | 365 | 340 | 0 | -25
YOAKUM | 0913-00-103 | DE WITT | VA | 2021-08-18 | 3289679.41 | 1404.5 | 3223344.01 | -66335.4 | 120 | 57 | 0 | -63
ATLANTA | 0084-01-090 | MORRIS | US 259 | 2021-08-19 | 2282831.61 | 0 | 2242781.22 | -40050.39 | 72 | 71 | 0 | -1
FORT WORTH | 0014-03-100 | JOHNSON | IH 35W | 2021-08-19 | 4345364.38 | 783795.81 | 4989792.78 | 644428.4 | 192 | 229 | 30 | 67
ABILENE | 0006-07-080 | CALLAHAN | IH 20 | 2021-08-20 | 10684704.91 | -613472.06 | 10571176.04 | -113528.87 | 310 | 355 | 16 | 61
FORT WORTH | 0902-90-113 | TARRANT | VA | 2021-08-20 | 2821090.59 | 0 | 2840425.77 | 19335.18 | 182 | 265 | 83 | 166
FORT WORTH | 1068-01-215 | TARRANT | IH 30 | 2021-08-20 | 314035.35 | 37288.93 | 362389.69 | 48354.34 | 85 | 99 | 0 | 14
FORT WORTH | 1068-01-221 | TARRANT | IH 30 | 2021-08-20 | 1477579.91 | -347370 | 1027804.78 | -449775.13 | 43 | 34 | 0 | -9
HOUSTON | 0051-03-111 | GALVESTON | SH 3 | 2021-08-23 | 1662371.85 | 0 | 1862144.55 | 199772.7 | 60 | 60 | 0 | 0
TYLER | 0910-16-152 | SMITH | VA | 2021-08-23 | 833358 | 0 | 755611.96 | -77746.04 | 44 | 27 | 0 | -17
FORT WORTH | 0902-00-218 | TARRANT | VA | 2021-08-24 | 4081763.15 | 97098.93 | 4060842.56 | -20920.59 | 213 | 184 | 0 | -29
PARIS | 0045-09-105 | LAMAR | BU 82-H | 2021-08-24 | 883850 | 0 | 883850 | 0 | 85 | 78 | 0 | -7
PARIS | 0189-01-011 | RED RIVER | SH 37 | 2021-08-24 | 2961890.31 | 636836.86 | 3539646.62 | 577756.31 | 240 | 294 | 60 | 114
CORPUS CHRISTI | 1206-01-019 | LIVE OAK | FM 1358 | 2021-08-25 | 1425037.96 | 0 | 1429837.57 | 4799.61 | 150 | 153 | 3 | 6
LUBBOCK | 0380-01-092 | LUBBOCK | US 62 | 2021-08-25 | 10343902.54 | 88948.29 | 10988378.6 | 644476.06 | 328 | 329 | 5 | 6
LUFKIN | 0911-30-030 | SAN AUGUSTINE | CR | 2021-08-25 | 1141154.95 | 0 | 1109038.75 | -32116.2 | 182 | 182 | 0 | 0
TYLER | 0429-01-023 | WOOD | SH 182 | 2021-08-25 | 3239526.94 | -90172.97 | 2998899.33 | -240627.61 | 387 | 444 | 7 | 64
WICHITA FALLS | 0282-03-030 | CLAY | SH 79 | 2021-08-25 | 1939028.78 | 0 | 2005811.38 | 66782.6 | 51 | 29 | 0 | -22
YOAKUM | 0143-10-052 | VICTORIA | US 87 | 2021-08-25 | 2084719.95 | -296.39 | 2496171.59 | 411451.64 | 51 | 37 | 0 | -14
TYLER | 0122-04-039 | ANDERSON | US 287 | 2021-08-26 | 1097777.77 | 37512.36 | 1056069.27 | -41708.5 | 105 | 89 | 0 | -16
TYLER | 0191-01-092 | SMITH | US 69 | 2021-08-26 | 2060599.8 | 126718.85 | 2063036.82 | 2437.02 | 43 | 39 | 10 | 6
TYLER | 0910-07-077 | GREGG | VA | 2021-08-26 | 220600 | 0 | 222200 | 1600 | 30 | 25 | 0 | -5
WACO | 2136-01-015 | BELL | FM 2268 | 2021-08-26 | 5238854.32 | 585768.47 | 5815659.52 | 576805.2 | 240 | 294 | 54 | 108
DALLAS | 0095-14-029 | KAUFMAN | IH 20 | 2021-08-30 | 21134032.94 | 362543.96 | 19232844.65 | -1901188.29 | 201 | 291 | 34 | 124
DALLAS | 0451-01-055 | ROCKWALL | SH 205 | 2021-08-30 | 6382562.98 | 240924.42 | 6511971.46 | 129408.48 | 88 | 88 | 0 | 0
SAN ANTONIO | 0328-05-044 | ATASCOSA | SH 97 | 2021-08-30 | 12537464.63 | 306764.33 | 12746025.79 | 208561.16 | 417 | 784 | 339 | 706
TYLER | 1124-03-012 | CHEROKEE | FM 241 | 2021-08-30 | 5515687.82 | 148492.76 | 5887602.29 | 371914.47 | 230 | 142 | 0 | -88
YOAKUM | 0089-03-092 | JACKSON | US 59 | 2021-08-30 | 1939359.9 | 29352.61 | 1994865.96 | 55506.06 | 165 | 90 | 0 | -75
FORT WORTH | 0013-10-086 | TARRANT | BU 287P | 2021-08-31 | 433943.75 | 0 | 422407.1 | -11536.65 | 95 | 87 | 0 | -8
TYLER | 0095-06-073 | VAN ZANDT | US 80 | 2021-08-31 | 2544980.75 | -119654.02 | 2500685.5 | -44295.25 | 185 | 179 | 5 | -1
YOAKUM | 0144-03-037 | CALHOUN | US 87 | 2021-08-31 | 981455.75 | -55155 | 912774.28 | -68681.47 | 120 | 56 | 0 | -64
YOAKUM | 0573-05-019 | DE WITT | FM 240 | 2021-08-31 | 1191777.38 | 114047.04 | 1354993.38 | 163216 | 67 | 51 | 0 | -16

## LINE_GRAPH_DATA (hidden)
COUNTIFS(FINL,">="&B4-DAY(B4)+1,FINL,"<="&EOMONTH(B4,0))
FY 2021 Monthly Measures | [9 empty] | YTD
Month | Total Contracts | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO
SEP-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
OCT-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NOV-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DEC-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JAN-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FEB-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAR-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
APR-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAY-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JUN-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JUL-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AUG-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FY21 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
|  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!

## Summary Previous FYs (hidden)
CONSTRUCTION SUMMARY PERFORMANCE REPORT | [12 empty] | 5- YEAR AVERAGES
FY | Projects Accepted | Percent On Budget | Percent On Time | Percent On Time Previous | Projects Awarded | Awarded Amounts Billions | Estimated Amounts Billions | Amounts Over / (Under) the Estimate | Percent Over the Estimate | Dollars per Project | Awarded Amounts | Estimated Amounts | Awarded Amounts | Estimated Amounts | Percent Over the Estimate | Projects Accepted | Projects Awarded
2009 | 802 | 83.92% | 57.11% | 72.57% | 699 | 3.0857 | 3.6429 | -0.5572 | -15.3% | 4414461.6445 | 3085708689.49 | 3642907501.26
2010 | 797 | 84.69% | 65.5% | 77.42% | 1063 | 3.2459 | 3.6441 | -0.39818 | -10.93% | 3053502.9899 | 3245873678.22 | 3644056349
2011 | 872 | 88.99% | 68.17% | 77.18% | 870 | 3.497 | 3.7036 | -0.20654 | -5.577% | 4019586.1947 | 3497039989.43 | 3703575068.62
2012 | 772 | 87.95% | 67.62% | 76.55% | 685 | 2.9722 | 3.0097 | -0.037491 | -1.246% | 4338962.4606 | 2972189285.54 | 3009680367 | 3.2002 | 3.5001 | -8.567% | 810.75 | 829.25
2013 | 682 | 86.07% | 63.49% | N/A | 797 | 4.2752 | 4.2598 | 0.015356 | 0.3605% | 5364094.8547 | 4275183599.18 | 4259827109.53 | 3.4152 | 3.652 | -6.484% | 785 | 822.8
2014 | 636 | 86.48% | 68.08% | N/A | 757 | 3.8596 | 3.9509 | -0.091307 | -2.311% | 5098575.683 | 3859621792 | 3950928942.48 | 3.57 | 3.7136 | -3.868% | 751.8 | 834.4
2015 | 607 | 86.16% | 63.92% | N/A | 856 | 4.3749 | 4.3622 | 0.012684 | 0.2908% | 5110843.7065 | 4374882212.76 | 4362198207.53 | 3.7958 | 3.8572 | -1.593% | 713.8 | 793
2016 | 711 | 83.4% | 63.29% | N/A | 737 | 4.3375 | 4.4843 | -0.14682 | -3.274% | 5885376.9172 | 4337522787.99 | 4484341769.73 | 3.9639 | 4.0134 | -1.234% | 681.6 | 766.4
2017 | 864 | 80.9% | 62.73% | N/A | 779 | 4.7365 | 5.0552 | -0.31875 | -6.305% | 6080199.4759 | 4736475391.74 | 5055222420.56 | 4.3167 | 4.4225 | -2.392% | 700 | 785.2
2018 | 859 | 83.82% | 64.96% | N/A | 825 | 5.7327 | 5.8693 | -0.13661 | -2.328% | 6948682.4486 | 5732663020.12 | 5869277068.62 | 4.6082 | 4.7444 | -2.87% | 735.4 | 790.8
2019 | 718 | 94.57% | 85.79% | N/A | 895 | 6.5145 | 6.3033 | 0.21118 | 3.35% | 7278753.2179 | 6514484130 | 6303301439 | 4.9259 | 5.0042 | -1.564% | 732.5 | 808.1667
2020 | #REF! | #REF! | #REF! |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 5.1392 | 5.2149 | -1.451% | #REF! | 818.4