## OTOB
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [13 empty] | Required Reporting per Texas Transportation Code §201.812 –
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | AUGUST | 31 | 2025 | 2024 | [6 empty] | Highway Construction Projects Completed March 1, 2025–August 31, 2025
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | CO BY THRD PRTY | AMOUNT PAID | UNDER OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | THIRD PARTY DAYS ADDED | UNDER OVER SCHEDULE
FORT WORTH | 0079-05-062 | ERATH | US 67 | 2025-03-01 | 1284729 | 12539.88 | 0 | 1251049.63 | -33679.37 | 192 | 127 | 0 | 0 | -65
WICHITA FALLS | 0283-01-018 | WICHITA | FM 2380 | 2025-03-03 | 7479603.5 | 32436 | 0 | 7124839.38 | -354764.12 | 119 | 98 | 0 | 0 | -21
BRYAN | 0578-03-051 | WALKER | FM 1374 | 2025-03-04 | 611096.36 | 0 | 0 | 657156.6 | 46060.24 | 15 | 20 | 0 | 0 | 5
CHILDRESS | 0925-09-036 | HALL | CR | 2025-03-04 | 879885.4 | 0 | 0 | 878743 | -1142.4 | 65 | 55 | 0 | 0 | -10
YOAKUM | 0839-04-013 | DEWITT | FM 951 | 2025-03-04 | 1049361.55 | 16952.98 | 0 | 1048786.84 | -574.71 | 107 | 94 | 0 | 0 | -13
YOAKUM | 0913-26-065 | COLORADO | CS | 2025-03-04 | 411526 | -502.59 | 0 | 420723.11 | 9197.11 | 60 | 75 | 0 | 0 | 15
PHARR | 0039-07-260 | CAMERON | IH 69E | 2025-03-05 | 489585.1 | 0 | 0 | 487380.6 | -2204.5 | 63 | 15 | 0 | 0 | -48
SAN ANGELO | 0907-00-201 | TOM GREEN | VA | 2025-03-05 | 3905830.24 | 424006.98 | 0 | 4492187.12 | 586356.88 | 498 | 670 | 173 | 0 | 172
WACO | 0231-07-009 | BELL | SS 172 | 2025-03-05 | 625499 | 6700 | 0 | 623685.57 | -1813.43 | 45 | 42 | 0 | 0 | -3
AUSTIN | 0113-09-077 | TRAVIS | US 290 | 2025-03-06 | 406602.55 | 0 | 0 | 391632.27 | -14970.28 | 38 | 21 | 0 | 0 | -17
PARIS | 0901-19-208 | GRAYSON | Various | 2025-03-06 | 1696572 | 0 | 0 | 1682037.08 | -14534.92 | 96 | 94 | 0 | 0 | -2
WICHITA FALLS | 0224-02-052 | CLAY | US 287 | 2025-03-06 | 5372832.45 | 0 | 0 | 5187895.83 | -184936.62 | 119 | 55 | 0 | 0 | -64
BEAUMONT | 0508-03-115 | CHAMBERS | SH 73 | 2025-03-07 | 3456563 | -170850 | 0 | 3302371.25 | -154191.75 | 120 | 134 | 21 | 0 | 14
BEAUMONT | 1024-02-049 | CHAMBERS | FM 1405 | 2025-03-07 | 101109.88 | 10390.39 | 0 | 112912.05 | 11802.17 | 25 | 18 | 0 | 0 | -7
DALLAS | 0081-06-042 | DENTON | US 377 | 2025-03-07 | 7494391.1 | 349781.72 | 0 | 7694876.88 | 200485.78 | 199 | 179 | 8 | 0 | -20
DALLAS | 2374-02-164 | DALLAS | IH 635 | 2025-03-07 | 4193300 | 388139.22 | 0 | 5004432.72 | 811132.72 | 125 | 127 | 3 | 0 | 2
HOUSTON | 0598-01-108 | HARRIS | SH 288 | 2025-03-07 | 3336063.58 | 760117.52 | 0 | 4770905.82 | 1434842.24 | 165 | 156 | 0 | 0 | -9
PHARR | 0220-07-068 | CAMERON | SH 48 | 2025-03-07 | 383790 | 0 | 0 | 365764 | -18026 | 70 | 80 | 0 | 0 | 10
SAN ANTONIO | 0142-03-031 | KERR | SH 27 | 2025-03-07 | 1836910.48 | 172424.46 | 0 | 1975169.23 | 138258.75 | 218 | 231 | 9 | 0 | 13
SAN ANTONIO | 0915-00-264 | BEXAR | Various | 2025-03-07 | 2147579.65 | 32557.14 | 20613.11 | 2048083.83 | -120108.93 | 150 | 132 | 0 | 0 | -18
AUSTIN | 2295-01-019 | WILLIAMSON | FM 973 | 2025-03-10 | 885042.65 | 158125 | 0 | 1068558.52 | 183515.87 | 47 | 26 | 0 | 0 | -21
LAREDO | 0018-05-090 | WEBB | IH 35 | 2025-03-10 | 3289936.68 | 157970.68 | 0 | 3614472.97 | 324536.29 | 96 | 76 | 0 | 0 | -20
WACO | 0909-00-075 | MCLENNAN | Various | 2025-03-10 | 1018951.35 | 220319.92 | 0 | 1305945.85 | 286994.5 | 45 | 46 | 12 | 0 | 1
ODESSA | 0479-03-021 | LOVING | SH 302 | 2025-03-11 | 31270742.8 | 1319708.85 | 0 | 35617076.5 | 4346333.7 | 478 | 374 | 0 | 0 | -104
WICHITA FALLS | 0224-01-062 | CLAY | US 287 | 2025-03-11 | 2393785.6 | 0 | 0 | 2804237.76 | 410452.16 | 51 | 111 | 0 | 0 | 60
YOAKUM | 0913-22-052 | GONZALES | CR | 2025-03-11 | 1049084.97 | -5410.32 | 0 | 1015670.44 | -33414.53 | 185 | 283 | 67 | 0 | 98
BEAUMONT | 0920-00-151 | JEFFERSON | Various | 2025-03-12 | 2072210 | 0 | 0 | 2048020 | -24190 | 87 | 103 | 20 | 0 | 16
BEAUMONT | 0951-01-068 | LIBERTY | SH 105 | 2025-03-12 | 1980516.24 | 266861.12 | 0 | 2282058.65 | 301542.41 | 51 | 79 | 30 | 0 | 28
TYLER | 2642-01-049 | GREGG | SL 281 | 2025-03-12 | 225254.7 | 0 | 0 | 238984.4 | 13729.7 | 45 | 23 | 0 | 0 | -22
AUSTIN | 0914-33-088 | HAYS | CR | 2025-03-13 | 1277863 | 146991.66 | 0 | 1440294.9 | 162431.9 | 120 | 133 | 15 | 0 | 13
BEAUMONT | 1275-01-045 | JASPER | FM 1005 | 2025-03-13 | 4779349.75 | 8011.82 | 0 | 4654149.08 | -125200.67 | 93 | 155 | 31 | 0 | 62
BRYAN | 0315-04-083 | GRIMES | SH 105 | 2025-03-13 | 2060026.16 | 0 | 0 | 2056719.89 | -3306.27 | 90 | 134 | 0 | 0 | 44
SAN ANTONIO | 0025-04-051 | GUADALUPE | UA 90 | 2025-03-13 | 2221434.35 | 118249.84 | 0 | 2383206.03 | 161771.68 | 150 | 122 | 6 | 0 | -28
CORPUS CHRISTI | 0916-28-077 | SAN PATRICIO | CR | 2025-03-14 | 796205.35 | 4851.28 | 0 | 793324.13 | -2881.22 | 96 | 278 | 11 | 0 | 182
EL PASO | 0924-06-712 | EL PASO | Various | 2025-03-14 | 1050190.66 | 0 | 0 | 1107109.76 | 56919.1 | 30 | 25 | 0 | 0 | -5
LAREDO | 0160-05-049 | VAL VERDE | US 277 | 2025-03-14 | 9710710.72 | -8056.29 | 0 | 10124593.32 | 413882.6 | 133 | 130 | 0 | 0 | -3
BRYAN | 0917-20-045 | FREESTONE | CR | 2025-03-17 | 581241.25 | 19442.49 | 0 | 659925.66 | 78684.41 | 158 | 99 | 0 | 0 | -59
DALLAS | 1012-01-017 | COLLIN | FM 543 | 2025-03-17 | 2920104.63 | 29283.42 | 0 | 2906402.79 | -13701.84 | 214 | 208 | 0 | 0 | -6
PHARR | 3093-01-002 | CAMERON | FM 3069 | 2025-03-17 | 5289300.97 | -48073.97 | 0 | 5591253.32 | 301952.35 | 224 | 206 | 26 | 0 | -18
SAN ANTONIO | 0521-04-204 | BEXAR | IH 410 | 2025-03-17 | 77332883.27 | 2144023.56 | 0 | 81160031.35 | 3827148.08 | 805 | 980 | 177 | 0 | 175
AUSTIN | 0914-04-331 | TRAVIS | CS | 2025-03-18 | 550669.94 | 143043.77 | 0 | 874407.61 | 323737.67 | 95 | 73 | 0 | 0 | -22
AUSTIN | 0914-19-033 | GILLESPIE | CR | 2025-03-18 | 1025365 | 4108 | 0 | 1168201.68 | 142836.68 | 110 | 96 | 0 | 0 | -14
EL PASO | 0924-06-644 | EL PASO | CS | 2025-03-18 | 746836 | 23045.17 | 15869.17 | 789331.17 | 26626 | 80 | 72 | 0 | 0 | -8
HOUSTON | 0271-16-167 | HARRIS | IH 610 | 2025-03-18 | 1439308.97 | 0 | 0 | 947480.66 | -491828.31 | 40 | 40 | 0 | 0 | 0
ODESSA | 0380-09-102 | MIDLAND | BS 349C | 2025-03-19 | 353315 | -21000 | 0 | 341196.84 | -12118.16 | 96 | 57 | 0 | 0 | -39
TYLER | 0392-03-052 | GREGG | US 259 | 2025-03-19 | 3787210.55 | 160032.92 | 0 | 4165761.59 | 378551.04 | 58 | 172 | 137 | 0 | 114
AMARILLO | 0041-01-050 | HARTLEY | US 87 | 2025-03-20 | 19650397.7 | 41948.34 | 0 | 20014711.76 | 364314.06 | 101 | 89 | 0 | 0 | -12
BRYAN | 0114-09-090 | WASHINGTON | US 290 | 2025-03-20 | 286956.5 | 11021.68 | 0 | 291314.32 | 4357.82 | 118 | 112 | 0 | 0 | -6
DALLAS | 0092-14-104 | DALLAS | IH 45 | 2025-03-20 | 3534464.3 | 89071.96 | 0 | 3594597.94 | 60133.64 | 102 | 160 | 2 | 0 | 58
TYLER | 0495-02-069 | VAN ZANDT | IH 20 | 2025-03-20 | 5701599.66 | 45449.62 | 0 | 5621765.61 | -79834.05 | 94 | 112 | 0 | 0 | 18
WICHITA FALLS | 0284-02-026 | THROCKMORTON | SH 79 | 2025-03-20 | 7963304.67 | 16006.79 | 0 | 7944026.56 | -19278.11 | 238 | 160 | 0 | 0 | -78
ATLANTA | 0010-19-014 | BOWIE | FM 991 | 2025-03-21 | 11823241.45 | 85973.67 | 0 | 10582326.01 | -1240915.44 | 88 | 106 | 18 | 0 | 18
BEAUMONT | 0028-06-087 | JEFFERSON | US 90 | 2025-03-21 | 13998169.35 | 147500 | 0 | 12952770.45 | -1045398.9 | 75 | 33 | 0 | 0 | -42
BEAUMONT | 0508-02-132 | CHAMBERS | IH 10 | 2025-03-21 | 1744247.6 | 476886.51 | 0 | 2342290.25 | 598042.65 | 71 | 111 | 40 | 0 | 40
BEAUMONT | 1146-01-029 | LIBERTY | FM 834 | 2025-03-21 | 4870507.63 | -184762.94 | 0 | 5109369.37 | 238861.74 | 188 | 180 | 0 | 0 | -8
CORPUS CHRISTI | 0916-28-081 | SAN PATRICIO | Various | 2025-03-21 | 445689 | 8356.32 | 0 | 459285.52 | 13596.52 | 102 | 74 | 0 | 0 | -28
CORPUS CHRISTI | 3026-01-034 | SAN PATRICIO | FM 2986 | 2025-03-21 | 417141.4 | 27035.97 | 0 | 448415.88 | 31274.48 | 99 | 88 | 7 | 0 | -11
EL PASO | 0001-02-076 | EL PASO | SH 20 | 2025-03-21 | 3070094.47 | 364463.4 | 0 | 3531097.76 | 461003.29 | 200 | 243 | 54 | 0 | 43
ABILENE | 1155-04-013 | BORDEN | FM 1785 | 2025-03-24 | 4392391.03 | 74459.32 | 0 | 4224257.95 | -168133.08 | 190 | 212 | 22 | 0 | 22
AUSTIN | 0015-08-431 | WILLIAMSON | IH 35 | 2025-03-24 | 5399229.07 | -71318.88 | 0 | 5868030.12 | 468801.05 | 105 | 38 | 0 | 0 | -67
BRYAN | 0540-04-005 | BRAZOS | FM 2154 | 2025-03-24 | 2432738.73 | 179678.38 | 648 | 2527857.65 | 94470.92 | 162 | 162 | 0 | 0 | 0
LUFKIN | 0911-00-096 | ANGELINA | Various | 2025-03-24 | 2621784 | 510613.65 | 0 | 3286725.46 | 664941.46 | 108 | 93 | 0 | 0 | -15
ODESSA | 0906-00-267 | ECTOR | Various | 2025-03-24 | 1139465 | 251532.3 | 0 | 1357331.31 | 217866.31 | 79 | 111 | 52 | 0 | 32
AUSTIN | 0285-02-015 | HAYS | RM 2325 | 2025-03-25 | 4429879.58 | -46692.15 | 0 | 4717432.36 | 287552.78 | 85 | 53 | 0 | 0 | -32
BEAUMONT | 0920-06-037 | NEWTON | CR | 2025-03-25 | 1497066 | 7250 | 0 | 1495161.22 | -1904.78 | 119 | 107 | 0 | 0 | -12
CORPUS CHRISTI | 1553-02-008 | LIVE OAK | FM 1545 | 2025-03-25 | 7861814.05 | 464739.06 | 0 | 8157726.66 | 295912.61 | 150 | 172 | 22 | 0 | 22
FORT WORTH | 0008-12-094 | TARRANT | IH 20 | 2025-03-25 | 6688663.45 | -391799.3 | 0 | 6595844.3 | -92819.15 | 214 | 214 | 0 | 0 | 0
LAREDO | 0483-01-056 | LA SALLE | SH 97 | 2025-03-25 | 67316512.39 | 3135681.6 | 0 | 71816890.2 | 4500377.81 | 464 | 894 | 452 | 0 | 430
LUBBOCK | 0052-01-042 | PARMER | US 70 | 2025-03-25 | 15350631.5 | -5243336.47 | 0 | 9756566.64 | -5594064.86 | 375 | 818 | -47 | 0 | 443
LUFKIN | 0118-08-090 | NACOGDOCHES | BS 21P | 2025-03-25 | 329755.01 | 6002 | 0 | 322148.8 | -7606.21 | 40 | 33 | 0 | 0 | -7
LUFKIN | 0336-05-068 | ANGELINA | SH 103 | 2025-03-25 | 317626.55 | 22400.44 | 0 | 354391.94 | 36765.39 | 37 | 37 | 0 | 0 | 0
LUFKIN | 0911-00-095 | ANGELINA | Various | 2025-03-25 | 3368123.02 | 0 | 0 | 3308511.41 | -59611.61 | 122 | 143 | 17 | 0 | 21
TYLER | 0910-07-082 | GREGG | CS | 2025-03-25 | 90510 | 4029.59 | 0 | 88939.92 | -1570.08 | 23 | 15 | 0 | 0 | -8
TYLER | 0910-16-183 | SMITH | CS | 2025-03-25 | 108505.5 | 0 | 0 | 109373.5 | 868 | 13 | 12 | 0 | 0 | -1
AUSTIN | 0016-03-124 | HAYS | IH 35 | 2025-03-26 | 1002855.18 | 108527.49 | 0 | 1097857.26 | 95002.08 | 29 | 15 | 0 | 0 | -14
BEAUMONT | 0920-38-279 | JEFFERSON | CS | 2025-03-26 | 917230 | 17574 | 0 | 934804 | 17574 | 49 | 33 | 0 | 0 | -16
FORT WORTH | 0747-03-082 | TARRANT | FM 157 | 2025-03-26 | 2090441.55 | 230708.95 | 0 | 2373001.95 | 282560.4 | 107 | 109 | 10 | 0 | 2
HOUSTON | 0271-15-094 | HARRIS | IH 610 | 2025-03-26 | 1178547.51 | 69988.75 | 0 | 1131882.3 | -46665.21 | 59 | 91 | 0 | 0 | 32
WACO | 0320-01-079 | BELL | SH 95 | 2025-03-26 | 2163604.22 | 11394.24 | 0 | 2148462.25 | -15141.97 | 90 | 117 | 16 | 0 | 27
BEAUMONT | 0508-02-129 | CHAMBERS | IH 10 | 2025-03-27 | 2423889.7 | -88750.22 | 0 | 2365373.7 | -58516 | 44 | 106 | 8 | 0 | 62
BEAUMONT | 1812-02-026 | CHAMBERS | FM 1942 | 2025-03-27 | 1093300.7 | 103120.8 | 0 | 1040189.37 | -53111.33 | 37 | 41 | 4 | 0 | 4
BRYAN | 0204-05-044 | MILAM | US 79 | 2025-03-27 | 937377.85 | 8240.97 | 0 | 893726.72 | -43651.13 | 75 | 74 | 0 | 0 | -1
SAN ANTONIO | 0072-05-096 | KENDALL | IH 10 | 2025-03-27 | 2404185.2 | 0 | 0 | 2558529.74 | 154344.54 | 160 | 160 | 0 | 0 | 0
SAN ANTONIO | 0366-02-094 | GUADALUPE | SH 123 | 2025-03-27 | 7325978.26 | -201337.08 | 0 | 7273795.43 | -52182.83 | 173 | 158 | 14 | 0 | -15
SAN ANTONIO | 0915-45-056 | MEDINA | CR | 2025-03-27 | 730221 | 45927.67 | 0 | 772374.27 | 42153.27 | 149 | 149 | 0 | 0 | 0
YOAKUM | 0709-03-011 | WHARTON | FM 3012 | 2025-03-27 | 5786574.01 | 692743.26 | 0 | 6741280.26 | 954706.25 | 180 | 176 | 0 | 0 | -4
AUSTIN | 0914-04-288 | TRAVIS | Various | 2025-03-28 | 971504 | -132082.6 | 0 | 645547.64 | -325956.36 | 16 | 25 | 0 | 0 | 9
AUSTIN | 1186-01-091 | TRAVIS | FM 969 | 2025-03-28 | 8953609.72 | 1818852.28 | 0 | 11008211.92 | 2054602.2 | 120 | 241 | 127 | 0 | 121
BEAUMONT | 0710-02-071 | ORANGE | FM 105 | 2025-03-28 | 5542611.78 | 439194.06 | 0 | 5881525.35 | 338913.57 | 90 | 72 | 0 | 0 | -18
BEAUMONT | 0920-00-165 | JEFFERSON | Various | 2025-03-28 | 891512 | -184734.15 | 0 | 758499.49 | -133012.51 | 93 | 30 | 0 | 0 | -63
BEAUMONT | 0920-12-047 | JASPER | Various | 2025-03-28 | 1396803.75 | 23277.53 | 0 | 1443483.78 | 46680.03 | 120 | 114 | 0 | 0 | -6
DALLAS | 2351-02-017 | COLLIN | FM 2478 | 2025-03-28 | 9301659.25 | 1044626.8 | 0 | 9678590.14 | 376930.89 | 215 | 196 | 0 | 0 | -19
EL PASO | 0002-04-034 | HUDSPETH | SH 20 | 2025-03-28 | 3183455.4 | 12567.37 | 0 | 3201240.48 | 17785.08 | 180 | 169 | 20 | 0 | -11
EL PASO | 0002-04-035 | HUDSPETH | SH 20 | 2025-03-28 | 3814947.9 | 579187.74 | 0 | 4476252.12 | 661304.22 | 143 | 104 | 4 | 0 | -39
HOUSTON | 0912-72-390 | HARRIS | Various | 2025-03-28 | 1389740 | 155342.23 | 155342.23 | 1327745.96 | -217336.27 | 166 | 178 | 20 | 20 | -8
TYLER | 0910-07-086 | GREGG | CS | 2025-03-28 | 439360.25 | 0 | 0 | 441957.45 | 2597.2 | 62 | 60 | 0 | 0 | -2
CHILDRESS | 0925-00-100 | CHILDRESS | Various | 2025-03-31 | 122600 | 474.75 | 0 | 118099.75 | -4500.25 | 39 | 15 | 0 | 0 | -24
DALLAS | 0196-02-132 | DENTON | IH 35E | 2025-03-31 | 17598674.69 | 176226.78 | 0 | 17632644.19 | 33969.5 | 378 | 412 | 39 | 0 | 34
AMARILLO | 0275-01-229 | POTTER | IH 40 | 2025-04-01 | 8159181.05 | 123896.3 | 0 | 8712295.93 | 553114.88 | 175 | 187 | 67 | 0 | 12
BEAUMONT | 0306-03-138 | JEFFERSON | SH 87 | 2025-04-01 | 6555483.35 | 289823.22 | 0 | 7015534.75 | 460051.4 | 90 | 77 | 0 | 0 | -13
BEAUMONT | 0920-30-093 | ORANGE | CS | 2025-04-01 | 601425 | -517.92 | 0 | 657971.09 | 56546.09 | 46 | 61 | 0 | 0 | 15
BEAUMONT | 0920-00-161 | JEFFERSON | Various | 2025-04-02 | 721370.25 | 0 | 0 | 678872.03 | -42498.22 | 59 | 44 | 0 | 0 | -15
SAN ANGELO | 0494-10-017 | REAGAN | SH 137 | 2025-04-03 | 29854259.38 | 1819735.64 | 0 | 33408819.06 | 3554559.68 | 430 | 446 | 0 | 0 | 16
YOAKUM | 0088-05-085 | VICTORIA | US 59 | 2025-04-03 | 28593622.7 | 5971251.3 | 0 | 34627620.6 | 6033997.9 | 600 | 783 | 205 | 0 | 183
YOAKUM | 0715-01-022 | GONZALES | FM 108 | 2025-04-03 | 12569350 | 246880.73 | 0 | 12537971.07 | -31378.93 | 250 | 492 | 242 | 0 | 242
DALLAS | 0047-06-161 | COLLIN | US 75 | 2025-04-04 | 43578573.64 | 5319727.35 | 0 | 48676615.53 | 5098041.89 | 498 | 563 | 155 | 0 | 65
LUBBOCK | 0067-07-100 | LUBBOCK | IH 27 | 2025-04-04 | 2286930.5 | 1897006.91 | 0 | 4237873.91 | 1950943.41 | 223 | 277 | 55 | 0 | 54
LUBBOCK | 0905-06-126 | LUBBOCK | CS | 2025-04-04 | 267401 | -20167.95 | 0 | 260508.02 | -6892.98 | 29 | 54 | 0 | 0 | 25
SAN ANGELO | 0077-06-101 | TOM GREEN | US 67 | 2025-04-04 | 1130457.59 | 390415.14 | 0 | 1509283.43 | 378825.84 | 127 | 544 | 80 | 0 | 417
WACO | 0121-02-062 | HILL | SH 22 | 2025-04-04 | 383252.5 | 3727.8 | 0 | 334785.3 | -48467.2 | 30 | 16 | 0 | 0 | -14
WACO | 0909-00-051 | MCLENNAN | Various | 2025-04-04 | 454340 | 6228.4 | 0 | 437878.4 | -16461.6 | 45 | 42 | 0 | 0 | -3
HOUSTON | 0912-73-232 | GALVESTON | Various | 2025-04-07 | 1093187.76 | -11990 | 0 | 923750.73 | -169437.03 | 70 | 61 | 0 | 0 | -9
BEAUMONT | 2120-01-028 | JASPER | FM 2246 | 2025-04-08 | 11322202.97 | 121228.34 | 0 | 11327004.29 | 4801.32 | 214 | 215 | 0 | 0 | 1
LUFKIN | 0911-40-030 | TRINITY | CR | 2025-04-08 | 499406.54 | 0 | 0 | 507218.38 | 7811.84 | 57 | 56 | 0 | 0 | -1
BEAUMONT | 0932-02-044 | JEFFERSON | FM 365 | 2025-04-09 | 7997540.61 | -193271.3 | 0 | 7429618.6 | -567922.01 | 150 | 143 | 0 | 0 | -7
TYLER | 0392-03-050 | GREGG | US 259 | 2025-04-09 | 5038500 | 138708.35 | 0 | 5246791.15 | 208291.15 | 76 | 104 | 2 | 0 | 28
WACO | 0909-00-068 | MCLENNAN | Various | 2025-04-09 | 2894300.49 | 29129.28 | 0 | 2895667.77 | 1367.28 | 60 | 23 | 0 | 0 | -37
HOUSTON | 2744-01-032 | MONTGOMERY | FM 2854 | 2025-04-10 | 10866955.64 | 989951.33 | 0 | 13710247.66 | 2843292.02 | 135 | 191 | 116 | 0 | 56
TYLER | 0123-03-022 | CHEROKEE | US 84 | 2025-04-10 | 7859265.16 | -46910.5 | 0 | 7899546.85 | 40281.69 | 295 | 295 | 0 | 0 | 0
BEAUMONT | 0508-04-177 | JEFFERSON | SH 73 | 2025-04-11 | 3316497.35 | -13739.51 | 0 | 3309781.55 | -6715.8 | 90 | 90 | 0 | 0 | 0
CORPUS CHRISTI | 0073-14-008 | LIVE OAK | UA 281 | 2025-04-11 | 148156.67 | 2084.5 | 0 | 146024.85 | -2131.82 | 46 | 33 | 0 | 0 | -13
CORPUS CHRISTI | 1557-01-043 | NUECES | FM 43 | 2025-04-11 | 5154966.44 | 797959.61 | 0 | 5829320.06 | 674353.62 | 187 | 368 | 150 | 0 | 181
FORT WORTH | 0902-90-300 | TARRANT | Various | 2025-04-11 | 473301 | 1979312.96 | 0 | 2336164.99 | 1862863.99 | 150 | 213 | 65 | 0 | 63
CORPUS CHRISTI | 0916-02-022 | KLEBERG | Various | 2025-04-14 | 797183.75 | -2240 | 0 | 722987.29 | -74196.46 | 102 | 139 | 53 | 0 | 37
ODESSA | 2224-01-118 | ECTOR | SL 338 | 2025-04-14 | 18181464.7 | 1016714.91 | 0 | 20309064.29 | 2127599.59 | 255 | 250 | 0 | 0 | -5
PARIS | 0680-05-014 | HOPKINS | FM 900 | 2025-04-14 | 3356595.02 | -34129.62 | 0 | 3370819.75 | 14224.73 | 223 | 128 | 0 | 0 | -95
SAN ANTONIO | 0291-02-038 | KERR | SH 16 | 2025-04-14 | 4178288.49 | 463399.71 | 0 | 4782368.3 | 604079.81 | 81 | 119 | 35 | 0 | 38
YOAKUM | 0026-02-039 | FAYETTE | US 90 | 2025-04-14 | 19785795.69 | -336832.83 | 0 | 18877082.59 | -908713.1 | 75 | 75 | 0 | 0 | 0
YOAKUM | 1090-01-027 | JACKSON | FM 530 | 2025-04-14 | 2346537.14 | 20466.8 | 0 | 2282968.16 | -63568.98 | 165 | 190 | 0 | 0 | 25
AUSTIN | 0071-06-062 | GILLESPIE | US 87 | 2025-04-15 | 6082477.49 | -348041.48 | 0 | 6243439.15 | 160961.66 | 117 | 67 | 15 | 0 | -50
BEAUMONT | 0028-03-110 | LIBERTY | US 90 | 2025-04-15 | 1094436 | 1256242.71 | 0 | 2127009.12 | 1032573.12 | 60 | 188 | 128 | 0 | 128
SAN ANTONIO | 0072-06-075 | KENDALL | IH 10 | 2025-04-15 | 60282257.43 | 7800955.8 | 0 | 66260186.2 | 5977928.77 | 720 | 1354 | 214 | 0 | 634
WACO | 0836-02-077 | BELL | SH 195 | 2025-04-15 | 5775775 | 210842.22 | 0 | 6319759.58 | 543984.58 | 60 | 72 | 45 | 0 | 12
ABILENE | 0006-01-107 | MITCHELL | IH 20 | 2025-04-16 | 10261309.24 | -111357.44 | 0 | 10723444.42 | 462135.18 | 88 | 88 | 0 | 0 | 0
AUSTIN | 3417-02-038 | WILLIAMSON | FM 734 | 2025-04-16 | 1681925 | 0 | 0 | 1732012.23 | 50087.23 | 60 | 52 | 0 | 0 | -8
DALLAS | 0197-02-133 | DALLAS | US 175 | 2025-04-16 | 2097982.44 | 0 | 0 | 2140842.92 | 42860.48 | 200 | 200 | 0 | 0 | 0
AMARILLO | 0356-01-107 | HUTCHINSON | SH 136 | 2025-04-17 | 9658644.05 | 526827.17 | 0 | 11044418.48 | 1385774.43 | 100 | 116 | 32 | 0 | 16
AMARILLO | 2127-01-010 | HUTCHINSON | RM 2277 | 2025-04-17 | 3371388.86 | 288107.2 | 0 | 3705117.3 | 333728.44 | 230 | 454 | 3 | 0 | 224
ATLANTA | 0919-30-061 | TITUS | CR | 2025-04-17 | 723296.87 | 0 | 0 | 710900.66 | -12396.21 | 79 | 71 | 0 | 0 | -8
BROWNWOOD | 0257-05-046 | COMANCHE | SH 6 | 2025-04-17 | 13793112.53 | 3647460.29 | 0 | 17534215.64 | 3741103.11 | 368 | 629 | 224 | 0 | 261
FORT WORTH | 0249-08-042 | PALO PINTO | US 281 | 2025-04-17 | 22988075.85 | -612702.26 | 0 | 22202401.42 | -785674.43 | 363 | 530 | 0 | 0 | 167
LAREDO | 0922-20-020 | LA SALLE | CR | 2025-04-17 | 3804555.96 | 25889.12 | 0 | 3920882.48 | 116326.52 | 419 | 408 | 0 | 0 | -11
LAREDO | 2660-01-012 | DIMMIT | FM 2688 | 2025-04-17 | 12957924.78 | -81451.02 | 0 | 13016746.25 | 58821.47 | 292 | 242 | 0 | 0 | -50
CORPUS CHRISTI | 0102-16-001 | NUECES | US 77 | 2025-04-18 | 118322898.22 | 8941721.42 | 0 | 128461082.51 | 10138184.29 | 917 | 1126 | 262 | 0 | 209
BEAUMONT | 0339-04-040 | HARDIN | SH 105 | 2025-04-22 | 1536305.3 | 107259.41 | 0 | 1612201.42 | 75896.12 | 90 | 77 | 30 | 0 | -13
BEAUMONT | 0667-02-117 | JEFFERSON | FM 366 | 2025-04-23 | 5074278.87 | 18493.38 | 0 | 4983967.62 | -90311.25 | 60 | 51 | 0 | 0 | -9
BROWNWOOD | 0011-07-060 | STEPHENS | US 180 | 2025-04-24 | 6649967.98 | 244055.75 | 0 | 7132847.6 | 482879.62 | 75 | 42 | 0 | 0 | -33
BRYAN | 0050-03-100 | GRIMES | SH 6 | 2025-04-24 | 5798125.91 | 1509761.45 | 0 | 7523098.16 | 1724972.25 | 72 | 176 | 95 | 0 | 104
SAN ANTONIO | 1741-02-036 | BEXAR | FM 2790 | 2025-04-24 | 7692727.42 | 572407.87 | 96923 | 8415889.39 | 626238.97 | 255 | 255 | 10 | 0 | 0
AMARILLO | 0795-05-010 | DONLEY | FM 291 | 2025-04-25 | 3892082 | 117885.82 | 0 | 4073611.36 | 181529.36 | 210 | 279 | 0 | 0 | 69
BRYAN | 0917-27-047 | WALKER | CR | 2025-04-25 | 832940.17 | 12101.6 | 0 | 831557.18 | -1382.99 | 110 | 109 | 0 | 0 | -1
CHILDRESS | 0925-15-014 | DICKENS | CR | 2025-04-25 | 1446464 | 0 | 0 | 1421286 | -25178 | 119 | 115 | 0 | 0 | -4
PARIS | 0091-10-002 | GRAYSON | FS 121 | 2025-04-25 | 9300300.06 | 112531.87 | 0 | 9500736.59 | 200436.53 | 328 | 348 | 0 | 0 | 20
ATLANTA | 0495-08-138 | HARRISON | IH 20 | 2025-04-28 | 4714765 | 363325 | 0 | 5247421.36 | 532656.36 | 148 | 176 | 19 | 0 | 28
SAN ANTONIO | 0017-04-044 | ATASCOSA | IH 35 | 2025-04-28 | 6383622.46 | 1534369.51 | 0 | 8143491.37 | 1759868.91 | 282 | 340 | 44 | 0 | 58
WICHITA FALLS | 0903-00-123 | WICHITA | Various | 2025-04-29 | 1166854 | 110772.23 | 0 | 1377963.23 | 211109.23 | 153 | 123 | 0 | 0 | -30
AUSTIN | 0683-04-022 | TRAVIS | RM 3238 | 2025-04-30 | 15859606.92 | 879973.14 | 372558.34 | 18407994.18 | 2175828.92 | 287 | 333 | 48 | 0 | 46
BEAUMONT | 0028-06-083 | JEFFERSON | US 90 | 2025-04-30 | 3878702.08 | 377535.41 | 0 | 4658078.26 | 779376.18 | 320 | 369 | 97 | 0 | 49
BRYAN | 1953-01-028 | MILAM | FM 2095 | 2025-04-30 | 2461069.87 | -57872 | 0 | 2360695.51 | -100374.36 | 116 | 145 | 0 | 0 | 29
FORT WORTH | 0014-16-287 | TARRANT | IH 35W | 2025-04-30 | 3964154.99 | 283251.18 | 0 | 4061023.11 | 96868.12 | 299 | 298 | 0 | 0 | -1
SAN ANTONIO | 0253-03-074 | COMAL | US 281 | 2025-04-30 | 1048990 | 0 | 0 | 1007536.64 | -41453.36 | 165 | 119 | 0 | 0 | -46
FORT WORTH | 0008-03-124 | PARKER | IH 20 | 2025-05-01 | 18575904.96 | -1241527.26 | 0 | 17948547.2 | -627357.76 | 256 | 252 | 16 | 0 | -4
PHARR | 0433-02-052 | WILLACY | SH 186 | 2025-05-01 | 20899927.85 | 2230075 | 0 | 23767971.33 | 2868043.48 | 560 | 1148 | 551 | 0 | 588
YOAKUM | 0143-07-039 | GONZALES | US 87 | 2025-05-01 | 8424542.38 | -78435.51 | 0 | 8331065.44 | -93476.94 | 370 | 412 | 42 | 0 | 42
AMARILLO | 0169-07-053 | GRAY | US 60 | 2025-05-02 | 16536378.97 | 675903.25 | 0 | 19834094.35 | 3297715.38 | 351 | 333 | 0 | 0 | -18
AUSTIN | 3417-03-033 | TRAVIS | FM 734 | 2025-05-02 | 3643668.43 | -184467.52 | 0 | 3636712.57 | -6955.86 | 63 | 41 | 0 | 0 | -22
BEAUMONT | 0920-12-048 | JASPER | CS | 2025-05-02 | 619481.5 | 46025.28 | 0 | 721301.23 | 101819.73 | 41 | 54 | 13 | 0 | 13
SAN ANTONIO | 0915-00-228 | BEXAR | VA | 2025-05-02 | 1625675.84 | 268259.08 | 224746.91 | 1291526.3 | -558896.45 | 320 | 288 | 0 | 0 | -32
DALLAS | 0095-14-033 | KAUFMAN | IH 20 | 2025-05-05 | 2192309.35 | -35409.5 | 0 | 2164798.27 | -27511.08 | 400 | 222 | 0 | 0 | -178
ODESSA | 0906-00-205 | ECTOR | Various | 2025-05-06 | 1677753 | 524518.88 | 0 | 2245715.71 | 567962.71 | 260 | 237 | 0 | 0 | -23
SAN ANGELO | 0907-24-056 | TOM GREEN | GR | 2025-05-06 | 273114.6 | 0 | 0 | 275850.01 | 2735.41 | 51 | 19 | 0 | 0 | -32
SAN ANTONIO | 0143-04-071 | WILSON | US 87 | 2025-05-07 | 370530 | 0 | 0 | 368337.82 | -2192.18 | 74 | 36 | 0 | 0 | -38
ATLANTA | 2030-01-011 | UPSHUR | FM 556 | 2025-05-08 | 2318245.79 | 17577.72 | 0 | 2499443.74 | 181197.95 | 186 | 126 | 5 | 0 | -60
CHILDRESS | 0844-03-013 | COLLINGSWORTH | FM 1547 | 2025-05-08 | 10872131.3 | 79123.6 | 0 | 11045357.34 | 173226.04 | 237 | 226 | 0 | 0 | -11
HOUSTON | 3256-01-121 | HARRIS | SL 8 | 2025-05-08 | 3744941.62 | 1274569.06 | 0 | 5071428.42 | 1326486.8 | 150 | 145 | 0 | 0 | -5
LUBBOCK | 0297-01-014 | YOAKUM | US 380 | 2025-05-08 | 6041330 | -155073.5 | 0 | 5777525.56 | -263804.44 | 59 | 56 | 5 | 0 | -3
HOUSTON | 0110-05-140 | HARRIS | IH 45 | 2025-05-09 | 423534.75 | 12436.9 | 0 | 455684 | 32149.25 | 69 | 47 | 0 | 0 | -22
HOUSTON | 0720-06-002 | HARRIS | SH 249 | 2025-05-09 | 375697.38 | 0 | 0 | 365887.23 | -9810.15 | 78 | 67 | 0 | 0 | -11
SAN ANTONIO | 0748-06-016 | ATASCOSA | FM 1099 | 2025-05-09 | 14508838.6 | -8456.71 | 0 | 14375438.99 | -133399.61 | 298 | 269 | 0 | 0 | -29
LAREDO | 0922-00-067 | WEBB | Various | 2025-05-12 | 1775792.1 | 20594.28 | 0 | 1797862.07 | 22069.97 | 90 | 80 | 0 | 0 | -10
BEAUMONT | 0920-03-081 | HARDIN | CR | 2025-05-13 | 775736.52 | -48496.83 | 0 | 708168.92 | -67567.6 | 75 | 86 | 0 | 0 | 11
CORPUS CHRISTI | 0102-01-123 | NUECES | SH 44 | 2025-05-13 | 279981.1 | 4789.75 | 0 | 275172.85 | -4808.25 | 40 | 30 | 0 | 0 | -10
CORPUS CHRISTI | 1558-03-110 | NUECES | FM 70 | 2025-05-13 | 980441 | 206088.31 | 0 | 1134807.73 | 154366.73 | 99 | 114 | 24 | 0 | 15
LUFKIN | 2553-01-115 | ANGELINA | US 59 | 2025-05-13 | 19326241.39 | 872998.04 | 0 | 20660064.75 | 1333823.36 | 295 | 623 | 328 | 0 | 328
ATLANTA | 0096-10-028 | HARRISON | US 80 | 2025-05-14 | 3801385.64 | -171725 | 0 | 3712006.86 | -89378.78 | 47 | 53 | 0 | 0 | 6
BROWNWOOD | 0007-04-134 | EASTLAND | SH 112 | 2025-05-14 | 1727088.92 | 173199.09 | 0 | 1956381.3 | 229292.38 | 109 | 108 | 17 | 0 | -1
YOAKUM | 0269-02-068 | LAVACA | US 77 | 2025-05-14 | 2786917.2 | -796.55 | 0 | 2425397.26 | -361519.94 | 105 | 80 | 0 | 0 | -25
AUSTIN | 0914-00-483 | TRAVIS | Various | 2025-05-15 | 662612.5 | 5440 | 0 | 718893.9 | 56281.4 | 81 | 27 | 0 | 0 | -54
HOUSTON | 1685-05-132 | HARRIS | SH 6 | 2025-05-15 | 289671.24 | -58704.65 | 0 | 238486.91 | -51184.33 | 44 | 31 | 0 | 0 | -13
BEAUMONT | 0368-01-093 | CHAMBERS | SH 124 | 2025-05-16 | 4794059.28 | -220476.79 | 0 | 4929893.6 | 135834.32 | 77 | 73 | 0 | 0 | -4
BRYAN | 0049-09-096 | BRAZOS | US 190 | 2025-05-16 | 1888555 | 18751.09 | 0 | 1847457.03 | -41097.97 | 170 | 175 | 0 | 0 | 5
BRYAN | 1400-02-025 | GRIMES | FM 1774 | 2025-05-16 | 6403546.1 | 807198.96 | 0 | 7186766.08 | 783219.98 | 190 | 190 | 0 | 0 | 0
CHILDRESS | 0925-00-095 | CHILDRESS | Various | 2025-05-16 | 1197204.5 | -6524.69 | 0 | 1231509.81 | 34305.31 | 185 | 142 | 0 | 0 | -43
WACO | 0014-10-071 | MCLENNAN | BU 77L | 2025-05-16 | 1121180.8 | 119457.65 | 0 | 1206857.45 | 85676.65 | 30 | 29 | 0 | 0 | -1
AUSTIN | 0265-02-036 | TRAVIS | SH 71 | 2025-05-17 | 60525748.15 | 9204442.41 | 1202465.98 | 72152483.78 | 10424269.65 | 608 | 830 | 223 | 0 | 222
ABILENE | 0908-00-131 | CALLAHAN | Various | 2025-05-19 | 562852.76 | -23485.5 | 0 | 546640.08 | -16212.68 | 144 | 81 | 0 | 0 | -63
CORPUS CHRISTI | 0100-08-105 | BEE | US 181 | 2025-05-19 | 142685 | 120210.6 | 0 | 222501 | 79816 | 51 | 59 | 16 | 0 | 8
FORT WORTH | 0902-50-122 | JOHNSON | Various | 2025-05-19 | 2237555.89 | 81307.42 | 0 | 2515958.31 | 278402.42 | 171 | 323 | 66 | 0 | 152
PARIS | 0136-03-066 | DELTA | SH 24 | 2025-05-19 | 6659254.35 | 326511.97 | 0 | 7930165.43 | 1270911.08 | 69 | 119 | 50 | 0 | 50
WICHITA FALLS | 0814-01-037 | BAYLOR | FM 422 | 2025-05-19 | 2860939.1 | -62996.45 | 0 | 2848108.29 | -12830.81 | 144 | 145 | 0 | 0 | 1
ABILENE | 0693-01-034 | HOWARD | SH 350 | 2025-05-20 | 17873873 | 484525.4 | 0 | 19870794.35 | 1996921.35 | 237 | 209 | 0 | 0 | -28
AMARILLO | 0168-07-050 | DEAF SMITH | US 60 | 2025-05-20 | 23784485.6 | 779637.34 | 0 | 25942988.73 | 2158503.13 | 194 | 252 | 12 | 0 | 58
HOUSTON | 0978-01-039 | GALVESTON | FM 517 | 2025-05-20 | 519798.14 | 42067.87 | 0 | 537199.32 | 17401.18 | 120 | 84 | 0 | 0 | -36
HOUSTON | 1706-02-008 | MONTGOMERY | FM 1791 | 2025-05-20 | 1006888.63 | 105813.75 | 0 | 1138912.94 | 132024.31 | 38 | 27 | 0 | 0 | -11
PHARR | 0921-02-508 | HIDALGO | CS | 2025-05-20 | 192172.57 | 5840.05 | 0 | 188762.83 | -3409.74 | 57 | 51 | 0 | 0 | -6
BRYAN | 0114-10-104 | WASHINGTON | US 290 | 2025-05-21 | 2162426.54 | 1052951.07 | 0 | 3090337.03 | 927910.49 | 80 | 79 | 8 | 0 | -1
TYLER | 0118-04-032 | CHEROKEE | SH 21 | 2025-05-21 | 5923688.84 | 823675.61 | 0 | 7247750.57 | 1324061.73 | 182 | 182 | 0 | 0 | 0
YOAKUM | 0269-06-059 | DEWITT | US 183 | 2025-05-21 | 3564628.12 | 134224.52 | 0 | 3632594.83 | 67966.71 | 135 | 170 | 35 | 0 | 35
AUSTIN | 1234-01-013 | TRAVIS | FM 1100 | 2025-05-22 | 4953190.2 | 126537.36 | 0 | 4979183.46 | 25993.26 | 48 | 42 | 0 | 0 | -6
CORPUS CHRISTI | 0617-01-170 | NUECES | SH 358 | 2025-05-22 | 49960151.47 | 5083368.93 | 87401.6 | 58239189.98 | 8191636.91 | 871 | 1045 | 174 | 0 | 174
PHARR | 1804-01-082 | HIDALGO | SS 115 | 2025-05-22 | 8569908.66 | 0 | 0 | 8948394.85 | 378486.19 | 140 | 139 | 0 | 0 | -1
SAN ANGELO | 0077-09-011 | TOM GREEN | BU 67H | 2025-05-22 | 525028.5 | 0 | 0 | 545819.69 | 20791.19 | 58 | 63 | 0 | 0 | 5
TYLER | 0492-03-040 | WOOD | FM 14 | 2025-05-22 | 2614763.55 | 141004.98 | 0 | 2853199.75 | 238436.2 | 72 | 108 | 39 | 0 | 36
ATLANTA | 0085-02-054 | BOWIE | US 259 | 2025-05-23 | 20975945.57 | 201406.77 | 0 | 21448943.02 | 472997.45 | 276 | 232 | 32 | 0 | -44
HOUSTON | 1402-03-012 | MONTGOMERY | FM 1375 | 2025-05-23 | 2012093.41 | 931081.89 | 0 | 3118513.81 | 1106420.4 | 58 | 58 | 0 | 0 | 0
AMARILLO | 0455-01-048 | HUTCHINSON | SH 152 | 2025-05-27 | 7851871.78 | 184853.66 | 0 | 8627355.05 | 775483.27 | 114 | 117 | 42 | 0 | 3
AUSTIN | 0016-02-167 | HAYS | IH 35 | 2025-05-27 | 5777708.42 | 119547.82 | 0 | 6092173.03 | 314464.61 | 382 | 483 | 0 | 0 | 101
HOUSTON | 3256-04-077 | HARRIS | SL 8 | 2025-05-27 | 494671.7 | 42834.99 | 0 | 672380.15 | 177708.45 | 66 | 47 | 0 | 0 | -19
TYLER | 1669-01-007 | RUSK | FM 348 | 2025-05-27 | 1892089.55 | 32399.68 | 0 | 2044038.19 | 151948.64 | 114 | 116 | 0 | 0 | 2
WACO | 0724-01-056 | CORYELL | FM 116 | 2025-05-27 | 10787639.6 | 99690.07 | 0 | 11011532.36 | 223892.76 | 540 | 577 | 0 | 0 | 37
YOAKUM | 0913-22-016 | GONZALES | CR | 2025-05-27 | 1278588.55 | 18558.75 | 0 | 1304217.12 | 25628.57 | 165 | 158 | 0 | 0 | -7
ABILENE | 0006-02-130 | NOLAN | IH 20 | 2025-05-28 | 6255551.5 | 0 | 0 | 6179388.5 | -76163 | 66 | 66 | 0 | 0 | 0
AUSTIN | 0700-03-145 | TRAVIS | SH 71 | 2025-05-28 | 13908750.59 | 920663.83 | 154373.13 | 16019628.6 | 1956504.88 | 253 | 511 | 273 | 30 | 228
AUSTIN | 2103-01-044 | WILLIAMSON | RM 2243 | 2025-05-28 | 1696964.36 | 0 | 0 | 1817438.93 | 120474.57 | 47 | 55 | 0 | 0 | 8
HOUSTON | 0114-12-012 | HARRIS | US 290 | 2025-05-28 | 3991011.23 | 923906.33 | 0 | 4928936.19 | 937924.96 | 53 | 128 | 3 | 0 | 75
PARIS | 0136-07-051 | LAMAR | US 271 | 2025-05-28 | 13467877.6 | -201130.3 | 0 | 14619342.16 | 1151464.56 | 144 | 161 | 59 | 0 | 17
PHARR | 1803-02-049 | HIDALGO | FM 1925 | 2025-05-28 | 346821.94 | 5725.21 | 0 | 336840.76 | -9981.18 | 143 | 143 | 0 | 0 | 0
TYLER | 0495-05-061 | SMITH | IH 20 | 2025-05-28 | 693237 | 51567.5 | 0 | 768867.59 | 75630.59 | 18 | 21 | 0 | 0 | 3
WACO | 0258-09-142 | MCLENNAN | SH 6 | 2025-05-28 | 54894543.25 | 2621572.5 | 0 | 60330298.15 | 5435754.9 | 570 | 570 | 0 | 0 | 0
LUFKIN | 0911-39-069 | SHELBY | CR | 2025-05-29 | 584994.7 | 0 | 0 | 581238.56 | -3756.14 | 103 | 62 | 0 | 0 | -41
PHARR | 0039-07-256 | CAMERON | IH 69E | 2025-05-29 | 5394454.04 | 170159.47 | 0 | 5207241.05 | -187212.99 | 184 | 412 | 201 | 0 | 228
YOAKUM | 0114-08-036 | FAYETTE | US 290 | 2025-05-29 | 5309909.13 | -576056.18 | 0 | 4714037.21 | -595871.92 | 120 | 60 | 0 | 0 | -60
BRYAN | 0114-09-089 | WASHINGTON | US 290 | 2025-05-30 | 1254827.8 | 22213.43 | 0 | 1263239.16 | 8411.36 | 199 | 241 | 45 | 0 | 42
CORPUS CHRISTI | 1122-01-033 | KARNES | FM 791 | 2025-05-30 | 165558 | 0 | 0 | 158505 | -7053 | 46 | 21 | 0 | 0 | -25
FORT WORTH | 0080-01-056 | ERATH | US 377 | 2025-05-30 | 7391389.42 | 836386.4 | 0 | 8881989.97 | 1490600.55 | 86 | 72 | 0 | 0 | -14
FORT WORTH | 0902-90-141 | TARRANT | VA | 2025-05-30 | 38841809.37 | -5728997.02 | 2107858.52 | 34490303.23 | -6459364.66 | 1014 | 1235 | 424 | 0 | 221
BRYAN | 0117-05-059 | MADISON | SH 21 | 2025-06-02 | 938332.3 | 48827.35 | 0 | 1066702.62 | 128370.32 | 41 | 25 | 0 | 0 | -16
BRYAN | 0213-01-048 | WALKER | US 190 | 2025-06-02 | 1036981.25 | 108231 | 0 | 1125927.68 | 88946.43 | 97 | 90 | 0 | 0 | -7
CHILDRESS | 0449-01-023 | COLLINGSWORTH | FM 338 | 2025-06-02 | 7122576.6 | -39697.98 | 0 | 7622742.84 | 500166.24 | 182 | 166 | 3 | 0 | -16
WICHITA FALLS | 0423-02-025 | MONTAGUE | FM 677 | 2025-06-02 | 2630598.36 | 3812 | 0 | 2689463.38 | 58865.02 | 220 | 163 | 0 | 0 | -57
HOUSTON | 0177-07-118 | HARRIS | IH 69 | 2025-06-03 | 975659.05 | 29499.32 | 0 | 1424839.1 | 449180.05 | 109 | 92 | 0 | 0 | -17
ODESSA | 0003-06-098 | REEVES | IH 20 | 2025-06-03 | 16682423.5 | 488199.25 | 0 | 17886893.26 | 1204469.76 | 336 | 213 | 0 | 0 | -123
SAN ANGELO | 0558-10-042 | CROCKETT | US 190 | 2025-06-03 | 2124528 | 261701.55 | 0 | 2420373.02 | 295845.02 | 152 | 199 | 17 | 0 | 47
TYLER | 0910-16-163 | SMITH | CS | 2025-06-03 | 739937 | -33575 | 0 | 727273.08 | -12663.92 | 64 | 63 | 0 | 0 | -1
AUSTIN | 3277-01-025 | TRAVIS | FM 3177 | 2025-06-04 | 2361951 | 74425.59 | 0 | 2456001.23 | 94050.23 | 104 | 105 | 10 | 0 | 1
BROWNWOOD | 0923-17-091 | COMANCHE | CR | 2025-06-04 | 1187288.1 | 0 | 0 | 1226054.84 | 38766.74 | 136 | 129 | 0 | 0 | -7
HOUSTON | 2941-02-062 | HARRIS | FM 2920 | 2025-06-04 | 3615522.52 | 1532681.12 | 0 | 5153436.45 | 1537913.93 | 209 | 314 | 105 | 0 | 105
TYLER | 0108-03-044 | HENDERSON | SH 19 | 2025-06-04 | 178438.61 | 3003.5 | 0 | 182268.7 | 3830.09 | 15 | 16 | 0 | 0 | 1
YOAKUM | 0846-03-048 | MATAGORDA | FM 521 | 2025-06-04 | 6283882.19 | 14288 | 0 | 6335285.38 | 51403.19 | 205 | 185 | 0 | 0 | -20
BROWNWOOD | 0923-09-066 | EASTLAND | CR | 2025-06-05 | 1317857.3 | 0 | 0 | 1335892.8 | 18035.5 | 233 | 194 | 0 | 0 | -39
BRYAN | 0050-03-114 | GRIMES | SH 6 | 2025-06-05 | 2245311.7 | 0 | 0 | 2268898.54 | 23586.84 | 164 | 164 | 0 | 0 | 0
DALLAS | 0009-04-077 | ROCKWALL | SH 66 | 2025-06-05 | 2188896 | 140531.31 | 0 | 2318457.31 | 129561.31 | 112 | 97 | 0 | 0 | -15
CHILDRESS | 0449-01-024 | COLLINGSWORTH | FM 338 | 2025-06-06 | 4695146.2 | -38080 | 0 | 4912999.57 | 217853.37 | 109 | 112 | 3 | 0 | 3
EL PASO | 0002-02-061 | EL PASO | SH 20 | 2025-06-06 | 1502236.93 | 76047.7 | 0 | 1682340.84 | 180103.91 | 177 | 171 | 4 | 0 | -6
LUFKIN | 0911-00-112 | ANGELINA | VA | 2025-06-06 | 963892.2 | 99529.48 | 0 | 1115746.51 | 151854.31 | 61 | 124 | 56 | 0 | 63
HOUSTON | 0976-03-111 | GALVESTON | FM 518 | 2025-06-09 | 2777975.08 | 151284.91 | 0 | 3019549.73 | 241574.65 | 180 | 201 | 48 | 0 | 21
PARIS | 0045-18-043 | GRAYSON | US 82 | 2025-06-10 | 5645403.84 | -94128.09 | 0 | 6262300.47 | 616896.63 | 79 | 66 | 0 | 0 | -13
PARIS | 2876-01-006 | HUNT | FM 2649 | 2025-06-10 | 6681139.87 | 439099.9 | 0 | 7272660.46 | 591520.59 | 303 | 284 | 16 | 0 | -19
SAN ANTONIO | 0521-05-148 | BEXAR | IH 410 | 2025-06-10 | 22297585.78 | 3239506.52 | 0 | 27359454.89 | 5061869.11 | 540 | 669 | 167 | 0 | 129
FORT WORTH | 1181-03-040 | JOHNSON | FM 917 | 2025-06-11 | 4410629.3 | 27310.08 | 0 | 4374576.52 | -36052.78 | 278 | 414 | 7 | 0 | 136
LUFKIN | 2750-01-005 | ANGELINA | FM 2680 | 2025-06-11 | 2660027.39 | 3009.84 | 0 | 2580936.77 | -79090.62 | 114 | 188 | 16 | 0 | 74
WICHITA FALLS | 0044-04-047 | MONTAGUE | US 82 | 2025-06-11 | 48462414.09 | 1957377.36 | 0 | 51786360.92 | 3323946.83 | 719 | 668 | 0 | 0 | -51
YOAKUM | 0334-08-037 | FAYETTE | FM 154 | 2025-06-11 | 1340282.24 | 32086.25 | 0 | 1441314.9 | 101032.66 | 65 | 49 | 0 | 0 | -16
ATLANTA | 0085-03-017 | BOWIE | FM 2735 | 2025-06-12 | 1493307.9 | 227770.91 | 0 | 1620248.18 | 126940.28 | 285 | 352 | 68 | 0 | 67
AUSTIN | 0914-33-105 | HAYS | Various | 2025-06-12 | 601590 | 182548.93 | 0 | 796777.62 | 195187.62 | 19 | 15 | 0 | 0 | -4
BEAUMONT | 0932-02-052 | JEFFERSON | FM 365 | 2025-06-12 | 1947312.09 | 397138.52 | 0 | 2400605.59 | 453293.5 | 195 | 339 | 0 | 0 | 144
HOUSTON | 0912-72-405 | HARRIS | CS | 2025-06-12 | 745291.25 | 0 | 0 | 737693.47 | -7597.78 | 142 | 160 | 0 | 0 | 18
HOUSTON | 3538-01-035 | MONTGOMERY | SH 242 | 2025-06-12 | 36793630.18 | 2075787.21 | 0 | 38931097.76 | 2137467.58 | 602 | 747 | 164 | 0 | 145
LAREDO | 0018-06-212 | WEBB | IH 35 | 2025-06-12 | 29750032.69 | 960642.97 | 0 | 30765685.77 | 1015653.08 | 315 | 312 | 0 | 0 | -3
LAREDO | 0086-14-101 | WEBB | SS 260 | 2025-06-12 | 916544 | -43447.38 | 0 | 887187.74 | -29356.26 | 120 | 96 | 0 | 0 | -24
WACO | 1219-02-017 | CORYELL | FM 182 | 2025-06-12 | 3507187.52 | 46946.6 | 0 | 3602550.2 | 95362.68 | 270 | 274 | 0 | 0 | 4
AUSTIN | 0015-11-074 | TRAVIS | SL 275 | 2025-06-13 | 3285366.49 | -235958.67 | 0 | 3184853.62 | -100512.87 | 59 | 59 | 0 | 0 | 0
HOUSTON | 0027-10-075 | HARRIS | UA 90 | 2025-06-13 | 12079142.9 | 237413.49 | 0 | 12451387.52 | 372244.62 | 301 | 297 | 0 | 0 | -4
TYLER | 0165-01-107 | SMITH | SH 110 | 2025-06-13 | 6495390 | 0 | 0 | 6308879.62 | -186510.38 | 47 | 79 | 0 | 0 | 32
AUSTIN | 1755-01-021 | WILLIAMSON | RM 1869 | 2025-06-16 | 3853599.28 | 73752.08 | 0 | 4061137.59 | 207538.31 | 176 | 178 | 8 | 0 | 2
BRYAN | 0917-31-034 | MADISON | CR | 2025-06-16 | 669117.6 | 1443.13 | 0 | 676358.99 | 7241.39 | 153 | 153 | 0 | 0 | 0
CORPUS CHRISTI | 0916-00-250 | NUECES | Various | 2025-06-16 | 3123217.4 | 67498.55 | 0 | 3372662.8 | 249445.4 | 277 | 153 | 0 | 0 | -124
YOAKUM | 0346-06-049 | LAVACA | SH 111 | 2025-06-16 | 1589955.1 | 62334.88 | 0 | 1638369.68 | 48414.58 | 120 | 160 | 24 | 0 | 40
AUSTIN | 1378-01-051 | TRAVIS | RM 1431 | 2025-06-17 | 5205668.65 | 587966.24 | 0 | 5848153.72 | 642485.07 | 232 | 236 | 25 | 0 | 4
BEAUMONT | 0508-04-183 | JEFFERSON | SH 73 | 2025-06-17 | 4485762.8 | 0 | 0 | 4202296.84 | -283465.96 | 94 | 86 | 0 | 0 | -8
HOUSTON | 0912-37-240 | MONTGOMERY | CR | 2025-06-17 | 759105.5 | 28354.8 | 0 | 775717.89 | 16612.39 | 82 | 109 | 0 | 0 | 27
SAN ANGELO | 2284-01-032 | TOM GREEN | FM 388 | 2025-06-17 | 355503.25 | 0 | 0 | 393740.12 | 38236.87 | 50 | 41 | 0 | 0 | -9
ODESSA | 0005-14-084 | MIDLAND | IH 20 | 2025-06-18 | 59101873.57 | 17055783.48 | 0 | 76253119.72 | 17151246.15 | 459 | 711 | 253 | 0 | 252
YOAKUM | 0515-03-055 | CALHOUN | FM 1090 | 2025-06-18 | 1007461.9 | 598333.07 | 0 | 1674702.02 | 667240.12 | 30 | 30 | 0 | 0 | 0
PARIS | 0435-01-083 | LAMAR | FM 38 | 2025-06-19 | 3732598.33 | 0 | 0 | 3907672.33 | 175074 | 238 | 159 | 0 | 0 | -79
PARIS | 1690-01-134 | LAMAR | US 82 | 2025-06-19 | 2962393.9 | 31672.74 | 0 | 2999057.61 | 36663.71 | 110 | 120 | 11 | 0 | 10
AUSTIN | 0015-13-417 | TRAVIS | IH 35 | 2025-06-20 | 7604085.43 | -452760.42 | 0 | 7460532.33 | -143553.1 | 81 | 67 | 0 | 0 | -14
SAN ANGELO | 0069-07-111 | TOM GREEN | US 87 | 2025-06-20 | 987486.86 | 28908.94 | 0 | 1011160.07 | 23673.21 | 116 | 96 | 0 | 0 | -20
TYLER | 0910-12-139 | VAN ZANDT | CR | 2025-06-20 | 1393629.5 | 13250 | 0 | 1284743.36 | -108886.14 | 120 | 92 | 0 | 0 | -28
CHILDRESS | 0925-00-081 | CHILDRESS | Various | 2025-06-23 | 1788474.59 | 6800.56 | 0 | 1812791.1 | 24316.51 | 63 | 39 | 0 | 0 | -24
FORT WORTH | 0013-08-140 | WISE | US 81 | 2025-06-23 | 25723015.35 | 201480.63 | 0 | 25767854.92 | 44839.57 | 406 | 434 | 87 | 0 | 28
TYLER | 0522-02-040 | VAN ZANDT | SH 243 | 2025-06-23 | 500565.55 | 29011.72 | 0 | 532377.71 | 31812.16 | 60 | 37 | 0 | 0 | -23
YOAKUM | 0027-04-041 | WHARTON | UA 90 | 2025-06-23 | 2611508.96 | 99533.02 | 0 | 2636363.74 | 24854.78 | 210 | 243 | 33 | 0 | 33
YOAKUM | 0241-03-029 | MATAGORDA | SH 60 | 2025-06-23 | 4538993.47 | 121245.65 | 0 | 4523129.03 | -15864.44 | 195 | 195 | 0 | 0 | 0
YOAKUM | 0913-00-116 | DEWITT | Various | 2025-06-23 | 1439926.58 | -26853.96 | 0 | 1490190.94 | 50264.36 | 60 | 60 | 0 | 0 | 0
AMARILLO | 0455-02-027 | CARSON | SH 152 | 2025-06-24 | 8225269.8 | 131739.75 | 0 | 8288153.48 | 62883.68 | 335 | 618 | 0 | 0 | 283
DALLAS | 0196-01-118 | DENTON | IH 35E | 2025-06-24 | 14210383.8 | -36557.8 | 0 | 14240510.92 | 30127.12 | 184 | 180 | 0 | 0 | -4
HOUSTON | 0111-09-042 | BRAZORIA | BS 288B | 2025-06-24 | 10948342.43 | -166269.35 | 0 | 10341573.82 | -606768.61 | 163 | 165 | 11 | 0 | 2
FORT WORTH | 1094-02-017 | TARRANT | FM 731 | 2025-06-25 | 434716 | 0 | 0 | 408755.74 | -25960.26 | 60 | 60 | 0 | 0 | 0
HOUSTON | 0502-01-232 | HARRIS | IH 610 | 2025-06-25 | 288348.04 | 0 | 0 | 420299.47 | 131951.43 | 17 | 20 | 0 | 0 | 3
HOUSTON | 0976-01-044 | HARRIS | FM 865 | 2025-06-25 | 398115.17 | -3287.63 | 0 | 516400.73 | 118285.56 | 68 | 68 | 0 | 0 | 0
ABILENE | 0264-02-029 | NOLAN | SH 70 | 2025-06-26 | 5657526.63 | 13304.52 | 0 | 5698461.22 | 40934.59 | 106 | 72 | 0 | 0 | -34
DALLAS | 0281-01-040 | COLLIN | SH 78 | 2025-06-26 | 1995099 | 0 | 0 | 2046318.26 | 51219.26 | 154 | 157 | 3 | 0 | 3
EL PASO | 0001-02-067 | EL PASO | SH 20 | 2025-06-26 | 12401685.1 | -428867.06 | 0 | 12586972.59 | 185287.49 | 244 | 162 | 0 | 0 | -82
HOUSTON | 1685-05-137 | HARRIS | SH 6 | 2025-06-26 | 223865 | 9781.06 | 0 | 208266.74 | -15598.26 | 25 | 24 | 0 | 0 | -1
WICHITA FALLS | 0125-01-034 | BAYLOR | US 183 | 2025-06-26 | 7724536.69 | -129354.75 | 0 | 8126988.18 | 402451.49 | 210 | 215 | 0 | 0 | 5
DALLAS | 0009-02-074 | DALLAS | SH 78 | 2025-06-27 | 861720 | 0 | 0 | 855706.02 | -6013.98 | 85 | 63 | 0 | 0 | -22
EL PASO | 0374-02-120 | EL PASO | US 62 | 2025-06-27 | 9875874.6 | 781220.6 | 0 | 10746744.89 | 870870.29 | 270 | 164 | 0 | 0 | -106
FORT WORTH | 0013-07-087 | WISE | US 81 | 2025-06-27 | 2289336.4 | 726604.22 | 0 | 3015425.14 | 726088.74 | 169 | 163 | 0 | 0 | -6
HOUSTON | 0051-02-108 | HARRIS | SH 3 | 2025-06-27 | 5450259.59 | 1330210.57 | 0 | 4631563.06 | -818696.53 | 223 | 481 | 263 | 0 | 258
ODESSA | 0140-02-052 | PECOS | IH 10 | 2025-06-27 | 1622640 | 85713.06 | 0 | 1742388.06 | 119748.06 | 217 | 312 | 95 | 0 | 95
WACO | 3623-01-008 | CORYELL | SH 9 | 2025-06-27 | 1170676.75 | 227270.8 | 0 | 1407381.63 | 236704.88 | 60 | 66 | 5 | 0 | 6
AMARILLO | 2635-03-024 | RANDALL | SL 335 | 2025-06-30 | 25974526.55 | 107770.5 | 0 | 26209776.98 | 235250.43 | 684 | 864 | 40 | 0 | 180
FORT WORTH | 0008-05-031 | TARRANT | SH 180 | 2025-06-30 | 1663320.5 | 64517.88 | 0 | 1708141.9 | 44821.4 | 362 | 357 | 0 | 0 | -5
HOUSTON | 0089-09-058 | FORT BEND | US 59 | 2025-07-01 | 100144090.32 | 3064099.96 | 0 | 102539213.39 | 2395123.07 | 919 | 1120 | 201 | 0 | 201
HOUSTON | 0367-05-050 | GALVESTON | SH 87 | 2025-07-01 | 32943459 | 519234.44 | 0 | 33462693.45 | 519234.45 | 650 | 1330 | 580 | 0 | 680
HOUSTON | 0912-72-749 | HARRIS | Various | 2025-07-01 | 2695934.98 | 354899.19 | 0 | 3303471.67 | 607536.69 | 64 | 100 | 36 | 0 | 36
DALLAS | 0048-04-094 | ELLIS | IH 35E | 2025-07-02 | 45984067.41 | 2162296.63 | 0 | 48478849.18 | 2494781.77 | 548 | 781 | 265 | 0 | 233
YOAKUM | 0269-02-063 | LAVACA | US 77 | 2025-07-02 | 3442520.81 | 75331.82 | 0 | 3532767.96 | 90247.15 | 199 | 282 | 52 | 0 | 83
YOAKUM | 0913-18-036 | JACKSON | CR | 2025-07-02 | 1283044.74 | 18499.58 | 0 | 1308648.92 | 25604.18 | 180 | 169 | 0 | 0 | -11
HOUSTON | 0111-01-096 | HARRIS | FM 521 | 2025-07-03 | 226988.26 | 72254.29 | 0 | 371713.14 | 144724.88 | 31 | 24 | 0 | 0 | -7
PHARR | 0621-01-118 | HIDALGO | SH 336 | 2025-07-03 | 19151 | 0 | 0 | 21917.49 | 2766.49 | 20 | 1 | 0 | 0 | -19
SAN ANGELO | 0907-26-006 | SCHLEICHER | CS | 2025-07-03 | 767531.16 | 16616.76 | 0 | 775674.27 | 8143.11 | 209 | 88 | 0 | 0 | -121
AUSTIN | 0683-03-047 | HAYS | RM 12 | 2025-07-09 | 581998.75 | 65764.92 | 0 | 695076.28 | 113077.53 | 23 | 17 | 0 | 0 | -6
BEAUMONT | 0244-07-009 | JASPER | FM 1747 | 2025-07-09 | 1733589.28 | 1200 | 0 | 1884906.46 | 151317.18 | 123 | 124 | 1 | 0 | 1
DALLAS | 0092-14-108 | DALLAS | IH 45 | 2025-07-09 | 3175651 | 0 | 0 | 3295680.53 | 120029.53 | 262 | 115 | 0 | 0 | -147
DALLAS | 0918-46-345 | DENTON | Various | 2025-07-09 | 1824550.75 | 115138.23 | 0 | 1753158.14 | -71392.61 | 96 | 81 | 0 | 0 | -15
EL PASO | 0924-00-110 | EL PASO | Various | 2025-07-09 | 3850596.14 | 477661.8 | 0 | 4363148.55 | 512552.41 | 98 | 127 | 29 | 0 | 29
HOUSTON | 0976-07-016 | GALVESTON | SH 96 | 2025-07-09 | 7736540.02 | -1731627.14 | 0 | 6617469.42 | -1119070.6 | 211 | 117 | 5 | 0 | -94
HOUSTON | 1685-01-107 | HARRIS | FM 1960 | 2025-07-09 | 1450429.42 | 44460.27 | 0 | 1359118.41 | -91311.01 | 187 | 184 | 0 | 0 | -3
TYLER | 0495-04-076 | SMITH | IH 20 | 2025-07-09 | 6035177.89 | 143275.83 | 0 | 6332407.19 | 297229.3 | 102 | 153 | 0 | 0 | 51
BROWNWOOD | 0054-06-112 | BROWN | US 67 | 2025-07-10 | 5210426.35 | 0 | 0 | 5273789.31 | 63362.96 | 59 | 59 | 0 | 0 | 0
CORPUS CHRISTI | 1095-03-017 | KARNES | FM 743 | 2025-07-11 | 2555558.85 | 97688.07 | 0 | 2750935.16 | 195376.31 | 127 | 97 | 13 | 0 | -30
DALLAS | 0451-03-013 | COLLIN | SH 205 | 2025-07-11 | 31480212.92 | 1220525.08 | 0 | 32352073.4 | 871860.48 | 431 | 529 | 99 | 0 | 98
DALLAS | 3090-01-012 | NAVARRO | FM 3041 | 2025-07-11 | 6473924.21 | 299561.39 | 0 | 6646804.82 | 172880.61 | 247 | 244 | 0 | 0 | -3
FORT WORTH | 0902-90-104 | TARRANT | VA | 2025-07-11 | 1850378.36 | 31727.63 | 0 | 1673366.18 | -177012.18 | 250 | 358 | 108 | 0 | 108
LAREDO | 2150-04-087 | WEBB | FM 1472 | 2025-07-11 | 428776.36 | -26599.35 | 0 | 383015.75 | -45760.61 | 60 | 60 | 0 | 0 | 0
BRYAN | 0315-07-040 | WASHINGTON | SH 105 | 2025-07-14 | 4395394.43 | 662.66 | 0 | 4478968.16 | 83573.73 | 168 | 167 | 0 | 0 | -1
BRYAN | 0917-12-086 | MILAM | CR | 2025-07-14 | 774755.25 | 102024.44 | 0 | 849478.83 | 74723.58 | 121 | 97 | 0 | 0 | -24
BRYAN | 0917-17-076 | GRIMES | CR | 2025-07-14 | 2278373.18 | 121718.83 | 0 | 2746753.76 | 468380.58 | 292 | 188 | 0 | 0 | -104
ODESSA | 2906-01-006 | MIDLAND | RM 1492 | 2025-07-14 | 16251844.27 | 986458.97 | 0 | 18038834.83 | 1786990.56 | 402 | 399 | 20 | 0 | -3
ABILENE | 0005-06-126 | HOWARD | IH 20 | 2025-07-15 | 7152987.39 | 0 | 0 | 7465479.02 | 312491.63 | 108 | 105 | 0 | 0 | -3
AUSTIN | 0204-01-074 | WILLIAMSON | US 79 | 2025-07-15 | 3597980.3 | 0 | 0 | 3485329.99 | -112650.31 | 368 | 167 | 0 | 0 | -201
HOUSTON | 0500-03-629 | HARRIS | IH 45 | 2025-07-15 | 2552371.96 | 133872.78 | 0 | 3414673.46 | 862301.5 | 199 | 199 | 0 | 0 | 0
HOUSTON | 3510-06-026 | HARRIS | SH 99 | 2025-07-15 | 2373433.8 | 45670 | 0 | 2443357.38 | 69923.58 | 195 | 138 | 0 | 0 | -57
WACO | 0418-02-035 | HILL | SH 171 | 2025-07-15 | 8755569.66 | 213001.03 | 0 | 8821103.1 | 65533.44 | 150 | 161 | 12 | 0 | 11
BROWNWOOD | 0054-08-027 | MILLS | US 84 | 2025-07-16 | 11688750.48 | 420287.34 | 0 | 11352933.16 | -335817.32 | 92 | 93 | 13 | 0 | 1
BRYAN | 0186-05-044 | WASHINGTON | BS 36J | 2025-07-16 | 1547419.83 | -58530.17 | 0 | 1456668.34 | -90751.49 | 111 | 101 | 0 | 0 | -10
HOUSTON | 0271-07-324 | HARRIS | IH 10 | 2025-07-16 | 1723423.74 | 33180.96 | 0 | 2033285.27 | 309861.53 | 51 | 48 | 0 | 0 | -3
PARIS | 0190-01-038 | FRANKLIN | SH 37 | 2025-07-16 | 167535.9 | 4100.5 | 0 | 175480.9 | 7945 | 22 | 16 | 0 | 0 | -6
YOAKUM | 0840-02-024 | DEWITT | FM 682 | 2025-07-16 | 2141121.59 | 44508.41 | 0 | 2137261.89 | -3859.7 | 120 | 109 | 0 | 0 | -11
BEAUMONT | 0214-03-034 | NEWTON | SH 63 | 2025-07-17 | 2254911 | 23620.36 | 0 | 2437399.35 | 182488.35 | 199 | 365 | 6 | 0 | 166
BEAUMONT | 0920-00-157 | JEFFERSON | Various | 2025-07-17 | 2547180 | -145860 | 0 | 2394311.7 | -152868.3 | 50 | 27 | 0 | 0 | -23
DALLAS | 0816-05-025 | COLLIN | FM 2862 | 2025-07-17 | 7607273.37 | 466201.28 | 0 | 7510761.53 | -96511.84 | 230 | 200 | 0 | 0 | -30
SAN ANGELO | 0907-00-215 | TOM GREEN | Various | 2025-07-17 | 2217486.98 | 2620 | 0 | 2220185.98 | 2699 | 49 | 46 | 0 | 0 | -3
AUSTIN | 0071-03-043 | MASON | US 87 | 2025-07-18 | 1748508.34 | 0 | 0 | 1855210 | 106701.66 | 48 | 16 | 0 | 0 | -32
DALLAS | 0009-11-241 | DALLAS | IH 30 | 2025-07-18 | 142404495.37 | 740136.82 | 0 | 138105608.6 | -4298886.77 | 938 | 893 | 0 | 0 | -45
DALLAS | 0092-02-141 | DALLAS | IH 45 | 2025-07-18 | 4336407.9 | 636533.68 | 0 | 4972324.42 | 635916.52 | 186 | 237 | 51 | 0 | 51
FORT WORTH | 2465-01-020 | JOHNSON | FM 2280 | 2025-07-18 | 6362225.25 | 143762.16 | 0 | 6350596.82 | -11628.43 | 171 | 199 | 32 | 0 | 28
LAREDO | 0483-01-052 | LA SALLE | SH 97 | 2025-07-18 | 7207235.43 | -47378.39 | 0 | 8125538.74 | 918303.31 | 150 | 108 | 0 | 0 | -42
LUBBOCK | 0130-04-035 | HOCKLEY | SH 114 | 2025-07-18 | 1890330 | -72880.69 | 0 | 1864664.11 | -25665.89 | 165 | 253 | 0 | 0 | 88
PHARR | 0038-07-078 | STARR | US 83 | 2025-07-18 | 7818779.68 | 213309.92 | 0 | 9365613.68 | 1546834 | 132 | 138 | 12 | 0 | 6
SAN ANTONIO | 0915-00-257 | BEXAR | Various | 2025-07-18 | 5176271.91 | 191216.47 | 0 | 5540280.64 | 364008.73 | 191 | 191 | 0 | 0 | 0
AMARILLO | 0041-05-055 | POTTER | US 87 | 2025-07-21 | 2894785.3 | 0 | 0 | 2905385.01 | 10599.71 | 163 | 82 | 0 | 0 | -81
BEAUMONT | 0952-01-062 | LIBERTY | FM 1008 | 2025-07-21 | 2261889.84 | 298604.61 | 0 | 2537564.71 | 275674.87 | 62 | 62 | 0 | 0 | 0
TYLER | 0910-00-133 | SMITH | Various | 2025-07-21 | 548791.16 | 93016.16 | 0 | 628163.16 | 79372 | 105 | 99 | 24 | 0 | -6
WACO | 0909-37-068 | HILL | HCR 2340 | 2025-07-21 | 759759.1 | 0 | 0 | 746724.8 | -13034.3 | 75 | 75 | 0 | 0 | 0
YOAKUM | 0266-01-086 | FAYETTE | SH 71 | 2025-07-21 | 3518108.38 | 351849.01 | 0 | 3923455.83 | 405347.45 | 120 | 218 | 76 | 0 | 98
YOAKUM | 0446-01-053 | LAVACA | UA 90 | 2025-07-21 | 2404305.49 | 0 | 0 | 2396428.03 | -7877.46 | 180 | 197 | 17 | 0 | 17
YOAKUM | 0913-09-070 | WHARTON | CR | 2025-07-21 | 1496610.96 | -27314.26 | 0 | 1549806.5 | 53195.54 | 210 | 191 | 0 | 0 | -19
YOAKUM | 0913-20-089 | AUSTIN | CR | 2025-07-21 | 725918.9 | 0 | 0 | 739253.44 | 13334.54 | 151 | 121 | 0 | 0 | -30
ATLANTA | 0462-03-048 | PANOLA | SH 315 | 2025-07-22 | 5970136.32 | 1398412.1 | 0 | 7520128.52 | 1549992.2 | 199 | 242 | 0 | 0 | 43
CHILDRESS | 0132-01-055 | DICKENS | US 82 | 2025-07-22 | 11319017.73 | -119023.5 | 0 | 11263307.04 | -55710.69 | 99 | 101 | 0 | 0 | 2
CORPUS CHRISTI | 1123-02-016 | KARNES | FM 81 | 2025-07-22 | 8531763.88 | 691850.25 | 0 | 9328216.91 | 796453.03 | 415 | 441 | 32 | 0 | 26
BROWNWOOD | 0923-09-069 | EASTLAND | VA | 2025-07-23 | 709237.96 | 74715.48 | 0 | 841125.7 | 131887.74 | 77 | 181 | 64 | 0 | 104
BRYAN | 0185-06-012 | MILAM | FM 845 | 2025-07-23 | 3982426.27 | 205913.3 | 0 | 3829081.88 | -153344.39 | 165 | 151 | 0 | 0 | -14
BRYAN | 0382-05-020 | LEON | SH 7 | 2025-07-23 | 658885 | 146435.47 | 0 | 789283.36 | 130398.36 | 168 | 62 | 0 | 0 | -106
HOUSTON | 0192-02-059 | BRAZORIA | SH 6 | 2025-07-23 | 5272928.8 | 3982005.52 | 0 | 9631682.9 | 4358754.1 | 118 | 430 | 221 | 0 | 312
HOUSTON | 0912-00-698 | HARRIS | Various | 2025-07-23 | 3246728 | 0 | 0 | 3257828 | 11100 | 126 | 123 | 0 | 0 | -3
AUSTIN | 0152-01-089 | TRAVIS | US 183 | 2025-07-24 | 855115.15 | 35023.76 | 0 | 854677.92 | -437.23 | 39 | 39 | 0 | 0 | 0
BEAUMONT | 0920-00-170 | JEFFERSON | Various | 2025-07-24 | 181194 | 0 | 0 | 165560.9 | -15633.1 | 9 | 9 | 0 | 0 | 0
CORPUS CHRISTI | 0373-02-097 | NUECES | SH 44 | 2025-07-24 | 4274964.92 | -48829.94 | 0 | 4120506.24 | -154458.68 | 24 | 34 | 0 | 0 | 10
PARIS | 0901-22-122 | HUNT | CS | 2025-07-24 | 1080968.31 | 48199 | 0 | 1034099.42 | -46868.89 | 207 | 125 | 0 | 0 | -82
SAN ANTONIO | 3212-04-009 | KENDALL | FM 3351 | 2025-07-24 | 6260528.55 | 101447.28 | 0 | 6382550.1 | 122021.55 | 213 | 187 | 0 | 0 | -26
BEAUMONT | 0200-15-026 | JEFFERSON | US 69 | 2025-07-25 | 7063405.84 | -673103.66 | 0 | 6270632.99 | -792772.85 | 104 | 130 | 41 | 0 | 26
BROWNWOOD | 0274-01-038 | MILLS | US 183 | 2025-07-25 | 996130 | 66708.46 | 0 | 1052658.64 | 56528.64 | 65 | 80 | 0 | 0 | 15
CORPUS CHRISTI | 0916-00-242 | NUECES | Various | 2025-07-25 | 916587.74 | 26529.78 | 0 | 949235.95 | 32648.21 | 80 | 61 | 3 | 0 | -19
HOUSTON | 0271-17-176 | HARRIS | IH 610 | 2025-07-25 | 3121846.99 | 145722.88 | 0 | 3190194.77 | 68347.78 | 272 | 262 | 0 | 0 | -10
HOUSTON | 0720-03-147 | HARRIS | SH 249 | 2025-07-25 | 464642.33 | 9400 | 0 | 602987.69 | 138345.36 | 68 | 88 | 0 | 0 | 20
YOAKUM | 0143-09-070 | DEWITT | US 87 | 2025-07-25 | 99937.48 | 0 | 0 | 92239.73 | -7697.75 | 50 | 341 | 0 | 0 | 291
YOAKUM | 1132-01-035 | VICTORIA | FM 1686 | 2025-07-25 | 2595422.1 | -75601.19 | 0 | 2529850.21 | -65571.89 | 174 | 213 | 24 | 0 | 39
AMARILLO | 0904-00-207 | POTTER | Various | 2025-07-28 | 3292241.77 | 212850 | 0 | 3359404.43 | 67162.66 | 93 | 113 | 0 | 0 | 20
DALLAS | 0918-00-365 | DALLAS | Various | 2025-07-28 | 446143.32 | 0 | 0 | 462977.32 | 16834 | 50 | 48 | 0 | 0 | -2
FORT WORTH | 0259-03-061 | SOMERVELL | US 67 | 2025-07-28 | 636773.13 | -35786.9 | 0 | 560630.13 | -76143 | 86 | 88 | 0 | 0 | 2
WICHITA FALLS | 0044-01-110 | WICHITA | US 82 | 2025-07-28 | 11122261.59 | 0 | 0 | 10756883.7 | -365377.89 | 68 | 68 | 0 | 0 | 0
PHARR | 0331-04-069 | CAMERON | PR 100 | 2025-07-29 | 9814198 | 4682703.35 | 0 | 14296494.27 | 4482296.27 | 576 | 701 | 170 | 0 | 125
PHARR | 0818-01-020 | BROOKS | FM 755 | 2025-07-29 | 5005655.5 | 134853.85 | 0 | 5258176.17 | 252520.67 | 100 | 83 | 0 | 0 | -17
SAN ANTONIO | 0215-09-035 | GUADALUPE | FM 725 | 2025-07-29 | 10378165.6 | 812592.2 | 0 | 11342105.42 | 963939.82 | 395 | 481 | 86 | 0 | 86
CORPUS CHRISTI | 0074-04-047 | SAN PATRICIO | IH 37 | 2025-07-30 | 6031422.07 | -10315.75 | 0 | 5972429.35 | -58992.72 | 153 | 153 | 0 | 0 | 0
CORPUS CHRISTI | 0101-03-123 | SAN PATRICIO | US 181 | 2025-07-30 | 2721211 | 27725.79 | 0 | 2791429.01 | 70218.01 | 102 | 53 | 0 | 0 | -49
DALLAS | 0048-01-069 | DALLAS | SH 342 | 2025-07-30 | 7856752.26 | 404094.76 | 0 | 8366248.05 | 509495.79 | 236 | 202 | 3 | 0 | -34
FORT WORTH | 0258-02-059 | ERATH | SH 6 | 2025-07-30 | 30387611.21 | 5676728.98 | 5196.47 | 37501110.44 | 7108302.76 | 529 | 815 | 314 | 0 | 286
PARIS | 1709-02-021 | FANNIN | FM 1753 | 2025-07-30 | 2948142.08 | 0 | 0 | 2872589.46 | -75552.62 | 69 | 80 | 0 | 0 | 11
SAN ANTONIO | 0915-00-224 | BEXAR | VA | 2025-07-30 | 2764874.71 | 15922.82 | 0 | 2649505.63 | -115369.08 | 199 | 232 | 21 | 0 | 33
ATLANTA | 0495-09-056 | HARRISON | IH 20 | 2025-07-31 | 11887790.53 | 456360.31 | 0 | 12711451.5 | 823660.97 | 440 | 582 | 144 | 0 | 142
CORPUS CHRISTI | 0088-03-048 | GOLIAD | US 59 | 2025-07-31 | 10014542.27 | 304533.95 | 0 | 10966239.84 | 951697.57 | 76 | 157 | 87 | 0 | 81
FORT WORTH | 1181-03-041 | JOHNSON | FM 917 | 2025-07-31 | 90220 | 61430.52 | 0 | 150750.52 | 60530.52 | 40 | 9 | 0 | 0 | -31
ATLANTA | 3041-03-012 | HARRISON | FM 3001 | 2025-08-01 | 4618853.24 | -28807.8 | 0 | 4440168.95 | -178684.29 | 343 | 376 | 0 | 0 | 33
BROWNWOOD | 2013-02-014 | BROWN | FM 2125 | 2025-08-01 | 2672280.79 | 125365.85 | 0 | 2722526.73 | 50245.94 | 185 | 213 | 10 | 0 | 28
ODESSA | 0906-00-238 | ECTOR | Various | 2025-08-01 | 3391078.24 | 1372547.1 | 0 | 4532729.48 | 1141651.24 | 69 | 106 | 118 | 0 | 37
EL PASO | 0924-08-007 | CULBERSON | Various | 2025-08-04 | 752598 | 0 | 0 | 742748 | -9850 | 80 | 52 | 0 | 0 | -28
LUFKIN | 2662-03-003 | ANGELINA | FM 3124 | 2025-08-04 | 3926436.54 | 15829.77 | 0 | 3715109.61 | -211326.93 | 120 | 100 | 0 | 0 | -20
YOAKUM | 0027-03-071 | COLORADO | US 90A | 2025-08-04 | 4487326.99 | 34462.1 | 0 | 4882502.49 | 395175.5 | 160 | 159 | 0 | 0 | -1
YOAKUM | 0143-08-100 | DEWITT | US 87 | 2025-08-04 | 1282152.27 | 138170 | 0 | 1395502.87 | 113350.6 | 60 | 97 | 0 | 0 | 37
YOAKUM | 0179-04-097 | MATAGORDA | SH 35 | 2025-08-04 | 5092449.92 | 62303.58 | 0 | 5419985.25 | 327535.33 | 144 | 188 | 31 | 0 | 44
YOAKUM | 0187-03-064 | AUSTIN | SH 36 | 2025-08-04 | 10535006.21 | 281325.72 | 0 | 11087241.58 | 552235.37 | 339 | 456 | 92 | 0 | 117
BRYAN | 0049-09-087 | BRAZOS | BS 6-R | 2025-08-05 | 4137992.91 | 53916.23 | 26312 | 4353260.65 | 188955.74 | 151 | 230 | 0 | 0 | 79
BRYAN | 0552-02-027 | MADISON | FM 978 | 2025-08-05 | 2875306.35 | 18269.99 | 0 | 2897573.86 | 22267.51 | 187 | 187 | 0 | 0 | 0
BRYAN | 3282-01-008 | LEON | FM 745 | 2025-08-05 | 783652 | 53166.3 | 0 | 766754.02 | -16897.98 | 50 | 48 | 0 | 0 | -2
WICHITA FALLS | 0570-03-019 | YOUNG | FM 701 | 2025-08-05 | 7845445 | 45150 | 0 | 8040142.41 | 194697.41 | 336 | 303 | 0 | 0 | -33
HOUSTON | 0912-72-771 | HARRIS | Various | 2025-08-06 | 2164229.93 | 0 | 0 | 2270145.11 | 105915.18 | 153 | 100 | 0 | 0 | -53
PHARR | 0921-06-269 | CAMERON | Various | 2025-08-06 | 1429710.5 | 276864.37 | 0 | 1567887.8 | 138177.3 | 56 | 25 | 15 | 0 | -31
SAN ANTONIO | 0253-04-138 | BEXAR | US 281 | 2025-08-07 | 178383491.81 | 11213095.31 | 226130.02 | 193268885.04 | 14659263.21 | 1286 | 1302 | 16 | 0 | 16
SAN ANTONIO | 0848-04-049 | MEDINA | FM 462 | 2025-08-07 | 3176381.38 | -101000 | 0 | 3106659.98 | -69721.4 | 404 | 401 | 0 | 0 | -3
SAN ANTONIO | 0915-12-532 | BEXAR | CS | 2025-08-07 | 1567047.86 | 63912.62 | 0 | 1595165.57 | 28117.71 | 108 | 160 | 0 | 0 | 52
TYLER | 0108-12-018 | VAN ZANDT | SH 19 | 2025-08-07 | 8769308.82 | 867401.16 | 0 | 9924894.04 | 1155585.22 | 225 | 314 | 89 | 0 | 89
TYLER | 0165-02-065 | SMITH | US 271 | 2025-08-07 | 12377401.21 | -532176.74 | 0 | 11831883.94 | -545517.27 | 323 | 467 | 0 | 0 | 144
WICHITA FALLS | 0044-07-074 | COOKE | US 82 | 2025-08-07 | 53300 | 34184.5 | 0 | 88218.16 | 34918.16 | 91 | 19 | 0 | 0 | -72
ABILENE | 0006-10-011 | TAYLOR | FM 18 | 2025-08-08 | 4570547 | 0 | 0 | 4722699.83 | 152152.83 | 110 | 103 | 0 | 0 | -7
BEAUMONT | 0200-11-095 | JEFFERSON | US 69 | 2025-08-08 | 31528539.2 | 1751118.92 | 0 | 35876887.59 | 4348348.39 | 652 | 1130 | 478 | 0 | 478
BEAUMONT | 0213-06-041 | TYLER | US 190 | 2025-08-08 | 9062104.57 | -7327.89 | 0 | 8942443.41 | -119661.16 | 173 | 142 | 0 | 0 | -31
BRYAN | 0049-09-095 | BRAZOS | US 190 | 2025-08-08 | 24509977.03 | 428070.05 | 0 | 22450771.22 | -2059205.81 | 135 | 101 | 0 | 0 | -34
BRYAN | 0917-00-072 | BRAZOS | Various | 2025-08-08 | 326409 | -31138.81 | 0 | 300857.36 | -25551.64 | 51 | 53 | 0 | 0 | 2
CHILDRESS | 0275-12-085 | WHEELER | IH 40 | 2025-08-08 | 3449940.4 | -65400 | 0 | 3873869.49 | 423929.09 | 193 | 121 | 0 | 0 | -72
EL PASO | 0358-02-031 | BREWSTER | SH 118 | 2025-08-08 | 7843264.32 | -106854.32 | 0 | 7897740.89 | 54476.57 | 89 | 80 | 15 | 0 | -9
HOUSTON | 0912-31-307 | BRAZORIA | CR | 2025-08-08 | 3440532.59 | 184767.66 | 0 | 3545645.82 | 105113.23 | 219 | 278 | 168 | 0 | 59
BEAUMONT | 0920-00-132 | JEFFERSON | VA | 2025-08-11 | 1085377.86 | 3717.34 | 0 | 1113860.69 | 28482.83 | 85 | 80 | 0 | 0 | -5
HOUSTON | 0111-08-124 | BRAZORIA | SH 288 | 2025-08-11 | 2068826.46 | 2365765.5 | 0 | 4451110.25 | 2382283.79 | 51 | 175 | 134 | 0 | 124
TYLER | 0646-05-027 | HENDERSON | SH 198 | 2025-08-11 | 30355868.31 | 1605034.21 | 0 | 32253403.02 | 1897534.71 | 738 | 838 | 130 | 0 | 100
YOAKUM | 0266-05-048 | WHARTON | SH 71 | 2025-08-11 | 9682167.5 | 133280.8 | 0 | 9949860.14 | 267692.64 | 316 | 328 | 12 | 0 | 12
ATLANTA | 0062-07-103 | HARRISON | US 59 | 2025-08-12 | 1254209.2 | 0 | 0 | 1243208.98 | -11000.22 | 170 | 126 | 0 | 0 | -44
FORT WORTH | 0385-04-053 | HOOD | SH 144 | 2025-08-12 | 941155.73 | 0 | 0 | 835388.38 | -105767.35 | 85 | 49 | 0 | 0 | -36
WACO | 0909-00-066 | MCLENNAN | Various | 2025-08-12 | 830318.16 | 18900.64 | 0 | 798365.85 | -31952.31 | 75 | 35 | 0 | 0 | -40
HOUSTON | 0027-13-255 | HARRIS | IH 69 | 2025-08-13 | 670070 | -30668.07 | 0 | 634828.79 | -35241.21 | 99 | 151 | 4 | 0 | 52
HOUSTON | 0050-05-067 | WALLER | BU 290H | 2025-08-13 | 5433536.7 | 333668.37 | 0 | 6244928.87 | 811392.17 | 135 | 155 | 20 | 0 | 20
HOUSTON | 0114-11-094 | WALLER | US 290 | 2025-08-13 | 1970595 | 0 | 0 | 1976924.04 | 6329.04 | 189 | 38 | 0 | 0 | -151
SAN ANTONIO | 0465-01-063 | BEXAR | SH 218 | 2025-08-13 | 430569 | 2777.96 | 0 | 769963.76 | 339394.76 | 131 | 127 | 0 | 0 | -4
SAN ANTONIO | 0915-12-690 | BEXAR | CS | 2025-08-13 | 141123.05 | 0 | 0 | 144359.75 | 3236.7 | 24 | 16 | 0 | 0 | -8
WACO | 0209-01-070 | MCLENNAN | SL 2 | 2025-08-13 | 1279088.35 | 169928.28 | 0 | 1521964.11 | 242875.76 | 135 | 94 | 0 | 0 | -41
AMARILLO | 0168-05-043 | DEAF SMITH | US 60 | 2025-08-14 | 1956451.45 | 53014.4 | 0 | 2070287.68 | 113836.23 | 80 | 149 | 28 | 0 | 69
AMARILLO | 0904-00-209 | POTTER | Various | 2025-08-14 | 652371.94 | 0 | 0 | 616530.02 | -35841.92 | 67 | 27 | 0 | 0 | -40
AMARILLO | 1339-02-028 | LIPSCOMB | FM 1454 | 2025-08-14 | 10425012.35 | 72000 | 0 | 10559008.03 | 133995.68 | 315 | 315 | 2 | 0 | 0
BRYAN | 0110-01-049 | WALKER | SH 75 | 2025-08-14 | 946421.73 | 420628.33 | 0 | 1403318.92 | 456897.19 | 47 | 100 | 53 | 0 | 53
HOUSTON | 0051-03-119 | GALVESTON | SH 3 | 2025-08-14 | 1131153.8 | 114209.18 | 0 | 1212581.5 | 81427.7 | 357 | 290 | 0 | 0 | -67
HOUSTON | 1258-04-065 | HARRIS | FM 1093 | 2025-08-14 | 12691072.79 | -648129.67 | -648129.67 | 11989569.63 | -53373.49 | 850 | 838 | 0 | 0 | -12
PARIS | 2538-01-017 | HOPKINS | FM 2653 | 2025-08-14 | 995852.82 | 662106.25 | 0 | 1719147.13 | 723294.31 | 77 | 36 | 0 | 0 | -41
SAN ANTONIO | 0915-00-253 | BEXAR | Various | 2025-08-14 | 1505725.72 | 250964.03 | 0 | 1641758.26 | 136032.54 | 260 | 124 | 0 | 0 | -136
SAN ANTONIO | 0915-00-263 | BEXAR | Various | 2025-08-14 | 3699237.02 | 0 | 0 | 3533790.81 | -165446.21 | 154 | 74 | 0 | 0 | -80
WICHITA FALLS | 0802-02-078 | WICHITA | FM 369 | 2025-08-14 | 2148058.09 | -218826.63 | 0 | 2085123.05 | -62935.04 | 45 | 44 | 0 | 0 | -1
ATLANTA | 0218-02-055 | BOWIE | IH 369 | 2025-08-15 | 10246641.1 | -749124.49 | 0 | 9568683.66 | -677957.44 | 98 | 90 | 0 | 0 | -8
BEAUMONT | 0065-06-070 | HARDIN | US 69 | 2025-08-15 | 12495080.67 | -980579.76 | 0 | 11834751.66 | -660329.01 | 131 | 181 | 50 | 0 | 50
CORPUS CHRISTI | 0155-04-060 | GOLIAD | US 183 | 2025-08-15 | 91960.19 | 1718.8 | 0 | 93233.69 | 1273.5 | 32 | 12 | 0 | 0 | -20
DALLAS | 0092-13-033 | NAVARRO | BI 45F | 2025-08-15 | 4119672.99 | 73653.74 | 0 | 4180292.18 | 60619.19 | 106 | 90 | 0 | 0 | -16
FORT WORTH | 1853-01-046 | JOHNSON | FM 1434 | 2025-08-15 | 20892293.03 | 911456.99 | 0 | 20958663.56 | 66370.53 | 790 | 943 | 65 | 0 | 153
HOUSTON | 2523-01-026 | GALVESTON | FM 2004 | 2025-08-15 | 7147856.63 | 200155.24 | 0 | 8003197.67 | 855341.04 | 201 | 201 | 0 | 0 | 0
HOUSTON | 2524-02-022 | BRAZORIA | FM 2611 | 2025-08-15 | 12141991.68 | 793460.88 | 0 | 12748871.08 | 606879.4 | 350 | 447 | 98 | 0 | 97
SAN ANTONIO | 0016-08-043 | BEXAR | SL 368 | 2025-08-15 | 1884493.2 | 247693.19 | 0 | 2289151.14 | 404657.94 | 312 | 249 | 0 | 0 | -63
AUSTIN | 1149-01-031 | TRAVIS | FM 812 | 2025-08-17 | 457971.56 | 2012.43 | 0 | 450356.91 | -7614.65 | 73 | 70 | 0 | 0 | -3
BEAUMONT | 0065-07-062 | JEFFERSON | US 69 | 2025-08-19 | 21735071.85 | 3223715.83 | 0 | 25280852.99 | 3545781.14 | 412 | 642 | 241 | 0 | 230
BEAUMONT | 0200-14-099 | JEFFERSON | US 69 | 2025-08-19 | 12100656.82 | -172317.72 | 0 | 12106300.32 | 5643.5 | 267 | 354 | 87 | 0 | 87
DALLAS | 0619-03-061 | COLLIN | FM 544 | 2025-08-19 | 4570584.95 | 88798.16 | 0 | 4188250.39 | -382334.56 | 275 | 497 | 30 | 0 | 222
HOUSTON | 0500-03-107 | HARRIS | IH 45 | 2025-08-19 | 99783476.69 | 6492041.06 | 0 | 105755802.05 | 5972325.36 | 1427 | 1763 | 377 | 0 | 336
SAN ANGELO | 0474-01-005 | KIMBLE | PR 73 | 2025-08-19 | 2649387.4 | 85314.72 | 0 | 2701207.73 | 51820.33 | 150 | 337 | 0 | 0 | 187
SAN ANTONIO | 0915-12-698 | BEXAR | CS | 2025-08-19 | 1086718.34 | 4545 | 0 | 1150235.39 | 63517.05 | 129 | 92 | 0 | 0 | -37
ATLANTA | 1574-01-018 | MORRIS | FM 161 | 2025-08-20 | 3791092.27 | 220400.8 | 0 | 4002366.46 | 211274.19 | 193 | 187 | 12 | 0 | -6
CORPUS CHRISTI | 0916-28-071 | SAN PATRICIO | PR 25A | 2025-08-20 | 2440688.7 | -4446.4 | 0 | 2428143.69 | -12545.01 | 78 | 104 | 26 | 0 | 26
EL PASO | 0358-01-027 | JEFF DAVIS | SH 118 | 2025-08-20 | 4735264.7 | 1038993.74 | 0 | 5816961.1 | 1081696.4 | 54 | 79 | 35 | 0 | 25
AUSTIN | 0914-00-487 | TRAVIS | Various | 2025-08-21 | 520603.49 | -32852.52 | 0 | 472441.08 | -48162.41 | 41 | 28 | 0 | 0 | -13
BROWNWOOD | 0007-03-097 | EASTLAND | IH 20 | 2025-08-21 | 4992729.72 | 583970.45 | 0 | 5819116.08 | 826386.36 | 338 | 477 | 74 | 0 | 139
CORPUS CHRISTI | 0507-01-023 | SAN PATRICIO | SH 234 | 2025-08-21 | 3026453.85 | 363092.89 | 0 | 3458783.36 | 432329.51 | 130 | 152 | 30 | 0 | 22
TYLER | 0910-16-182 | SMITH | Various | 2025-08-21 | 232606.44 | 0 | 0 | 213982.84 | -18623.6 | 33 | 20 | 0 | 0 | -13
AUSTIN | 1533-01-022 | BASTROP | FM 1704 | 2025-08-22 | 2843419.14 | 359805.22 | 0 | 3525932.66 | 682513.52 | 58 | 28 | 0 | 0 | -30
BEAUMONT | 0787-02-022 | LIBERTY | FM 160 | 2025-08-22 | 3983905.56 | -4639.6 | 0 | 4019973.62 | 36068.06 | 150 | 93 | 0 | 0 | -57
BEAUMONT | 2562-01-023 | ORANGE | FM 1442 | 2025-08-22 | 7694479.73 | 534533.18 | 0 | 8468348.64 | 773868.91 | 165 | 476 | 14 | 0 | 311
BRYAN | 0540-02-027 | ROBERTSON | FM 46 | 2025-08-22 | 1750129.9 | 13194.36 | 0 | 1727371.47 | -22758.43 | 112 | 125 | 1 | 0 | 13
HOUSTON | 1413-01-019 | BRAZORIA | FM 1459 | 2025-08-22 | 134455 | -6450 | 0 | 129205 | -5250 | 51 | 7 | 0 | 0 | -44
SAN ANTONIO | 0253-04-158 | BEXAR | US 281 | 2025-08-22 | 2343347.79 | 534801.07 | 0 | 3418407.33 | 1075059.54 | 338 | 647 | 216 | 0 | 309
BROWNWOOD | 0257-03-033 | EASTLAND | SH 6 | 2025-08-25 | 10087854.94 | 745520.84 | 0 | 11781686.96 | 1693832.02 | 223 | 335 | 112 | 0 | 112
LUFKIN | 0911-00-085 | ANGELINA | Various | 2025-08-25 | 3846146.06 | 0 | 0 | 3747584.4 | -98561.66 | 134 | 49 | 0 | 0 | -85
PARIS | 0901-29-092 | LAMAR | CR | 2025-08-25 | 1489927.72 | 81295 | 0 | 1526985.13 | 37057.41 | 115 | 143 | 0 | 0 | 28
PHARR | 0039-02-040 | HIDALGO | US 83 | 2025-08-25 | 87222198.04 | 15198747.39 | 0 | 101371065.11 | 14148867.07 | 805 | 1502 | 427 | 0 | 697
WACO | 0909-22-197 | MCLENNAN | CS | 2025-08-25 | 674737.27 | 71549.32 | 0 | 746054.19 | 71316.92 | 90 | 89 | 0 | 0 | -1
WICHITA FALLS | 0044-11-004 | WICHITA | BU 287J | 2025-08-25 | 2555716.29 | -75666.67 | 0 | 2388384.85 | -167331.44 | 80 | 41 | 0 | 0 | -39
YOAKUM | 0266-01-083 | FAYETTE | SH 71 | 2025-08-25 | 15790738.51 | -147640.55 | 0 | 16249267.11 | 458528.6 | 195 | 164 | 0 | 0 | -31
YOAKUM | 0271-02-055 | AUSTIN | IH 10 | 2025-08-25 | 279088658.56 | 3054160.41 | 0 | 290775032.95 | 11686374.39 | 1160 | 1149 | 0 | 0 | -11
AUSTIN | 0114-07-087 | LEE | US 290 | 2025-08-26 | 2209194.34 | 0 | 0 | 1894417.09 | -314777.25 | 32 | 22 | 0 | 0 | -10
BRYAN | 0049-12-150 | BRAZOS | US 190 | 2025-08-26 | 1348041 | 36774.51 | 0 | 1415593.73 | 67552.73 | 44 | 28 | 0 | 0 | -16
BRYAN | 0506-01-123 | BRAZOS | FM 60 | 2025-08-26 | 1014086.7 | 15748.62 | 0 | 984090.67 | -29996.03 | 58 | 75 | 16 | 0 | 17
CORPUS CHRISTI | 0916-28-072 | SAN PATRICIO | CR | 2025-08-26 | 805423.65 | -6693.5 | 0 | 770925.45 | -34498.2 | 109 | 118 | 0 | 0 | 9
HOUSTON | 0271-16-168 | HARRIS | IH 610 | 2025-08-26 | 1546772.65 | 583791.14 | 0 | 1782494.41 | 235721.76 | 32 | 19 | 0 | 0 | -13
HOUSTON | 0389-13-065 | HARRIS | SH 146 | 2025-08-26 | 294412.42 | 0 | 0 | 288877.39 | -5535.03 | 68 | 71 | 0 | 0 | 3
HOUSTON | 0502-01-235 | HARRIS | SH 225 | 2025-08-26 | 1262658.44 | 0 | 0 | 1150405.37 | -112253.07 | 133 | 131 | 0 | 0 | -2
LAREDO | 0922-11-043 | VAL VERDE | PW | 2025-08-26 | 3978828.43 | 518645.42 | 0 | 4582236.67 | 603408.24 | 123 | 586 | 0 | 0 | 463
LUFKIN | 0109-03-041 | HOUSTON | US 287 | 2025-08-26 | 388546.19 | 0 | 0 | 390862.93 | 2316.74 | 81 | 47 | 0 | 0 | -34
PARIS | 0173-07-063 | HUNT | SH 34 | 2025-08-26 | 5815035.1 | 0 | 0 | 6174369.64 | 359334.54 | 68 | 68 | 0 | 0 | 0
WACO | 0413-01-033 | MCLENNAN | SH 164 | 2025-08-26 | 1443570.16 | -34485.18 | 0 | 1464614.76 | 21044.6 | 90 | 81 | 3 | 0 | -9
CHILDRESS | 0925-00-093 | CHILDRESS | Various | 2025-08-27 | 1520757.5 | 426500.11 | 0 | 2010659.17 | 489901.67 | 85 | 139 | 54 | 0 | 54
ABILENE | 0068-08-070 | HOWARD | US 87 | 2025-08-28 | 7656688.52 | -373619.04 | 0 | 8481299.93 | 824611.41 | 110 | 51 | 0 | 0 | -59
BEAUMONT | 0920-00-155 | JEFFERSON | Various | 2025-08-28 | 688995 | 36300 | 0 | 729487.43 | 40492.43 | 79 | 70 | 0 | 0 | -9
BROWNWOOD | 1028-01-030 | MILLS | FM 574 | 2025-08-28 | 3930712.13 | 155897.36 | 0 | 4227942.1 | 297229.97 | 238 | 254 | 14 | 0 | 16
FORT WORTH | 0774-01-019 | ERATH | FM 219 | 2025-08-28 | 8247728.35 | 3401236.93 | 0 | 11095586.38 | 2847858.03 | 384 | 307 | 34 | 0 | -77
PARIS | 0901-30-018 | RAINS | CR | 2025-08-28 | 424043 | 32772.5 | 0 | 452015.5 | 27972.5 | 56 | 56 | 0 | 0 | 0
PARIS | 0901-32-103 | FANNIN | CR | 2025-08-28 | 2295795.01 | 0 | 0 | 2311700.01 | 15905 | 310 | 176 | 0 | 0 | -134
TYLER | 0206-06-032 | RUSK | US 79 | 2025-08-28 | 4925092.76 | 0 | 0 | 4666568.49 | -258524.27 | 64 | 83 | 0 | 0 | 19
TYLER | 0910-16-168 | SMITH | Various | 2025-08-28 | 921722.85 | 103297.4 | 0 | 993981.59 | 72258.74 | 123 | 123 | 0 | 0 | 0
WACO | 0596-01-019 | HILL | FM 66 | 2025-08-28 | 2469349.43 | 2233.41 | 0 | 2446792.29 | -22557.14 | 150 | 149 | 0 | 0 | -1
YOAKUM | 0089-07-159 | WHARTON | US 59 | 2025-08-28 | 8528160.86 | -232546.6 | 0 | 8615397.53 | 87236.67 | 90 | 146 | 1 | 0 | 56
YOAKUM | 0179-04-099 | MATAGORDA | SH 35 | 2025-08-28 | 7279318.62 | 7491.52 | 0 | 7713722.62 | 434404 | 150 | 146 | 0 | 0 | -4
YOAKUM | 0267-02-042 | FAYETTE | SH 159 | 2025-08-28 | 495755.72 | 0 | 0 | 478309.2 | -17446.52 | 30 | 28 | 0 | 0 | -2
YOAKUM | 0269-03-036 | LAVACA | UA 77 | 2025-08-28 | 3098286.49 | 1274064.7 | 0 | 4320592.87 | 1222306.38 | 209 | 259 | 50 | 0 | 50
YOAKUM | 1133-02-032 | GONZALES | FM 794 | 2025-08-28 | 5212300.97 | 25312.81 | 0 | 5215640.8 | 3339.83 | 180 | 239 | 59 | 0 | 59
AUSTIN | 0114-02-113 | TRAVIS | US 290 | 2025-08-29 | 1219420.6 | 31458.99 | 0 | 1369209.79 | 149789.19 | 55 | 50 | 0 | 0 | -5
BROWNWOOD | 0288-01-039 | COMANCHE | SH 16 | 2025-08-29 | 1555599.3 | 2424024.16 | 0 | 4429528.78 | 2873929.48 | 204 | 496 | 374 | 0 | 292
DALLAS | 0816-02-083 | DENTON | FM 455 | 2025-08-29 | 4788222.29 | 438760.22 | 0 | 5267850.04 | 479627.75 | 138 | 223 | 84 | 0 | 85
EL PASO | 0003-01-055 | CULBERSON | IH 10 | 2025-08-29 | 29328228.91 | 11763074.67 | 0 | 41089066.14 | 11760837.23 | 440 | 1046 | 200 | 0 | 606
EL PASO | 0665-02-002 | EL PASO | SS 320 | 2025-08-29 | 17835785.54 | 22004.3 | 331120.92 | 18076512.15 | -90394.31 | 438 | 323 | 0 | 0 | -115
FORT WORTH | 0013-07-086 | WISE | US 81 | 2025-08-29 | 5886834.11 | -18664 | 0 | 5820540.08 | -66294.03 | 135 | 146 | 0 | 0 | 11
FORT WORTH | 0134-07-075 | WISE | US 380 | 2025-08-29 | 5064956.34 | 4265.19 | 0 | 4593460.73 | -471495.61 | 342 | 306 | 0 | 0 | -36
FORT WORTH | 0172-06-099 | TARRANT | US 287 | 2025-08-29 | 19292920.92 | 639112.74 | 0 | 20523147.25 | 1230226.33 | 150 | 223 | 73 | 0 | 73
FORT WORTH | 0902-20-236 | WISE | Various | 2025-08-29 | 149400 | 0 | 0 | 138300 | -11100 | 86 | 40 | 0 | 0 | -46
HOUSTON | 0500-03-635 | HARRIS | IH 45 | 2025-08-29 | 4137770.75 | 2 | 0 | 4043564.64 | -94206.11 | 118 | 117 | 0 | 0 | -1
TYLER | 0138-16-005 | GREGG | US 259 | 2025-08-29 | 4533082.58 | 55108.66 | 0 | 4449487.59 | -83594.99 | 106 | 213 | 2 | 0 | 107
ABILENE | 0106-07-030 | HASKELL | SH 6 | 2025-02-28 | 1729616.69 | 397361 | 0 | 1945755.07 | 216138.38 | 124 | 286 | 100 | 0 | 162
AUSTIN | 0016-16-028 | HAYS | RM 967 | 2025-02-28 | 8474686.36 | 483765.55 | 0 | 9067032.49 | 592346.13 | 320 | 240 | 0 | 0 | -80
EL PASO | 1046-01-032 | EL PASO | FM 659 | 2025-02-28 | 14610296.05 | 792269.45 | 0 | 15729724.12 | 1119428.07 | 283 | 373 | 92 | 0 | 90
TYLER | 0095-08-021 | SMITH | US 80 | 2025-02-28 | 21313599.05 | -389663.75 | 0 | 20436143.48 | -877455.57 | 170 | 164 | 0 | 0 | -6
YOAKUM | 0535-07-050 | FAYETTE | IH 10 | 2025-02-28 | 10399532.44 | -527095.35 | 0 | 9967394.07 | -432138.37 | 225 | 194 | 0 | 0 | -31
YOAKUM | 0715-03-014 | DEWITT | FM 108 | 2025-02-28 | 10571632.45 | -88996.04 | 0 | 10249109.68 | -322522.77 | 270 | 308 | 38 | 0 | 38
ABILENE | 0908-27-006 | KENT | CR | 2025-02-27 | 878015 | 24358.4 | 0 | 880172.15 | 2157.15 | 89 | 89 | 0 | 0 | 0
AMARILLO | 0030-07-022 | HEMPHILL | US 83 | 2025-02-27 | 5382629.98 | -48724.82 | 0 | 5644878.75 | 262248.77 | 71 | 62 | 0 | 0 | -9
FORT WORTH | 0008-03-134 | PARKER | US 180 | 2025-02-27 | 680358.25 | 52400.72 | 0 | 712703.35 | 32345.1 | 107 | 97 | 0 | 0 | -10
LUFKIN | 0911-08-049 | NACOGDOCHES | CR | 2025-02-27 | 2041759.25 | 0 | 0 | 2044351.26 | 2592.01 | 644 | 156 | 0 | 0 | -488
ATLANTA | 0919-00-093 | CASS | Various | 2025-02-26 | 134759 | 0 | 0 | 134145 | -614 | 20 | 8 | 0 | 0 | -12
FORT WORTH | 0008-16-042 | TARRANT | IH 20 | 2025-02-26 | 20961181.94 | 7155561.14 | 0 | 28304573.46 | 7343391.52 | 371 | 731 | 360 | 0 | 360
LUFKIN | 0176-06-016 | POLK | BU 59J | 2025-02-26 | 9240613.28 | 236699.62 | 0 | 9190460.25 | -50153.03 | 121 | 158 | 8 | 0 | 37
AUSTIN | 0252-02-063 | BURNET | US 281 | 2025-02-25 | 597524.87 | 19017.13 | 0 | 691648.28 | 94123.41 | 79 | 73 | 10 | 0 | -6
AUSTIN | 0914-05-214 | WILLIAMSON | RONALD REAGAN BLVD | 2025-02-25 | 2006827.14 | 13265.53 | 0 | 2071820.98 | 64993.84 | 103 | 74 | 2 | 0 | -29
BEAUMONT | 0177-03-096 | LIBERTY | US 59 | 2025-02-25 | 102144835.19 | 5099651.93 | 0 | 109065388.94 | 6920553.75 | 736 | 1125 | 433 | 0 | 389
BEAUMONT | 0932-01-118 | JEFFERSON | FM 365 | 2025-02-25 | 320758.82 | 60903.11 | 0 | 326778.1 | 6019.28 | 30 | 30 | 5 | 0 | 0
CORPUS CHRISTI | 0371-02-074 | REFUGIO | US 77 | 2025-02-25 | 9300599.86 | -1317703.95 | 0 | 7952741.63 | -1347858.23 | 170 | 173 | 3 | 0 | 3
AUSTIN | 0914-18-120 | BASTROP | Various | 2025-02-24 | 4210981.85 | 113436.27 | 0 | 4176501.74 | -34480.11 | 279 | 225 | 0 | 0 | -54
BROWNWOOD | 0011-07-062 | STEPHENS | US 180 | 2025-02-24 | 13778329.83 | 11370.03 | 0 | 11560613.02 | -2217716.81 | 85 | 55 | 0 | 0 | -30
WACO | 2311-01-042 | MCLENNAN | SL 340 | 2025-02-24 | 3759444.64 | 35828.05 | 0 | 3816287.97 | 56843.33 | 75 | 78 | 0 | 0 | 3
WICHITA FALLS | 0282-02-031 | CLAY | SH 79 | 2025-02-24 | 3246126.19 | 272.58 | 0 | 3153288.81 | -92837.38 | 60 | 137 | 2 | 0 | 77
CORPUS CHRISTI | 0916-38-015 | ARANSAS | VA | 2025-02-22 | 254251 | 3175 | 0 | 257281 | 3030 | 56 | 59 | 3 | 0 | 3
FORT WORTH | 0902-90-184 | TARRANT | VA | 2025-02-21 | 1484096.25 | 12504 | 0 | 1478427.81 | -5668.44 | 128 | 268 | 0 | 0 | 140
HOUSTON | 0912-37-252 | MONTGOMERY | Various | 2025-02-21 | 956940.66 | 0 | 0 | 995068.96 | 38128.3 | 100 | 89 | 0 | 0 | -11
ABILENE | 1360-01-030 | JONES | FM 1226 | 2025-02-20 | 1671853.75 | 0 | 0 | 1630600.65 | -41253.1 | 104 | 126 | 0 | 0 | 22
CORPUS CHRISTI | 0086-20-023 | NUECES | FM 665 | 2025-02-20 | 4508717.9 | 145854.1 | 0 | 4765319.56 | 256601.66 | 187 | 227 | 17 | 0 | 40
ODESSA | 2224-01-119 | ECTOR | SL 338 | 2025-02-20 | 7949949.69 | 156838.97 | 0 | 8176183.79 | 226234.1 | 155 | 111 | 0 | 0 | -44
TYLER | 0190-03-087 | WOOD | SH 37 | 2025-02-20 | 4577457.44 | 4387022.96 | 0 | 9359240.63 | 4781783.19 | 83 | 268 | 138 | 0 | 185
WACO | 3448-02-007 | MCLENNAN | FM 3268 | 2025-02-20 | 2735685.61 | 355133.62 | 0 | 2981185.01 | 245499.4 | 105 | 87 | 0 | 0 | -18
WICHITA FALLS | 0903-00-120 | WICHITA | VA | 2025-02-20 | 833158.86 | 0 | 0 | 807264.96 | -25893.9 | 78 | 103 | 0 | 0 | 25
BEAUMONT | 0389-02-057 | CHAMBERS | SH 146 | 2025-02-19 | 311550.68 | 63089.69 | 0 | 376736.58 | 65185.9 | 75 | 119 | 72 | 0 | 44
BEAUMONT | 0508-02-131 | CHAMBERS | IH 10 | 2025-02-19 | 1285256.5 | 2277.38 | 0 | 1306562.98 | 21306.48 | 79 | 72 | 0 | 0 | -7
HOUSTON | 1416-03-018 | MONTGOMERY | FM 1486 | 2025-02-19 | 4541531.81 | 250930.27 | 0 | 5290109.51 | 748577.7 | 107 | 142 | 0 | 0 | 35
AUSTIN | 0252-02-064 | BURNET | US 281 | 2025-02-18 | 5701426.3 | -198606.53 | 0 | 5411914.25 | -289512.05 | 72 | 57 | 2 | 0 | -15
AUSTIN | 0700-01-045 | BURNET | SH 71 | 2025-02-18 | 8763188.97 | 2393489.04 | 1567507.59 | 11694470.81 | 1363774.25 | 193 | 280 | 103 | 78 | 9
BRYAN | 0109-09-068 | WALKER | SH 19 | 2025-02-18 | 4204817.53 | -422452.91 | 0 | 3985459.3 | -219358.23 | 100 | 58 | 0 | 0 | -42
BRYAN | 0917-18-082 | ROBERTSON | CS | 2025-02-18 | 663959.11 | 0 | 0 | 643334.43 | -20624.68 | 71 | 65 | 0 | 0 | -6
TYLER | 0910-16-147 | SMITH | CS | 2025-02-18 | 1258293.7 | 2000 | 0 | 1382619.37 | 124325.67 | 180 | 147 | 0 | 0 | -33
DALLAS | 0195-02-087 | DENTON | IH 35 | 2025-02-14 | 1117242.04 | 29646.14 | 0 | 859724.51 | -257517.53 | 98 | 46 | 0 | 0 | -52
HOUSTON | 1912-01-022 | MONTGOMERY | FM 2090 | 2025-02-14 | 7041940.21 | 869384.6 | 0 | 9002022.69 | 1960082.48 | 124 | 118 | 0 | 0 | -6
LAREDO | 0542-01-102 | WEBB | BU 59Z | 2025-02-14 | 907084.3 | 103536.87 | 0 | 1053013.12 | 145928.82 | 60 | 58 | 0 | 0 | -2
PHARR | 0039-12-259 | CAMERON | BU 77X | 2025-02-14 | 6349769.9 | 57866.89 | 0 | 6698813.81 | 349043.91 | 125 | 92 | 0 | 0 | -33
PHARR | 0669-03-029 | HIDALGO | FM 2221 | 2025-02-14 | 802713.95 | 0 | 0 | 780422.31 | -22291.64 | 120 | 118 | 0 | 0 | -2
PHARR | 0921-06-363 | CAMERON | CS | 2025-02-14 | 64546 | -2583.24 | 0 | 56843.47 | -7702.53 | 7 | 6 | 0 | 0 | -1
PHARR | 1103-05-002 | STARR | FM 755 | 2025-02-14 | 763589.1 | 3150 | 0 | 769825.13 | 6236.03 | 100 | 119 | 19 | 0 | 19
TYLER | 0910-00-131 | SMITH | Various | 2025-02-14 | 2538364 | -373716.13 | 0 | 2213436.68 | -324927.32 | 196 | 163 | 1 | 0 | -33
WICHITA FALLS | 0903-00-119 | WICHITA | VA | 2025-02-14 | 689012.1 | 0 | 0 | 694186.09 | 5173.99 | 70 | 74 | 0 | 0 | 4
CORPUS CHRISTI | 0916-00-212 | NUECES | VA | 2025-02-13 | 1847391.5 | 0 | 0 | 1727039.46 | -120352.04 | 120 | 803 | 0 | 0 | 683
FORT WORTH | 0902-90-126 | TARRANT | SS 580 | 2025-02-12 | 438635 | 4161.35 | 0 | 444649.94 | 6014.94 | 64 | 66 | 0 | 0 | 2
LAREDO | 0038-01-097 | WEBB | US 83 | 2025-02-12 | 1040125 | 0 | 0 | 1027607.5 | -12517.5 | 108 | 50 | 0 | 0 | -58
ODESSA | 0292-01-034 | WINKLER | SH 18 | 2025-02-12 | 37268535.81 | 285594.57 | 0 | 42166837.42 | 4898301.61 | 265 | 444 | 179 | 0 | 179
ATLANTA | 0063-04-068 | PANOLA | US 59 | 2025-02-11 | 1105559.41 | 7825 | 0 | 1096061.62 | -9497.79 | 71 | 66 | 0 | 0 | -5
ATLANTA | 0096-03-075 | UPSHUR | US 80 | 2025-02-11 | 6277174.34 | 403397.36 | 0 | 6966176.19 | 689001.85 | 162 | 199 | 4 | 0 | 37
AUSTIN | 1378-03-039 | BURNET | RM 1431 | 2025-02-11 | 6275058.13 | -74485.43 | 0 | 5717124.87 | -557933.26 | 120 | 45 | 3 | 0 | -75
BEAUMONT | 2367-01-063 | JEFFERSON | SH 82 | 2025-02-11 | 6193763.91 | -31397.44 | 0 | 6107854.49 | -85909.42 | 88 | 88 | 0 | 0 | 0
CORPUS CHRISTI | 0180-05-065 | ARANSAS | BS 35-L | 2025-02-11 | 1836179 | 54711.51 | 0 | 1858442.03 | 22263.03 | 85 | 158 | 12 | 0 | 73
FORT WORTH | 0250-04-049 | ERATH | US 281 | 2025-02-11 | 11095984.14 | 216501.63 | 0 | 10729638.01 | -366346.13 | 128 | 127 | 0 | 0 | -1
FORT WORTH | 0902-90-210 | TARRANT | CS | 2025-02-10 | 734812.4 | 0 | 0 | 753595.33 | 18782.93 | 200 | 135 | 0 | 0 | -65
WACO | 0909-00-094 | MCLENNAN | Various | 2025-02-10 | 2897993.38 | 0 | 0 | 2522074.24 | -375919.14 | 60 | 37 | 0 | 0 | -23
SAN ANGELO | 0142-01-076 | KIMBLE | IH 10 | 2025-02-09 | 20144525.28 | 87075.06 | 0 | 21284986.77 | 1140461.49 | 107 | 136 | 50 | 0 | 29
AUSTIN | 0914-18-107 | BASTROP | CR | 2025-02-07 | 1478746.42 | 53001.11 | 0 | 1500023.33 | 21276.91 | 79 | 130 | 28 | 0 | 51
DALLAS | 1451-03-017 | NAVARRO | FM 55 | 2025-02-07 | 4964579.98 | 509878.47 | 0 | 5479022.27 | 514442.29 | 210 | 271 | 65 | 0 | 61
LUFKIN | 0064-01-069 | SHELBY | SH 87 | 2025-02-07 | 15659341.69 | 332973.58 | 0 | 14768418.71 | -890922.98 | 125 | 158 | 0 | 0 | 33
PARIS | 0901-22-117 | HUNT | CR | 2025-02-07 | 1348336.46 | -56800.5 | 0 | 1247653.44 | -100683.02 | 229 | 221 | 0 | 0 | -8
LUBBOCK | 0130-05-089 | LUBBOCK | US 62 | 2025-02-06 | 340196.25 | 0 | 0 | 337436.25 | -2760 | 32 | 27 | 0 | 0 | -5
LUBBOCK | 0905-00-120 | LUBBOCK | Various | 2025-02-06 | 1639160 | -489002.5 | 0 | 1191316.8 | -447843.2 | 68 | 68 | 0 | 0 | 0
LUBBOCK | 0905-00-130 | LUBBOCK | Various | 2025-02-06 | 1783751.6 | 0 | 0 | 2105529.2 | 321777.6 | 90 | 53 | 0 | 0 | -37
WICHITA FALLS | 0013-05-065 | MONTAGUE | US 81 | 2025-02-06 | 2243728.59 | 0 | 0 | 2039673.03 | -204055.56 | 193 | 130 | 0 | 0 | -63
AUSTIN | 0114-20-014 | TRAVIS | SL 212 | 2025-02-05 | 799753.9 | 10101.99 | 0 | 830885.08 | 31131.18 | 24 | 21 | 0 | 0 | -3
AUSTIN | 0150-04-046 | LLANO | SH 29 | 2025-02-05 | 7398988.99 | 999686.56 | 0 | 8798993.62 | 1400004.63 | 369 | 384 | 15 | 0 | 15
AUSTIN | 0204-02-036 | WILLIAMSON | US 79 | 2025-02-05 | 3840828.3 | 0 | 0 | 4168320.87 | 327492.57 | 68 | 37 | 0 | 0 | -31
DALLAS | 1568-02-014 | DENTON | FM 407 | 2025-02-05 | 8970766.9 | 858224.11 | 0 | 9411709.18 | 440942.28 | 203 | 205 | 2 | 0 | 2
SAN ANTONIO | 0658-01-045 | BEXAR | FM 1535 | 2025-02-05 | 15523367.42 | 1476602.74 | -218287.68 | 16730801.87 | 1425722.13 | 540 | 621 | 81 | 4 | 77
YOAKUM | 0535-08-089 | COLORADO | IH 10 | 2025-02-05 | 4831460.04 | -194250 | 0 | 4301678.99 | -529781.05 | 75 | 67 | 0 | 0 | -8
CHILDRESS | 0042-06-076 | DONLEY | US 287 | 2025-02-04 | 6446300.55 | -166311.3 | 0 | 6627654.34 | 181353.79 | 95 | 76 | 0 | 0 | -19
YOAKUM | 0179-04-102 | MATAGORDA | SH 35 | 2025-02-04 | 327710 | -9546.7 | 0 | 308254.04 | -19455.96 | 30 | 20 | 0 | 0 | -10
ABILENE | 0972-06-015 | HASKELL | FM 600 | 2025-02-03 | 2844984.65 | 0 | 0 | 2983799.43 | 138814.78 | 120 | 117 | 0 | 0 | -3
ABILENE | 0983-03-030 | NOLAN | FM 419 | 2025-02-03 | 3360261.38 | -119485.48 | 0 | 3421807.76 | 61546.38 | 94 | 79 | 0 | 0 | -15
AMARILLO | 0904-00-188 | POTTER | VA | 2025-02-03 | 1274691.7 | 135764.2 | 0 | 1402847.08 | 128155.38 | 214 | 214 | 0 | 0 | 0
BEAUMONT | 0388-02-069 | LIBERTY | SH 146 | 2025-02-03 | 3497274.25 | 70543.98 | 0 | 3391626.64 | -105647.61 | 69 | 52 | 0 | 0 | -17
BEAUMONT | 0920-02-090 | LIBERTY | CR | 2025-02-03 | 799669.8 | 0 | 0 | 835116.8 | 35447 | 81 | 83 | 0 | 0 | 2
BEAUMONT | 3510-10-022 | CHAMBERS | SH 99 | 2025-02-03 | 23691228.21 | 136464.96 | 0 | 23713870.76 | 22642.55 | 285 | 242 | 0 | 0 | -43
DALLAS | 0095-05-063 | KAUFMAN | US 80 | 2025-02-03 | 2155024 | 25100 | 0 | 2331185.46 | 176161.46 | 260 | 349 | 5 | 0 | 89
FORT WORTH | 0081-02-076 | TARRANT | US 377 | 2025-02-03 | 470872 | 1220 | 0 | 471477.56 | 605.56 | 64 | 68 | 4 | 0 | 4
SAN ANGELO | 0907-00-178 | TOM GREEN | VA | 2025-02-03 | 1264222.11 | 79417.66 | 0 | 1245863.83 | -18358.28 | 171 | 205 | 16 | 0 | 34
SAN ANTONIO | 2708-01-033 | BEXAR | FM 2696 | 2025-02-03 | 778577 | 111847.61 | 0 | 896148.62 | 117571.62 | 89 | 78 | 0 | 0 | -11
TYLER | 0191-01-093 | SMITH | US 69 | 2025-02-03 | 444558 | 18659 | 0 | 468710.5 | 24152.5 | 34 | 29 | 0 | 0 | -5
AUSTIN | 0366-01-081 | HAYS | SH 123 | 2025-02-01 | 2331672.3 | 111777.54 | 0 | 2587105.89 | 255433.59 | 187 | 116 | 0 | 0 | -71
LUBBOCK | 0302-04-022 | SWISHER | SH 86 | 2025-01-31 | 2320028 | 458561.72 | 0 | 3289949.44 | 969921.44 | 320 | 318 | 73 | 0 | -2
ODESSA | 0229-04-060 | UPTON | US 385 | 2025-01-31 | 5995947.22 | -12950.22 | 0 | 5859540.37 | -136406.85 | 120 | 186 | 68 | 0 | 66
ODESSA | 0479-03-016 | LOVING | SH 302 | 2025-01-31 | 36670137.75 | -329920.36 | 0 | 39347167.05 | 2677029.3 | 510 | 465 | 0 | 0 | -45
EL PASO | 0002-02-055 | EL PASO | SH 20 | 2025-01-30 | 2606597.5 | 1148552.72 | 0 | 3775359.48 | 1168761.98 | 120 | 235 | 68 | 0 | 115
EL PASO | 0924-00-105 | EL PASO | VA | 2025-01-30 | 1053915 | 158770 | 0 | 1031483.89 | -22431.11 | 186 | 185 | 0 | 0 | -1
FORT WORTH | 0171-03-077 | PARKER | SH 199 | 2025-01-30 | 734777 | -4867.5 | 0 | 647956.75 | -86820.25 | 43 | 33 | 0 | 0 | -10
LUBBOCK | 0052-04-053 | LAMB | US 84 | 2025-01-30 | 22788746.19 | 197274.01 | 0 | 21724655.89 | -1064090.3 | 64 | 58 | 0 | 0 | -6
LUBBOCK | 0905-06-118 | LUBBOCK | CS | 2025-01-30 | 12797068.28 | 274194.87 | 0 | 12929767.77 | 132699.49 | 256 | 379 | 123 | 0 | 123
LUFKIN | 0175-07-065 | NACOGDOCHES | US 59 | 2025-01-30 | 6975521.46 | 27969.52 | 0 | 7419588.94 | 444067.48 | 119 | 99 | 0 | 0 | -20
PARIS | 0901-00-063 | LAMAR | Various | 2025-01-30 | 3141295.36 | -259349.7 | 0 | 2757597.6 | -383697.76 | 101 | 63 | 0 | 0 | -38
WACO | 0833-01-009 | CORYELL | FM 217 | 2025-01-30 | 7582811.52 | -6609.71 | 0 | 6703339.31 | -879472.21 | 60 | 47 | 0 | 0 | -13
AUSTIN | 0384-04-034 | CALDWELL | FM 1854 | 2025-01-29 | 8806086.7 | 690144.5 | 0 | 9887536.59 | 1081449.89 | 188 | 55 | 3 | 0 | -133
AUSTIN | 2718-01-015 | TRAVIS | RM 2769 | 2025-01-29 | 2979802.82 | -80170.12 | 0 | 3523056.66 | 543253.84 | 53 | 47 | 0 | 0 | -6
PHARR | 0342-02-059 | HIDALGO | SH 107 | 2025-01-29 | 554000 | 0 | 0 | 561163.91 | 7163.91 | 104 | 22 | 0 | 0 | -82
PHARR | 0921-06-311 | CAMERON | CS | 2025-01-29 | 939378.65 | -112523.49 | 0 | 886323.15 | -53055.5 | 215 | 197 | 0 | 0 | -18
AUSTIN | 0700-04-053 | LLANO | SH 71 | 2025-01-28 | 3798987.88 | 152051.64 | 0 | 4024014.96 | 225027.08 | 52 | 51 | 2 | 0 | -1
SAN ANGELO | 0112-01-019 | KIMBLE | US 290 | 2025-01-28 | 4234053.39 | 191520.88 | 0 | 4449126.37 | 215072.98 | 235 | 563 | 324 | 0 | 328
SAN ANTONIO | 1740-03-019 | ATASCOSA | FM 1333 | 2025-01-28 | 4025335.99 | 153503.36 | 0 | 4202707.98 | 177371.99 | 109 | 152 | 45 | 0 | 43
LAREDO | 0018-02-086 | LA SALLE | IH 35 | 2025-01-27 | 11045137.85 | 359166.4 | 0 | 11602781.9 | 557644.05 | 263 | 311 | 9 | 0 | 48
LAREDO | 0922-00-084 | WEBB | Various | 2025-01-27 | 796188.5 | 18992.02 | 0 | 843502.66 | 47314.16 | 80 | 80 | 0 | 0 | 0
LUFKIN | 0063-07-003 | SHELBY | SL 157 | 2025-01-27 | 12827779.2 | 132034.91 | 0 | 11708879.28 | -1118899.92 | 106 | 102 | 0 | 0 | -4
WACO | 0015-01-258 | MCLENNAN | IH 35 | 2025-01-27 | 787764.5 | 0 | 0 | 759616.26 | -28148.24 | 60 | 58 | 0 | 0 | -2
CORPUS CHRISTI | 0738-01-001 | REFUGIO | FM 136 | 2025-01-24 | 1136958 | 0 | 0 | 1058863.84 | -78094.16 | 85 | 641 | 162 | 0 | 556
ODESSA | 2005-02-017 | ECTOR | FM 1882 | 2025-01-24 | 10165599.43 | 362129.9 | 0 | 10721567.72 | 555968.29 | 210 | 144 | 20 | 0 | -66
PHARR | 0861-01-068 | HIDALGO | FM 491 | 2025-01-24 | 3701235.71 | 107384.73 | 0 | 3699526.31 | -1709.4 | 180 | 236 | 26 | 0 | 56
ABILENE | 0006-04-080 | TAYLOR | IH 20 | 2025-01-23 | 12105731.79 | -24.84 | 0 | 12662770.77 | 557038.98 | 142 | 156 | 14 | 0 | 14
CHILDRESS | 0043-04-083 | HARDEMAN | US 287 | 2025-01-23 | 8059390.88 | 269727.25 | 0 | 8740321.8 | 680930.92 | 79 | 82 | 10 | 0 | 3
CHILDRESS | 0538-01-027 | KNOX | FM 267 | 2025-01-23 | 6913833.35 | -202800.17 | 0 | 6784248.83 | -129584.52 | 177 | 143 | 0 | 0 | -34
FORT WORTH | 1098-02-015 | TARRANT | FM 718 | 2025-01-22 | 2852725.75 | -485.62 | 0 | 2963467.28 | 110741.53 | 128 | 135 | 12 | 0 | 7
YOAKUM | 0913-00-114 | DEWITT | VA | 2025-01-22 | 1652900 | 0 | 0 | 1649500 | -3400 | 120 | 64 | 0 | 0 | -56
AUSTIN | 0112-03-036 | GILLESPIE | US 290 | 2025-01-21 | 3070929.9 | -74484.79 | 0 | 3033451.36 | -37478.54 | 57 | 53 | 0 | 0 | -4
AUSTIN | 1378-04-056 | BURNET | RM 1431 | 2025-01-21 | 7574977.47 | -152911.71 | 0 | 7990182.23 | 415204.76 | 145 | 108 | 0 | 0 | -37
CHILDRESS | 0105-02-023 | HALL | SH 86 | 2025-01-21 | 6639789.5 | 277903.7 | 0 | 7049215.48 | 409425.98 | 89 | 91 | 4 | 0 | 2
FORT WORTH | 0902-90-125 | TARRANT | CS | 2025-01-21 | 3861246.79 | -40246.25 | 0 | 3809318.98 | -51927.81 | 217 | 216 | 0 | 0 | -1
FORT WORTH | 1330-02-049 | TARRANT | FM 1187 | 2025-01-21 | 2305368.4 | 157196.59 | 0 | 2612336.12 | 306967.72 | 160 | 196 | 0 | 0 | 36
ABILENE | 0032-07-029 | STONEWALL | US 83 | 2025-01-17 | 19299562.06 | 67476.51 | 0 | 17886005.29 | -1413556.77 | 432 | 442 | 10 | 0 | 10
AUSTIN | 0112-02-036 | GILLESPIE | US 290 | 2025-01-17 | 3888100.8 | -242004.5 | 0 | 4196993.75 | 308892.95 | 158 | 100 | 0 | 0 | -58
AUSTIN | 1534-01-020 | BLANCO | RM 1623 | 2025-01-17 | 976312.12 | 22132.42 | 0 | 915159.91 | -61152.21 | 25 | 12 | 0 | 0 | -13
DALLAS | 0568-01-059 | ELLIS | SH 34 | 2025-01-17 | 3311895 | 117138.35 | 0 | 3287129.03 | -24765.97 | 157 | 227 | 75 | 0 | 70
TYLER | 0910-00-136 | SMITH | Various | 2025-01-17 | 932150 | 0 | 0 | 932725 | 575 | 38 | 28 | 0 | 0 | -10
LUFKIN | 0200-03-021 | ANGELINA | US 69 | 2025-01-14 | 37447954.88 | 2359974.98 | 0 | 40062516.18 | 2614561.3 | 475 | 556 | 81 | 0 | 81
AMARILLO | 1245-02-049 | POTTER | RM 1061 | 2025-01-13 | 12755021.41 | 117372.76 | 0 | 13377958.53 | 622937.12 | 288 | 311 | 10 | 0 | 23
CHILDRESS | 0043-23-008 | HARDEMAN | SL 285 | 2025-01-13 | 1870931 | 0 | 0 | 1905511.5 | 34580.5 | 134 | 133 | 0 | 0 | -1
LAREDO | 0542-01-101 | WEBB | US 59 | 2025-01-13 | 5349601.52 | 78136.6 | 0 | 5604708.45 | 255106.93 | 120 | 108 | 0 | 0 | -12
LAREDO | 2636-01-010 | MAVERICK | FM 2644 | 2025-01-13 | 2696125.5 | -32776.1 | 0 | 2863095.48 | 166969.98 | 125 | 125 | 0 | 0 | 0
ODESSA | 0005-01-116 | ECTOR | BI 20E | 2025-01-13 | 2412947.5 | 807438.4 | 0 | 3022910.89 | 609963.39 | 57 | 96 | 50 | 0 | 39
ODESSA | 0076-07-038 | UPTON | US 67 | 2025-01-13 | 18404584.67 | 42466.79 | 0 | 17726890.66 | -677694.01 | 92 | 105 | 15 | 0 | 13
ODESSA | 0292-03-032 | WARD | SH 18 | 2025-01-13 | 32902552.4 | -1658414.09 | 0 | 32065142.29 | -837410.11 | 244 | 244 | 12 | 0 | 0
CORPUS CHRISTI | 0516-02-029 | GOLIAD | SH 239 | 2025-01-10 | 7455639.89 | 824137.22 | 0 | 8147758.67 | 692118.78 | 246 | 375 | 129 | 0 | 129
EL PASO | 0924-06-700 | EL PASO | Various | 2025-01-10 | 458260 | 0 | 0 | 473775.2 | 15515.2 | 83 | 25 | 0 | 0 | -58
PARIS | 1290-07-001 | HUNT | SH 276 | 2025-01-10 | 14191646.9 | 136450.31 | 0 | 13726504.74 | -465142.16 | 384 | 583 | 0 | 0 | 199
SAN ANTONIO | 0073-09-040 | BEXAR | IH 37 | 2025-01-10 | 292836 | 0 | 0 | 292830 | -6 | 54 | 41 | 0 | 0 | -13
ABILENE | 0053-15-067 | NOLAN | FM 608 | 2025-01-09 | 8787859.33 | -465639.5 | 0 | 8072700.59 | -715158.74 | 263 | 274 | 11 | 0 | 11
FORT WORTH | 0312-05-031 | TARRANT | FM 730 | 2025-01-09 | 5888715.63 | 298188.8 | 0 | 6103147.13 | 214431.5 | 149 | 146 | 0 | 0 | -3
SAN ANGELO | 0034-03-019 | RUNNELS | US 83 | 2025-01-06 | 24497111.44 | 23500.59 | 0 | 25759058.93 | 1261947.49 | 578 | 587 | 12 | 0 | 9
YOAKUM | 0535-06-046 | FAYETTE | IH 10 | 2025-01-06 | 1588806.6 | 12293.32 | 0 | 1800499.2 | 211692.6 | 158 | 139 | 0 | 0 | -19
AUSTIN | 0016-02-170 | HAYS | IH 35 | 2025-01-05 | 4186521.77 | -588359.93 | 0 | 4432691.41 | 246169.64 | 64 | 57 | 0 | 0 | -7
AUSTIN | 0914-00-457 | TRAVIS | Various | 2025-01-04 | 2965162.9 | 62548.01 | 0 | 3207664.18 | 242501.28 | 178 | 178 | 0 | 0 | 0
BRYAN | 0675-04-069 | LEON | IH 45 | 2025-01-03 | 17287257.6 | -329848.03 | 0 | 17936875.62 | 649618.02 | 175 | 155 | 0 | 0 | -20
ODESSA | 0005-04-082 | MARTIN | IH 20 | 2025-01-03 | 1679659 | 20000 | 0 | 1633898.3 | -45760.7 | 80 | 120 | 40 | 0 | 40
ODESSA | 0548-02-043 | MARTIN | SH 176 | 2025-01-03 | 5880107.87 | -308029.96 | 0 | 5525804.79 | -354303.08 | 142 | 127 | 0 | 0 | -15
ODESSA | 0906-32-060 | MIDLAND | CS | 2025-01-03 | 496352.87 | 6163.24 | 6163.3 | 500570 | -1946.17 | 91 | 71 | 0 | 0 | -20
ODESSA | 1188-02-118 | MIDLAND | SL 250 | 2025-01-03 | 1609466.84 | -13134.93 | 0 | 1549504.39 | -59962.45 | 64 | 60 | 3 | 0 | -4
PHARR | 1586-01-089 | HIDALGO | FM 907 | 2025-01-03 | 1313573.1 | 20400 | 0 | 1290099.87 | -23473.23 | 140 | 190 | 50 | 0 | 50
WACO | 0909-22-190 | MCLENNAN | CS | 2025-01-03 | 648860 | 37382.05 | 0 | 869725.76 | 220865.76 | 45 | 58 | 10 | 0 | 13
SAN ANTONIO | 0025-10-097 | GUADALUPE | FM 78 | 2025-01-02 | 1371678.58 | 32871.91 | 0 | 1358169.73 | -13508.85 | 86 | 82 | 0 | 0 | -4
AMARILLO | 1245-01-019 | OLDHAM | RM 1061 | 2024-12-31 | 18084714.17 | -223034.59 | 0 | 18757957.09 | 673242.92 | 332 | 326 | 6 | 0 | -6
BRYAN | 0917-18-085 | ROBERTSON | CS | 2024-12-31 | 722351.41 | 0 | 0 | 746575.2 | 24223.79 | 159 | 80 | 0 | 0 | -79
ABILENE | 0437-01-025 | SHACKELFORD | US 283 | 2024-12-30 | 12676446.45 | 238500.44 | 0 | 11901429.7 | -775016.75 | 103 | 103 | 0 | 0 | 0
DALLAS | 0009-04-075 | ROCKWALL | SH 66 | 2024-12-30 | 19193970.72 | 165692.07 | 0 | 19333501.06 | 139530.34 | 243 | 216 | 0 | 0 | -27
SAN ANTONIO | 0236-04-029 | FRIO | FM 117 | 2024-12-30 | 22497898.08 | 418231.37 | 0 | 22674568.66 | 176670.58 | 588 | 583 | 1 | 0 | -5
ABILENE | 0006-03-145 | NOLAN | IH 20 | 2024-12-27 | 2739348.25 | 47750 | 0 | 2778375.49 | 39027.24 | 161 | 160 | 0 | 0 | -1
ABILENE | 0908-33-106 | TAYLOR | CS | 2024-12-27 | 1316532.4 | 810980 | 0 | 1361029.67 | 44497.27 | 133 | 131 | 0 | 0 | -2
EL PASO | 0020-01-021 | CULBERSON | US 90 | 2024-12-26 | 5952638.25 | 608732.82 | 0 | 6782347.1 | 829708.85 | 180 | 176 | 0 | 0 | -4
HOUSTON | 0367-02-082 | GALVESTON | SH 87 | 2024-12-23 | 9010882.36 | 1999617.37 | 0 | 11040074.82 | 2029192.46 | 126 | 175 | 59 | 0 | 49
HOUSTON | 0051-09-024 | GALVESTON | FM 3005 | 2024-12-20 | 35347635.33 | 433840 | 0 | 34884980.38 | -462654.95 | 450 | 539 | 89 | 0 | 89
LUBBOCK | 0052-02-037 | BAILEY | US 70 | 2024-12-20 | 1843790 | 0 | 0 | 1826121.63 | -17668.37 | 121 | 107 | 0 | 0 | -14
LUBBOCK | 0905-00-116 | LUBBOCK | Various | 2024-12-20 | 1311802.1 | 0 | 0 | 1357078.19 | 45276.09 | 85 | 107 | 22 | 0 | 22
AUSTIN | 1753-01-017 | MASON | RM 1871 | 2024-12-19 | 4178807.04 | 71745.07 | 0 | 3982822.91 | -195984.13 | 182 | 441 | 108 | 0 | 259
BEAUMONT | 0920-13-040 | TYLER | Various | 2024-12-19 | 262629.95 | 25684.63 | 0 | 328179.18 | 65549.23 | 22 | 9 | 0 | 0 | -13
CHILDRESS | 0031-01-022 | WHEELER | US 83 | 2024-12-19 | 12191889.22 | -154811.43 | 0 | 12447743.55 | 255854.33 | 237 | 207 | -2 | 0 | -30
LAREDO | 2150-04-076 | WEBB | FM 1472 | 2024-12-19 | 6359706.23 | 624484.13 | 0 | 6911593.72 | 551887.49 | 374 | 443 | 20 | 0 | 69
LUBBOCK | 0068-09-012 | LYNN | SL 76 | 2024-12-19 | 23982637.33 | 160410.89 | 0 | 23785167.9 | -197469.43 | 637 | 744 | 55 | 0 | 107
SAN ANTONIO | 0915-12-770 | BEXAR | Various | 2024-12-19 | 491128.33 | 9495.42 | 0 | 510254.23 | 19125.9 | 78 | 64 | 0 | 0 | -14
WICHITA FALLS | 0282-03-031 | CLAY | SH 79 | 2024-12-19 | 4472468.24 | 269903.58 | 0 | 4702841.5 | 230373.26 | 127 | 186 | 9 | 0 | 59
ABILENE | 0668-01-021 | HOWARD | FM 700 | 2024-12-18 | 588687 | -77100 | 0 | 521917 | -66770 | 38 | 56 | 0 | 0 | 18
PARIS | 0771-01-019 | RAINS | FM 2946 | 2024-12-18 | 1614607.12 | 112881.74 | 0 | 1683728.44 | 69121.32 | 103 | 119 | 16 | 0 | 16
WACO | 0909-36-182 | BELL | CS | 2024-12-18 | 461858.81 | 35772 | 0 | 496236.53 | 34377.72 | 45 | 40 | 0 | 0 | -5
WACO | 1054-02-023 | BOSQUE | FM 219 | 2024-12-18 | 10387524.22 | 161324.36 | 0 | 10026263.91 | -361260.31 | 300 | 324 | 25 | 0 | 24
AUSTIN | 0113-13-184 | TRAVIS | US 290 | 2024-12-17 | 2026821.23 | -46170.7 | 0 | 1974464.64 | -52356.59 | 48 | 18 | 0 | 0 | -30
AUSTIN | 0914-24-025 | BURNET | Various | 2024-12-17 | 1637722.85 | 143263.43 | 0 | 1879967.51 | 242244.66 | 68 | 118 | 50 | 0 | 50
CORPUS CHRISTI | 0073-07-068 | LIVE OAK | IH 37 | 2024-12-17 | 1030452.14 | 91817.27 | 0 | 1314043 | 283590.86 | 85 | 225 | 140 | 0 | 140
SAN ANGELO | 0036-05-044 | REAL | US 83 | 2024-12-17 | 10347155.74 | 3956291.82 | 0 | 11960596.98 | 1613441.24 | 96 | 76 | 2 | 0 | -20
SAN ANTONIO | 0216-01-057 | COMAL | SL 337 | 2024-12-17 | 14284639.49 | 499305.68 | 0 | 14810900.93 | 526261.44 | 350 | 436 | 86 | 0 | 86
AMARILLO | 1337-02-012 | LIPSCOMB | SH 23 | 2024-12-16 | 7414243.89 | 980074.07 | 0 | 8245860.29 | 831616.4 | 257 | 265 | 8 | 0 | 8
AUSTIN | 0113-07-072 | HAYS | US 290 | 2024-12-16 | 1960789.39 | 132580.06 | 11546.72 | 2195536.22 | 223200.11 | 141 | 122 | 0 | 0 | -19
BROWNWOOD | 0079-03-051 | COMANCHE | US 67 | 2024-12-16 | 850894.76 | 70500.55 | 0 | 872037.21 | 21142.45 | 75 | 153 | 48 | 0 | 78
BROWNWOOD | 0923-22-025 | STEPHENS | CS | 2024-12-16 | 1073352.2 | 67095.2 | 0 | 1161254.17 | 87901.97 | 115 | 106 | 0 | 0 | -9
CORPUS CHRISTI | 0617-01-206 | NUECES | SH 358 | 2024-12-16 | 7618726.75 | 434909.29 | 0 | 7831165.7 | 212438.95 | 55 | 178 | 99 | 0 | 123
DALLAS | 1311-01-060 | DENTON | FM 1171 | 2024-12-16 | 845850.43 | 16392.01 | 0 | 871581.6 | 25731.17 | 81 | 73 | 0 | 0 | -8
TYLER | 0245-06-087 | SMITH | SH 64 | 2024-12-16 | 2208247.24 | 16023.29 | 0 | 2185109.63 | -23137.61 | 115 | 107 | 0 | 0 | -8
YOAKUM | 0143-08-098 | DEWITT | US 87 | 2024-12-16 | 6692309 | 1667476.08 | 0 | 8550631.49 | 1858322.49 | 125 | 147 | 22 | 0 | 22
AMARILLO | 1819-01-015 | LIPSCOMB | FM 1920 | 2024-12-13 | 16356130.41 | 1804121.1 | 0 | 18093051.17 | 1736920.76 | 441 | 450 | 10 | 0 | 9
ATLANTA | 0010-12-075 | BOWIE | US 67 | 2024-12-13 | 1397827.97 | 0 | 0 | 1403519.39 | 5691.42 | 172 | 186 | 0 | 0 | 14
ATLANTA | 0248-05-065 | UPSHUR | US 271 | 2024-12-13 | 4881470.75 | 127363.92 | 0 | 5183042.62 | 301571.87 | 65 | 77 | 10 | 0 | 12
AUSTIN | 3417-03-021 | TRAVIS | FM 734 | 2024-12-13 | 5597210.35 | 616545.39 | 0 | 6272016.69 | 674806.34 | 155 | 155 | 0 | 0 | 0
EL PASO | 0924-06-689 | EL PASO | Various | 2024-12-13 | 832138 | -31343.57 | 0 | 872959.51 | 40821.51 | 120 | 119 | 2 | 0 | -1
DALLAS | 2979-01-013 | DENTON | FM 2931 | 2024-12-12 | 4665613.56 | 1373304.83 | 0 | 5829103.02 | 1163489.46 | 220 | 185 | 65 | 0 | -35
WACO | 0055-15-081 | MCLENNAN | US 84 | 2024-12-12 | 299986.38 | 0 | 0 | 293120.63 | -6865.75 | 45 | 23 | 0 | 0 | -22
WICHITA FALLS | 0146-07-033 | WILBARGER | US 70 | 2024-12-12 | 2143240 | 509332.34 | 0 | 2673976.28 | 530736.28 | 122 | 225 | 114 | 0 | 103
ODESSA | 0906-00-255 | ECTOR | Various | 2024-12-11 | 3569917.5 | 0 | 0 | 3627570.5 | 57653 | 253 | 140 | 0 | 0 | -113
AUSTIN | 0253-02-033 | BLANCO | US 281 | 2024-12-10 | 1151580.5 | -92138.87 | 0 | 989591.39 | -161989.11 | 88 | 82 | 0 | 0 | -6
BRYAN | 0917-20-046 | FREESTONE | CR | 2024-12-10 | 609028.19 | 0 | 0 | 599520.95 | -9507.24 | 74 | 98 | 0 | 0 | 24
FORT WORTH | 0014-03-087 | JOHNSON | IH 35W | 2024-12-10 | 13369086.3 | 375838.28 | 0 | 13829348.29 | 460261.99 | 231 | 400 | 169 | 0 | 169
DALLAS | 0047-07-242 | DALLAS | US 75 | 2024-12-09 | 5572514.47 | 0 | 0 | 5165749.3 | -406765.17 | 204 | 176 | 0 | 0 | -28
DALLAS | 0549-03-024 | COLLIN | SH 121 | 2024-12-09 | 91386585.26 | 1398398.73 | 0 | 94387841.53 | 3001256.27 | 1092 | 762 | 0 | 0 | -330
DALLAS | 0816-03-020 | DENTON | FM 455 | 2024-12-09 | 4243947.8 | 93904.16 | 0 | 4287876.13 | 43928.33 | 323 | 497 | 0 | 0 | 174
FORT WORTH | 0134-07-069 | WISE | US 380 | 2024-12-09 | 3489536.12 | 314942.67 | 0 | 3536563.14 | 47027.02 | 171 | 211 | 40 | 0 | 40
SAN ANTONIO | 0915-14-045 | WILSON | CR | 2024-12-06 | 557521.7 | 15484 | 0 | 567979.28 | 10457.58 | 175 | 81 | 0 | 0 | -94
TYLER | 1171-01-022 | VAN ZANDT | FM 859 | 2024-12-06 | 3629409.25 | 281395.76 | 0 | 3969899.22 | 340489.97 | 166 | 179 | 13 | 0 | 13
HOUSTON | 1259-01-043 | MONTGOMERY | FM 1097 | 2024-12-05 | 14690168.28 | 1573006.85 | 0 | 16771639.93 | 2081471.65 | 334 | 394 | 124 | 0 | 60
LUFKIN | 0809-02-070 | SHELBY | US 96 | 2024-12-05 | 9395982.34 | 1095466.59 | 0 | 9832229.15 | 436246.81 | 320 | 320 | 0 | 0 | 0
ATLANTA | 0218-03-094 | CASS | US 59 | 2024-12-04 | 7806579.99 | -85064.55 | 0 | 8906767.58 | 1100187.59 | 74 | 68 | 0 | 0 | -6
WACO | 0049-01-101 | MCLENNAN | SL 484 | 2024-12-04 | 850998.1 | -171413 | 0 | 696888.77 | -154109.33 | 60 | 60 | 0 | 0 | 0
AUSTIN | 0320-04-029 | WILLIAMSON | US 79 | 2024-12-03 | 5596125.31 | -46368.02 | 0 | 5926314.08 | 330188.77 | 112 | 99 | 0 | 0 | -13
DALLAS | 0918-47-212 | DALLAS | CS | 2024-12-03 | 2040000 | 0 | 0 | 2089849.53 | 49849.53 | 360 | 513 | 0 | 0 | 153
YOAKUM | 0408-01-043 | FAYETTE | SH 159 | 2024-12-03 | 5331593.91 | 125891.05 | 0 | 5464571.69 | 132977.78 | 294 | 293 | 0 | 0 | -1
YOAKUM | 0913-28-088 | FAYETTE | CR | 2024-12-03 | 1728303.93 | 25044.54 | 0 | 1757900.51 | 29596.58 | 195 | 185 | 0 | 0 | -10
AMARILLO | 0041-02-016 | HARTLEY | US 385 | 2024-12-02 | 9656579.22 | 1326671.9 | 0 | 11122673.72 | 1466094.5 | 327 | 469 | 165 | 0 | 142
AMARILLO | 0904-00-232 | POTTER | Various | 2024-12-02 | 1635105 | -70990 | 0 | 1553315 | -81790 | 67 | 37 | 0 | 0 | -30
DALLAS | 0173-01-049 | ELLIS | SH 34 | 2024-12-02 | 6698765.23 | 2007181.59 | 0 | 8438092.45 | 1739327.22 | 172 | 168 | 10 | 0 | -4
DALLAS | 0196-01-117 | DENTON | US 77 | 2024-12-02 | 3803760.4 | 52377.78 | 0 | 4017457.22 | 213696.82 | 118 | 100 | 0 | 0 | -18
FORT WORTH | 0019-01-148 | JOHNSON | SH 174 | 2024-12-01 | 1433900.47 | 98402.93 | 0 | 1543091.63 | 109191.16 | 360 | 80 | 0 | 0 | -280
BROWNWOOD | 0128-01-111 | BROWN | US 377 | 2024-11-26 | 4045900.2 | 1024102.87 | 0 | 5887682.54 | 1841782.34 | 149 | 222 | 56 | 0 | 73
DALLAS | 2374-04-091 | DALLAS | IH 20 | 2024-11-26 | 190482.1 | 0 | 0 | 187107.34 | -3374.76 | 49 | 18 | 0 | 0 | -31
LUBBOCK | 0067-05-053 | HALE | IH 27 | 2024-11-26 | 2049918.5 | -202952.25 | 0 | 1971470.9 | -78447.6 | 209 | 270 | 30 | 0 | 61
WACO | 3534-02-007 | BELL | SH 201 | 2024-11-26 | 5861341.86 | 9285.43 | 0 | 5608743 | -252598.86 | 120 | 103 | 0 | 0 | -17
ABILENE | 0296-01-039 | SCURRY | US 180 | 2024-11-25 | 3120194.7 | 0 | 0 | 3281803.41 | 161608.71 | 53 | 45 | 0 | 0 | -8
ABILENE | 2638-03-012 | CALLAHAN | SH 206 | 2024-11-25 | 1595477.54 | 0 | 0 | 1611398.68 | 15921.14 | 31 | 31 | 0 | 0 | 0
BROWNWOOD | 0055-01-031 | MILLS | US 84 | 2024-11-25 | 4495363.25 | 17707.25 | 0 | 4288037.74 | -207325.51 | 53 | 51 | 0 | 0 | -2
SAN ANTONIO | 0017-04-042 | ATASCOSA | IH 35 | 2024-11-25 | 12910717.48 | 3365790.31 | 0 | 17232769.49 | 4322052.01 | 345 | 345 | 0 | 0 | 0
YOAKUM | 0315-09-011 | AUSTIN | FM 2502 | 2024-11-25 | 1284265 | 76593.4 | 0 | 1430603.65 | 146338.65 | 105 | 123 | 12 | 0 | 18
AUSTIN | 0016-02-169 | HAYS | IH 35 | 2024-11-22 | 915988.85 | 0 | 0 | 841231.36 | -74757.49 | 23 | 5 | 0 | 0 | -18
BRYAN | 0338-01-052 | GRIMES | SH 105 | 2024-11-22 | 6022301.01 | 4034857.46 | 0 | 10087359.54 | 4065058.53 | 254 | 342 | 155 | 0 | 88
CORPUS CHRISTI | 0074-01-060 | LIVE OAK | IH 37 | 2024-11-22 | 5101524.26 | -145374.59 | 0 | 4959038.4 | -142485.86 | 46 | 38 | 0 | 0 | -8
DALLAS | 3427-03-007 | COLLIN | FM 3356 | 2024-11-22 | 5796924.02 | -178064.57 | 0 | 5223395.51 | -573528.51 | 189 | 185 | 0 | 0 | -4
EL PASO | 0924-06-663 | EL PASO | Various | 2024-11-22 | 995591.48 | 331869.02 | 0 | 1338931.33 | 343339.85 | 80 | 231 | 153 | 0 | 151
FORT WORTH | 0134-05-034 | JACK | SH 59 | 2024-11-22 | 3685479.68 | 43305.4 | 0 | 3797961.77 | 112482.09 | 234 | 349 | 108 | 0 | 115
FORT WORTH | 1600-02-019 | JOHNSON | FM 1807 | 2024-11-22 | 3153376.15 | 233893.09 | 0 | 3159646.24 | 6270.09 | 64 | 64 | 0 | 0 | 0
LUFKIN | 0809-02-069 | SHELBY | US 96 | 2024-11-22 | 16435546.93 | 481457.2 | 0 | 15902457.89 | -533089.04 | 402 | 311 | 0 | 0 | -91
ODESSA | 2224-01-099 | ECTOR | SL 338 | 2024-11-22 | 15760357.9 | 4576076.03 | 0 | 21459652.4 | 5699294.5 | 400 | 648 | 250 | 0 | 248
SAN ANGELO | 0907-00-226 | TOM GREEN | CS | 2024-11-22 | 1186200 | -21718.03 | 0 | 1167254.97 | -18945.03 | 149 | 201 | 0 | 0 | 52
SAN ANTONIO | 0915-14-048 | WILSON | CS | 2024-11-22 | 1044921 | 55316.68 | 55316.68 | 1085147.75 | -15089.93 | 55 | 69 | 21 | 21 | -7
YOAKUM | 0913-28-075 | FAYETTE | CR | 2024-11-22 | 805990.58 | 0 | 0 | 787929.1 | -18061.48 | 103 | 101 | 0 | 0 | -2
AMARILLO | 0275-01-199 | POTTER | IH 40 | 2024-11-21 | 50032707.74 | 1494118.8 | 0 | 53685534.42 | 3652826.68 | 575 | 974 | 168 | 0 | 399
CORPUS CHRISTI | 0101-02-039 | BEE | US 181 | 2024-11-21 | 9794885.95 | 1753263.7 | 0 | 11558804.84 | 1763918.89 | 139 | 160 | 25 | 0 | 21
SAN ANGELO | 0463-04-024 | GLASSCOCK | SH 158 | 2024-11-21 | 26934934.66 | -117385.1 | 0 | 26988805.51 | 53870.85 | 517 | 532 | 17 | 0 | 15
ABILENE | 0007-01-062 | CALLAHAN | IH 20 | 2024-11-20 | 7267838.13 | -648453.06 | 0 | 6357347.48 | -910490.65 | 191 | 197 | 15 | 0 | 6
ABILENE | 2597-01-008 | HOWARD | FM 2599 | 2024-11-20 | 5256051.97 | 54273.5 | 0 | 5633680.64 | 377628.67 | 121 | 180 | 0 | 0 | 59
ATLANTA | 1511-01-013 | UPSHUR | FM 993 | 2024-11-20 | 1523718.09 | 27520 | 0 | 1622349.71 | 98631.62 | 103 | 65 | 4 | 0 | -38
AUSTIN | 2293-01-032 | HAYS | FM 2439 | 2024-11-20 | 958354.16 | 146633.41 | 0 | 1037314.21 | 78960.05 | 29 | 13 | 0 | 0 | -16
BEAUMONT | 2782-01-013 | TYLER | FM 1632 | 2024-11-20 | 5136533.23 | 63500 | 0 | 5230237.45 | 93704.22 | 129 | 100 | 5 | 0 | -29
CORPUS CHRISTI | 0102-03-087 | NUECES | US 77 | 2024-11-20 | 7712829.03 | 413355.78 | 0 | 8271901.17 | 559072.14 | 219 | 385 | 168 | 0 | 166
FORT WORTH | 0902-00-339 | TARRANT | Various | 2024-11-20 | 3471786.5 | 748884.41 | 0 | 4093607.44 | 621820.94 | 421 | 334 | 0 | 0 | -87
PHARR | 0255-08-111 | HIDALGO | IH 69C | 2024-11-20 | 6495030.9 | 228296.65 | 0 | 7024789.07 | 529758.17 | 120 | 87 | 0 | 0 | -33
WICHITA FALLS | 0043-05-112 | WILBARGER | US 287 | 2024-11-20 | 3882921.05 | 28486.8 | 0 | 3755218.91 | -127702.14 | 210 | 205 | 8 | 0 | -5
CORPUS CHRISTI | 0916-35-233 | NUECES | CR | 2024-11-19 | 114728 | 3990 | 0 | 117088 | 2360 | 50 | 17 | 0 | 0 | -33
LAREDO | 0018-04-065 | WEBB | IH 35 | 2024-11-19 | 16568075.25 | 1257149.43 | 0 | 18328090.29 | 1760015.04 | 222 | 191 | 5 | 0 | -31
WACO | 0184-01-068 | CORYELL | SH 36 | 2024-11-19 | 291325 | 524 | 0 | 291849 | 524 | 75 | 58 | 0 | 0 | -17
WACO | 0231-04-060 | BELL | IH 14 | 2024-11-19 | 39466124 | 3682657.34 | 0 | 44795767.17 | 5329643.17 | 360 | 525 | 165 | 0 | 165
SAN ANGELO | 0158-01-081 | RUNNELS | US 67 | 2024-11-18 | 5693419.75 | 7333.9 | 0 | 5707561.75 | 14142 | 379 | 391 | 0 | 0 | 12
AMARILLO | 0904-00-181 | POTTER | Various | 2024-11-15 | 1771464.25 | 29220 | 0 | 1866000.78 | 94536.53 | 194 | 122 | 0 | 0 | -72
ODESSA | 3570-01-012 | ECTOR | FM 3503 | 2024-11-15 | 5107417.37 | 199997.11 | 0 | 6260310.89 | 1152893.52 | 137 | 95 | 0 | 0 | -42
AUSTIN | 0914-00-455 | TRAVIS | VA | 2024-11-14 | 1305817.91 | 122372.23 | 0 | 1511179.01 | 205361.1 | 218 | 159 | 0 | 0 | -59
BRYAN | 0917-19-053 | WASHINGTON | CR | 2024-11-14 | 815696.28 | 0 | 0 | 818354.01 | 2657.73 | 110 | 109 | 0 | 0 | -1
PARIS | 0009-07-043 | HUNT | SS 302 | 2024-11-14 | 4906019.96 | -206295.27 | 0 | 4616946.55 | -289073.41 | 123 | 115 | 0 | 0 | -8
WACO | 0231-03-145 | BELL | US 190 | 2024-11-14 | 44733665.59 | 766643.4 | 0 | 48205163.22 | 3471497.63 | 375 | 605 | 255 | 0 | 230
WACO | 0867-01-017 | HAMILTON | FM 932 | 2024-11-14 | 13587882.83 | -323157.03 | 0 | 13379432.69 | -208450.14 | 405 | 399 | 0 | 0 | -6
EL PASO | 0924-00-109 | EL PASO | Various | 2024-11-13 | 2271557.75 | -134856.3 | 0 | 2267863.17 | -3694.58 | 340 | 145 | 0 | 0 | -195
LAREDO | 0922-00-074 | WEBB | VA | 2024-11-13 | 2435839.81 | 66235.27 | 0 | 2349306.74 | -86533.07 | 378 | 377 | 0 | 0 | -1
LUBBOCK | 0905-00-119 | LUBBOCK | Various | 2024-11-12 | 7117196.6 | 0 | 0 | 7504466.81 | 387270.21 | 85 | 68 | 0 | 0 | -17
SAN ANTONIO | 0915-12-693 | BEXAR | CR | 2024-11-12 | 1705802.68 | 62470.85 | 0 | 1779546.18 | 73743.5 | 130 | 124 | 10 | 0 | -6
TYLER | 0910-34-037 | HENDERSON | Various | 2024-11-12 | 173162 | 8500 | 0 | 174709.34 | 1547.34 | 64 | 31 | 0 | 0 | -33
AUSTIN | 0471-04-035 | CALDWELL | SH 21 | 2024-11-08 | 9312831.73 | -339.43 | 0 | 9950251.61 | 637419.88 | 109 | 86 | 4 | 0 | -23
EL PASO | 2121-02-178 | EL PASO | IH 10 | 2024-11-08 | 5680916.35 | -1013474.58 | 0 | 4550932.85 | -1129983.5 | 77 | 63 | 0 | 0 | -14
EL PASO | 2121-04-114 | EL PASO | IH 10 | 2024-11-08 | 18039540.88 | 1229607.66 | 0 | 19341952.98 | 1302412.1 | 330 | 447 | 148 | 0 | 117
SAN ANTONIO | 0142-10-028 | KENDALL | RM 473 | 2024-11-08 | 640687.25 | 0 | 0 | 665487.12 | 24799.87 | 32 | 32 | 0 | 0 | 0
SAN ANTONIO | 0366-03-068 | GUADALUPE | SH 123 | 2024-11-08 | 24608308.91 | 728174.34 | 0 | 26636326.9 | 2028017.99 | 482 | 920 | 488 | 0 | 438
WACO | 0120-03-031 | BOSQUE | SH 22 | 2024-11-08 | 9797442.66 | 2091696.91 | 0 | 11972697.88 | 2175255.22 | 210 | 308 | 70 | 0 | 98
WACO | 0774-03-015 | HAMILTON | FM 1602 | 2024-11-08 | 127891 | 850 | 0 | 123907 | -3984 | 30 | 22 | 0 | 0 | -8
FORT WORTH | 0902-00-340 | TARRANT | Various | 2024-11-06 | 2414176 | 65644.42 | 0 | 2494190.49 | 80014.49 | 342 | 194 | 0 | 0 | -148
YOAKUM | 0913-09-106 | WHARTON | CR | 2024-11-05 | 958659 | -95810 | 0 | 829123.35 | -129535.65 | 120 | 126 | 0 | 0 | 6
DALLAS | 0918-47-438 | DALLAS | Various | 2024-11-04 | 3959735.05 | -741038.04 | 0 | 3210740.89 | -748994.16 | 93 | 88 | 0 | 0 | -5
FORT WORTH | 0902-00-357 | TARRANT | Various | 2024-11-04 | 4647055 | 0 | 0 | 4655773.99 | 8718.99 | 365 | 365 | 0 | 0 | 0
ODESSA | 0228-04-043 | ANDREWS | US 385 | 2024-11-04 | 37642802.47 | -1301884.08 | 0 | 36413663.01 | -1229139.46 | 373 | 433 | 64 | 0 | 60
SAN ANGELO | 0333-02-013 | STERLING | SH 163 | 2024-11-04 | 2615605 | 157665.7 | 0 | 2708747.7 | 93142.7 | 187 | 213 | 24 | 0 | 26
CHILDRESS | 0042-07-071 | DONLEY | US 287 | 2024-11-01 | 576583 | 0 | 0 | 586894.57 | 10311.57 | 48 | 12 | 0 | 0 | -36
DALLAS | 0918-47-359 | DALLAS | FD | 2024-11-01 | 2217976.4 | 0 | 0 | 2080564.9 | -137411.5 | 105 | 127 | 0 | 0 | 22
WACO | 0909-00-052 | MCLENNAN | Various | 2024-11-01 | 436915 | 0 | 0 | 414510 | -22405 | 45 | 25 | 0 | 0 | -20
WICHITA FALLS | 1609-01-029 | COOKE | FM 1630 | 2024-11-01 | 4611140.62 | -127243.59 | 0 | 4565170.85 | -45969.77 | 170 | 144 | 0 | 0 | -26
DALLAS | 0281-01-037 | COLLIN | SH 78 | 2024-10-31 | 3966360.02 | 0 | 0 | 3900192.97 | -66167.05 | 142 | 50 | 0 | 0 | -92
FORT WORTH | 0094-02-143 | TARRANT | SH 183 | 2024-10-31 | 300690.78 | -12496 | 0 | 275976.78 | -24714 | 72 | 65 | 0 | 0 | -7
LAREDO | 0017-08-118 | LA SALLE | IH 35 | 2024-10-31 | 1863389 | 129936.3 | 0 | 2114362.44 | 250973.44 | 49 | 74 | 39 | 0 | 25
PARIS | 0901-29-102 | LAMAR | Various | 2024-10-31 | 297263 | -51920 | 0 | 265882.5 | -31380.5 | 64 | 23 | 0 | 0 | -41
WACO | 0833-02-020 | BOSQUE | FM 217 | 2024-10-31 | 12983870.35 | -489446.09 | 0 | 12586655.19 | -397215.16 | 315 | 317 | 16 | 0 | 2
LUFKIN | 3264-01-010 | ANGELINA | FM 326 | 2024-10-30 | 2637474.14 | 16798.4 | 0 | 2488350.16 | -149123.98 | 171 | 218 | 32 | 0 | 47
SAN ANTONIO | 0348-07-018 | ATASCOSA | FM 99 | 2024-10-30 | 15357877.23 | 264607.29 | 0 | 15856763.87 | 498886.64 | 743 | 502 | 0 | 0 | -241
WACO | 0019-03-028 | HILL | SH 171 | 2024-10-30 | 5859952.5 | 243970 | 0 | 6394099.02 | 534146.52 | 270 | 258 | 0 | 0 | -12
CHILDRESS | 0541-01-033 | BRISCOE | SH 256 | 2024-10-29 | 7556670.11 | 10148.54 | 0 | 8264327.16 | 707657.05 | 57 | 35 | 0 | 0 | -22
CHILDRESS | 0704-02-022 | CHILDRESS | FM 268 | 2024-10-29 | 17182340.87 | 668265.84 | 0 | 18254137.33 | 1071796.46 | 443 | 335 | 41 | 0 | -108
FORT WORTH | 0008-12-092 | TARRANT | SH 183 | 2024-10-29 | 4619873.98 | -210867.42 | 0 | 4311408.16 | -308465.82 | 128 | 131 | 0 | 0 | 3
HOUSTON | 0178-03-158 | BRAZORIA | SH 35 | 2024-10-29 | 4500659.53 | -494684.95 | 0 | 4087418.22 | -413241.31 | 101 | 114 | 0 | 0 | 13
SAN ANGELO | 0141-02-033 | SUTTON | IH 10 | 2024-10-29 | 21298153.59 | -1416598.59 | 0 | 20933481.12 | -364672.47 | 221 | 316 | 0 | 0 | 95
ABILENE | 0908-23-053 | FISHER | CR | 2024-10-28 | 917198 | 65883 | 0 | 961219 | 44021 | 96 | 96 | 0 | 0 | 0
AUSTIN | 0914-00-470 | TRAVIS | Various | 2024-10-28 | 648422.03 | -59419.35 | 0 | 612529.68 | -35892.35 | 28 | 61 | 33 | 0 | 33
BROWNWOOD | 0257-04-029 | EASTLAND | SH 6 | 2024-10-28 | 10587368.26 | 810758.46 | 0 | 11373705.68 | 786337.42 | 230 | 306 | 81 | 0 | 76
CORPUS CHRISTI | 0326-03-107 | NUECES | SH 286 | 2024-10-28 | 396817.5 | 32567.59 | 0 | 407126.32 | 10308.82 | 44 | 76 | 20 | 0 | 32
SAN ANTONIO | 0017-13-012 | ATASCOSA | SH 132 | 2024-10-28 | 6628642 | 304378.55 | 0 | 6641766.36 | 13124.36 | 410 | 291 | 0 | 0 | -119
EL PASO | 2121-04-110 | EL PASO | IH 10 | 2024-10-27 | 2756557.25 | 668639.65 | 0 | 3511031.47 | 754474.22 | 124 | 86 | 0 | 0 | -38
HOUSTON | 0508-01-345 | HARRIS | IH 10 | 2024-10-25 | 14598295.77 | 5695539.68 | 0 | 19217067.76 | 4618771.99 | 398 | 582 | 185 | 0 | 184
AUSTIN | 1197-01-025 | HAYS | RM 150 | 2024-10-23 | 1083995.67 | -55516.88 | 0 | 1097456.99 | 13461.32 | 32 | 8 | 0 | 0 | -24
ABILENE | 0007-02-057 | CALLAHAN | IH 20 | 2024-10-22 | 5593534.43 | 41475.38 | 0 | 5875233.87 | 281699.44 | 152 | 156 | 5 | 0 | 4
AMARILLO | 0030-05-073 | HEMPHILL | US 60 | 2024-10-22 | 8566511.52 | 214509 | 0 | 9179770.01 | 613258.49 | 188 | 185 | 15 | 0 | -3
AMARILLO | 0169-02-068 | POTTER | US 60 | 2024-10-22 | 2207755 | 40274.87 | 0 | 2161342.01 | -46412.99 | 106 | 130 | 15 | 0 | 24
HOUSTON | 0050-06-094 | HARRIS | BU 290H | 2024-10-22 | 78734.4 | -1353.35 | 0 | 78021.05 | -713.35 | 90 | 38 | 0 | 0 | -52
HOUSTON | 3050-02-024 | MONTGOMERY | FM 2978 | 2024-10-22 | 15788778.29 | 8646460.83 | 271903.17 | 25152892.81 | 9092211.35 | 457 | 516 | 147 | 0 | 59
PHARR | 0921-02-483 | HIDALGO | VA | 2024-10-22 | 1287240.2 | 7455 | 0 | 1251923.4 | -35316.8 | 239 | 175 | 0 | 0 | -64
AUSTIN | 0286-01-065 | HAYS | SH 80 | 2024-10-21 | 1035073.1 | -49943.43 | 0 | 1033959.71 | -1113.39 | 32 | 26 | 0 | 0 | -6
BRYAN | 0116-03-066 | BURLESON | SH 21 | 2024-10-21 | 2941282.43 | 0 | 0 | 2924522.07 | -16760.36 | 133 | 133 | 0 | 0 | 0
ODESSA | 0140-01-081 | PECOS | IH 10 | 2024-10-21 | 14363577.76 | 0 | 0 | 13997772 | -365805.76 | 67 | 67 | 0 | 0 | 0
ODESSA | 0140-02-050 | PECOS | IH 10 | 2024-10-21 | 1938518 | 0 | 0 | 1797376.5 | -141141.5 | 124 | 63 | 0 | 0 | -61
DALLAS | 0918-11-100 | KAUFMAN | CR | 2024-10-18 | 1534309.5 | -6280 | 0 | 1500205.46 | -34104.04 | 303 | 202 | 0 | 0 | -101
DALLAS | 2678-02-008 | DENTON | FM 428 | 2024-10-18 | 6544754.19 | 366604.15 | 0 | 6231734.75 | -313019.44 | 214 | 254 | 39 | 0 | 40
HOUSTON | 0912-72-363 | HARRIS | CS | 2024-10-18 | 17999505.15 | 825689.79 | 825689.79 | 18670205.06 | -154989.88 | 436 | 675 | 123 | 0 | 239
PARIS | 0136-01-066 | HUNT | SH 224 | 2024-10-18 | 2620776.26 | -81357.79 | 0 | 2510214.82 | -110561.44 | 129 | 122 | 0 | 0 | -7
CORPUS CHRISTI | 0074-01-059 | LIVE OAK | IH 37 | 2024-10-17 | 3899642.24 | 387661.42 | 0 | 3927143.28 | 27501.04 | 37 | 53 | 0 | 0 | 16
LUBBOCK | 0905-00-129 | LUBBOCK | Various | 2024-10-17 | 5367023.85 | 312700.85 | 0 | 5668931.6 | 301907.75 | 80 | 126 | 0 | 0 | 46
LUFKIN | 0118-08-075 | NACOGDOCHES | SH 21 | 2024-10-17 | 2490124.75 | 13526.48 | 0 | 2537576.6 | 47451.85 | 230 | 291 | 61 | 0 | 61
ABILENE | 0006-05-117 | TAYLOR | IH 20 | 2024-10-16 | 9498596.31 | 175866.4 | 0 | 10353585.12 | 854988.81 | 240 | 348 | 40 | 0 | 108
AMARILLO | 0397-01-045 | GRAY | SH 152 | 2024-10-16 | 15464360.41 | 380420.07 | 0 | 17561815.39 | 2097454.98 | 266 | 271 | 31 | 0 | 5
CORPUS CHRISTI | 0100-08-095 | BEE | US 181 | 2024-10-16 | 14739738.04 | 118985.18 | 0 | 15241699.63 | 501961.59 | 184 | 365 | 181 | 0 | 181
HOUSTON | 0976-01-043 | HARRIS | FM 865 | 2024-10-16 | 3261336.96 | 549088.09 | 0 | 4287775.15 | 1026438.19 | 32 | 123 | 91 | 0 | 91
DALLAS | 0135-10-057 | DENTON | US 377 | 2024-10-15 | 20616736.66 | 695263.96 | 0 | 21294967.41 | 678230.75 | 836 | 890 | 54 | 0 | 54
DALLAS | 3325-01-014 | NAVARRO | FM 3243 | 2024-10-15 | 5724413.87 | 295327.09 | 0 | 5945844.75 | 221430.88 | 241 | 281 | 10 | 0 | 40
HOUSTON | 0675-08-114 | MONTGOMERY | IH 45 | 2024-10-15 | 7473853.32 | 98328.98 | 0 | 7627958.41 | 154105.09 | 252 | 251 | 0 | 0 | -1
HOUSTON | 0720-02-097 | MONTGOMERY | FM 149 | 2024-10-15 | 272609.79 | 146040.59 | 0 | 409073.71 | 136463.92 | 53 | 45 | 0 | 0 | -8
PHARR | 0039-18-123 | HIDALGO | IH 2 | 2024-10-15 | 6490669.1 | 9450 | 0 | 6431368.33 | -59300.77 | 100 | 77 | 0 | 0 | -23
WACO | 0909-22-188 | MCLENNAN | CS | 2024-10-15 | 448310 | -353.44 | 0 | 427156.24 | -21153.76 | 45 | 34 | 0 | 0 | -11
BRYAN | 0116-03-071 | BURLESON | SH 21 | 2024-10-14 | 1020603 | 0 | 0 | 927635.66 | -92967.34 | 70 | 29 | 0 | 0 | -41
BRYAN | 1507-02-016 | BURLESON | FM 696 | 2024-10-14 | 2574156.03 | 139938 | 0 | 2812606.51 | 238450.48 | 87 | 243 | 32 | 0 | 156
ODESSA | 0292-04-072 | WARD | SH 18 | 2024-10-14 | 13110325.39 | 783923.8 | 0 | 12839913.06 | -270412.33 | 83 | 25 | 0 | 0 | -58
BRYAN | 0049-14-014 | ROBERTSON | FM 46 | 2024-10-11 | 2552415.92 | 0 | 0 | 2575307.36 | 22891.44 | 65 | 100 | 16 | 0 | 35
TYLER | 0378-06-022 | CHEROKEE | SH 135 | 2024-10-11 | 4193458.94 | -146013.19 | 0 | 4106229.88 | -87229.06 | 153 | 150 | 0 | 0 | -3
LAREDO | 0018-02-089 | LA SALLE | IH 35 | 2024-10-10 | 1081952 | -1000.8 | 0 | 1128761.19 | 46809.19 | 105 | 105 | 0 | 0 | 0
LAREDO | 0037-09-033 | WEBB | US 83 | 2024-10-10 | 48720816.8 | 213508.15 | 0 | 49672485.96 | 951669.16 | 734 | 963 | 0 | 0 | 229
CHILDRESS | 0042-09-124 | HALL | US 287 | 2024-10-09 | 13478722.75 | 358966.57 | 0 | 14977060.49 | 1498337.74 | 420 | 481 | 53 | 0 | 61
PHARR | 0684-01-073 | CAMERON | FM 511 | 2024-10-08 | 4012543.76 | 0 | 0 | 3814613.62 | -197930.14 | 100 | 66 | 0 | 0 | -34
AUSTIN | 3136-01-200 | TRAVIS | SL 1 | 2024-10-07 | 4337214.75 | -73814.62 | 0 | 4487085.66 | 149870.91 | 96 | 90 | 0 | 0 | -6
AMARILLO | 0090-05-111 | POTTER | IH 40 | 2024-10-03 | 4121379.4 | 0 | 0 | 4143239.09 | 21859.69 | 107 | 100 | 0 | 0 | -7
AMARILLO | 0904-00-213 | POTTER | Various | 2024-10-03 | 576034.65 | 0 | 0 | 576030.03 | -4.62 | 43 | 25 | 0 | 0 | -18
BRYAN | 0917-12-084 | MILAM | CR | 2024-10-03 | 515115 | 0 | 0 | 499447 | -15668 | 89 | 256 | 0 | 0 | 167
ODESSA | 0139-06-021 | REEVES | US 285 | 2024-10-03 | 58528500.77 | -3781717.37 | 0 | 55093305.03 | -3435195.74 | 805 | 744 | 0 | 0 | -61
TYLER | 0443-01-034 | VAN ZANDT | SH 198 | 2024-10-03 | 234450 | 0 | 0 | 239400 | 4950 | 16 | 10 | 0 | 0 | -6
YOAKUM | 0089-06-093 | WHARTON | US 59 | 2024-10-03 | 2182905.02 | 0 | 0 | 2182996.49 | 91.47 | 72 | 51 | 0 | 0 | -21
YOAKUM | 0913-09-102 | WHARTON | CR | 2024-10-03 | 1244083.83 | 0 | 0 | 1237442.91 | -6640.92 | 238 | 138 | 0 | 0 | -100
YOAKUM | 0913-09-109 | WHARTON | CR | 2024-10-03 | 1626862.5 | 0 | 0 | 1595307.1 | -31555.4 | 184 | 140 | 0 | 0 | -44
YOAKUM | 0913-09-117 | WHARTON | CR | 2024-10-03 | 535853.15 | 0 | 0 | 530542.04 | -5311.11 | 59 | 51 | 0 | 0 | -8
ATLANTA | 0402-03-042 | HARRISON | SH 154 | 2024-10-02 | 3492422.9 | 64108 | 0 | 3448374.25 | -44048.65 | 197 | 176 | 0 | 0 | -21
FORT WORTH | 0902-39-029 | PALO PINTO | CR | 2024-10-02 | 724492 | 0 | 0 | 706661.51 | -17830.49 | 64 | 110 | 19 | 0 | 46
HOUSTON | 0027-12-166 | FORT BEND | IH 69 | 2024-10-02 | 800573.3 | 33526.41 | 0 | 845974.12 | 45400.82 | 90 | 58 | 0 | 0 | -32
EL PASO | 1158-01-011 | CULBERSON | FM 2185 | 2024-10-01 | 6981728.75 | 723068.71 | 0 | 7761157.77 | 779429.02 | 120 | 93 | 0 | 0 | -27
SAN ANTONIO | 1433-01-029 | BEXAR | FM 2252 | 2024-10-01 | 6580022.65 | 677818.31 | 194928.97 | 7766645.36 | 991693.74 | 303 | 435 | 135 | 95 | 37
WICHITA FALLS | 0124-04-038 | WILBARGER | US 183 | 2024-10-01 | 15116541.73 | 1411392.53 | 0 | 15220263.64 | 103721.91 | 359 | 582 | 11 | 0 | 223
FORT WORTH | 0363-01-147 | TARRANT | SH 26 | 2024-09-30 | 2429784.57 | -31077.75 | 0 | 2529099.42 | 99314.85 | 85 | 50 | 0 | 0 | -35
YOAKUM | 0913-17-044 | DEWITT | Various | 2024-09-30 | 151104 | 2500 | 0 | 151109 | 5 | 59 | 50 | 0 | 0 | -9
YOAKUM | 0913-28-093 | FAYETTE | Various | 2024-09-30 | 286575.5 | 4072.2 | 0 | 279161.2 | -7414.3 | 62 | 44 | 0 | 0 | -18
AUSTIN | 0113-05-049 | BLANCO | US 290 | 2024-09-27 | 13188475.9 | 96516.1 | 0 | 12132563.88 | -1055912.02 | 193 | 186 | 0 | 0 | -7
DALLAS | 0009-02-073 | DALLAS | SH 78 | 2024-09-27 | 2754566.08 | 12308.88 | 0 | 2639074.54 | -115491.54 | 103 | 71 | 0 | 0 | -32
DALLAS | 0092-06-105 | NAVARRO | IH 45 | 2024-09-27 | 6333011.92 | 1618510.08 | 0 | 7856117.24 | 1523105.32 | 237 | 236 | 0 | 0 | -1
EL PASO | 0924-06-647 | EL PASO | CR | 2024-09-27 | 730107.5 | 20648.8 | 0 | 743278.87 | 13171.37 | 137 | 104 | 0 | 0 | -33
FORT WORTH | 0008-14-124 | TARRANT | IH 820 | 2024-09-27 | 1932277.5 | -18287.44 | 0 | 1933545.43 | 1267.93 | 171 | 159 | 5 | 0 | -12
PARIS | 0901-27-046 | RED RIVER | CS | 2024-09-27 | 1091166.37 | -35385 | 0 | 1093703.94 | 2537.57 | 172 | 171 | 0 | 0 | -1
TYLER | 0910-07-084 | GREGG | Various | 2024-09-27 | 224591.52 | 19400 | 0 | 245400.52 | 20809 | 17 | 11 | 0 | 0 | -6
TYLER | 0910-08-081 | ANDERSON | VA | 2024-09-27 | 757095 | 0 | 0 | 772371 | 15276 | 47 | 45 | 0 | 0 | -2
TYLER | 0910-16-169 | SMITH | VA | 2024-09-27 | 157495 | 0 | 0 | 159155.64 | 1660.64 | 86 | 81 | 0 | 0 | -5
ATLANTA | 0919-13-017 | PANOLA | CR | 2024-09-26 | 968856.5 | 50000 | 0 | 990490.18 | 21633.68 | 53 | 26 | 0 | 0 | -27
SAN ANGELO | 0907-00-214 | TOM GREEN | Various | 2024-09-26 | 3746246.46 | -46151.04 | 0 | 3671169.58 | -75076.88 | 79 | 59 | 10 | 0 | -20
TYLER | 0108-02-033 | VAN ZANDT | SH 19 | 2024-09-26 | 12108565.85 | -342423 | 0 | 12285353.8 | 176787.95 | 434 | 335 | 4 | 0 | -99
WACO | 0386-02-026 | BOSQUE | SH 144 | 2024-09-26 | 4557803.14 | -439335 | 0 | 4071307.47 | -486495.67 | 90 | 82 | 0 | 0 | -8
AUSTIN | 0113-02-062 | GILLESPIE | US 290 | 2024-09-25 | 12252579.88 | 2488329.93 | 112013 | 14837828.62 | 2473235.74 | 284 | 269 | 47 | 16 | -31
ODESSA | 2262-01-020 | WARD | FM 1776 | 2024-09-25 | 5823543.4 | 549242.94 | 0 | 6643923.43 | 820380.03 | 120 | 163 | 21 | 0 | 43
TYLER | 0634-01-014 | CHEROKEE | FM 22 | 2024-09-25 | 5533705.84 | -4395.13 | 0 | 5247508.68 | -286197.16 | 249 | 383 | 0 | 0 | 134
ABILENE | 0407-06-047 | TAYLOR | US 277 | 2024-09-24 | 2639408.32 | -118410.62 | 0 | 2480617.87 | -158790.45 | 106 | 64 | 0 | 0 | -42
ODESSA | 0103-01-044 | REEVES | SH 17 | 2024-09-24 | 6972496.49 | 12956.15 | 0 | 7397640.93 | 425144.44 | 155 | 155 | 0 | 0 | 0
SAN ANGELO | 0141-03-062 | SUTTON | IH 10 | 2024-09-24 | 11863753.83 | 954893.06 | 0 | 12545116.84 | 681363.01 | 130 | 146 | 10 | 0 | 16
TYLER | 0198-01-032 | HENDERSON | BU 175G | 2024-09-24 | 695973.8 | 120282.22 | 0 | 895991.03 | 200017.23 | 71 | 71 | 0 | 0 | 0
WACO | 0015-01-256 | MCLENNAN | IH 35 | 2024-09-24 | 341697 | 0 | 0 | 336766.59 | -4930.41 | 45 | 47 | 0 | 0 | 2
ABILENE | 1652-01-015 | FISHER | FM 419 | 2024-09-23 | 684071 | 0 | 0 | 663485 | -20586 | 74 | 51 | 0 | 0 | -23
DALLAS | 0092-14-098 | DALLAS | IH 45 | 2024-09-23 | 5125904.79 | 57252.48 | 0 | 4375512.56 | -750392.23 | 365 | 365 | 25 | 0 | 0
DALLAS | 1047-03-076 | DALLAS | FM 1382 | 2024-09-23 | 4000858.2 | -449833.97 | 0 | 3390183.92 | -610674.28 | 97 | 162 | 0 | 0 | 65
WACO | 0231-03-154 | BELL | IH 14 | 2024-09-23 | 4494840 | -39536.35 | 0 | 4608112.02 | 113272.02 | 234 | 200 | 0 | 0 | -34
AUSTIN | 2210-01-008 | TRAVIS | RM 2322 | 2024-09-20 | 1340428.6 | 0 | 0 | 1181127.76 | -159300.84 | 23 | 16 | 0 | 0 | -7
DALLAS | 0095-04-072 | KAUFMAN | US 80 | 2024-09-20 | 2575586.68 | 255202.52 | 0 | 3159226.65 | 583639.97 | 320 | 294 | 0 | 0 | -26
DALLAS | 0172-05-124 | ELLIS | US 287 | 2024-09-20 | 1859514.08 | 108812.16 | 0 | 1983774.71 | 124260.63 | 142 | 75 | 0 | 0 | -67
DALLAS | 0581-01-156 | DALLAS | SL 12 | 2024-09-20 | 7277370.47 | 415689.5 | 0 | 7456808.48 | 179438.01 | 188 | 187 | 0 | 0 | -1
DALLAS | 1663-03-020 | NAVARRO | FM 744 | 2024-09-20 | 5714506.65 | 727434.42 | 0 | 6027970.2 | 313463.55 | 370 | 348 | 0 | 0 | -22
HOUSTON | 0912-70-093 | HARRIS | CS | 2024-09-20 | 4947623.92 | 417891.26 | 311029.98 | 5318772.71 | 60118.81 | 192 | 466 | 274 | 0 | 274
WACO | 0209-01-071 | MCLENNAN | US 77 | 2024-09-20 | 796944.5 | 25043 | 0 | 835148.07 | 38203.57 | 75 | 71 | 0 | 0 | -4
DALLAS | 2374-04-090 | DALLAS | IH 20 | 2024-09-19 | 4350740.31 | 293289.9 | 0 | 4732772.96 | 382032.65 | 150 | 173 | 25 | 0 | 23
SAN ANTONIO | 0024-01-109 | UVALDE | US 90 | 2024-09-19 | 1194194.94 | 112.8 | 0 | 1206183.18 | 11988.24 | 60 | 59 | 0 | 0 | -1
TYLER | 0910-07-078 | GREGG | CS | 2024-09-19 | 638112.63 | 69403.25 | 0 | 732238.84 | 94126.21 | 58 | 97 | 39 | 0 | 39
WICHITA FALLS | 0823-01-038 | COOKE | FM 373 | 2024-09-19 | 903763.84 | -152701.96 | 0 | 703937.21 | -199826.63 | 34 | 33 | 0 | 0 | -1
AUSTIN | 2690-01-038 | WILLIAMSON | FM 971 | 2024-09-17 | 4469902 | 30024.34 | 0 | 4562391.73 | 92489.73 | 107 | 106 | 0 | 0 | -1
FORT WORTH | 0013-10-089 | TARRANT | BU 287P | 2024-09-13 | 406337.7 | 71788.3 | 14760 | 462398.7 | 41301 | 85 | 79 | 0 | 0 | -6
LAREDO | 0018-05-104 | WEBB | IH 35 | 2024-09-13 | 14045933.92 | 1048045.63 | 0 | 14084633.62 | 38699.7 | 245 | 235 | 0 | 0 | -10
AUSTIN | 0273-04-048 | WILLIAMSON | US 183 | 2024-09-11 | 5760579.27 | -155804.07 | 0 | 5427306.05 | -333273.22 | 234 | 382 | 99 | 0 | 148
AUSTIN | 0150-04-048 | LLANO | SH 29 | 2024-09-10 | 5448731.92 | 1429767.8 | 0 | 7550747.28 | 2102015.36 | 221 | 281 | 60 | 0 | 60
AMARILLO | 0042-03-044 | ARMSTRONG | US 287 | 2024-09-09 | 2102432.75 | 53509.2 | 0 | 2137603.46 | 35170.71 | 104 | 147 | 0 | 0 | 43
AUSTIN | 2100-01-060 | TRAVIS | RM 2222 | 2024-09-09 | 15507841.22 | 2397655.87 | 114232.23 | 17475155.04 | 1853081.59 | 295 | 366 | 71 | 0 | 71
WACO | 0014-06-045 | HILL | SH 81 | 2024-09-09 | 1619000 | 179258.15 | 0 | 1733204.28 | 114204.28 | 134 | 169 | 36 | 0 | 35
YOAKUM | 3173-01-004 | WHARTON | FM 3086 | 2024-09-09 | 3597289.16 | -117688 | 0 | 3447687.98 | -149601.18 | 120 | 156 | 16 | 0 | 36
HOUSTON | 1257-01-052 | FORT BEND | FM 1092 | 2024-09-07 | 4238148.2 | 201880.79 | 0 | 4839461.23 | 601313.03 | 103 | 103 | 0 | 0 | 0
ABILENE | 0908-21-039 | MITCHELL | CR | 2024-09-05 | 711084 | 0 | 0 | 711462.4 | 378.4 | 84 | 84 | 0 | 0 | 0
SAN ANGELO | 0907-24-054 | TOM GREEN | Various | 2024-09-05 | 1415245.12 | 3346.71 | 0 | 1453701.56 | 38456.44 | 63 | 59 | 0 | 0 | -4
YOAKUM | 0446-02-037 | COLORADO | UA 90 | 2024-09-05 | 3351389.94 | 23531.19 | 0 | 3364858.2 | 13468.26 | 191 | 202 | 0 | 0 | 11
YOAKUM | 0913-20-093 | AUSTIN | CR | 2024-09-05 | 1258243.84 | 16329 | 0 | 1267589.34 | 9345.5 | 172 | 156 | 0 | 0 | -16
YOAKUM | 0913-28-082 | FAYETTE | CR | 2024-09-05 | 1338296.75 | 0 | 0 | 1335409.45 | -2887.3 | 135 | 115 | 0 | 0 | -20
YOAKUM | 1302-02-013 | WHARTON | FM 647 | 2024-09-05 | 1267616.62 | 0 | 0 | 756731.62 | -510885 | 97 | 411 | 70 | 0 | 314
AMARILLO | 0169-03-039 | CARSON | US 60 | 2024-09-04 | 3699105.45 | 16867.91 | 0 | 3789077.89 | 89972.44 | 91 | 83 | 0 | 0 | -8
SAN ANTONIO | 0072-05-090 | KENDALL | IH 10 | 2024-09-04 | 5699777.56 | 1330293.68 | 0 | 6282530.92 | 582753.36 | 104 | 101 | 0 | 0 | -3
WACO | 0055-15-072 | MCLENNAN | US 84 | 2024-09-04 | 9930693.78 | 316574.78 | 0 | 10889532.96 | 958839.18 | 240 | 303 | 63 | 0 | 63
LUFKIN | 0597-04-005 | SAN AUGUSTINE | FM 2923 | 2024-09-03 | 1771724.54 | 1000 | 0 | 1793350.64 | 21626.1 | 79 | 61 | 0 | 0 | -18
PARIS | 0901-19-219 | GRAYSON | Various | 2024-09-01 | 744555 | 0 | 0 | 656390 | -88165 | 138 | 138 | 0 | 0 | 0
PARIS | 1452-01-018 | LAMAR | FM 1507 | 2024-09-01 | 1480238.25 | 0 | 0 | 1447773.03 | -32465.22 | 160 | 153 | 0 | 0 | -7