## Sheet1
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED
DISTRICT | COUNTY | HIGHWAY | C C S J | DATE FINAL ESTIMATE PAID | CONTRACT AWARD | CHANGE ORDERS | AMOUNT PAID | UNDER/OVER BUDGET | CONTRACT DAYS | DAYS ADDED | DAYS USED | UNDER/OVER SCHEDULE
ABILENE | CALLAHAN | IH 20 | 701056 | 2017-12-20 | 8458527.23 | 86923.5 | 8204413.33 | -341037.4 | 70 | 0 | 64 | -6
ABILENE | CALLAHAN | SH 36 | 18102029 | 2017-09-15 | 5388974.28 | 411912.32 | 6048340.61 | 247454.01 | 129 | 20 | 149 | 0
ABILENE | CALLAHAN | US 283 | 43702016 | 2018-01-22 | 1793913.92 | 115671.72 | 1941234.47 | 31648.83 | 84 | 8 | 95 | 3
ABILENE | HOWARD | FM 821 | 115602021 | 2018-01-05 | 9379399.55 | -21331.24 | 9357539.99 | -528.32 | 256 | 0 | 348 | 92
ABILENE | HOWARD | FM 846 | 187202017 | 2018-01-05 | 9519743.52 | -174016.92 | 9432329.3 | 86602.7 | 311 | 0 | 292 | -19
ABILENE | HOWARD | FM 2230 | 214901009 | 2018-02-20 | 6178220.66 | 586699.81 | 6591136.86 | -173783.61 | 331 | 71 | 374 | -28
ABILENE | JONES | US 180 | 29604019 | 2017-10-26 | 2950708.42 | -174531.04 | 2603057.73 | -173119.65 | 94 | 0 | 106 | 12
ABILENE | JONES | FM 3116 | 272102013 | 2017-09-20 | 1045832.5 | 0 | 1035930.81 | -9901.69 | 93 | 0 | 102 | 9
ABILENE | MITCHELL | BI 20-J | 512013 | 2018-01-04 | 2838058.33 | -154403.42 | 2576738.96 | -106915.95 | 56 | 0 | 77 | 21
ABILENE | SCURRY | FM 1610 | 153102012 | 2018-02-15 | 5397845.79 | -13509.84 | 5314089.75 | -70246.2 | 220 | 5 | 261 | 36
ABILENE | TAYLOR | IH 20 | 604079 | 2018-01-31 | 1158772.03 | 0 | 1068971.42 | -89800.61 | 80 | 0 | 78 | -2
ABILENE | TAYLOR | SH 351 | 1101030 | 2017-11-29 | 6920469.81 | 132546.68 | 7586524.32 | 533507.83 | 270 | 77 | 326 | -21
ABILENE | TAYLOR | US 83 | 3401129 | 2018-01-02 | 2346055.5 | 1853.23 | 2385208.18 | 37299.45 | 87 | 0 | 57 | -30
ABILENE | TAYLOR | FM 1235 | 66303027 | 2017-12-07 | 4552099.47 | -404822.41 | 4297421.17 | 150144.11 | 280 | -23 | 263 | 6
AMARILLO | CARSON | SH 207 | 35602043 | 2017-10-05 | 8607481.82 | 29097.95 | 8722069.47 | 85489.7 | 110 | 9 | 145 | 26
AMARILLO | DEAF SMITH | US 385 | 22604025 | 2017-12-06 | 8318208.23 | 0.03 | 8992604.4 | 674396.14 | 77 | 2 | 102 | 23
AMARILLO | POTTER | CR | 90402037 | 2018-02-01 | 1220116.75 | 144331.28 | 1372642.83 | 8194.8 | 56 | 27 | 95 | 12
AMARILLO | ROBERTS | SH 70 | 49004037 | 2018-02-13 | 5139086.58 | 172096.25 | 5222476.33 | -88706.5 | 197 | 40 | 341 | 104
ATLANTA | BOWIE | FM 991 | 1019011 | 2017-11-30 | 3968760.1 | 0 | 4234892.75 | 266132.65 | 60 | 0 | 64 | 4
ATLANTA | BOWIE | US 59 | 21701034 | 2018-01-11 | 1377443.86 | -40574.63 | 1369446.61 | 32577.38 | 40 | 0 | 44 | 4
ATLANTA | BOWIE | FM 3378 | 252602010 | 2018-01-26 | 897910.6 | -4543.15 | 881212.22 | -12155.23 | 75 | 2 | 73 | -4
ATLANTA | HARRISON | US 59 | 6207086 | 2017-12-21 | 5747430.1 | 574288.92 | 6352296.11 | 30577.09 | 195 | 20 | 258 | 43
ATLANTA | HARRISON | US 59 | 6207087 | 2017-10-05 | 3413079.11 | 270172.63 | 4272548.2 | 589296.46 | 55 | 13 | 75 | 7
ATLANTA | HARRISON | US 59 | 6301091 | 2017-11-30 | 256403 | 0 | 257873.35 | 1470.35 | 140 | 0 | 77 | -63
ATLANTA | HARRISON | FM 1186 | 6301092 | 2017-12-28 | 814705.32 | 0 | 792335.76 | -22369.56 | 90 | 0 | 104 | 14
ATLANTA | HARRISON | US 59 | 6309015 | 2017-09-06 | 4850066.35 | 83177.69 | 4690353.74 | -242890.3 | 160 | 0 | 145 | -15
ATLANTA | HARRISON | US 80 | 9609076 | 2017-10-05 | 1295848.08 | 33760 | 1321524.43 | -8083.65 | 48 | 0 | 33 | -15
ATLANTA | HARRISON | IH 20 | 49508086 | 2017-10-24 | 4874784.26 | 15899.13 | 4924961 | 34277.61 | 225 | 0 | 374 | 149
ATLANTA | HARRISON | FM 450 | 84306019 | 2017-12-13 | 474176.69 | 10720.27 | 487413.22 | 2516.26 | 68 | 0 | 47 | -21
ATLANTA | HARRISON | FM 2625 | 328301014 | 2018-01-18 | 4532166.52 | -14127.74 | 4497252.77 | -20786.01 | 225 | 0 | 165 | -60
ATLANTA | PANOLA | US 59 | 6303060 | 2017-12-29 | 524435.7 | 0 | 501818.32 | -22617.38 | 190 | 0 | 72 | -118
ATLANTA | PANOLA | BU 79-G | 24602049 | 2018-01-18 | 876859.3 | 0 | 899214.51 | 22355.21 | 39 | 0 | 31 | -8
ATLANTA | PANOLA | FM 31 | 64002029 | 2017-12-12 | 3629436.31 | 2058 | 3490971.81 | -140522.5 | 176 | 0 | 174 | -2
ATLANTA | PANOLA | FM 123 | 73101051 | 2017-12-21 | 3958704.28 | 54573.09 | 4054374.49 | 41097.12 | 129 | 0 | 159 | 30
ATLANTA | TITUS | US 67 | 1006040 | 2017-10-24 | 6550235.52 | -378727.25 | 5941054.18 | -230454.09 | 50 | 0 | 63 | 13
ATLANTA | TITUS | US 67 | 1006041 | 2017-12-28 | 1861333.54 | 0 | 1761314.1 | -100019.44 | 129 | 0 | 128 | -1
AUSTIN | BASTROP | US 290 | 11404068 | 2017-12-21 | 2027917 | 69879.3 | 1890806.14 | -206990.16 | 120 | 0 | 118 | -2
AUSTIN | BASTROP | SH 21 | 47201042 | 2017-11-13 | 286003.25 | 932.8 | 298827.78 | 11891.73 | 30 | 0 | 28 | -2
AUSTIN | BASTROP | CS | 91418091 | 2017-09-21 | 529317.55 | 0 | 518173.55 | -11144 | 95 | 0 | 90 | -5
AUSTIN | BASTROP | FM 696 | 107301020 | 2017-09-19 | 2191679 | 67327.07 | 2263323.59 | 4317.52 | 202 | 64 | 266 | 0
AUSTIN | BASTROP | FM 1209 | 217601008 | 2017-11-10 | 1990497.91 | 19524.44 | 2061202.59 | 51180.24 | 124 | 0 | 117 | -7
AUSTIN | BASTROP | FM 2571 | 268601012 | 2018-02-02 | 1637667.96 | -174347.93 | 1481076.3 | 17756.27 | 43 | 0 | 42 | -1
AUSTIN | BLANCO | US 281 | 25203051 | 2018-01-12 | 896922.59 | 0 | 915357.38 | 18434.79 | 57 | 0 | 66 | 9
AUSTIN | BLANCO | RM 2766 | 267701009 | 2018-02-08 | 4294899.97 | 976977.99 | 5267808.96 | -4069 | 184 | 104 | 306 | 18
AUSTIN | BURNET | US 281 | 25107025 | 2018-01-23 | 3585893.33 | 151938.3 | 3531309.72 | -206521.91 | 58 | 15 | 51 | -22
AUSTIN | BURNET | US 183 | 27302023 | 2017-12-22 | 2450973.55 | 17169.4 | 2537906.89 | 69763.94 | 161 | 0 | 174 | 13
AUSTIN | BURNET | US 183 | 27302026 | 2018-02-08 | 2446345.7 | -81148.52 | 2591834.88 | 226637.7 | 49 | 0 | 39 | -10
AUSTIN | BURNET | RM 1431 | 137804048 | 2018-01-18 | 1437078.59 | -891.51 | 1412935.08 | -23252 | 53 | 0 | 41 | -12
AUSTIN | BURNET | RM 1431 | 137804050 | 2018-01-23 | 790288.76 | 174510.09 | 1085560.19 | 120761.34 | 19 | 10 | 21 | -8
AUSTIN | BURNET | RM 2341 | 220601015 | 2017-12-20 | 3547716.58 | -90891.3 | 3431340.2 | -25485.08 | 187 | 0 | 198 | 11
AUSTIN | CALDWELL | US 183 | 15203056 | 2018-01-29 | 2746129.86 | 47304.93 | 2621939.5 | -171495.29 | 213 | 64 | 355 | 78
AUSTIN | CALDWELL | SH 142 | 38401021 | 2017-10-11 | 2587289.35 | 631 | 2543704.6 | -44215.75 | 45 | 0 | 45 | 0
AUSTIN | CALDWELL | SH 21 | 47104029 | 2017-11-03 | 2356387.83 | 20261.25 | 2302379.19 | -74269.89 | 36 | 0 | 77 | 41
AUSTIN | GILLESPIE | SH 16 | 29003029 | 2017-12-27 | 2194472.98 | 0 | 2178372.94 | -16100.04 | 59 | 0 | 32 | -27
AUSTIN | GILLESPIE | SH 16 | 29101049 | 2018-01-02 | 12994506.11 | -466570.27 | 12487014.38 | -40921.46 | 333 | 58 | 368 | -23
AUSTIN | HAYS | IH 35 | 1602138 | 2017-11-01 | 1477885 | -145212 | 1243417 | -89256 | 101 | 0 | 203 | 102
AUSTIN | HAYS | RM 12 | 28503057 | 2017-11-09 | 3090648.52 | -33514.37 | 3063491.59 | 6357.44 | 161 | 0 | 167 | 6
AUSTIN | HAYS | RM 12 | 68305012 | 2018-02-26 | 1059478.79 | 200682.3 | 1268444.34 | 8283.25 | 98 | 0 | 76 | -22
AUSTIN | HAYS | FM 2439 | 229301023 | 2017-09-01 | 2961890.51 | 23911.29 | 2915473.48 | -70328.32 | 95 | 30 | 188 | 63
AUSTIN | LEE | FM 448 | 33406026 | 2017-10-04 | 3138496.55 | -230198.62 | 2871091.66 | -37206.27 | 95 | 0 | 91 | -4
AUSTIN | LEE | FM 1624 | 153701016 | 2017-12-06 | 1148468.6 | 2683.86 | 1107315.46 | -43837 | 108 | 0 | 100 | -8
AUSTIN | LEE | FM 1697 | 156402010 | 2018-01-23 | 455922 | 0 | 430788 | -25134 | 57 | 0 | 53 | -4
AUSTIN | MASON | SH 71 | 57701026 | 2017-10-17 | 944570.87 | -41317.83 | 874950.64 | -28302.4 | 108 | 0 | 65 | -43
AUSTIN | TRAVIS | SL 275 | 1511061 | 2018-02-26 | 620866.15 | 12163.73 | 509398.24 | -123631.64 | 195 | 0 | 208 | 13
AUSTIN | TRAVIS | SL 275 | 1511063 | 2018-01-31 | 213085.5 | -5475 | 204485.61 | -3124.89 | 40 | 0 | 43 | 3
AUSTIN | TRAVIS | IH 35 | 1513366 | 2017-09-21 | 1115771.6 | -2611.34 | 1130957.01 | 17796.75 | 224 | 5 | 289 | 60
AUSTIN | TRAVIS | LP 275 | 1601108 | 2017-11-09 | 6316700.21 | 966838.53 | 7503751.31 | 220212.57 | 224 | 183 | 407 | 0
AUSTIN | TRAVIS | US 290 | 11308076 | 2017-10-12 | 6523371.5 | 1785432.94 | 8451258.5 | 142454.06 | 335 | 115 | 407 | -43
AUSTIN | TRAVIS | US 290 | 11308083 | 2017-10-11 | 352286.84 | 73770.23 | 432811.87 | 6754.8 | 19 | 0 | 18 | -1
AUSTIN | TRAVIS | SL 343 | 11309071 | 2017-11-10 | 320046.68 | -10150 | 300218.03 | -9678.65 | 21 | 0 | 19 | -2
AUSTIN | TRAVIS | US 290 | 11313158 | 2017-11-10 | 1364134 | -237645 | 1059172 | -67317 | 60 | 29 | 89 | 0
AUSTIN | TRAVIS | SL 360 | 11313161 | 2017-12-19 | 1169830.75 | 339295.18 | 1924806.92 | 415680.99 | 48 | 26 | 74 | 0
AUSTIN | TRAVIS | US 183 | 15201078 | 2017-12-11 | 432340.5 | 23432.4 | 490546.14 | 34773.24 | 60 | 10 | 72 | 2
AUSTIN | TRAVIS | RM 620 | 68302063 | 2017-11-07 | 1419535.8 | -131647.71 | 1336742.02 | 48853.93 | 58 | 0 | 48 | -10
AUSTIN | TRAVIS | VA | 91400343 | 2018-01-10 | 614705.1 | 0 | 590175.54 | -24529.56 | 132 | 0 | 139 | 7
AUSTIN | TRAVIS | FM 973 | 120003028 | 2017-10-10 | 13848703.79 | 647979.59 | 14670387.62 | 173704.24 | 296 | 54 | 349 | -1
AUSTIN | TRAVIS | RM 1431 | 137801036 | 2018-01-11 | 1136825.4 | 47149 | 1247819.24 | 63844.84 | 99 | 0 | 99 | 0
AUSTIN | TRAVIS | SL 1 | 313601161 | 2017-09-21 | 1080839.66 | 0 | 1015038.93 | -65800.73 | 43 | 0 | 30 | -13
AUSTIN | TRAVIS | FM 734 | 341701028 | 2017-12-21 | 839340.91 | 49445.47 | 911704.04 | 22917.66 | 76 | 0 | 73 | -3
AUSTIN | WILLIAMSON | IH 35 | 1509166 | 2017-09-18 | 5626066.72 | 323906.18 | 6191225.58 | 241252.68 | 231 | 19 | 212 | -38
AUSTIN | WILLIAMSON | US 79 | 20401067 | 2017-10-12 | 265696 | 0 | 254444.07 | -11251.93 | 28 | 4 | 54 | 22
AUSTIN | WILLIAMSON | SH 95 | 32003095 | 2018-02-12 | 861567.42 | 79793.27 | 949311.76 | 7951.07 | 39 | 0 | 39 | 0
AUSTIN | WILLIAMSON | SH 95 | 32101054 | 2018-01-31 | 13427785.21 | 289849.74 | 14589649.01 | 872014.06 | 263 | 0 | 254 | -9
AUSTIN | WILLIAMSON | FM 487 | 120102018 | 2017-12-20 | 7137507.42 | 76238.61 | 7133365.26 | -80380.77 | 263 | 0 | 263 | 0
AUSTIN | WILLIAMSON | FM 487 | 120102021 | 2017-09-01 | 9058441.27 | -20140.48 | 8685673.78 | -352627.01 | 306 | 21 | 327 | 0
AUSTIN | WILLIAMSON | FM 972 | 120201017 | 2018-01-09 | 4156413.83 | 195467.12 | 4644619.59 | 292738.64 | 234 | 0 | 226 | -8
AUSTIN | WILLIAMSON | RM 1431 | 137802039 | 2017-12-20 | 3965954.63 | 311076.44 | 4323983.92 | 46952.85 | 108 | 72 | 175 | -5
BEAUMONT | CHAMBERS | SH 61 | 24203074 | 2018-02-02 | 889007.06 | 25000 | 945160.03 | 31152.97 | 67 | 2 | 69 | 0
BEAUMONT | CHAMBERS | SH 61 | 24203075 | 2018-02-28 | 244900.27 | 0 | 233244.32 | -11655.95 | 31 | 0 | 29 | -2
BEAUMONT | HARDIN | US 69 | 20010079 | 2018-02-23 | 7502185.05 | 499340.43 | 7941926.93 | -59598.55 | 208 | 17 | 219 | -6
BEAUMONT | HARDIN | FM 418 | 20012015 | 2018-01-24 | 134987.65 | 0 | 116818.12 | -18169.53 | 26 | 0 | 10 | -16
BEAUMONT | JASPER | FM 105 | 71001049 | 2018-02-14 | 1012112.48 | 0 | 990368.83 | -21743.65 | 32 | 0 | 21 | -11
BEAUMONT | JASPER | FM 777 | 110901023 | 2017-12-29 | 368813 | 7024 | 339466.1 | -36370.9 | 50 | 2 | 58 | 6
BEAUMONT | JEFFERSON | US 90 | 2806081 | 2018-01-25 | 8722487 | 166109.65 | 8561504.36 | -327092.29 | 45 | 5 | 41 | -9
BEAUMONT | JEFFERSON | US 69 | 20014080 | 2017-12-07 | 3588710.24 | 94913.99 | 3705723.27 | 22099.04 | 206 | 0 | 155 | -51
BEAUMONT | JEFFERSON | SH 73 | 30603123 | 2017-12-21 | 26599824.2 | 1593685.41 | 28461789 | 268279.39 | 614 | 0 | 686 | 72
BEAUMONT | JEFFERSON | CS | 92038254 | 2017-10-02 | 749492.52 | 121635.92 | 891317.99 | 20189.55 | 68 | 25 | 91 | -2
BEAUMONT | JEFFERSON | FM 365 | 93202055 | 2018-01-16 | 400896.15 | 0 | 406114.11 | 5217.96 | 45 | 29 | 74 | 0
BEAUMONT | LIBERTY | US 90 | 2803100 | 2017-12-12 | 2871187.1 | 252002.75 | 3048329.18 | -74860.67 | 152 | 123 | 291 | 16
BEAUMONT | LIBERTY | US 90 | 2803103 | 2017-12-04 | 760550.58 | 0 | 749004.66 | -11545.92 | 80 | 0 | 78 | -2
BEAUMONT | LIBERTY | FM 686 | 106701026 | 2017-12-19 | 1690130.3 | -156198.06 | 1485161.81 | -48770.43 | 84 | 0 | 81 | -3
BEAUMONT | LIBERTY | FM 2830 | 288701012 | 2017-10-13 | 999523.59 | 0 | 991646.9 | -7876.69 | 89 | 0 | 51 | -38
BEAUMONT | NEWTON | SH 87 | 30505044 | 2017-10-20 | 2174628.1 | 25017.2 | 2009989.22 | -189656.08 | 45 | 0 | 37 | -8
BEAUMONT | NEWTON | FM 1012 | 127701015 | 2017-10-30 | 1777740.74 | 80488.39 | 1852718.3 | -5510.83 | 101 | 46 | 202 | 55
BEAUMONT | ORANGE | FM 105 | 88302068 | 2017-09-18 | 2668330.65 | 11900 | 2563541.67 | -116688.98 | 69 | 55 | 121 | -3
BEAUMONT | ORANGE | FM 1130 | 128401072 | 2017-10-02 | 836255.8 | 17973.5 | 855745.7 | 1516.4 | 90 | 3 | 88 | -5
BROWNWOOD | BROWN | US 67 | 5406097 | 2017-11-16 | 3342055.98 | -21633.92 | 3284857.1 | -35564.96 | 68 | 0 | 80 | 12
BROWNWOOD | BROWN | US 183 | 12703031 | 2017-09-08 | 4279334.28 | -62224.23 | 4085009.2 | -132100.85 | 168 | 0 | 248 | 80
BROWNWOOD | BROWN | CS | 92306075 | 2017-10-31 | 427889.98 | -1026 | 427222.98 | 359 | 63 | 8 | 70 | -1
BROWNWOOD | COLEMAN | US 67 | 5404107 | 2018-02-12 | 6367226.55 | 6721.62 | 5916933.1 | -457015.07 | 72 | 0 | 86 | 14
BROWNWOOD | EASTLAND | FM 2214 | 169702019 | 2017-12-11 | 5299577.48 | 479775.77 | 6312427.68 | 533074.43 | 272 | 93 | 459 | 94
BROWNWOOD | EASTLAND | SH 206 | 263801023 | 2017-12-11 | 712723.5 | 94530.6 | 737885.12 | -69368.98 | 43 | 0 | 41 | -2
BROWNWOOD | MC CULLOCH | US 87 | 7102032 | 2017-12-21 | 285999.99 | -85729 | 174265 | -26005.99 | 68 | 0 | 23 | -45
BROWNWOOD | MC CULLOCH | US 190 | 27201031 | 2017-10-27 | 1798595.5 | 0 | 1758794.77 | -39800.73 | 230 | 0 | 227 | -3
BROWNWOOD | MC CULLOCH | SH 71 | 110201041 | 2017-12-15 | 12668777.79 | 476690.52 | 13334855.45 | 189387.14 | 575 | 115 | 684 | -6
BROWNWOOD | SAN SABA | FM 580 | 23114017 | 2017-11-10 | 5387952.96 | 28925 | 5852042.32 | 435164.36 | 474 | 0 | 465 | -9
BROWNWOOD | STEPHENS | US 180 | 1107047 | 2017-09-08 | 4046707.37 | 63936.95 | 4369367.05 | 258722.73 | 175 | 41 | 216 | 0
BRYAN | BRAZOS | US 190 | 4909071 | 2017-10-20 | 737879 | 123424.22 | 862741.98 | 1438.76 | 88 | 20 | 102 | -6
BRYAN | BRAZOS | SH 21 | 11604101 | 2018-01-25 | 1604739.83 | 564972.63 | 2183570.71 | 13858.25 | 35 | 64 | 91 | -8
BRYAN | BRAZOS | FM 2818 | 239901076 | 2017-12-01 | 641000 | 1064.27 | 639054.27 | -3010 | 59 | 0 | 59 | 0
BRYAN | BRAZOS | SH 30 | 244601026 | 2017-12-05 | 1679419 | 8898.93 | 1593687.17 | -94630.76 | 50 | 0 | 44 | -6
BRYAN | BRAZOS | SH 47 | 313802011 | 2017-09-06 | 65138.9 | 158550.43 | 224577.73 | 888.4 | 12 | 7 | 14 | -5
BRYAN | FREESTONE | US 79 | 20506028 | 2017-12-11 | 7487647.25 | 491648.71 | 7949600.24 | -29695.72 | 223 | 9 | 261 | 29
BRYAN | MADISON | FM 247 | 57801029 | 2018-01-30 | 4354851.44 | 56210.19 | 4302714.65 | -108346.98 | 154 | 0 | 156 | 2
BRYAN | MILAM | US 190 | 18503029 | 2017-10-12 | 117701.7 | 0 | 118015.23 | 313.53 | 11 | 0 | 7 | -4
BRYAN | MILAM | US 190 | 18504045 | 2018-02-22 | 3448084.06 | 0 | 3416973.23 | -31110.83 | 82 | 0 | 82 | 0
BRYAN | ROBERTSON | SH 6 | 4906076 | 2017-10-19 | 83985.19 | -1001.54 | 65730.65 | -17253 | 39 | 0 | 35 | -4
CHILDRESS | CHILDRESS | US 62 | 3106032 | 2018-01-16 | 5285892.91 | 187593.01 | 5843035.34 | 369549.42 | 138 | 5 | 123 | -20
CHILDRESS | CHILDRESS | FM 401 | 325901042 | 2018-01-16 | 447421.5 | 0 | 446784 | -637.5 | 68 | 0 | 53 | -15
CHILDRESS | DICKENS | US 82 | 13106053 | 2017-09-15 | 171970.75 | 8145 | 177572.65 | -2543.1 | 32 | 0 | 32 | 0
CHILDRESS | HALL | FM 94 | 70403014 | 2018-01-11 | 6463984.5 | -48529.82 | 6806033.45 | 390578.77 | 240 | 38 | 278 | 0
CHILDRESS | HARDEMAN | US 287 | 4302073 | 2017-12-14 | 4283750.17 | 0 | 4613472.34 | 329722.17 | 91 | 0 | 66 | -25
CHILDRESS | HARDEMAN | SH 6 | 9801038 | 2018-02-15 | 5217313.46 | 148117.84 | 5124121.58 | -241309.72 | 107 | 68 | 172 | -3
CHILDRESS | WHEELER | US 83 | 3008035 | 2018-01-16 | 9811524.16 | 127673.72 | 10207795.9 | 268598.02 | 204 | 28 | 204 | -28
CHILDRESS | WHEELER | FM 592 | 76105013 | 2017-10-13 | 2138189 | -110148.62 | 2009675.02 | -18365.36 | 170 | 14 | 183 | -1
CORPUS CHRISTI | ARANSAS | FM 1069 | 50704041 | 2017-11-28 | 340987.21 | 0 | 317550.18 | -23437.03 | 85 | 0 | 37 | -48
CORPUS CHRISTI | ARANSAS | SH 188 | 260701011 | 2017-12-15 | 1142011.55 | 43752.1 | 1202603.82 | 16840.17 | 51 | 5 | 65 | 9
CORPUS CHRISTI | BEE | SH 202 | 44703039 | 2017-11-10 | 8641470.29 | 16035.84 | 8483677.88 | -173828.25 | 204 | 0 | 219 | 15
CORPUS CHRISTI | BEE | FM 798 | 111701015 | 2018-02-28 | 4270569.91 | 48436.61 | 4407586.01 | 88579.49 | 220 | 0 | 198 | -22
CORPUS CHRISTI | GOLIAD | US 183 | 15504051 | 2017-09-11 | 4784121.15 | -27452.23 | 4614760.67 | -141908.25 | 114 | 18 | 142 | 10
CORPUS CHRISTI | JIM WELLS | US 281 | 25501081 | 2017-09-21 | 1764248.12 | 69079.46 | 1901781.08 | 68453.5 | 36 | 43 | 75 | -4
CORPUS CHRISTI | JIM WELLS | FM 1931 | 169301020 | 2018-01-11 | 3432309.48 | 47976.14 | 3466277.87 | -14007.75 | 99 | 6 | 104 | -1
CORPUS CHRISTI | KARNES | FM 99 | 34806023 | 2018-01-25 | 8219037.3 | 418821.76 | 8577289.38 | -60569.68 | 167 | 122 | 314 | 25
CORPUS CHRISTI | KARNES | SH 239 | 51601015 | 2018-01-23 | 8525937.55 | 1694206.55 | 10503939.28 | 283795.18 | 185 | 104 | 344 | 55
CORPUS CHRISTI | KARNES | SH 239 | 51601016 | 2017-12-20 | 9602591.47 | 128377.66 | 10226108.72 | 495139.59 | 200 | 87 | 287 | 0
CORPUS CHRISTI | KLEBERG | SH 285 | 10206030 | 2018-02-23 | 11286378.44 | 357812.51 | 11994764.9 | 350573.95 | 162 | 134 | 389 | 93
CORPUS CHRISTI | KLEBERG | SH 141 | 38304055 | 2017-10-13 | 783875.25 | 1608.36 | 729724.86 | -55758.75 | 261 | 0 | 178 | -83
CORPUS CHRISTI | LIVE OAK | IH 37 | 7307061 | 2017-11-28 | 12504557.19 | -291508.23 | 12408231.24 | 195182.28 | 119 | 141 | 255 | -5
CORPUS CHRISTI | LIVE OAK | IH 37 | 7307063 | 2017-12-11 | 728162.74 | 5146 | 742166.33 | 8857.59 | 81 | 0 | 45 | -36
CORPUS CHRISTI | LIVE OAK | IH 37 | 7402079 | 2018-02-23 | 5498583.77 | -13905.05 | 5522241.35 | 37562.63 | 82 | 0 | 35 | -47
CORPUS CHRISTI | LIVE OAK | US 281 | 25401141 | 2017-09-28 | 1411480.04 | 31510.63 | 1660628.06 | 217637.39 | 55 | 4 | 58 | -1
CORPUS CHRISTI | NUECES | US 181 | 10106110 | 2017-11-10 | 1496152.32 | 91463.26 | 1574708.47 | -12907.11 | 119 | 70 | 174 | -15
CORPUS CHRISTI | NUECES | VA | 91600082 | 2017-11-20 | 839680 | 16175.97 | 833004.97 | -22851 | 100 | 0 | 68 | -32
CORPUS CHRISTI | SAN PATRICIO | US 77 | 37201096 | 2018-01-25 | 2636291.7 | 5482.26 | 2637811.52 | -3962.44 | 85 | 5 | 73 | -17
DALLAS | COLLIN | US 75 | 4706160 | 2018-01-17 | 682700.6 | 18466.38 | 755330.63 | 54163.65 | 104 | 0 | 66 | -38
DALLAS | COLLIN | FM 455 | 284501019 | 2017-10-31 | 607568.4 | -80371.14 | 504597.85 | -22599.41 | 48 | 3 | 54 | 3
DALLAS | DALLAS | SH 180 | 808075 | 2017-12-19 | 2234365.6 | -459509.98 | 1801591.91 | 26736.29 | 92 | 0 | 31 | -61
DALLAS | DALLAS | SH 310 | 9202122 | 2018-01-12 | 1320321.1 | 67869.62 | 1296693.21 | -91497.51 | 62 | 0 | 82 | 20
DALLAS | DALLAS | SH 310 | 9202123 | 2017-11-15 | 2145801 | 191190.86 | 2353985.04 | 16993.18 | 250 | 0 | 160 | -90
DALLAS | DALLAS | US 80 | 9502113 | 2018-02-23 | 1949706.72 | 0 | 1777332.41 | -172374.31 | 160 | 0 | 380 | 220
DALLAS | DALLAS | US 80 | 9502119 | 2017-10-23 | 3008042.49 | 223388.67 | 3248664.69 | 17233.53 | 124 | 25 | 168 | 19
DALLAS | DALLAS | US 175 | 19702118 | 2018-01-26 | 1511372.54 | 74887.31 | 1288840.61 | -297419.24 | 77 | 6 | 64 | -19
DALLAS | DALLAS | US 67 | 26102076 | 2017-09-29 | 1080056.11 | 10004.61 | 1069267 | -20793.72 | 137 | 10 | 161 | 14
DALLAS | DALLAS | IH 35E | 44202158 | 2017-09-22 | 1285285 | 0 | 1302317.1 | 17032.1 | 134 | 0 | 123 | -11
DALLAS | DALLAS | CS | 91845731 | 2017-11-21 | 3181746.72 | 70002.38 | 3248827.5 | -2921.6 | 247 | 39 | 286 | 0
DALLAS | DALLAS | CS | 91845747 | 2018-01-16 | 15998353.36 | 3282018.17 | 18679964.95 | -600406.58 | 366 | 341 | 706 | -1
DALLAS | DALLAS | CS | 91845761 | 2018-02-16 | 2944434.81 | 307253.9 | 3211831.51 | -39857.2 | 353 | 118 | 478 | 7
DALLAS | DALLAS | IH 30 | 106804154 | 2017-09-29 | 9814841.5 | 475344.81 | 10148882.66 | -141303.65 | 321 | 186 | 574 | 67
DALLAS | DALLAS | IH 20 | 237404077 | 2017-09-29 | 1241391.43 | 5410.9 | 1270507.95 | 23705.62 | 122 | 0 | 114 | -8
DALLAS | DENTON | US 377 | 8106029 | 2017-10-02 | 7501346.55 | -29155.58 | 7367439 | -104751.97 | 264 | 20 | 429 | 145
DALLAS | DENTON | SH 114 | 35302029 | 2017-12-18 | 28612477.14 | -1265696.8 | 26988269.9 | -358510.44 | 569 | 0 | 514 | -55
DALLAS | DENTON | FM 1171 | 131101034 | 2017-11-28 | 45721253.13 | 1522508.63 | 47377406.13 | 133644.37 | 693 | 0 | 630 | -63
DALLAS | DENTON | FM 1385 | 131501025 | 2018-01-23 | 9063184.19 | 472330.66 | 9680526.81 | 145011.96 | 378 | 26 | 356 | -48
DALLAS | DENTON | FM 407 | 178501035 | 2017-11-28 | 498172.5 | -138691.45 | 358680.51 | -800.54 | 150 | 0 | 128 | -22
DALLAS | ELLIS | SH 342 | 4803093 | 2018-02-13 | 11359831.33 | 144126 | 11120490.67 | -383466.66 | 120 | 6 | 125 | -1
DALLAS | ELLIS | FM 66 | 59602038 | 2017-09-01 | 1798061.6 | 31115.8 | 1814649.62 | -14527.78 | 343 | 0 | 297 | -46
DALLAS | ELLIS | CR | 91822141 | 2017-09-01 | 1038508.4 | 2500 | 1026985.12 | -14023.28 | 82 | 4 | 94 | 8
DALLAS | ELLIS | FM 876 | 105102017 | 2018-02-28 | 1721378.55 | 85183.55 | 1677980.46 | -128581.64 | 360 | 0 | 352 | -8
DALLAS | KAUFMAN | US 80 | 9503088 | 2018-02-14 | 9634025.22 | 738392.3 | 9626686.78 | -745730.74 | 281 | 49 | 327 | -3
DALLAS | KAUFMAN | SH 34 | 17303015 | 2017-12-13 | 23009384.97 | 558880.92 | 23241843.03 | -326422.86 | 506 | 5 | 456 | -55
DALLAS | KAUFMAN | US 175 | 19703075 | 2018-02-28 | 4046960.2 | 21862.39 | 3833112.4 | -235710.19 | 76 | 0 | 72 | -4
DALLAS | KAUFMAN | US 175 | 19705056 | 2018-01-18 | 287000 | 0 | 279280.1 | -7719.9 | 60 | 0 | 65 | 5
DALLAS | KAUFMAN | IH 20 | 49501070 | 2017-11-13 | 2582661.45 | 57197.67 | 2452198.9 | -187660.22 | 143 | 1 | 104 | -40
DALLAS | KAUFMAN | FM 148 | 75102023 | 2017-11-15 | 10805279.1 | 1563479.76 | 12133360.55 | -235398.31 | 246 | 141 | 384 | -3
DALLAS | KAUFMAN | FM 1836 | 139701030 | 2018-01-12 | 6141935.92 | 10520.19 | 5548594.7 | -603861.41 | 218 | 0 | 214 | -4
DALLAS | KAUFMAN | FM 1836 | 139701031 | 2018-01-23 | 5943147.3 | 130681.72 | 5267956.25 | -805872.77 | 166 | 22 | 260 | 72
DALLAS | NAVARRO | SH 14 | 9302015 | 2017-11-13 | 6571060.16 | 63626.76 | 6835439.84 | 200752.92 | 378 | 193 | 750 | 179
DALLAS | NAVARRO | SH 22 | 12105050 | 2017-11-21 | 1989594.44 | 232135.93 | 1726010.95 | -495719.42 | 56 | 20 | 64 | -12
DALLAS | ROCKWALL | IH 30 | 912214 | 2018-01-29 | 3485857.41 | 54563.27 | 3500401.42 | -40019.26 | 155 | 0 | 165 | 10
DALLAS | ROCKWALL | FM 3549 | 101501022 | 2017-10-19 | 2576274.6 | 448424.73 | 2991711.37 | -32987.96 | 165 | 31 | 195 | -1
DALLAS | ROCKWALL | FM 1138 | 101603013 | 2018-02-05 | 1956520.15 | 13185.46 | 1869221.98 | -100483.63 | 70 | 0 | 101 | 31
EL PASO | EL PASO | CS | 92406311 | 2017-10-25 | 15520544.4 | 642345.22 | 16373416.99 | 210527.37 | 280 | 26 | 306 | 0
EL PASO | EL PASO | VA | 92406491 | 2018-02-23 | 324898.83 | -17258.74 | 307640.09 | 0 | 120 | 0 | 76 | -44
EL PASO | EL PASO | CS | 92406520 | 2017-11-29 | 373864.65 | 62672.87 | 420013.87 | -16523.65 | 150 | 0 | 110 | -40
EL PASO | EL PASO | IH 10 | 212101092 | 2017-12-12 | 12757146.91 | 994500.48 | 14226711.23 | 475063.84 | 206 | 60 | 264 | -2
EL PASO | EL PASO | SL 375 | 255201054 | 2018-02-27 | 3200881.7 | 219028.36 | 3445898.48 | 25988.42 | 252 | 0 | 252 | 0
EL PASO | EL PASO | SS 6 | 357201003 | 2017-09-27 | 242881.39 | 24303.8 | 270266.19 | 3081 | 40 | 0 | 40 | 0
EL PASO | EL PASO | SS 6 | 357201004 | 2017-10-31 | 1734404.3 | 116144.43 | 2077637.3 | 227088.57 | 80 | 40 | 119 | -1
EL PASO | EL PASO | SS 6 | 357201005 | 2017-09-28 | 198745.08 | 15661.09 | 214406.17 | 2.5466e-11 | 40 | 0 | 40 | 0
EL PASO | HUDSPETH | RM 1111 | 128202018 | 2017-09-29 | 1291694 | 14825.93 | 1300151.88 | -6368.05 | 160 | 0 | 155 | -5
EL PASO | HUDSPETH | RM 1111 | 128202025 | 2017-12-22 | 4749629.99 | 9251.9 | 4718665.95 | -40215.94 | 60 | 0 | 30 | -30
EL PASO | JEFF DAVIS | SH 166 | 41503021 | 2018-01-31 | 188280 | 3032 | 189312 | -2000 | 40 | 0 | 40 | 0
FORT WORTH | ERATH | US 67 | 7908003 | 2018-02-15 | 12608803.66 | 35213.06 | 13112891.01 | 468874.29 | 380 | 108 | 466 | -22
FORT WORTH | ERATH | SH 6 | 25801028 | 2017-09-13 | 6192975.12 | 490913.09 | 6021423.09 | -662465.12 | 272 | 26 | 215 | -83
FORT WORTH | ERATH | FM 914 | 55003024 | 2017-09-14 | 3426804.42 | 113188.14 | 3472150.8 | -67841.76 | 215 | 0 | 149 | -66
FORT WORTH | JACK | US 281 | 24907069 | 2017-10-12 | 237243.3 | -3675 | 231762.68 | -1805.62 | 64 | 0 | 64 | 0
FORT WORTH | JACK | FM 1191 | 133303018 | 2018-02-13 | 5404940.22 | 232295.26 | 5665953.57 | 28718.09 | 230 | 15 | 266 | 21
FORT WORTH | JOHNSON | US 67 | 26001056 | 2017-10-26 | 56819.85 | 150 | 55241.37 | -1728.48 | 20 | 0 | 8 | -12
FORT WORTH | PALO PINTO | CR | 90239030 | 2017-10-26 | 410120.2 | 0 | 404310.15 | -5810.05 | 128 | 0 | 85 | -43
FORT WORTH | PARKER | FM 3325 | 351601015 | 2017-09-13 | 3283284.2 | 154316.86 | 3467617.59 | 30016.53 | 256 | 125 | 381 | 0
FORT WORTH | TARRANT | IH 820 | 813229 | 2017-10-02 | 675364.7 | 841818.72 | 1627227.58 | 110044.16 | 76 | 18 | 94 | 0
FORT WORTH | TARRANT | SH 183 | 9401030 | 2018-02-26 | 10591980.89 | 1321513.71 | 11928207.38 | 14712.78 | 524 | 257 | 781 | 0
FORT WORTH | TARRANT | SH 114 | 35303095 | 2018-01-18 | 410000 | 23795.4 | 430545.4 | -3250 | 85 | 28 | 113 | 0
FORT WORTH | TARRANT | FM 157 | 74704065 | 2017-09-11 | 5294353.95 | 2341895.5 | 8065430.22 | 429180.77 | 281 | 94 | 375 | 0
FORT WORTH | TARRANT | VA | 90200134 | 2018-02-13 | 476055.25 | 220331.33 | 1006738.85 | 310352.27 | 128 | 10 | 281 | 143
FORT WORTH | TARRANT | VA | 90200138 | 2017-09-06 | 749479.32 | 2756.55 | 735448.17 | -16787.7 | 60 | 11 | 68 | -3
FORT WORTH | TARRANT | VA | 90248058 | 2017-09-05 | 1966433.15 | -240250.78 | 1524237.02 | -201945.35 | 110 | 16 | 198 | 72
FORT WORTH | TARRANT | VA | 90248844 | 2017-09-05 | 1813396.74 | 14786.36 | 1660361.96 | -167821.14 | 216 | 298 | 514 | 0
FORT WORTH | WISE | US 380 | 13407073 | 2018-02-09 | 241382.82 | 0 | 239022.82 | -2360 | 107 | 0 | 35 | -72
FORT WORTH | WISE | FM 51 | 31203030 | 2017-09-06 | 5354817.23 | -1859472 | 3980459.84 | 485114.61 | 128 | 0 | 99 | -29
FORT WORTH | WISE | FM 2123 | 160602019 | 2018-02-14 | 2779919.35 | 115858.08 | 2762023.91 | -133753.52 | 190 | 0 | 190 | 0
HOUSTON | BRAZORIA | CS | 91231203 | 2017-09-19 | 2748072 | 209763.22 | 2960627.59 | 2792.37 | 270 | 35 | 305 | 0
HOUSTON | BRAZORIA | CR | 91231224 | 2017-11-17 | 14518735.55 | 3012174.8 | 14792334.86 | -2738575.49 | 365 | 195 | 524 | -36
HOUSTON | BRAZORIA | CR | 91231265 | 2017-12-12 | 448817.82 | 32174.14 | 450411.85 | -30580.11 | 70 | 0 | 98 | 28
HOUSTON | BRAZORIA | CS | 91231270 | 2017-09-19 | 4837804.77 | 471140.09 | 5312902.07 | 3957.21 | 300 | 56 | 344 | -12
HOUSTON | BRAZORIA | CR | 91231294 | 2017-11-08 | 12154201.39 | 519364.19 | 12818674.88 | 145109.3 | 357 | 5 | 333 | -29
HOUSTON | BRAZORIA | FM 518 | 97602091 | 2017-12-13 | 5218685.97 | 50722.08 | 5445638.02 | 176229.97 | 122 | 0 | 122 | 0
HOUSTON | BRAZORIA | FM 523 | 100301091 | 2017-09-13 | 7475838.93 | 336477.74 | 8083615.54 | 271298.87 | 112 | 12 | 124 | 0
HOUSTON | FORT BEND | US 90A | 2706057 | 2017-11-06 | 741888.35 | 82329.52 | 940730.95 | 116513.08 | 26 | 11 | 45 | 8
HOUSTON | FORT BEND | CS | 91234182 | 2017-10-24 | 6588849.4 | 61347.42 | 6627714.72 | -22482.1 | 245 | 0 | 178 | -67
HOUSTON | GALVESTON | SH 87 | 5104063 | 2017-11-10 | 699482.62 | 76894.59 | 880510.29 | 104133.08 | 139 | 0 | 92 | -47
HOUSTON | GALVESTON | SS 342 | 5108017 | 2018-02-21 | 1738923.02 | 383548.37 | 2222570.23 | 100098.84 | 45 | 0 | 36 | -9
HOUSTON | GALVESTON | SH 6 | 19204104 | 2017-11-15 | 3198543.72 | 318640.42 | 3723621.12 | 206436.98 | 45 | 3 | 44 | -4
HOUSTON | GALVESTON | IH 45 | 50004126 | 2018-02-16 | 4689018.6 | 1233497.15 | 5805983.46 | -116532.29 | 60 | 19 | 87 | 8
HOUSTON | GALVESTON | FM 519 | 62801022 | 2017-09-29 | 3878490.98 | -192652.46 | 3685579.54 | -258.98 | 165 | 0 | 83 | -82
HOUSTON | GALVESTON | FM 1765 | 68601046 | 2017-11-17 | 481773.82 | 52023.16 | 516930.07 | -16866.91 | 45 | 0 | 43 | -2
HOUSTON | GALVESTON | FM 517 | 97802069 | 2017-11-14 | 246122.55 | 12613.52 | 258123.4 | -612.67 | 70 | 0 | 45 | -25
HOUSTON | GALVESTON | FM 517 | 97802076 | 2017-11-10 | 617038.32 | -51531.66 | 573037.66 | 7531 | 60 | 0 | 33 | -27
HOUSTON | GALVESTON | FM 517 | 100202019 | 2017-11-09 | 3082200.72 | 341525.13 | 3534845.66 | 111119.81 | 75 | 0 | 68 | -7
HOUSTON | HARRIS | US 59 | 2713190 | 2017-10-23 | 18777770 | 1195250.25 | 20569519.91 | 596499.66 | 478 | 2 | 480 | 0
HOUSTON | HARRIS | US 290 | 5008091 | 2017-12-13 | 446813.33 | 122614.29 | 605076.05 | 35648.43 | 108 | 0 | 96 | -12
HOUSTON | HARRIS | IH 45 | 11005119 | 2017-12-14 | 2603483.83 | 559789.93 | 3519662.03 | 356388.27 | 89 | 56 | 129 | -16
HOUSTON | HARRIS | IH 45 | 11006136 | 2018-01-23 | 279667.05 | 7312.16 | 315760.18 | 28780.97 | 60 | 0 | 56 | -4
HOUSTON | HARRIS | IH 10 | 27107242 | 2017-09-19 | 48579333.53 | 5703272.91 | 58287332.17 | 4004725.73 | 777 | 184 | 917 | -44
HOUSTON | HARRIS | IH 10 | 27107292 | 2017-12-01 | 3594471.43 | 571671.63 | 4123106.05 | -43037.01 | 156 | 0 | 156 | 0
HOUSTON | HARRIS | IH 610 | 27116134 | 2017-12-07 | 699002 | 12491.84 | 734453.82 | 22959.98 | 123 | 19 | 145 | 3
HOUSTON | HARRIS | IH 45 | 50003571 | 2017-12-11 | 3594528.4 | 2909733.01 | 6694748.31 | 190486.9 | 195 | 0 | 147 | -48
HOUSTON | HARRIS | IH 45 | 50003577 | 2018-02-01 | 24847758.17 | 694227.56 | 25623564.26 | 81578.53 | 449 | 41 | 490 | 0
HOUSTON | HARRIS | SH 225 | 50201209 | 2017-09-12 | 229926.4 | 0 | 233310.26 | 3383.86 | 50 | 0 | 32 | -18
HOUSTON | HARRIS | SH 225 | 50201211 | 2017-12-19 | 684681.9 | 0 | 741165.93 | 56484.03 | 84 | 0 | 97 | 13
HOUSTON | HARRIS | IH 10 | 50801341 | 2018-01-19 | 1482325.53 | 0 | 1511119.46 | 28793.93 | 119 | 0 | 105 | -14
HOUSTON | HARRIS | IH 10 | 50801350 | 2017-09-14 | 428325.12 | 82967.59 | 492962.51 | -18330.2 | 108 | 0 | 70 | -38
HOUSTON | HARRIS | SS 330 | 50807286 | 2018-01-31 | 2251558.83 | 269254.8 | 2692010.28 | 171196.65 | 52 | 60 | 100 | -12
HOUSTON | HARRIS | VA | 91200424 | 2017-12-21 | 2697458.33 | -94765.8 | 2423628.89 | -179063.64 | 228 | 0 | 275 | 47
HOUSTON | HARRIS | CS | 91270067 | 2018-02-05 | 582538.5 | 0 | 572570.98 | -9967.52 | 45 | 15 | 60 | 0
HOUSTON | HARRIS | CS | 91270068 | 2017-09-28 | 499113.91 | 67438.9 | 470481.51 | -96071.3 | 60 | 25 | 167 | 82
HOUSTON | HARRIS | VA | 91270085 | 2018-02-21 | 810065.52 | 0 | 809934.24 | -131.28 | 90 | 0 | 83 | -7
HOUSTON | HARRIS | VA | 91270094 | 2017-12-07 | 1698653.4 | 1628671.75 | 3890808.88 | 563483.73 | 304 | 16 | 292 | -28
HOUSTON | HARRIS | VA | 91271631 | 2017-11-17 | 5688316.22 | 1417991.28 | 6948572.09 | -157735.41 | 368 | 0 | 362 | -6
HOUSTON | HARRIS | CS | 91272063 | 2017-12-15 | 1096120.32 | 82376.25 | 1171585.71 | -6910.86 | 150 | 35 | 185 | 0
HOUSTON | HARRIS | CS | 91272230 | 2017-09-26 | 2825133.25 | 332030.36 | 3327370.16 | 170206.55 | 401 | 0 | 242 | -159
HOUSTON | HARRIS | CS | 91272285 | 2017-11-28 | 548724.81 | 1819.22 | 497277.05 | -53266.98 | 90 | 0 | 196 | 106
HOUSTON | HARRIS | FM 529 | 100601059 | 2017-09-21 | 7690213.53 | 696173.73 | 8449345.44 | 62958.18 | 322 | 28 | 350 | 0
HOUSTON | HARRIS | FM 529 | 100601072 | 2018-02-26 | 92050.2 | 0 | 95138.37 | 3088.17 | 30 | 0 | 14 | -16
HOUSTON | HARRIS | FM 1093 | 125804060 | 2017-09-12 | 493967.08 | -57147 | 586654.86 | 149834.78 | 79 | 0 | 75 | -4
HOUSTON | HARRIS | FM 1960 | 168503096 | 2017-10-25 | 191207.77 | 76766.5 | 231971.76 | -36002.51 | 42 | 0 | 30 | -12
HOUSTON | HARRIS | FM 2920 | 294101024 | 2018-02-01 | 3817766.77 | 63790.29 | 4198598.09 | 317041.03 | 70 | 0 | 70 | 0
HOUSTON | HARRIS | FM 2920 | 294102050 | 2017-09-20 | 2999793.89 | 11558.22 | 3081227.87 | 69875.76 | 75 | 6 | 81 | 0
HOUSTON | HARRIS | FM 270 | 331201008 | 2017-12-07 | 3845442.26 | 59378.15 | 3979634.3 | 74813.89 | 225 | 0 | 225 | 0
HOUSTON | MONTGOMERY | FM 1485 | 106203051 | 2018-02-22 | 978908.2 | -25830 | 1064737.86 | 111659.66 | 91 | 0 | 82 | -9
HOUSTON | MONTGOMERY | FM 1097 | 125901041 | 2017-09-28 | 238826.4 | 0 | 224085.22 | -14741.18 | 22 | 0 | 22 | 0
HOUSTON | MONTGOMERY | FM 1314 | 198601044 | 2017-10-25 | 1385318.81 | 28962.78 | 1406626.27 | -7655.32 | 43 | 1 | 44 | 0
HOUSTON | WALLER | US 290 | 11411076 | 2018-01-17 | 181056.63 | 33925.25 | 246012.26 | 31030.38 | 23 | 0 | 16 | -7
HOUSTON | WALLER | IH 10 | 27104091 | 2018-02-14 | 4962242.32 | 211476 | 5431472.75 | 257754.43 | 90 | 27 | 112 | -5
LAREDO | DUVAL | SH 44 | 23706043 | 2017-09-11 | 6984698.92 | -41943.32 | 6738628.57 | -204127.03 | 128 | 0 | 117 | -11
LAREDO | DUVAL | SH 339 | 62301022 | 2017-11-06 | 1222988.25 | -1211.04 | 1276875.45 | 55098.24 | 94 | 0 | 46 | -48
LAREDO | LA SALLE | FM 468 | 154502021 | 2017-10-16 | 9571743.1 | 100872.03 | 9585232.78 | -87382.35 | 223 | 20 | 239 | -4
LAREDO | MAVERICK | US 57 | 27602028 | 2017-11-16 | 1770045.27 | 32930.77 | 1979126.39 | 176150.35 | 145 | 0 | 81 | -64
LAREDO | MAVERICK | US 277 | 30001091 | 2017-11-13 | 307234.04 | -809.98 | 283379.12 | -23044.94 | 51 | 0 | 34 | -17
LAREDO | WEBB | US 83 | 8601084 | 2018-01-18 | 4395787.29 | -166931.38 | 4393655.88 | 164799.97 | 75 | 0 | 72 | -3
LAREDO | WEBB | SH 44 | 23703032 | 2018-01-16 | 12273762.93 | 386900.94 | 11312097.5 | -1348566.37 | 228 | 90 | 339 | 21
LAREDO | WEBB | FM 1472 | 215004067 | 2018-02-16 | 4677325.89 | 262644.44 | 4662851.21 | -277119.12 | 136 | 0 | 136 | 0
LUBBOCK | BAILEY | US 70 | 5202035 | 2018-01-18 | 12311087.55 | 501984.14 | 12808018.44 | -5053.25 | 68 | 0 | 62 | -6
LUBBOCK | CROSBY | FM 651 | 80602021 | 2018-01-17 | 1189744.5 | 21641.46 | 973518.93 | -237867.03 | 102 | 26 | 128 | 0
LUBBOCK | DAWSON | SH 349 | 38006015 | 2018-01-30 | 18313514.73 | 1122296.23 | 19297424.91 | -138386.05 | 339 | 164 | 533 | 30
LUBBOCK | DAWSON | FM 2051 | 125502007 | 2018-01-23 | 553859.57 | 8674.97 | 535832.25 | -26702.29 | 45 | 5 | 57 | 7
LUBBOCK | FLOYD | SH 207 | 45308017 | 2017-12-29 | 6982818.62 | 24270.28 | 6658401.84 | -348687.06 | 242 | 0 | 240 | -2
LUBBOCK | GARZA | US 84 | 5304042 | 2018-02-26 | 2405439.7 | -39699.7 | 2163443.87 | -202296.13 | 51 | 23 | 87 | 13
LUBBOCK | HOCKLEY | US 385 | 22705020 | 2018-02-14 | 18382007.77 | 2319501.12 | 20554951.87 | -146557.02 | 272 | 60 | 366 | 34
LUBBOCK | HOCKLEY | US 385 | 22705021 | 2017-11-16 | 1157336.3 | -2608.76 | 1172431.79 | 17704.25 | 48 | 0 | 133 | 85
LUBBOCK | LAMB | US 84 | 5204047 | 2018-01-18 | 15470250.46 | 0 | 15061948.97 | -408301.49 | 68 | 0 | 57 | -11
LUBBOCK | LUBBOCK | US 84 | 5318042 | 2018-02-14 | 532293.75 | 0 | 514376.65 | -17917.1 | 75 | 0 | 75 | 0
LUBBOCK | LUBBOCK | SL 289 | 78301099 | 2018-02-13 | 7588838.6 | 0 | 6719653.91 | -869184.69 | 85 | 0 | 100 | 15
LUBBOCK | LUBBOCK | VA | 90500091 | 2017-10-11 | 431447.62 | 0 | 428732.72 | -2714.9 | 51 | 0 | 46 | -5
LUBBOCK | LUBBOCK | CS | 90506089 | 2018-02-26 | 874627.01 | 54749.32 | 830301.54 | -99074.79 | 85 | 0 | 74 | -11
LUBBOCK | LUBBOCK | CS | 90506110 | 2018-02-27 | 93214.4 | 0 | 103421.14 | 10206.74 | 25 | 0 | 19 | -6
LUBBOCK | LYNN | US 87 | 6802047 | 2017-11-16 | 13165349.95 | 115222.13 | 13980035.72 | 699463.64 | 136 | 19 | 139 | -16
LUBBOCK | LYNN | SL 472 | 6813003 | 2018-01-26 | 754509.86 | 0 | 640443.37 | -114066.49 | 21 | 0 | 18 | -3
LUBBOCK | SWISHER | VA | 90517014 | 2018-01-12 | 297989.32 | 0 | 297989.32 | 0 | 90 | 0 | 83 | -7
LUFKIN | ANGELINA | US 59 | 17602090 | 2017-12-14 | 52179225.21 | 742113.11 | 52811281.14 | -110057.18 | 764 | 116 | 876 | -4
LUFKIN | ANGELINA | US 59 | 17602102 | 2017-12-20 | 18772914.68 | -346986.26 | 19057765.08 | 631836.66 | 515 | 22 | 518 | -19
LUFKIN | ANGELINA | US 69 | 20001082 | 2017-10-05 | 861310.5 | 2334 | 936388.27 | 72743.77 | 85 | 20 | 107 | 2
LUFKIN | ANGELINA | BU 69-J | 20001090 | 2017-10-23 | 255255.15 | 0 | 306476.15 | 51221 | 30 | 0 | 30 | 0
LUFKIN | HOUSTON | SH 19 | 10905040 | 2018-02-27 | 921752.5 | 9750 | 903122.64 | -28379.86 | 140 | 22 | 158 | -4
LUFKIN | HOUSTON | SH 21 | 11706044 | 2018-01-16 | 11812489.64 | 57903.28 | 11144323.69 | -726069.23 | 314 | 0 | 309 | -5
LUFKIN | HOUSTON | SH 7 | 33601046 | 2018-02-05 | 10296162.55 | 620064.32 | 10552537.97 | -363688.9 | 390 | 17 | 355 | -52
LUFKIN | HOUSTON | VA | 91128037 | 2017-12-12 | 746460.56 | 65926.81 | 805378.39 | -7008.98 | 164 | 11 | 131 | -44
LUFKIN | HOUSTON | CR | 91128040 | 2017-10-16 | 1080977.2 | 2688.12 | 1051151.92 | -32513.4 | 168 | 0 | 137 | -31
LUFKIN | HOUSTON | FM 3151 | 187503022 | 2018-02-28 | 3146993.46 | 0 | 2819758.48 | -327234.98 | 114 | 0 | 131 | 17
LUFKIN | NACOGDOCHES | US 59 | 17601107 | 2017-11-20 | 1598523.47 | -8998.97 | 1505891.23 | -83633.27 | 37 | 0 | 19 | -18
LUFKIN | NACOGDOCHES | SH 7 | 55303033 | 2018-01-17 | 44900 | 0 | 44350 | -550 | 15 | 0 | 15 | 0
LUFKIN | NACOGDOCHES | FM 95 | 70603020 | 2018-01-31 | 1783241.53 | 31120.77 | 1789978.27 | -24384.03 | 120 | 18 | 147 | 9
LUFKIN | POLK | US 59 | 17604081 | 2017-11-27 | 796806.25 | 17517.56 | 809540.55 | -4783.26 | 114 | 4 | 100 | -18
LUFKIN | POLK | VA | 91104054 | 2017-09-19 | 2009215 | 29187 | 2031171.75 | -7230.25 | 127 | 10 | 127 | -10
LUFKIN | POLK | CR | 91104059 | 2017-12-21 | 1215872.88 | 6615.67 | 1210067.34 | -12421.21 | 151 | 38 | 188 | -1
LUFKIN | POLK | CR | 91104060 | 2017-12-21 | 1889227.89 | 0 | 1841393.73 | -47834.16 | 177 | 0 | 142 | -35
LUFKIN | SAN AUGUSTINE | US 96 | 80904046 | 2017-10-26 | 3951203.54 | 2577.15 | 3934351.67 | -19429.02 | 152 | 26 | 174 | -4
LUFKIN | SAN JACINTO | US 59 | 17702080 | 2018-01-29 | 12895988.97 | 4352313.83 | 18253075.96 | 1004773.16 | 535 | 398 | 933 | 0
LUFKIN | SHELBY | SH 7 | 5904045 | 2017-12-21 | 1260125.9 | 0 | 1060197.68 | -199928.22 | 123 | 0 | 141 | 18
LUFKIN | SHELBY | SH 7 | 5905044 | 2018-01-10 | 831249.46 | 0 | 719832.66 | -111416.8 | 36 | 0 | 49 | 13
LUFKIN | SHELBY | US 96 | 6306096 | 2018-01-29 | 2189250.49 | -397139.07 | 2186665.09 | 394553.67 | 53 | 0 | 46 | -7
LUFKIN | SHELBY | FM 415 | 12308010 | 2018-01-31 | 1352960.21 | 22250.84 | 1366705.24 | -8505.81 | 119 | 5 | 125 | 1
LUFKIN | SHELBY | FM 417 | 81002019 | 2017-12-21 | 5757568.55 | 16957.54 | 5456901.28 | -317624.81 | 155 | 6 | 161 | 0
LUFKIN | SHELBY | CR | 91139046 | 2018-01-31 | 1129593.9 | 0 | 1147380 | 17786.1 | 220 | 0 | 182 | -38
LUFKIN | SHELBY | CR | 91139048 | 2018-01-31 | 432714 | 0 | 388310.7 | -44403.3 | 103 | 0 | 79 | -24
LUFKIN | SHELBY | CR | 91139054 | 2018-01-24 | 552047.24 | 11350 | 572032.25 | 8635.01 | 77 | 0 | 58 | -19
ODESSA | ANDREWS | FM 181 | 96103014 | 2018-01-30 | 7466995.99 | 304754.26 | 8243017.06 | 471266.81 | 56 | 0 | 80 | 24
ODESSA | CROCKETT | US 67 | 7603019 | 2018-02-01 | 2756477.84 | 73188.09 | 2859157.02 | 29491.09 | 226 | 0 | 212 | -14
ODESSA | ECTOR | IH 20 | 407121 | 2017-10-04 | 10110072.95 | 430055.03 | 10534004.41 | -6123.57 | 210 | 82 | 287 | -5
ODESSA | ECTOR | VA | 90600156 | 2018-01-17 | 960040.86 | 0 | 1003829.03 | 43788.17 | 68 | 0 | 77 | 9
ODESSA | ECTOR | VA | 90600173 | 2018-01-18 | 524246.68 | 20523.23 | 527498.95 | -17270.96 | 42 | 0 | 75 | 33
ODESSA | MARTIN | IH 20 | 504072 | 2018-02-27 | 1987502.23 | 0 | 2016414.09 | 28911.86 | 88 | 0 | 57 | -31
ODESSA | MIDLAND | SH 349 | 38009081 | 2018-01-26 | 3699830.35 | 0 | 3766544.91 | 66714.56 | 100 | 0 | 94 | -6
ODESSA | MIDLAND | FM 1788 | 171801033 | 2017-12-19 | 10991276.15 | 0 | 11178926.37 | 187650.22 | 360 | 15 | 322 | -53
ODESSA | MIDLAND | FM 1788 | 171807037 | 2017-11-13 | 17335339.76 | 0 | 17591796.54 | 256456.78 | 240 | 0 | 316 | 76
ODESSA | PECOS | US 285 | 13908037 | 2018-02-21 | 1244957 | 93678.07 | 1398058.56 | 59423.49 | 58 | 30 | 82 | -6
ODESSA | REEVES | IH 10 | 44106035 | 2017-11-17 | 8383558.38 | 14860.28 | 8144811.4 | -253607.26 | 100 | 0 | 147 | 47
PARIS | FANNIN | SH 121 | 54901029 | 2018-01-12 | 6855007.15 | -113921.62 | 6518801.77 | -222283.76 | 284 | 36 | 725 | 405
PARIS | FRANKLIN | IH 30 | 61002052 | 2017-09-29 | 16431004.72 | -121530.86 | 15863245.63 | -446228.23 | 223 | 0 | 173 | -50
PARIS | GRAYSON | SH 56 | 4503048 | 2018-01-16 | 2250480.47 | -367944.68 | 1979221.31 | 96685.52 | 45 | 0 | 73 | 28
PARIS | GRAYSON | US 377 | 8107023 | 2017-11-07 | 1372921.84 | -88627.9 | 1096587.79 | -187706.15 | 70 | 0 | 93 | 23
PARIS | GRAYSON | CR | 90119182 | 2018-02-27 | 931194.17 | 0 | 923895.17 | -7299 | 125 | 0 | 126 | 1
PARIS | HOPKINS | FM 1870 | 73505017 | 2018-01-24 | 1704856.89 | 11898.77 | 1657838.4 | -58917.26 | 120 | 0 | 120 | 0
PARIS | HOPKINS | CR | 90128088 | 2017-09-28 | 565395.05 | 0 | 537880.38 | -27514.67 | 128 | 0 | 72 | -56
PARIS | HUNT | CR | 90122107 | 2017-12-19 | 520226.2 | 0 | 510391.65 | -9834.55 | 122 | 0 | 72 | -50
PARIS | LAMAR | FM 137 | 43501068 | 2017-10-23 | 3768340.08 | -54813.28 | 3477776.82 | -235749.98 | 171 | 0 | 187 | 16
PARIS | LAMAR | CR | 90129065 | 2018-02-07 | 656785.4 | 0 | 619958 | -36827.4 | 209 | 0 | 228 | 19
PARIS | RED RIVER | CS | 90127029 | 2017-11-20 | 1506400.3 | 70588 | 1550672.8 | -26315.5 | 190 | 0 | 204 | 14
PHARR | CAMERON | IH 69E | 3907248 | 2018-02-09 | 293349 | 8925 | 314852.74 | 12578.74 | 85 | 0 | 59 | -26
PHARR | CAMERON | IH 69E | 3916063 | 2018-01-08 | 4333333.26 | 109855.82 | 4470074.31 | 26885.23 | 300 | 91 | 457 | 66
PHARR | CAMERON | US 281 | 22003027 | 2017-10-25 | 5229348.78 | 926118.31 | 6368826.88 | 213359.79 | 380 | 0 | 353 | -27
PHARR | CAMERON | US 281 | 22003028 | 2018-01-26 | 7709997.35 | 424911.52 | 8302738.92 | 167830.05 | 400 | 49 | 477 | 28
PHARR | CAMERON | SH 345 | 63001051 | 2017-12-14 | 296534 | 130680 | 454138.7 | 26924.7 | 80 | 35 | 92 | -23
PHARR | CAMERON | CR | 92106248 | 2017-09-01 | 1371236.75 | 51453.08 | 1371741.07 | -50948.76 | 240 | 5 | 241 | -4
PHARR | CAMERON | CS | 92106284 | 2017-12-19 | 117134.8 | 12940 | 129129.8 | -945 | 55 | 0 | 35 | -20
PHARR | HIDALGO | US 281 | 25509095 | 2018-02-14 | 4450423.06 | 0 | 4672294.11 | 221871.05 | 95 | 0 | 95 | 0
PHARR | HIDALGO | FM 88 | 69803084 | 2017-12-21 | 3148990.49 | 26933.5 | 3209037.96 | 33113.97 | 164 | 0 | 379 | 215
PHARR | HIDALGO | CS | 92102170 | 2018-01-31 | 5474037.5 | 149766.79 | 5301468.96 | -322335.33 | 480 | 6 | 427 | -59
PHARR | HIDALGO | CS | 92102266 | 2018-01-30 | 4251199.44 | 174777.97 | 4173880.23 | -252097.18 | 465 | 0 | 373 | -92
PHARR | HIDALGO | CS | 92102324 | 2018-02-09 | 487776.99 | 0 | 451358.76 | -36418.23 | 101 | 0 | 81 | -20
PHARR | HIDALGO | VA | 92102339 | 2017-09-20 | 1398543.35 | 39474.12 | 1418711.79 | -19305.68 | 199 | 0 | 199 | 0
PHARR | HIDALGO | FM 1925 | 180302028 | 2017-11-22 | 3554904.04 | 18600 | 3734658.43 | 161154.39 | 220 | 0 | 209 | -11
PHARR | STARR | US 83 | 3807067 | 2018-01-03 | 1161596.05 | 8867.25 | 1229206.11 | 58742.81 | 147 | 0 | 192 | 45
PHARR | WILLACY | IH 69E | 32710058 | 2017-12-19 | 4120397.03 | 43386 | 4406717.3 | 242934.27 | 90 | 5 | 92 | -3
PHARR | ZAPATA | US 83 | 3802031 | 2017-12-21 | 18535903.43 | 759985.13 | 19481819.01 | 185930.45 | 536 | 0 | 536 | 0
SAN ANGELO | CONCHO | US 87 | 7004035 | 2018-02-07 | 7317864.52 | 40197.47 | 6713718.82 | -644343.17 | 87 | 0 | 95 | 8
SAN ANGELO | CONCHO | FM 765 | 87004039 | 2017-11-13 | 2858761.68 | 18775.04 | 2771173.68 | -106363.04 | 174 | 5 | 155 | -24
SAN ANGELO | CROCKETT | IH 10 | 14011043 | 2017-11-17 | 14033551.42 | 1753982.21 | 16275916.44 | 488382.81 | 220 | 20 | 211 | -29
SAN ANGELO | IRION | US 67 | 7702031 | 2018-02-22 | 30896539.76 | 796715.01 | 32409794.97 | 716540.2 | 375 | 18 | 381 | -12
SAN ANGELO | MENARD | US 83 | 3505057 | 2018-02-22 | 1881273.2 | -19048 | 1945021.81 | 82796.61 | 80 | 0 | 65 | -15
SAN ANGELO | STERLING | US 87 | 6904042 | 2017-10-30 | 7904447.75 | 251039.22 | 8551566.88 | 396079.91 | 102 | 13 | 208 | 93
SAN ANTONIO | ATASCOSA | SH 97 | 32803032 | 2017-11-13 | 11864971.99 | 363209.13 | 12319522.08 | 91340.96 | 286 | 38 | 324 | 0
SAN ANTONIO | BEXAR | IH 35 | 1710269 | 2018-02-12 | 8209726.76 | 379970.45 | 9259138.75 | 669441.54 | 222 | 179 | 401 | 0
SAN ANTONIO | BEXAR | IH 35 | 1710271 | 2018-01-17 | 2254455.7 | 61437.61 | 2126864.52 | -189028.79 | 58 | 0 | 100 | 42
SAN ANTONIO | BEXAR | US 281 | 7308188 | 2018-02-28 | 2131726.3 | 3489.24 | 2256808.36 | 121592.82 | 64 | 0 | 59 | -5
SAN ANTONIO | BEXAR | SL 13 | 52101050 | 2018-01-10 | 2849994.41 | 276753.82 | 3372542.8 | 245794.57 | 89 | 14 | 101 | -2
SAN ANTONIO | BEXAR | IH 410 | 52105139 | 2017-09-29 | 6711711.71 | 82025.83 | 6734283.17 | -59454.37 | 110 | 15 | 132 | 7
SAN ANTONIO | BEXAR | CR | 91512439 | 2018-01-17 | 527480.77 | 183373.59 | 739681.55 | 28827.19 | 69 | 91 | 160 | 0
SAN ANTONIO | COMAL | SH 46 | 21507025 | 2017-11-12 | 2086418.25 | 4162.25 | 2151051.5 | 60471 | 169 | 0 | 161 | -8
SAN ANTONIO | COMAL | US 281 | 25303068 | 2017-11-12 | 3132254.38 | 970313.54 | 3923322.52 | -179245.4 | 138 | 333 | 626 | 155
SAN ANTONIO | KERR | SH 39 | 19302031 | 2018-02-28 | 7644985.94 | 77918.5 | 7664340.47 | -58563.97 | 345 | 177 | 605 | 83
SAN ANTONIO | KERR | SH 39 | 19302043 | 2018-02-28 | 1346273.4 | -77355.97 | 1268917.45 | 0.02 | 60 | 50 | 103 | -7
SAN ANTONIO | KERR | VA | 91515096 | 2018-01-10 | 321149.13 | 24142.73 | 345291.84 | -0.02 | 48 | 0 | 43 | -5
SAN ANTONIO | UVALDE | US 83 | 3607033 | 2018-02-12 | 1056313.61 | -24393.74 | 1030549.88 | -1369.99 | 78 | 0 | 80 | 2
SAN ANTONIO | UVALDE | US 83 | 3608051 | 2018-02-12 | 2165894.31 | 33865.45 | 2163649.74 | -36110.02 | 308 | 21 | 375 | 46
SAN ANTONIO | UVALDE | RM 187 | 67801033 | 2017-09-29 | 153862 | 13848.5 | 166570.5 | -1140 | 55 | 36 | 91 | 0
TYLER | ANDERSON | CR | 91008069 | 2018-01-26 | 499832.22 | -304.5 | 490535.53 | -8992.19 | 60 | 41 | 118 | 17
TYLER | GREGG | VA | 91007068 | 2017-12-13 | 254158.62 | 8302.04 | 261840.49 | -620.17 | 92 | 0 | 63 | -29
TYLER | HENDERSON | SH 31 | 16303048 | 2017-11-13 | 2305309.45 | 93111.45 | 2317114.11 | -81306.79 | 90 | 0 | 88 | -2
TYLER | HENDERSON | SH 31 | 16401069 | 2017-10-13 | 3640350.87 | -270461.93 | 3304711.63 | -65177.31 | 60 | 45 | 105 | 0
TYLER | RUSK | US 79 | 20607058 | 2018-02-28 | 6661253.87 | 795582.5 | 7458597.31 | 1760.94 | 263 | 2 | 246 | -19
TYLER | SMITH | CR | 91016131 | 2017-10-27 | 947499.8 | 1200 | 969445.11 | 20745.31 | 183 | 0 | 177 | -6
TYLER | VAN ZANDT | SH 19 | 10812017 | 2017-09-27 | 716585.54 | -106088.62 | 617458.87 | 6961.95 | 30 | 0 | 29 | -1
TYLER | VAN ZANDT | CR | 91012034 | 2017-09-27 | 1432779 | -26226.74 | 1393658.43 | -12893.83 | 272 | 0 | 211 | -61
WACO | BELL | SS 290 | 1504087 | 2017-11-13 | 1274187.44 | -109137.4 | 1229324 | 64273.96 | 45 | 0 | 45 | 0
WACO | BELL | FM 817 | 1505047 | 2017-11-28 | 115598.2 | 0 | 108619.9 | -6978.3 | 30 | 0 | 30 | 0
WACO | BELL | US 190 | 23103103 | 2018-02-05 | 9587760.87 | 468255.08 | 10442066.72 | 386050.77 | 277 | 115 | 425 | 33
WACO | BELL | FM 3470 | 353401011 | 2017-10-19 | 3489225.84 | 247411.5 | 3893560.55 | 156923.21 | 64 | 0 | 54 | -10
WACO | CORYELL | US 190 | 23102058 | 2017-09-20 | 3387358.77 | -744315.18 | 2511488.41 | -131555.18 | 75 | -15 | 59 | -1
WACO | CORYELL | US 281 | 25103021 | 2018-01-03 | 8827091 | 5000 | 8835356.26 | 3265.26 | 45 | 0 | 53 | 8
WACO | CORYELL | FM 1996 | 56701027 | 2017-12-12 | 2775913.74 | 132350.12 | 3037446.98 | 129183.12 | 170 | 0 | 170 | 0
WACO | HAMILTON | CR | 90929020 | 2017-09-11 | 906649 | 0 | 897659.5 | -8989.5 | 191 | 0 | 147 | -44
WACO | HILL | FM 339 | 166201015 | 2017-09-11 | 653974.75 | 10286.08 | 648695.53 | -15565.3 | 106 | 0 | 99 | -7
WACO | LIMESTONE | US 84 | 5603061 | 2017-09-18 | 1218683.3 | 12000 | 1229357.04 | -1326.26 | 45 | 0 | 43 | -2
WACO | LIMESTONE | FM 2705 | 275401008 | 2018-01-16 | 4733942.79 | 41412.92 | 4670524.7 | -104831.01 | 294 | 0 | 298 | 4
WACO | LIMESTONE | FM 3371 | 345901024 | 2017-11-20 | 651104.75 | -71688 | 578859.85 | -556.9 | 75 | 0 | 86 | 11
WACO | MC LENNAN | IH 35 | 1501186 | 2018-01-18 | 212440194.93 | 7591329.88 | 223780548.9 | 3749024.09 | 1138 | 169 | 1306 | -1
WACO | MC LENNAN | CR | 90922167 | 2017-11-27 | 697709.55 | 0 | 700232.73 | 2523.18 | 234 | 0 | 155 | -79
WACO | MC LENNAN | CS | 90922173 | 2017-11-27 | 372720.55 | 0 | 365523.88 | -7196.67 | 107 | 0 | 78 | -29
WACO | MC LENNAN | CR | 90922174 | 2017-09-18 | 453594.1 | 0 | 450197.4 | -3396.7 | 128 | 0 | 113 | -15
WICHITA FALLS | ARCHER | SH 114 | 13307026 | 2017-11-13 | 273290.91 | 0 | 272263.84 | -1027.07 | 27 | 0 | 24 | -3
WICHITA FALLS | ARCHER | US 281 | 24904039 | 2017-11-15 | 10168493.22 | -133743.48 | 10197505.53 | 162755.79 | 345 | 3 | 318 | -30
WICHITA FALLS | COOKE | IH 35 | 19501099 | 2017-11-15 | 2144827.68 | 368971.54 | 2516676.83 | 2877.61 | 200 | 55 | 289 | 34
WICHITA FALLS | COOKE | CR | 90315082 | 2018-01-09 | 837893.66 | 0 | 819281.92 | -18611.74 | 107 | 0 | 93 | -14
WICHITA FALLS | COOKE | FM 1199 | 319202009 | 2017-12-07 | 793931 | 0 | 929565.47 | 135634.47 | 34 | 0 | 32 | -2
WICHITA FALLS | MONTAGUE | US 81 | 1302021 | 2017-11-09 | 5209700.38 | 0 | 5463854.66 | 254154.28 | 74 | 0 | 77 | 3
WICHITA FALLS | MONTAGUE | US 81 | 1303035 | 2018-02-16 | 758517 | 90332.96 | 883160.56 | 34310.6 | 50 | 26 | 71 | -5
WICHITA FALLS | MONTAGUE | US 81 | 1305058 | 2017-12-01 | 3543752.8 | 0 | 3489361.98 | -54390.82 | 102 | 0 | 86 | -16
WICHITA FALLS | MONTAGUE | US 82 | 4404060 | 2018-02-23 | 268000 | 0 | 260562 | -7438 | 30 | 0 | 29 | -1
WICHITA FALLS | WICHITA | US 287 | 4309124 | 2017-09-18 | 2435987.72 | -11253.56 | 2371730.69 | -53003.47 | 37 | 0 | 113 | 76
WICHITA FALLS | WICHITA | SH 240 | 15603046 | 2017-09-26 | 320260 | 0 | 291707.64 | -28552.36 | 161 | 0 | 166 | 5
WICHITA FALLS | WICHITA | IH 44 | 15607107 | 2017-10-13 | 1445742 | -2249.32 | 1492087.82 | 48595.14 | 85 | 10 | 95 | 0
WICHITA FALLS | WICHITA | US 281 | 24901045 | 2017-09-12 | 2947967.38 | 163936 | 3590837.28 | 478933.9 | 59 | 19 | 151 | 73
WICHITA FALLS | WICHITA | FM 171 | 68101021 | 2018-01-31 | 4534926.9 | 73416.71 | 4045913.48 | -562430.13 | 170 | 18 | 224 | 36
WICHITA FALLS | WICHITA | FM 369 | 80202052 | 2017-12-19 | 1792483.5 | 132584 | 1829890.49 | -95177.01 | 202 | 17 | 213 | -6
YOAKUM | COLORADO | FM 109 | 71602038 | 2017-12-12 | 533118.53 | 11493.03 | 585630.77 | 41019.21 | 50 | 0 | 50 | 0
YOAKUM | FAYETTE | SH 71 | 26508065 | 2017-11-03 | 1780622.9 | 138125.6 | 1949942.18 | 31193.68 | 30 | 11 | 38 | -3
YOAKUM | GONZALES | US 90A | 2505020 | 2018-01-17 | 7274576.88 | 0 | 7289758.88 | 15182 | 60 | 0 | 60 | 0
YOAKUM | GONZALES | SH 80 | 34801013 | 2017-12-11 | 2463486.15 | 7586.34 | 2395200.96 | -75871.53 | 105 | 6 | 110 | -1
YOAKUM | JACKSON | CR | 91318028 | 2017-10-19 | 925264.6 | 75955.81 | 996557.03 | -4663.38 | 75 | 6 | 89 | 8
YOAKUM | MATAGORDA | SH 60 | 24103025 | 2017-10-13 | 100967.03 | 3115.56 | 98880.21 | -5202.38 | 30 | 0 | 14 | -16
YOAKUM | VICTORIA | US 59 | 8805087 | 2017-10-06 | 1504543.16 | 1002318.95 | 2572196.58 | 65334.47 | 25 | 31 | 55 | -1
YOAKUM | VICTORIA | US 59 | 8805089 | 2017-11-29 | 14995694.93 | 434296.1 | 15278314.1 | -151676.93 | 270 | 146 | 416 | 0
YOAKUM | WHARTON | US 59 | 8906085 | 2017-12-21 | 1880242.1 | 7738.71 | 1919068.37 | 31087.56 | 60 | 0 | 55 | -5
YOAKUM | WHARTON | CR | 91309064 | 2017-10-09 | 528449.32 | 14975.93 | 540271.4 | -3153.85 | 75 | 0 | 58 | -17
YOAKUM | WHARTON | CR | 91309067 | 2018-01-11 | 289824 | 0 | 278672.2 | -11151.8 | 60 | 0 | 69 | 9