## Sheet1
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED
DISTRICT | COUNTY | HIGHWAY | C C S J | DATE FINAL ESTIMATE PAID | CONTRACT AWARD | CHANGE ORDERS | AMOUNT PAID | UNDER/OVER BUDGET | CONTRACT DAYS | DAYS ADDED | DAYS USED | UNDER/OVER SCHEDULE
ABILENE | CALLAHAN | FM 18 | 611022 | 2018-11-01 | 1810774.89 | 209253.46 | 2054601.63 | 34573.28 | 63 | 2 | 64 | -1
ABILENE | CALLAHAN | IH 20 | 701054 | 2019-01-15 | 8248492.44 | 77820.66 | 8964788.6 | 638475.5 | 303 | 0 | 259 | -44
ABILENE | CALLAHAN | CR | 90834022 | 2018-09-28 | 1472447.5 | 54790 | 1527827.5 | 590 | 241 | 0 | 201 | -40
ABILENE | HASKELL | US 277 | 15704051 | 2018-09-24 | 708783 | 0 | 708851.25 | 68.25 | 88 | 15 | 100 | -3
ABILENE | HOWARD | IH 20 | 506119 | 2018-09-10 | 1664669.16 | 28652.91 | 1644893.16 | -48428.91 | 93 | 0 | 93 | 0
ABILENE | HOWARD | IH 20 | 506120 | 2018-11-05 | 1637144.66 | 0 | 1637988.27 | 843.61 | 80 | 0 | 43 | -37
ABILENE | JONES | US 83 | 3305091 | 2018-09-28 | 5078876 | 140087.92 | 5786525.67 | 567561.75 | 110 | 0 | 82 | -28
ABILENE | JONES | US 83 | 3305092 | 2019-01-28 | 9187304.69 | 231846.87 | 8856936.86 | -562214.7 | 88 | 0 | 82 | -6
ABILENE | MITCHELL | BS 208B | 33202026 | 2018-10-26 | 1291681.52 | 123625.96 | 1354788.57 | -60518.91 | 50 | 0 | 46 | -4
ABILENE | NOLAN | BI 20-L | 614004 | 2019-01-03 | 1848432.22 | 100935.04 | 1956428.5 | 7061.24 | 90 | 50 | 140 | 0
ABILENE | TAYLOR | IH 20 | 606099 | 2018-10-05 | 14639000 | 225180.5 | 14719347.87 | -144832.63 | 445 | 0 | 361 | -84
ABILENE | TAYLOR | SH 351 | 1101036 | 2019-02-05 | 1708497.38 | -1630 | 1740552.03 | 33684.65 | 67 | 0 | 67 | 0
ABILENE | TAYLOR | VA | 90800087 | 2019-02-15 | 1386588.15 | 963832.16 | 2412691.41 | 62271.1 | 60 | 0 | 56 | -4
ABILENE | TAYLOR | SL 322 | 239801051 | 2018-11-12 | 763962.2 | 33932.75 | 795254.2 | -2640.75 | 93 | 0 | 77 | -16
AMARILLO | LIPSCOMB | SH 15 | 35501048 | 2018-12-19 | 8150619.8 | 352604.3 | 8589168.42 | 85944.32 | 77 | 19 | 159 | 63
AMARILLO | OCHILTREE | US 83 | 3002044 | 2018-10-26 | 2999163.7 | 169845.75 | 3410361.06 | 241351.61 | 131 | 4 | 136 | 1
AMARILLO | POTTER | VA | 90400180 | 2018-09-12 | 482197.48 | 0 | 467648.43 | -14549.05 | 36 | 0 | 26 | -10
ATLANTA | BOWIE | US 67 | 1011069 | 2019-01-22 | 1398421.5 | 70170.79 | 1473788.14 | 5195.85 | 192 | 47 | 235 | -4
ATLANTA | BOWIE | US 67 | 1011070 | 2018-12-20 | 3481443.5 | 236157.9 | 3939018.01 | 221416.61 | 55 | 0 | 49 | -6
ATLANTA | BOWIE | US 259 | 8504035 | 2018-12-14 | 5371369.95 | 75945.65 | 5652720.5 | 205404.9 | 317 | 0 | 248 | -69
ATLANTA | BOWIE | US 71 | 21702035 | 2019-01-22 | 435854.53 | 0 | 438497.75 | 2643.22 | 160 | 0 | 115 | -45
ATLANTA | BOWIE | US 59 | 21801095 | 2018-09-11 | 175785.35 | 0 | 176388.91 | 603.56 | 72 | 0 | 54 | -18
ATLANTA | BOWIE | IH 30 | 61006080 | 2018-09-11 | 640525.98 | 0 | 640256.7 | -269.28 | 96 | 0 | 91 | -5
ATLANTA | BOWIE | IH 30 | 61006088 | 2019-02-13 | 798693 | 20194.1 | 843502.68 | 24615.58 | 69 | 0 | 61 | -8
ATLANTA | CASS | SH 77 | 27703027 | 2019-02-19 | 3512191.16 | 4833 | 3672660.12 | 155635.96 | 70 | 0 | 76 | 6
ATLANTA | HARRISON | US 59 | 6301095 | 2018-09-24 | 2387610.51 | 2100 | 2533641.74 | 143931.23 | 50 | 0 | 47 | -3
ATLANTA | HARRISON | IH 20 | 49508100 | 2019-01-09 | 13599302.66 | 661867.06 | 15034808.84 | 773639.12 | 250 | 0 | 231 | -19
ATLANTA | HARRISON | FM 2625 | 84307016 | 2019-01-09 | 2284633.31 | 35126 | 2282445.54 | -37313.77 | 124 | 0 | 124 | 0
ATLANTA | HARRISON | FM 1997 | 191902037 | 2018-09-11 | 823436.65 | 8796 | 831627.29 | -605.36 | 114 | 1 | 108 | -7
ATLANTA | PANOLA | US 59 | 6310013 | 2018-09-28 | 260188.2 | 0 | 260229.03 | 40.83 | 90 | 0 | 49 | -41
ATLANTA | PANOLA | SH 43 | 20704036 | 2018-09-17 | 2083697.62 | 25113.86 | 2109751.84 | 940.36 | 40 | 0 | 38 | -2
ATLANTA | PANOLA | SH 149 | 39303034 | 2018-12-19 | 4016607.46 | 18360 | 4098014.15 | 63046.69 | 82 | 5 | 99 | 12
ATLANTA | TITUS | SH 49 | 24801072 | 2018-10-10 | 418186.6 | 0 | 418276.6 | 90 | 161 | 0 | 143 | -18
ATLANTA | TITUS | IH 30 | 61003079 | 2019-01-11 | 33725327.54 | 4178284.48 | 40740908.03 | 2837296.01 | 595 | 166 | 742 | -19
ATLANTA | UPSHUR | US 271 | 24804068 | 2018-11-15 | 370150 | 34408.9 | 385304.5 | -19254.4 | 90 | 25 | 100 | -15
ATLANTA | UPSHUR | SH 154 | 40201023 | 2018-09-25 | 1158627.94 | 0 | 1115842.27 | -42785.67 | 76 | 0 | 108 | 32
AUSTIN | BASTROP | SH 71 | 26505079 | 2019-02-19 | 5983021.72 | -272929.33 | 6182508.67 | 472416.28 | 95 | 9 | 104 | 0
AUSTIN | BURNET | SH 29 | 15101051 | 2019-02-04 | 612820.24 | 22165.28 | 652240.67 | 17255.15 | 70 | 0 | 69 | -1
AUSTIN | BURNET | US 183 | 27302024 | 2019-02-11 | 1383923.15 | -72930 | 1189443.7 | -121549.45 | 17 | 0 | 9 | -8
AUSTIN | GILLESPIE | US 87 | 7201052 | 2019-02-08 | 963063.11 | 1950 | 1017530.5 | 52517.39 | 240 | 0 | 179 | -61
AUSTIN | GILLESPIE | US 87 | 7201053 | 2019-02-04 | 885285.24 | -43185.51 | 789603.32 | -52496.41 | 37 | 0 | 24 | -13
AUSTIN | HAYS | IH 35 | 1602145 | 2018-11-16 | 8969400.82 | 801053.36 | 10083115.66 | 312661.48 | 270 | 112 | 382 | 0
AUSTIN | HAYS | IH 35 | 1602148 | 2019-02-04 | 1054131.89 | 730537.39 | 1860307.11 | 75637.83 | 28 | 8 | 28 | -8
AUSTIN | HAYS | SH 21 | 47102071 | 2019-01-08 | 630023 | -65171.97 | 584321.82 | 19470.79 | 30 | 0 | 28 | -2
AUSTIN | HAYS | CR | 91433070 | 2018-10-12 | 149765 | -3427 | 149797 | 3459 | 38 | 0 | 38 | 0
AUSTIN | LEE | US 290 | 11407080 | 2018-11-13 | 844010.32 | 17208.17 | 894330.52 | 33112.03 | 100 | 0 | 74 | -26
AUSTIN | LEE | US 290 | 11407082 | 2018-09-10 | 1336982.72 | 57131.21 | 1378273.43 | -15840.5 | 118 | 0 | 85 | -33
AUSTIN | LEE | CR | 91421031 | 2018-09-27 | 313217.77 | -10103.3 | 293098.71 | -10015.76 | 72 | 0 | 61 | -11
AUSTIN | TRAVIS | IH 35 | 1601114 | 2018-10-03 | 630022 | -686 | 625084 | -4252 | 120 | 0 | 86 | -34
AUSTIN | TRAVIS | IH 35 | 1601117 | 2018-10-08 | 9232872.16 | 1445059.43 | 11062681.36 | 384749.77 | 306 | 41 | 347 | 0
AUSTIN | TRAVIS | US 290 | 11308077 | 2019-02-28 | 1856165.1 | 459907.97 | 2538897.15 | 222824.08 | 87 | 64 | 149 | -2
AUSTIN | TRAVIS | US 290 | 11402100 | 2018-12-14 | 834000 | 0 | 829619.8 | -4380.2 | 120 | 0 | 109 | -11
AUSTIN | TRAVIS | US 183 | 15109145 | 2018-09-06 | 2711157.55 | -275101.91 | 2539755.7 | 103700.06 | 54 | 0 | 74 | 20
AUSTIN | TRAVIS | SH 130 | 44006014 | 2018-10-23 | 642322 | 0 | 662521 | 20199 | 60 | 0 | 60 | 0
AUSTIN | TRAVIS | VA | 91400319 | 2018-12-11 | 1113486.73 | 13123.36 | 1191395.92 | 64785.83 | 365 | 0 | 365 | 0
AUSTIN | TRAVIS | VA | 91400320 | 2018-11-14 | 452778.7 | -6395 | 529117.09 | 82733.39 | 77 | 0 | 47 | -30
AUSTIN | TRAVIS | VA | 91400393 | 2018-12-28 | 496481.33 | 2507.73 | 520193.97 | 21204.91 | 180 | 0 | 129 | -51
AUSTIN | TRAVIS | CR | 91404227 | 2018-10-19 | 377671.08 | 0 | 403485.84 | 25814.76 | 109 | 0 | 84 | -25
AUSTIN | TRAVIS | CR | 91404305 | 2018-11-26 | 329780.76 | 4503.7 | 347413.68 | 13129.22 | 71 | 0 | 45 | -26
AUSTIN | TRAVIS | FM 2304 | 268901026 | 2018-10-12 | 355908.71 | 110422.61 | 514030.83 | 47699.51 | 36 | 0 | 35 | -1
AUSTIN | TRAVIS | LP 1 | 313601172 | 2018-09-05 | 7773016.78 | 1519627.97 | 9394767.89 | 102123.14 | 549 | 194 | 736 | -7
AUSTIN | TRAVIS | FM 3177 | 327701022 | 2018-10-17 | 2045353.1 | -4330.58 | 2184677.45 | 143654.93 | 240 | 10 | 239 | -11
AUSTIN | WILLIAMSON | IH 35 | 1509180 | 2019-01-22 | 9242850.12 | 55057.14 | 9287546.42 | -10360.84 | 289 | 38 | 327 | 0
AUSTIN | WILLIAMSON | SH 29 | 33702040 | 2018-10-31 | 1319538.69 | -69681.6 | 1263755.05 | 13897.96 | 37 | 0 | 24 | -13
AUSTIN | WILLIAMSON | RM 620 | 68301094 | 2018-12-14 | 471769.13 | 0 | 510187.72 | 38418.59 | 33 | 0 | 31 | -2
AUSTIN | WILLIAMSON | FM 1660 | 120001023 | 2018-12-20 | 4076992.45 | 15655.2 | 4004611.81 | -88035.84 | 145 | 0 | 145 | 0
BEAUMONT | HARDIN | SH 105 | 33903037 | 2019-01-09 | 220428.17 | 10588.46 | 229942.8 | -1073.83 | 43 | 10 | 35 | -18
BEAUMONT | HARDIN | FM 92 | 70302059 | 2018-11-13 | 61300.14 | -10274.05 | 53775.22 | 2749.13 | 12 | 0 | 7 | -5
BEAUMONT | HARDIN | FM 421 | 81303043 | 2018-09-26 | 1375866.73 | 946952.34 | 2462579.14 | 139760.07 | 50 | 20 | 70 | 0
BEAUMONT | HARDIN | FM 770 | 109601061 | 2019-01-09 | 228356 | 128598 | 353926.06 | -3027.94 | 38 | 41 | 90 | 11
BEAUMONT | JASPER | US 190 | 21308077 | 2018-09-04 | 7078117.16 | 190964.79 | 6975558.12 | -293523.83 | 252 | 13 | 468 | 203
BEAUMONT | JASPER | FM 777 | 110901021 | 2018-11-02 | 499477.5 | 38803.8 | 523834.23 | -14447.07 | 44 | 8 | 47 | -5
BEAUMONT | JEFFERSON | VA | 92000118 | 2019-01-23 | 706493.95 | 0 | 693371 | -13122.95 | 225 | 0 | 51 | -174
BEAUMONT | JEFFERSON | CS | 92038256 | 2018-12-19 | 225289 | 5274 | 217401.86 | -13161.14 | 56 | 2 | 58 | 0
BEAUMONT | LIBERTY | US 90 | 2803106 | 2018-10-04 | 8551356.02 | 728353.78 | 8948355.71 | -331354.09 | 45 | 15 | 56 | -4
BEAUMONT | NEWTON | CR | 92006033 | 2018-11-02 | 646004.2 | 78495.45 | 640959.94 | -83539.71 | 96 | 5 | 133 | 32
BEAUMONT | ORANGE | CS | 92030079 | 2018-12-03 | 316837.1 | 93622.71 | 388288.93 | -22170.88 | 50 | 2 | 44 | -8
BEAUMONT | TYLER | FM 2992 | 304301011 | 2019-01-28 | 509224.47 | 17370 | 482837.57 | -43756.9 | 56 | 0 | 21 | -35
BEAUMONT | TYLER | FM 3065 | 309201009 | 2018-11-02 | 1224577.5 | 4151.38 | 1206649.22 | -22079.66 | 118 | 2 | 74 | -46
BROWNWOOD | COLEMAN | US 67 | 7803055 | 2018-09-25 | 1678694.17 | 60554.33 | 1733915.01 | -5333.49 | 187 | 0 | 148 | -39
BROWNWOOD | COMANCHE | SH 36 | 18301043 | 2019-02-11 | 918207.81 | 145177.1 | 1105959.01 | 42574.1 | 34 | 0 | 30 | -4
BROWNWOOD | LAMPASAS | US 190 | 23101056 | 2018-11-30 | 667334.23 | 742813.82 | 1306735.07 | -103412.98 | 22 | 15 | 19 | -18
BROWNWOOD | MC CULLOCH | SH 71 | 110201042 | 2018-09-27 | 3342926.21 | 121200.38 | 3507938.37 | 43811.78 | 306 | 0 | 273 | -33
BROWNWOOD | MILLS | FM 45 | 48007009 | 2018-10-12 | 4563803.88 | 153055.21 | 5028466.35 | 311607.26 | 255 | 124 | 378 | -1
BROWNWOOD | STEPHENS | CR | 92322021 | 2018-12-20 | 676266.5 | -8478 | 697540.7 | 29752.2 | 102 | 11 | 106 | -7
BRYAN | BRAZOS | SH 21 | 11701046 | 2018-09-05 | 2625544.77 | 268248.31 | 2878915.57 | -14877.51 | 185 | 25 | 185 | -25
BRYAN | BRAZOS | FM 158 | 21203057 | 2019-01-22 | 1380692.25 | 196865.52 | 1476133.97 | -101423.8 | 177 | 0 | 153 | -24
BRYAN | BRAZOS | FM 2154 | 54004072 | 2018-09-12 | 2056099.02 | 151282.69 | 1988213.24 | -219168.47 | 97 | 23 | 111 | -9
BRYAN | BRAZOS | FM 159 | 54005046 | 2018-10-02 | 2209014.25 | -233636.17 | 1945605.11 | -29772.97 | 203 | 33 | 232 | -4
BRYAN | BURLESON | SH 21 | 11603060 | 2018-12-14 | 323412.25 | 8622.5 | 323195.41 | -8839.34 | 91 | 10 | 120 | 19
BRYAN | BURLESON | FM 60 | 71301032 | 2019-02-20 | 2429597.65 | 0 | 2293411.15 | -136186.5 | 100 | 0 | 156 | 56
BRYAN | FREESTONE | IH 45 | 67501066 | 2019-02-21 | 2450487.6 | 308184.89 | 2714967.42 | -43705.07 | 110 | 44 | 179 | 25
BRYAN | FREESTONE | PW | 91720036 | 2018-10-30 | 1862429.04 | 126800.41 | 1974067.1 | -15162.35 | 175 | 45 | 220 | 0
BRYAN | GRIMES | CR | 91717065 | 2018-10-03 | 905681.32 | 7202.39 | 912038.35 | -845.36 | 196 | 0 | 174 | -22
BRYAN | GRIMES | FM 1696 | 156203018 | 2018-12-06 | 5527215.43 | 230653.55 | 5802256.93 | 44387.95 | 215 | 53 | 277 | 9
BRYAN | MADISON | SH 21 | 11704040 | 2018-09-04 | 7687430.72 | 6501.87 | 8119976.27 | 426043.68 | 199 | 5 | 203 | -1
BRYAN | MILAM | FM 485 | 26207033 | 2018-11-12 | 668667.6 | 30445 | 730314.57 | 31201.97 | 70 | 3 | 68 | -5
BRYAN | MILAM | CR | 91712080 | 2018-10-03 | 447590 | 2462.78 | 444466.55 | -5586.23 | 82 | 0 | 76 | -6
BRYAN | ROBERTSON | US 79 | 4907063 | 2018-11-05 | 1388888.87 | 25104.2 | 1369718.81 | -44274.26 | 157 | 12 | 169 | 0
BRYAN | ROBERTSON | SH 14 | 4915013 | 2018-09-12 | 918845.69 | -75608.26 | 854999.64 | 11762.21 | 93 | 0 | 82 | -11
BRYAN | WALKER | US 190 | 21202039 | 2018-10-11 | 862850 | 686401.76 | 1676231.96 | 126980.2 | 36 | 30 | 56 | -10
BRYAN | WALKER | CR | 91727044 | 2018-11-05 | 504029.64 | 0 | 504631.16 | 601.52 | 99 | 0 | 66 | -33
CHILDRESS | BRISCOE | SH 86 | 30302019 | 2018-11-15 | 380262.3 | -7191.32 | 362727.44 | -10343.54 | 54 | 0 | 31 | -23
CHILDRESS | CHILDRESS | US 287 | 4301079 | 2018-09-16 | 1893993.38 | 320804.8 | 2265779.41 | 50981.23 | 150 | 81 | 228 | -3
CHILDRESS | CHILDRESS | US 287 | 4301080 | 2018-11-15 | 4151266.7 | 1801.5 | 3747809.39 | -405258.81 | 72 | 0 | 49 | -23
CHILDRESS | COLLINGSWORTH | US 83 | 3103042 | 2019-02-25 | 4173323.91 | -15163.75 | 4235781.26 | 77621.1 | 85 | 5 | 103 | 13
CHILDRESS | DICKENS | US 82 | 13202033 | 2018-09-16 | 2645236.16 | 0 | 2797622.82 | 152386.66 | 54 | 0 | 48 | -6
CHILDRESS | DONLEY | US 287 | 4206071 | 2019-02-21 | 1185394.6 | 0 | 1128564.94 | -56829.66 | 70 | 0 | 97 | 27
CHILDRESS | HALL | US 287 | 4209123 | 2019-01-15 | 4165121.12 | 88697.71 | 4435383.16 | 181564.33 | 56 | 17 | 56 | -17
CORPUS CHRISTI | ARANSAS | SH 35 | 18003035 | 2018-12-14 | 98162590.05 | 6402866.27 | 104114468.2 | -450988.12 | 968 | 610 | 1578 | 0
CORPUS CHRISTI | BEE | FM 351 | 241202014 | 2018-11-29 | 2807514.44 | 13445.84 | 2949200.95 | 128240.67 | 84 | 9 | 92 | -1
CORPUS CHRISTI | JIM WELLS | US 281 | 25407009 | 2018-10-19 | 6433805.7 | 341253.34 | 6923236.13 | 148177.09 | 160 | 10 | 160 | -10
CORPUS CHRISTI | KARNES | US 181 | 10006064 | 2018-09-26 | 2735640.96 | 174911.33 | 2900964.27 | -9588.02 | 48 | 10 | 58 | 0
CORPUS CHRISTI | KARNES | BU 181F | 10010015 | 2019-01-10 | 5799223.7 | 0 | 5554244.92 | -244978.78 | 73 | 0 | 54 | -19
CORPUS CHRISTI | KARNES | SH 239 | 51601015 | 2018-09-26 | 8525937.55 | 1720228.7 | 10599484.25 | 353318 | 185 | 159 | 344 | 0
CORPUS CHRISTI | KLEBERG | US 77 | 10204104 | 2018-10-29 | 3317124.65 | 43992.06 | 3370202.71 | 9086 | 60 | 5 | 154 | 89
CORPUS CHRISTI | LIVE OAK | FM 99 | 34811015 | 2018-12-07 | 2680558.94 | 120534.74 | 3097853.59 | 296759.91 | 102 | 49 | 148 | -3
CORPUS CHRISTI | LIVE OAK | US 59 | 44701063 | 2019-02-26 | 8991858.57 | 275447.51 | 9582054.42 | 314748.34 | 187 | 71 | 254 | -4
CORPUS CHRISTI | NUECES | IH 37 | 7406226 | 2018-12-06 | 6667563.56 | 355552.65 | 7346678.77 | 323562.56 | 100 | 73 | 172 | -1
CORPUS CHRISTI | NUECES | SH 44 | 10201106 | 2018-11-16 | 16390152.96 | 1801196.05 | 18997428.06 | 806079.05 | 356 | 115 | 471 | 0
CORPUS CHRISTI | NUECES | SH 286 | 32601052 | 2018-11-29 | 45818725.48 | 755818.72 | 46935427.91 | 360883.71 | 687 | 143 | 822 | -8
CORPUS CHRISTI | NUECES | SH 44 | 37302093 | 2018-12-13 | 4986828.05 | 1301139.88 | 6370482.67 | 82514.74 | 187 | 41 | 199 | -29
CORPUS CHRISTI | NUECES | SH 358 | 61701185 | 2018-10-18 | 935810.65 | 0 | 878202.63 | -57608.02 | 119 | 0 | 261 | 142
CORPUS CHRISTI | NUECES | SH 361 | 226303039 | 2018-10-24 | 6542666.53 | 142071.72 | 6712122.49 | 27384.24 | 181 | 28 | 245 | 36
CORPUS CHRISTI | NUECES | SH 361 | 226303041 | 2018-11-30 | 5552811.6 | -267349.72 | 5323119.3 | 37657.42 | 183 | 39 | 223 | 1
CORPUS CHRISTI | REFUGIO | US 77 | 37102069 | 2018-12-14 | 5008823.01 | -79.85 | 5396028.4 | 387285.24 | 102 | 106 | 208 | 0
CORPUS CHRISTI | REFUGIO | US 77 | 37102072 | 2018-12-14 | 4610259.16 | 0 | 4733865.07 | 123605.91 | 85 | 47 | 145 | 13
CORPUS CHRISTI | SAN PATRICIO | SL 90 | 18009018 | 2019-01-22 | 205057 | 10042.83 | 228082.83 | 12983 | 60 | 0 | 51 | -9
CORPUS CHRISTI | SAN PATRICIO | US 77 | 37201098 | 2018-12-10 | 3022420.5 | -0.02 | 3099932.54 | 77512.06 | 102 | 0 | 84 | -18
CORPUS CHRISTI | SAN PATRICIO | VA | 91628067 | 2019-02-28 | 609894 | -1077.6 | 588616.22 | -20200.18 | 60 | 31 | 99 | 8
CORPUS CHRISTI | SAN PATRICIO | FM 1945 | 120802012 | 2018-12-10 | 492135.9 | 0 | 485212.53 | -6923.37 | 85 | 0 | 78 | -7
DALLAS | COLLIN | SH 289 | 9105073 | 2018-09-21 | 474267.76 | 50080.66 | 532093.28 | 7744.86 | 156 | 0 | 94 | -62
DALLAS | COLLIN | FM 75 | 38701014 | 2018-12-20 | 1442556.4 | -69159.28 | 1234870.63 | -138526.49 | 105 | 0 | 105 | 0
DALLAS | COLLIN | FM 2862 | 81605019 | 2018-09-04 | 1597549.75 | 0 | 1489057.51 | -108492.24 | 185 | 0 | 179 | -6
DALLAS | COLLIN | FM 2755 | 274501008 | 2018-12-20 | 1442157.61 | 90192.06 | 1438919.7 | -93429.97 | 69 | 0 | 50 | -19
DALLAS | DALLAS | IH 30 | 911227 | 2019-01-25 | 2749311.95 | -2659.64 | 2779820.45 | 33168.14 | 200 | 0 | 189 | -11
DALLAS | DALLAS | SH 342 | 4801064 | 2019-01-09 | 11384511.2 | -155957.08 | 10773481.07 | -455073.05 | 150 | 53 | 203 | 0
DALLAS | DALLAS | IH 345 | 9214080 | 2018-09-04 | 30450159 | 738983.03 | 27831944.1 | -3357197.93 | 504 | 28 | 532 | 0
DALLAS | DALLAS | SS 366 | 19607031 | 2018-11-20 | 674379.67 | 1590.75 | 549650.4 | -126320.02 | 60 | 0 | 78 | 18
DALLAS | DALLAS | CS | 91845864 | 2019-01-11 | 3435737.14 | 1584406.14 | 5064886.29 | 44743.01 | 276 | 52 | 322 | -6
DALLAS | DALLAS | IH 635 | 237402149 | 2018-10-26 | 821756.18 | 183200.9 | 984100.77 | -20856.31 | 148 | 41 | 182 | -7
DALLAS | DALLAS | IH 20 | 237403077 | 2018-12-07 | 7377285.89 | 1041755.49 | 8435723.46 | 16682.08 | 294 | 107 | 456 | 55
DALLAS | DENTON | US 380 | 13409029 | 2018-11-20 | 26379472.05 | -618283.16 | 27227905.76 | 1466716.87 | 588 | 6 | 593 | -1
DALLAS | DENTON | SH 114 | 35302074 | 2019-02-13 | 24897375.14 | 983294.27 | 26058373.68 | 177704.27 | 439 | 154 | 479 | -114
DALLAS | DENTON | FM 455 | 81602076 | 2018-09-04 | 4986228.11 | -92631.32 | 4609989.14 | -283607.65 | 236 | 0 | 236 | 0
DALLAS | DENTON | FM 423 | 131502009 | 2019-02-26 | 29826069.71 | 1634176.34 | 31956693.89 | 496447.84 | 603 | 18 | 680 | 59
DALLAS | DENTON | FM 720 | 156701025 | 2019-01-31 | 15597320.25 | 2438727.88 | 18264744.11 | 228695.98 | 420 | 184 | 604 | 0
DALLAS | DENTON | FM 423 | 156702032 | 2019-02-28 | 57943494.3 | 7315743.17 | 64914619.67 | -344617.8 | 756 | 55 | 810 | -1
DALLAS | DENTON | FM 2499 | 268101012 | 2019-02-21 | 34857000 | 5430400.16 | 40245471.71 | -41928.45 | 505 | 195 | 689 | -11
DALLAS | ELLIS | FM 66 | 59602043 | 2018-09-21 | 4255415.48 | 573846.13 | 4494481.42 | -334780.19 | 136 | 10 | 289 | 143
DALLAS | KAUFMAN | IH 20 | 9514028 | 2019-01-18 | 1088533 | -63243 | 978032.16 | -47257.84 | 78 | 0 | 95 | 17
DALLAS | KAUFMAN | FM 2578 | 255501011 | 2018-09-24 | 6878335.7 | -10800.72 | 6199388.6 | -668146.38 | 247 | 0 | 312 | 65
DALLAS | KAUFMAN | FM 2932 | 298101007 | 2019-01-09 | 4016437.41 | 25443.81 | 3935667.69 | -106213.53 | 206 | 10 | 218 | 2
DALLAS | NAVARRO | CR | 91818126 | 2018-11-29 | 1122177.77 | 13289.4 | 1049217.04 | -86250.13 | 341 | 0 | 338 | -3
DALLAS | NAVARRO | FM 1126 | 128901029 | 2019-02-26 | 6714487.74 | 147372.04 | 7002372.21 | 140512.43 | 386 | 19 | 405 | 0
DALLAS | ROCKWALL | FM 740 | 101403049 | 2018-10-12 | 12967453.42 | 1430142.61 | 14216807.68 | -180788.35 | 412 | 153 | 565 | 0
EL PASO | EL PASO | FM 76 | 67402011 | 2018-09-18 | 1296296 | 100081.19 | 1794100.42 | 397723.23 | 130 | 0 | 104 | -26
EL PASO | HUDSPETH | IH 10 | 205045 | 2019-02-02 | 603661 | 27665.24 | 610448.31 | -20877.93 | 140 | 0 | 140 | 0
EL PASO | HUDSPETH | US 62 | 37405027 | 2018-10-02 | 54568 | -7800 | 43636 | -3132 | 22 | 0 | 20 | -2
EL PASO | PRESIDIO | FM 170 | 95708027 | 2019-02-04 | 1271914.4 | 167201.86 | 1618237.86 | 179121.6 | 140 | 5 | 114 | -31
FORT WORTH | ERATH | FM 8 | 55002038 | 2019-02-15 | 6225724.96 | -497001.2 | 5815097.4 | 86373.64 | 74 | 74 | 149 | 1
FORT WORTH | HOOD | US 377 | 8004096 | 2018-09-14 | 3213559.48 | 278870.43 | 3412603.28 | -79826.63 | 32 | 7 | 39 | 0
FORT WORTH | JOHNSON | SH 174 | 1901144 | 2019-02-22 | 3929910.02 | 72567.39 | 4105426.13 | 102948.72 | 213 | 34 | 234 | -13
FORT WORTH | JOHNSON | FM 1807 | 160002017 | 2019-01-15 | 8282797.46 | 130892.75 | 7960886.59 | -452803.62 | 278 | 67 | 427 | 82
FORT WORTH | JOHNSON | FM 2738 | 301002014 | 2019-02-20 | 3409657.16 | 197889.09 | 3854164.49 | 246618.24 | 218 | 12 | 221 | -9
FORT WORTH | JOHNSON | FM 3136 | 334801019 | 2018-10-22 | 6829235.17 | 695477.33 | 7650838.39 | 126125.89 | 384 | 12 | 360 | -36
FORT WORTH | PALO PINTO | SH 16 | 708028 | 2018-10-15 | 131854.9 | 0 | 137354.29 | 5499.39 | 85 | 0 | 55 | -30
FORT WORTH | PALO PINTO | FM 2201 | 199301015 | 2018-09-07 | 4655964.1 | 671818.22 | 4815304.63 | -512477.69 | 277 | 13 | 220 | -70
FORT WORTH | PALO PINTO | FM 2353 | 229001009 | 2018-12-21 | 5278946.23 | 1146387.86 | 5994856.88 | -430477.21 | 299 | 65 | 363 | -1
FORT WORTH | PALO PINTO | SH 337 | 283901012 | 2019-02-20 | 89999 | 0 | 89280.9 | -718.1 | 43 | 0 | 7 | -36
FORT WORTH | PARKER | US 180 | 802072 | 2018-12-18 | 2644391.29 | 670423.09 | 3240679.63 | -74134.75 | 59 | 3 | 84 | 22
FORT WORTH | PARKER | IH 20 | 803103 | 2019-02-20 | 4795524.9 | 284250 | 5626856.76 | 547081.86 | 190 | 290 | 536 | 56
FORT WORTH | PARKER | IH 20 | 803107 | 2019-02-08 | 2047763.19 | 93123.2 | 2113626.04 | -27260.35 | 85 | 0 | 63 | -22
FORT WORTH | PARKER | SH 199 | 17103067 | 2019-02-20 | 3096310.69 | 445.41 | 2842858.61 | -253897.49 | 128 | 0 | 120 | -8
FORT WORTH | PARKER | IH 20 | 31407054 | 2019-01-17 | 1697511.95 | -96580.32 | 1695058.29 | 94126.66 | 64 | 7 | 71 | 0
FORT WORTH | PARKER | FM 1885 | 53905015 | 2018-12-11 | 5556310.37 | 832114.8 | 6334872.57 | -53552.6 | 299 | 35 | 324 | -10
FORT WORTH | PARKER | VA | 90238124 | 2019-02-14 | 985856.49 | -83436.63 | 827441.42 | -74978.44 | 86 | 61 | 157 | 10
FORT WORTH | PARKER | FM 1189 | 146801024 | 2019-01-15 | 6481549.55 | 1178941.93 | 7063855.18 | -596636.3 | 253 | 163 | 342 | -74
FORT WORTH | PARKER | FM 730 | 160101031 | 2018-11-15 | 179200 | 0 | 183705 | 4505 | 40 | 0 | 35 | -5
FORT WORTH | PARKER | FM 1187 | 229101013 | 2019-02-05 | 6785848.58 | -475974.28 | 5119026.54 | -1190847.76 | 374 | 0 | 205 | -169
FORT WORTH | SOMERVELL | US 67 | 25902050 | 2018-12-21 | 8834162.22 | 198653.63 | 9239335.43 | 206519.58 | 125 | 0 | 117 | -8
FORT WORTH | TARRANT | SS 580 | 804046 | 2018-12-18 | 3743231.89 | 56446.58 | 3727720.36 | -71958.11 | 152 | 0 | 156 | 4
FORT WORTH | TARRANT | IH 20 | 812090 | 2018-09-26 | 88581.65 | 2890.4 | 87763.92 | -3708.13 | 27 | 0 | 11 | -16
FORT WORTH | TARRANT | IH 820 | 813233 | 2019-01-24 | 1173740.01 | 10410.76 | 1170483.83 | -13666.94 | 65 | 45 | 110 | 0
FORT WORTH | TARRANT | IH 820 | 815049 | 2018-10-13 | 3652534.53 | 117580.97 | 3821797.44 | 51681.94 | 256 | 39 | 383 | 88
FORT WORTH | TARRANT | US 377 | 8101046 | 2018-10-18 | 4198919.2 | 332784.52 | 4401920.02 | -129783.7 | 236 | 229 | 514 | 49
FORT WORTH | TARRANT | US 287 | 17209033 | 2018-11-08 | 4196348.59 | 59569.68 | 4524327.01 | 268408.74 | 277 | 0 | 273 | -4
FORT WORTH | TARRANT | US 287 | 17209034 | 2019-02-21 | 1869823.09 | 37257.21 | 1988372.44 | 81292.14 | 128 | 9 | 118 | -19
FORT WORTH | TARRANT | VA | 90200135 | 2019-02-22 | 1617402.2 | 7604.68 | 1613514.18 | -11492.7 | 120 | 47 | 155 | -12
FORT WORTH | TARRANT | VA | 90200142 | 2018-12-07 | 1179390.47 | 173443.56 | 990876.58 | -361957.45 | 300 | 10 | 294 | -16
FORT WORTH | TARRANT | CS | 90248838 | 2019-02-19 | 10457967.33 | 1358495.6 | 11838518.33 | 22055.4 | 380 | 191 | 571 | 0
FORT WORTH | TARRANT | IH 30 | 106801216 | 2019-02-15 | 997337.74 | -1235.54 | 1068598.74 | 72496.54 | 128 | 0 | 126 | -2
FORT WORTH | TARRANT | IH 30 | 106802142 | 2019-01-25 | 4616649.64 | -266561.34 | 4422492.64 | 72404.34 | 150 | 0 | 107 | -43
FORT WORTH | TARRANT | SS 341 | 106803022 | 2019-02-27 | 282864.35 | 0 | 258095.4 | -24768.95 | 64 | 69 | 133 | 0
FORT WORTH | TARRANT | FM 1187 | 133001062 | 2019-02-20 | 5144732.72 | -1460377.98 | 3232871.02 | -451483.72 | 299 | -163 | 149 | 13
FORT WORTH | TARRANT | SH 360 | 226602146 | 2019-01-18 | 281936.15 | 8119.01 | 296937.04 | 6881.88 | 24 | 10 | 34 | 0
FORT WORTH | TARRANT | IH 20 | 237405081 | 2019-01-17 | 966661 | 1650.5 | 1067114.32 | 98802.82 | 121 | 0 | 103 | -18
FORT WORTH | WISE | US 380 | 13407073 | 2018-09-06 | 241382.82 | 0 | 239022.82 | -2360 | 107 | 0 | 34 | -73
FORT WORTH | WISE | FM 455 | 135204014 | 2018-12-11 | 83369.31 | 40.66 | 83392.77 | -17.2 | 30 | 0 | 26 | -4
HOUSTON | BRAZORIA | SH 35 | 17802087 | 2018-11-21 | 470431.75 | 4813 | 542660.5 | 67415.75 | 75 | 0 | 68 | -7
HOUSTON | BRAZORIA | SH 35 | 17802088 | 2018-09-14 | 261915.9 | 12150.88 | 276801.55 | 2734.77 | 81 | 0 | 35 | -46
HOUSTON | BRAZORIA | SH 288 | 59802106 | 2018-09-24 | 9196617.22 | 437532.33 | 9467027.61 | -167121.94 | 290 | 32 | 304 | -18
HOUSTON | BRAZORIA | FM 521 | 84703035 | 2018-11-19 | 7645090.82 | 402439.09 | 8123462.05 | 75932.14 | 191 | 36 | 227 | 0
HOUSTON | BRAZORIA | FM 524 | 100401063 | 2019-01-30 | 438751.1 | 34948.2 | 438904.55 | -34794.75 | 104 | 0 | 83 | -21
HOUSTON | FORT BEND | US 90A | 2708172 | 2019-01-14 | 2933336.32 | -62915.86 | 3167467.99 | 297047.53 | 120 | 0 | 109 | -11
HOUSTON | FORT BEND | SS 10 | 18705048 | 2018-10-25 | 11736891.34 | -212971.12 | 11445911.28 | -78008.94 | 219 | 0 | 210 | -9
HOUSTON | FORT BEND | SH 36 | 18705060 | 2018-11-07 | 4918131.86 | 84548.1 | 5658585.51 | 655905.55 | 120 | 0 | 99 | -21
HOUSTON | FORT BEND | IH 10 | 27105042 | 2019-01-25 | 2297994.98 | 170125.43 | 2666348.99 | 198228.58 | 151 | 0 | 149 | -2
HOUSTON | FORT BEND | FM 360 | 52706019 | 2018-09-13 | 1482901.93 | 87410.66 | 1736240.59 | 165928 | 90 | 0 | 44 | -46
HOUSTON | FORT BEND | CS | 91234143 | 2018-10-18 | 3825527.24 | 140232.2 | 3910781.55 | -54977.89 | 176 | 0 | 130 | -46
HOUSTON | FORT BEND | VA | 91234187 | 2019-02-15 | 992940.66 | -15721.13 | 1030604.63 | 53385.1 | 91 | 0 | 62 | -29
HOUSTON | FORT BEND | FM 1994 | 196501006 | 2019-01-29 | 1774560.91 | 241012.09 | 2309854.56 | 294281.56 | 45 | 0 | 43 | -2
HOUSTON | FORT BEND | PR 72 | 342201011 | 2019-01-25 | 563996.22 | -109153.64 | 443777.54 | -11065.04 | 30 | 0 | 30 | 0
HOUSTON | GALVESTON | SH 146 | 38906106 | 2019-01-02 | 7195186.58 | -283958.43 | 7537861.48 | 626633.33 | 120 | 27 | 147 | 0
HOUSTON | GALVESTON | SH 146 | 38906107 | 2019-01-17 | 219473.36 | 0 | 198484.64 | -20988.72 | 36 | 0 | 16 | -20
HOUSTON | GALVESTON | IH 45 | 50004134 | 2019-01-17 | 960543.48 | 257709.67 | 1261394.5 | 43141.35 | 45 | 52 | 67 | -30
HOUSTON | GALVESTON | FM 518 | 97603103 | 2019-01-25 | 227694.62 | -4800 | 210489.52 | -12405.1 | 45 | 0 | 41 | -4
HOUSTON | GALVESTON | FM 2094 | 97604020 | 2019-02-25 | 213735.35 | 0 | 228615.25 | 14879.9 | 180 | 0 | 71 | -109
HOUSTON | GALVESTON | FM 3436 | 97802078 | 2019-02-11 | 625529.3 | 4357.28 | 676857.35 | 46970.77 | 45 | 0 | 42 | -3
HOUSTON | GALVESTON | FM 270 | 331202014 | 2018-11-05 | 2299180.8 | 267877.94 | 2788996.31 | 221937.57 | 122 | 0 | 118 | -4
HOUSTON | HARRIS | SS 527 | 2715026 | 2018-10-26 | 2585958.26 | 60639.33 | 3238794.65 | 592197.06 | 220 | 15 | 196 | -39
HOUSTON | HARRIS | BU 90-U | 2801101 | 2019-02-26 | 554115.5 | 1251198.96 | 2140953.42 | 335638.96 | 55 | 0 | 74 | 19
HOUSTON | HARRIS | SH 3 | 5102100 | 2018-11-05 | 345345.91 | 0 | 303028.98 | -42316.93 | 60 | 0 | 60 | 0
HOUSTON | HARRIS | IH 10 | 27106121 | 2018-09-11 | 1856137.55 | 220685.35 | 2044276.46 | -32546.44 | 90 | 0 | 83 | -7
HOUSTON | HARRIS | IH 10 | 27107242 | 2018-09-10 | 48579333.53 | 5800447 | 58299846.45 | 3920065.92 | 777 | 184 | 917 | -44
HOUSTON | HARRIS | IH 10 | 27107312 | 2019-01-15 | 12293403.13 | 1022825.43 | 14207806.63 | 891578.07 | 170 | 47 | 317 | 100
HOUSTON | HARRIS | SH 225 | 50201211 | 2018-09-13 | 684681.9 | 0 | 750363.65 | 65681.75 | 84 | 0 | 97 | 13
HOUSTON | HARRIS | VA | 91200380 | 2019-01-25 | 1515998.78 | 126930.46 | 1622098.48 | -20830.76 | 437 | 0 | 285 | -152
HOUSTON | HARRIS | VA | 91200385 | 2018-09-18 | 911168.15 | 85757.9 | 1198840.83 | 201914.78 | 270 | 0 | 182 | -88
HOUSTON | HARRIS | VA | 91200417 | 2018-11-21 | 859065.05 | 213962.97 | 1106078.81 | 33050.79 | 220 | 24 | 213 | -31
HOUSTON | HARRIS | VA | 91200424 | 2019-02-26 | 2697458.33 | -94765.8 | 2423628.89 | -179063.64 | 228 | 0 | 275 | 47
HOUSTON | HARRIS | VA | 91200440 | 2019-02-01 | 772662.59 | -21420 | 873562.59 | 122320 | 135 | 0 | 129 | -6
HOUSTON | HARRIS | VA | 91200513 | 2019-01-28 | 927576.88 | 0 | 979332.01 | 51755.13 | 119 | 0 | 104 | -15
HOUSTON | HARRIS | VA | 91270085 | 2018-11-29 | 810065.52 | 0 | 809934.24 | -131.28 | 90 | 0 | 83 | -7
HOUSTON | HARRIS | CS | 91270091 | 2019-02-25 | 1844818.4 | -5611.38 | 1807515.25 | -31691.77 | 254 | 0 | 254 | 0
HOUSTON | HARRIS | CR | 91271894 | 2018-11-29 | 10341416.18 | 1261776.35 | 11426681.13 | -176511.4 | 250 | 66 | 316 | 0
HOUSTON | HARRIS | VA | 91272294 | 2019-01-07 | 1678207.72 | 0 | 1790145.24 | 111937.52 | 190 | 0 | 185 | -5
HOUSTON | HARRIS | CR | 91272335 | 2018-11-08 | 1789743.3 | 69956.84 | 2007140.12 | 147439.98 | 200 | 0 | 190 | -10
HOUSTON | HARRIS | FM 2100 | 106202026 | 2019-02-04 | 234040.68 | 106890.68 | 369989.1 | 29057.74 | 36 | 18 | 52 | -2
HOUSTON | HARRIS | FM 1942 | 106205009 | 2018-10-03 | 3477178.18 | 494946.95 | 4001490.39 | 29365.26 | 157 | 0 | 139 | -18
HOUSTON | HARRIS | SL 8 | 325601105 | 2018-10-10 | 3448134.33 | 230648.56 | 3984164.16 | 305381.27 | 80 | 0 | 79 | -1
HOUSTON | HARRIS | SL 8 | 325601109 | 2019-02-27 | 486999.66 | 0 | 477664.69 | -9334.97 | 50 | 0 | 53 | 3
HOUSTON | HARRIS | FM 270 | 331201008 | 2018-09-24 | 3845442.26 | 59378.15 | 3979634.3 | 74813.89 | 225 | 0 | 225 | 0
HOUSTON | HARRIS | SH 99 | 351005036 | 2018-11-27 | 3069959.8 | 465386.66 | 4020884.03 | 485537.57 | 97 | 35 | 132 | 0
HOUSTON | MONTGOMERY | IH 69 | 17705093 | 2018-12-17 | 7416768.12 | 447100.17 | 7944119.46 | 80251.17 | 248 | 0 | 238 | -10
HOUSTON | MONTGOMERY | FM 1097 | 170603008 | 2019-01-30 | 5759460.11 | 11516.97 | 5671363.05 | -99614.03 | 113 | 0 | 96 | -17
LAREDO | DIMMIT | FM 190 | 96301032 | 2018-11-13 | 4902990.18 | 400367.14 | 5481860.24 | 178502.92 | 228 | 66 | 294 | 0
LAREDO | DUVAL | VA | 92223009 | 2018-09-27 | 1157974.5 | 58941.8 | 1152416.74 | -64499.56 | 180 | 0 | 156 | -24
LAREDO | VAL VERDE | US 277 | 16004049 | 2019-01-11 | 2245195.89 | 41042.82 | 2286238.72 | 0.01 | 153 | 0 | 75 | -78
LAREDO | WEBB | IH 35 | 1803056 | 2018-10-08 | 1393636.95 | 55444.61 | 1440562.88 | -8518.68 | 97 | 0 | 53 | -44
LAREDO | WEBB | SH 44 | 23703030 | 2018-09-27 | 3538171.86 | -10014.41 | 3526997.55 | -1159.9 | 256 | 0 | 253 | -3
LAREDO | WEBB | VA | 92200056 | 2019-01-18 | 1498321.43 | 22328.97 | 1464764.43 | -55885.97 | 281 | 5 | 388 | 102
LUBBOCK | BAILEY | US 70 | 14501032 | 2019-01-17 | 192966.41 | 0 | 209364.43 | 16398.02 | 30 | 0 | 21 | -9
LUBBOCK | COCHRAN | SH 114 | 13002023 | 2018-12-18 | 1040662.59 | 0 | 978637.32 | -62025.27 | 70 | 0 | 75 | 5
LUBBOCK | FLOYD | SH 207 | 45307013 | 2018-11-26 | 6244705.71 | 1498452.88 | 7768215.51 | 25056.92 | 115 | 23 | 145 | 7
LUBBOCK | LAMB | SL 430 | 5213005 | 2018-11-26 | 746928.46 | -13991.7 | 754171.15 | 21234.39 | 50 | 0 | 47 | -3
LUBBOCK | LUBBOCK | US 84 | 5301120 | 2018-10-23 | 14947745.77 | 123940.95 | 14831157.03 | -240529.69 | 306 | 78 | 384 | 0
LUBBOCK | LUBBOCK | VA | 90500082 | 2018-09-13 | 3492691.68 | 914639.89 | 4305002.45 | -102329.12 | 100 | 60 | 177 | 17
LUBBOCK | LUBBOCK | CS | 90506086 | 2019-02-04 | 4085773.03 | -14796.21 | 4093722.43 | 22745.61 | 256 | 0 | 224 | -32
LUFKIN | ANGELINA | US 69 | 20001089 | 2018-11-20 | 164664.83 | 0 | 156227.5 | -8437.33 | 32 | 0 | 28 | -4
LUFKIN | HOUSTON | SH 21 | 11706049 | 2019-01-29 | 1384827 | 0 | 1354947.54 | -29879.46 | 76 | 0 | 100 | 24
LUFKIN | HOUSTON | FM 227 | 93702033 | 2019-01-31 | 3134729.03 | 236294.41 | 3256896.21 | -114127.23 | 166 | 50 | 215 | -1
LUFKIN | NACOGDOCHES | SH 7 | 5901060 | 2018-09-04 | 11201892.34 | 586154.8 | 11345241.87 | -442805.27 | 91 | 31 | 122 | 0
LUFKIN | NACOGDOCHES | SH 103 | 33606028 | 2018-12-17 | 597891.99 | 13138.91 | 744617.37 | 133586.47 | 74 | 19 | 90 | -3
LUFKIN | POLK | US 59 | 17701103 | 2018-10-24 | 562884.58 | 2651.25 | 431225.2 | -134310.63 | 17 | 0 | 14 | -3
LUFKIN | POLK | FM 356 | 47511031 | 2018-11-13 | 7653712 | 55731.27 | 7815967.65 | 106524.38 | 162 | 62 | 228 | 4
LUFKIN | SAN JACINTO | US 59 | 17702089 | 2018-10-19 | 8948536.84 | 1921533.77 | 11191372.47 | 321301.86 | 230 | 189 | 409 | -10
LUFKIN | SAN JACINTO | VA | 91107038 | 2018-10-26 | 646827 | 47740.37 | 696382.13 | 1814.76 | 116 | 11 | 81 | -46
LUFKIN | SAN JACINTO | FM 1127 | 168101012 | 2018-11-20 | 1585479.8 | 0 | 1408280.17 | -177199.63 | 153 | 7 | 162 | 2
LUFKIN | SHELBY | SH 7 | 5903020 | 2018-10-29 | 1821663.85 | 2755.88 | 1773317.66 | -51102.07 | 39 | 0 | 39 | 0
LUFKIN | SHELBY | CR | 91139038 | 2018-10-01 | 619833.67 | 154.5 | 616300.52 | -3687.65 | 144 | 0 | 122 | -22
LUFKIN | TRINITY | US 287 | 31901064 | 2018-09-28 | 1947390.02 | 27378 | 2075692.7 | 100924.68 | 80 | 0 | 79 | -1
ODESSA | ANDREWS | SH 176 | 54805048 | 2018-09-10 | 10506607.73 | 112625.4 | 11490946.8 | 871713.67 | 360 | 3 | 305 | -58
ODESSA | ECTOR | VA | 90600159 | 2018-12-06 | 1063374.41 | 0 | 1044373.95 | -19000.46 | 64 | 0 | 33 | -31
ODESSA | ECTOR | VA | 90600161 | 2019-01-03 | 1029975.87 | 0 | 1029975.87 | 0 | 69 | 0 | 58 | -11
ODESSA | ECTOR | SH 191 | 229601051 | 2018-11-09 | 4387311.96 | 219830.41 | 4564960.86 | -42181.51 | 120 | 24 | 142 | -2
ODESSA | MARTIN | IH 20 | 504071 | 2019-02-01 | 5784004.91 | 264404 | 6103096.14 | 54687.23 | 137 | 0 | 83 | -54
ODESSA | MIDLAND | SH 158 | 46303049 | 2018-11-12 | 3997554.79 | 0 | 4072785.27 | 75230.48 | 60 | 0 | 51 | -9
ODESSA | PECOS | US 67 | 7502027 | 2018-09-10 | 2345678.9 | 0 | 1919350.84 | -426328.06 | 160 | 0 | 179 | 19
ODESSA | REEVES | RM 652 | 245103015 | 2018-10-12 | 3993994.33 | 25683 | 3922948.92 | -96728.41 | 173 | 6 | 182 | 3
ODESSA | UPTON | SH 349 | 38011025 | 2018-09-10 | 17114217.07 | 85739.09 | 17633900.19 | 433944.03 | 374 | 40 | 410 | -4
ODESSA | WARD | BI 20-D | 403049 | 2018-10-29 | 562624.3 | 22292.45 | 616270.01 | 31353.26 | 180 | 0 | 25 | -155
ODESSA | WARD | FM 1776 | 226201016 | 2018-11-30 | 9505066.17 | 0 | 9497027.32 | -8038.85 | 75 | 0 | 52 | -23
PARIS | FRANKLIN | FM 21 | 63301021 | 2018-12-18 | 1539938.35 | 0 | 1571991.15 | 32052.8 | 95 | 0 | 70 | -25
PARIS | GRAYSON | FM 902 | 51001026 | 2018-11-30 | 7337375.52 | -609445.59 | 6611338.92 | -116591.01 | 304 | 0 | 342 | 38
PARIS | GRAYSON | FM 121 | 72901037 | 2019-02-28 | 4609064.04 | -67194.36 | 4472054.43 | -69815.25 | 272 | 0 | 272 | 0
PARIS | HUNT | SH 34 | 17307055 | 2018-09-24 | 1683587.85 | 0 | 1555306.13 | -128281.72 | 102 | 0 | 89 | -13
PHARR | BROOKS | US 281 | 25504085 | 2019-01-17 | 1269572.56 | 72796.27 | 1401269.9 | 58901.07 | 90 | 207 | 297 | 0
PHARR | BROOKS | US 281 | 25505040 | 2019-01-11 | 2511870.22 | 0 | 2751934.96 | 240064.74 | 69 | 0 | 69 | 0
PHARR | CAMERON | SH 48 | 22007058 | 2018-10-03 | 280100.65 | 0 | 276453.55 | -3647.1 | 78 | 0 | 78 | 0
PHARR | CAMERON | CS | 92106270 | 2018-09-07 | 899908.1 | 47635.79 | 884006.77 | -63537.12 | 140 | 31 | 161 | -10
PHARR | CAMERON | FM 803 | 113802015 | 2018-10-03 | 10494854.48 | 801950 | 11704207.13 | 407402.65 | 560 | 70 | 630 | 0
PHARR | HIDALGO | IH 69C | 25507141 | 2018-11-07 | 1572940.52 | 99601.59 | 1716786.26 | 44244.15 | 79 | 0 | 61 | -18
PHARR | HIDALGO | CS | 92102140 | 2019-01-31 | 5206108.37 | 138640.04 | 5581750.74 | 237002.33 | 440 | 15 | 301 | -154
PHARR | HIDALGO | VA | 92102318 | 2019-01-15 | 1608279.03 | 33823.8 | 1598042.32 | -44060.51 | 335 | 0 | 295 | -40
PHARR | HIDALGO | VA | 92102347 | 2019-01-31 | 3174549.5 | 11922.45 | 3301912.77 | 115440.82 | 371 | 0 | 307 | -64
PHARR | HIDALGO | FM 1925 | 180301037 | 2018-09-05 | 8117383.1 | 7590.31 | 8560282.08 | 435308.67 | 420 | 0 | 285 | -135
PHARR | STARR | US 83 | 3807058 | 2019-02-01 | 1229939.11 | 27604.18 | 1370170.41 | 112627.12 | 100 | 67 | 192 | 25
PHARR | STARR | US 83 | 3901085 | 2019-01-09 | 1786301.9 | 0 | 1774361.3 | -11940.6 | 240 | 0 | 231 | -9
PHARR | STARR | FM 755 | 110304027 | 2019-02-08 | 10733925.44 | 1514074.74 | 12393049.87 | 145049.69 | 380 | 389 | 869 | 100
PHARR | WILLACY | CR | 92127035 | 2019-01-23 | 826051.45 | 301564.92 | 1114179.03 | -13437.34 | 184 | 0 | 167 | -17
SAN ANGELO | CONCHO | FM 380 | 55502020 | 2019-02-06 | 2162110.6 | 116509.64 | 2400119.03 | 121498.79 | 135 | 66 | 316 | 115
SAN ANGELO | CONCHO | FM 765 | 87004040 | 2019-01-14 | 2792437.52 | 376.96 | 2730993.02 | -61821.46 | 165 | 0 | 195 | 30
SAN ANGELO | CROCKETT | IH 10 | 14011044 | 2018-10-30 | 4567928.74 | 27403.21 | 4442396.59 | -152935.36 | 75 | 3 | 92 | 14
SAN ANGELO | REAGAN | US 67 | 7701029 | 2019-02-28 | 6531381.35 | 37307.96 | 6925991.64 | 357302.33 | 131 | 0 | 115 | -16
SAN ANGELO | RUNNELS | US 67 | 15801080 | 2018-11-27 | 105297 | 9266.1 | 157113.4 | 42550.3 | 11 | 2 | 13 | 0
SAN ANGELO | SUTTON | SL 467 | 14114016 | 2018-11-01 | 5905799.1 | -655.75 | 5801197.42 | -103945.93 | 128 | 0 | 40 | -88
SAN ANGELO | SUTTON | US 277 | 16001040 | 2018-10-30 | 1633755.5 | 0 | 1652161.2 | 18405.7 | 37 | 0 | 40 | 3
SAN ANGELO | TOM GREEN | US 67 | 7706095 | 2018-09-28 | 6339169.41 | 1056338.41 | 7749099.64 | 353591.82 | 175 | 136 | 315 | 4
SAN ANTONIO | ATASCOSA | SH 97 | 32806028 | 2018-11-27 | 18692104.35 | 1917480.22 | 21224755.09 | 615170.52 | 331 | 143 | 474 | 0
SAN ANTONIO | ATASCOSA | SH 16 | 61302058 | 2018-10-10 | 13488214.03 | 423791.97 | 13624465.14 | -287540.86 | 146 | 178 | 407 | 83
SAN ANTONIO | BEXAR | IH 35 | 1709098 | 2018-10-05 | 329686.97 | 0 | 337161.97 | 7475 | 40 | 0 | 14 | -26
SAN ANTONIO | BEXAR | IH 10 | 7207059 | 2019-02-01 | 19342271.59 | 1690000.42 | 21030267.61 | -2004.4 | 376 | 202 | 545 | -33
SAN ANTONIO | BEXAR | US 281 | 7308181 | 2019-02-21 | 8673181.42 | 831991.48 | 10426660.53 | 921487.63 | 333 | 20 | 313 | -40
SAN ANTONIO | BEXAR | IH 410 | 52104278 | 2019-02-21 | 3839721.96 | 153380.68 | 4140096.93 | 146994.29 | 88 | 21 | 109 | 0
SAN ANTONIO | BEXAR | VA | 91500155 | 2019-02-26 | 998524.12 | -55502.28 | 934928.12 | -8093.72 | 208 | 570 | 813 | 35
SAN ANTONIO | BEXAR | VA | 91500166 | 2019-01-17 | 1355867.97 | 16000 | 1079784.84 | -292083.13 | 320 | 0 | 290 | -30
SAN ANTONIO | BEXAR | VA | 91512555 | 2019-02-21 | 5286690.36 | 88508.21 | 5058670.49 | -316528.08 | 309 | 29 | 329 | -9
SAN ANTONIO | KENDALL | IH 10 | 7206071 | 2019-02-01 | 3536440.57 | 26494.91 | 3194381.11 | -368554.37 | 136 | 125 | 640 | 379
SAN ANTONIO | KENDALL | US 87 | 7214028 | 2019-01-31 | 1983029 | 641492.93 | 2624521.97 | 0.04 | 80 | 0 | 63 | -17
SAN ANTONIO | KENDALL | RM 473 | 14210024 | 2019-01-17 | 184057.65 | 18182.45 | 207295.28 | 5055.18 | 59 | 0 | 34 | -25
SAN ANTONIO | KENDALL | CS | 91511028 | 2019-01-31 | 514522.7 | -9606 | 495157.11 | -9759.59 | 86 | 5 | 107 | 16
SAN ANTONIO | KERR | IH 10 | 14214062 | 2018-09-06 | 2211020.1 | 165361.05 | 2493851.15 | 117470 | 87 | 11 | 98 | 0
SAN ANTONIO | MEDINA | FM 462 | 84801041 | 2019-01-30 | 2846962.56 | 79089.94 | 2755770.87 | -170281.63 | 198 | 0 | 196 | -2
SAN ANTONIO | WILSON | CR | 91514031 | 2019-02-26 | 315294.86 | 43215.78 | 342347.45 | -16163.19 | 86 | 6 | 92 | 0
TYLER | ANDERSON | US 287 | 12204038 | 2019-01-17 | 11487064.25 | 29289.67 | 11431919.57 | -84434.35 | 110 | 22 | 144 | 12
TYLER | ANDERSON | US 79 | 20507043 | 2018-11-26 | 41986850.18 | 1802932.66 | 45956373.14 | 2166590.3 | 880 | 147 | 1001 | -26
TYLER | GREGG | IH 20 | 49507075 | 2018-12-06 | 2447523.75 | 26765.28 | 2591521.35 | 117232.32 | 50 | 0 | 50 | 0
TYLER | HENDERSON | US 175 | 19801023 | 2019-02-21 | 39261003.89 | 1881464.98 | 45265660.64 | 4123191.77 | 605 | 51 | 650 | -6
TYLER | SMITH | US 69 | 19101085 | 2019-02-13 | 3628777 | -49632.63 | 3691039.27 | 111894.9 | 62 | 0 | 57 | -5
TYLER | SMITH | VA | 91000104 | 2018-09-25 | 159363.94 | 20584.81 | 160478.76 | -19469.99 | 36 | 14 | 83 | 33
TYLER | SMITH | FM 850 | 116301022 | 2018-09-27 | 1077661.37 | -12835.6 | 1088780.6 | 23954.83 | 100 | 9 | 109 | 0
TYLER | VAN ZANDT | US 80 | 9507059 | 2019-02-11 | 10067448.29 | -362818.27 | 9067503.17 | -637126.85 | 91 | 8 | 100 | 1
TYLER | VAN ZANDT | IH 20 | 49502063 | 2018-10-19 | 2403541.75 | 4430.8 | 2611925.65 | 203953.1 | 313 | 0 | 211 | -102
TYLER | VAN ZANDT | IH 20 | 49503061 | 2018-09-14 | 4570487.36 | 1439822.93 | 5937634.19 | -72676.1 | 215 | 166 | 380 | -1
TYLER | VAN ZANDT | FM 16 | 52203026 | 2018-10-16 | 496651.35 | -26106.41 | 441039.87 | -29505.07 | 48 | 0 | 45 | -3
TYLER | VAN ZANDT | FM 314 | 74501015 | 2018-11-19 | 11961746.05 | -369312.65 | 11137518.47 | -454914.93 | 486 | 71 | 551 | -6
TYLER | VAN ZANDT | CR | 91012066 | 2019-02-21 | 1498798.05 | 31189.7 | 1592112.35 | 62124.6 | 162 | 0 | 162 | 0
WACO | BELL | FM 817 | 1505049 | 2019-02-22 | 1599937.89 | 108847.61 | 1696770.87 | -12014.63 | 170 | 0 | 162 | -8
WACO | BELL | IH 35 | 1506071 | 2018-11-12 | 106887770.94 | 6391431.6 | 111499012.6 | -1780189.94 | 1224 | 354 | 1770 | 192
WACO | BELL | IH 35 | 1507065 | 2018-11-12 | 70449357.09 | 2924918.53 | 73702268.1 | 327992.48 | 920 | 239 | 1350 | 191
WACO | BELL | FM 2305 | 23205016 | 2018-11-13 | 888222 | 7565.8 | 906512.32 | 10724.52 | 30 | 0 | 23 | -7
WACO | BELL | FM 2410 | 230402042 | 2018-10-09 | 795655.68 | 63582.28 | 899030.82 | 39792.86 | 36 | 0 | 36 | 0
WACO | BELL | FM 2484 | 230403012 | 2018-10-24 | 824244.8 | 73398.96 | 823507.56 | -74136.2 | 165 | 9 | 195 | 21
WACO | BOSQUE | CR | 90928022 | 2018-10-05 | 1451177 | 32387.6 | 1532619.43 | 49054.83 | 170 | 0 | 182 | 12
WACO | CORYELL | US 84 | 5505050 | 2018-11-07 | 7919405.82 | 27999.9 | 8090772.07 | 143366.35 | 45 | 0 | 50 | 5
WACO | FALLS | SH 7 | 38201044 | 2018-12-06 | 2882946.87 | -290312.72 | 2608337.82 | 15703.67 | 94 | 0 | 75 | -19
WACO | FALLS | FM 935 | 75204024 | 2018-12-06 | 3524688.87 | 18550 | 3450100.09 | -93138.78 | 277 | 0 | 223 | -54
WACO | FALLS | FM 434 | 107701025 | 2019-02-21 | 1114102.36 | 27390.48 | 1173168.55 | 31675.71 | 149 | 2 | 140 | -11
WACO | HAMILTON | SH 6 | 25803042 | 2018-10-18 | 278277.5 | 0 | 167471.37 | -110806.13 | 30 | 0 | 174 | 144
WACO | HILL | SH 81 | 1405039 | 2019-01-23 | 1999584.5 | 0 | 2038351.83 | 38767.33 | 75 | 0 | 47 | -28
WACO | LIMESTONE | FM 1245 | 119103030 | 2018-12-20 | 3635770.18 | -43927.16 | 3941847.27 | 350004.25 | 90 | 9 | 98 | -1
WACO | MC LENNAN | US 84 | 5601033 | 2018-11-02 | 9405386.36 | 273032.35 | 9465198.76 | -213219.95 | 404 | 15 | 359 | -60
WACO | MC LENNAN | SH 6 | 25809139 | 2018-09-04 | 14481308.41 | 604442.58 | 15211406.69 | 125655.7 | 255 | 93 | 363 | 15
WACO | MC LENNAN | SH 317 | 39803058 | 2019-01-23 | 9139073.58 | 743721.01 | 10261042.63 | 378248.04 | 361 | 60 | 394 | -27
WACO | MC LENNAN | FM 1637 | 83303049 | 2018-12-06 | 278606.89 | -14640 | 294644.22 | 30677.33 | 30 | 0 | 32 | 2
WACO | MC LENNAN | CR | 90922175 | 2019-02-05 | 586252.76 | 0 | 575086.86 | -11165.9 | 128 | 0 | 111 | -17
WACO | MC LENNAN | FM 3223 | 333001010 | 2018-11-20 | 845727.71 | 58436.7 | 830622.29 | -73542.12 | 45 | 0 | 40 | -5
WICHITA FALLS | ARCHER | US 277 | 15605049 | 2019-02-26 | 14393280.57 | 183645.95 | 15110184.15 | 533257.63 | 313 | 33 | 467 | 121
WICHITA FALLS | CLAY | FM 810 | 39102018 | 2018-09-27 | 1895820.8 | 0 | 1900963.7 | 5142.9 | 170 | 0 | 123 | -47
WICHITA FALLS | COOKE | US 82 | 4407070 | 2019-01-07 | 95022 | 0 | 95165.9 | 143.9 | 28 | 0 | 28 | 0
WICHITA FALLS | COOKE | US 82 | 4408067 | 2018-11-16 | 4684274.46 | 979702.28 | 5985496.32 | 321519.58 | 192 | 171 | 362 | -1
WICHITA FALLS | COOKE | US 82 | 4501061 | 2018-12-17 | 2124211.95 | 0 | 2355793.78 | 231581.83 | 50 | 0 | 45 | -5
WICHITA FALLS | MONTAGUE | US 81 | 1305060 | 2019-01-17 | 3439171.42 | 6271.6 | 3521217.41 | 75774.39 | 100 | 6 | 129 | 23
WICHITA FALLS | MONTAGUE | SH 59 | 23902037 | 2019-01-07 | 1182793.98 | 0 | 1173085.34 | -9708.64 | 60 | 0 | 66 | 6
WICHITA FALLS | WICHITA | IH 44 | 15607109 | 2018-09-14 | 1167403.5 | 19380 | 1199260.6 | 12477.1 | 85 | 2 | 82 | -5
WICHITA FALLS | WICHITA | FM 369 | 80202066 | 2018-10-25 | 2496814.42 | 262701.85 | 2593643.75 | -165872.52 | 268 | 20 | 275 | -13
WICHITA FALLS | WICHITA | VA | 90300083 | 2018-10-01 | 938930 | 0 | 954411.14 | 15481.14 | 68 | 0 | 62 | -6
WICHITA FALLS | WICHITA | CS | 90303083 | 2018-11-30 | 1293885 | -20368.8 | 1304038.18 | 30521.98 | 123 | 0 | 86 | -37
WICHITA FALLS | WICHITA | FM 2650 | 264401010 | 2019-01-10 | 4231186.98 | 210242.86 | 4207010.59 | -234419.25 | 149 | 80 | 223 | -6
WICHITA FALLS | WILBARGER | US 287 | 4305106 | 2018-12-21 | 6016230.12 | 0 | 6094523.2 | 78293.08 | 62 | 0 | 62 | 0
WICHITA FALLS | WILBARGER | FM 91 | 70201014 | 2019-02-04 | 2458571.5 | 64855.03 | 2573148.17 | 49721.64 | 187 | 15 | 241 | 39
WICHITA FALLS | YOUNG | SH 114 | 13308035 | 2018-11-19 | 1069536.55 | 136992.63 | 1300016.92 | 93487.74 | 54 | 5 | 48 | -11
YOAKUM | AUSTIN | SH 159 | 40802045 | 2018-12-21 | 11278713.11 | 730490 | 12352511.96 | 343308.85 | 417 | 37 | 454 | 0
YOAKUM | AUSTIN | FM 1458 | 52703024 | 2018-12-11 | 1002148.6 | 0 | 1014256.6 | 12108 | 90 | 0 | 90 | 0
YOAKUM | AUSTIN | FM 1094 | 172102012 | 2018-10-22 | 3954433.25 | 0 | 3854012.03 | -100421.22 | 150 | 0 | 155 | 5
YOAKUM | DE WITT | US 87 | 14308087 | 2018-11-16 | 930045 | -4199.11 | 878008.15 | -47837.74 | 149 | 3 | 214 | 62
YOAKUM | DE WITT | SH 119 | 35903026 | 2018-12-21 | 5170038.51 | 10781.16 | 5051908.89 | -128910.78 | 150 | 96 | 244 | -2
YOAKUM | DE WITT | CR | 91317041 | 2018-12-31 | 323694 | 0 | 300270 | -23424 | 45 | 0 | 67 | 22
YOAKUM | DE WITT | FM 966 | 216602007 | 2018-12-14 | 338050 | 0 | 325827 | -12223 | 45 | 0 | 44 | -1
YOAKUM | FAYETTE | SH 71 | 26507049 | 2018-10-01 | 2399994.55 | 0 | 2560164.31 | 160169.76 | 45 | 0 | 44 | -1
YOAKUM | FAYETTE | SH 71 | 26601075 | 2018-12-14 | 681093.2 | 2829.25 | 690097.45 | 6175 | 90 | 1 | 83 | -8
YOAKUM | FAYETTE | SH 95 | 32401026 | 2018-09-19 | 1046229.46 | 0 | 1033366.3 | -12863.16 | 30 | 0 | 54 | 24
YOAKUM | FAYETTE | CR | 91328064 | 2018-12-14 | 349287.93 | 0 | 338155.93 | -11132 | 90 | 0 | 44 | -46
YOAKUM | FAYETTE | FM 1457 | 144101012 | 2018-10-18 | 1089950.26 | 82107.69 | 1184542.56 | 12484.61 | 120 | 0 | 106 | -14
YOAKUM | GONZALES | SH 80 | 28704037 | 2018-11-19 | 3460417.8 | 4500 | 3561503.27 | 96585.47 | 60 | 0 | 60 | 0
YOAKUM | LAVACA | FM 531 | 26910023 | 2018-10-18 | 1574475.26 | 13864.69 | 1558532.84 | -29807.11 | 120 | 0 | 145 | 25
YOAKUM | LAVACA | FM 532 | 100703021 | 2018-09-14 | 2844207.33 | 29097.6 | 2952972.43 | 79667.5 | 120 | 7 | 126 | -1
YOAKUM | MATAGORDA | BS 35-H | 17914008 | 2018-11-15 | 1611272.54 | 1378.65 | 1616098.24 | 3447.05 | 45 | 0 | 48 | 3
YOAKUM | WHARTON | CR | 91309060 | 2018-10-19 | 902792.1 | 0 | 890288.68 | -12503.42 | 100 | 0 | 109 | 9
YOAKUM | WHARTON | CR | 91309069 | 2019-02-20 | 425246.7 | 0 | 405601.85 | -19644.85 | 75 | 0 | 75 | 0