## BUDGET-SCHEDULE
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [11 empty] | Highway Construction Projects Completed September 1, 2019–February 29, 2020
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | FEBRUARY | 29 | 2020
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | AMOUNT PAID | UNDER/OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | OVER/UNDER SCHEDULE | OT | NOT
CHILDRESS | 0541-01-029 | BRISCOE | SH 256 | 2019-09-03 | 7280426.67 | 10551.15 | 7632142.79 | 351716.12 | 72 | 37 | 0 | 35 | 1 | 0
AUSTIN | 0320-03-099 | WILLIAMSON | SH 95 | 2019-09-04 | 1149642.65 | 99261.02 | 1270376.8 | 120734.15 | 64 | 90 | 26 | 0 | 0 | 1
BEAUMONT | 0920-00-119 | JEFFERSON | VA | 2019-09-05 | 624968.15 | 0 | 622906.32 | -2061.83 | 175 | 32 | 0 | 143 | 1 | 0
YOAKUM | 0913-20-084 | AUSTIN | CR | 2019-09-05 | 525692.63 | 0 | 486738.83 | -38953.8 | 60 | 71 | 0 | -11 | 0 | 1
ABILENE | 0033-06-107 | TAYLOR | US 83 | 2019-09-06 | 8326091.95 | 713281.3 | 9409092.04 | 1083000.09 | 294 | 371 | 83 | 6 | 0 | 1
WACO | 1594-02-012 | CORYELL | FM 1783 | 2019-09-06 | 1048921.12 | 27987.66 | 1075435.86 | 26514.74 | 170 | 152 | 0 | 18 | 1 | 0
DALLAS | 0596-02-039 | ELLIS | FM 66 | 2019-09-10 | 3421432.25 | 350096.59 | 3642333.21 | 220900.96 | 396 | 489 | 15 | -78 | 0 | 1
DALLAS | 0918-00-267 | DALLAS | VA | 2019-09-10 | 1699468.03 | 38587.97 | 1749673.92 | 50205.89 | 240 | 244 | 5 | 1 | 1 | 0
FORT WORTH | 0902-20-111 | WISE | CR | 2019-09-10 | 516000 | 0 | 504465.72 | -11534.28 | 107 | 120 | 13 | 0 | 0 | 1
CORPUS CHRISTI | 1052-01-076 | NUECES | FM 666 | 2019-09-11 | 8117215.71 | 216664.15 | 8485418.5 | 368202.79 | 204 | 298 | 84 | -10 | 0 | 1
YOAKUM | 1411-02-011 | AUSTIN | FM 1457 | 2019-09-11 | 4469341.79 | -30284.63 | 4427707.49 | -41634.3 | 150 | 182 | 32 | 0 | 0 | 1
TYLER | 0096-04-066 | GREGG | US 80 | 2019-09-12 | 3538933.21 | 154691.64 | 3832243.66 | 293310.45 | 190 | 304 | 117 | 3 | 0 | 1
WACO | 0774-03-014 | HAMILTON | FM 1602 | 2019-09-12 | 3288708.72 | 1290803.28 | 4152416.04 | 863707.32 | 255 | 285 | 30 | 0 | 0 | 1
CHILDRESS | 0032-05-041 | KING | US 83 | 2019-09-13 | 4186076.22 | 60828.18 | 4221760.29 | 35684.07 | 68 | 80 | 5 | -7 | 0 | 1
PARIS | 2659-02-001 | HUNT | SS 1570 | 2019-09-13 | 7109675.99 | 171804.39 | 7169206.01 | 59530.02 | 300 | 283 | 0 | 17 | 1 | 0
TYLER | 1673-02-017 | VAN ZANDT | FM 1861 | 2019-09-13 | 2436392.26 | 436727.75 | 2658601.12 | 222208.86 | 136 | 191 | 55 | 0 | 0 | 1
PHARR | 0482-02-033 | BROOKS | SH 285 | 2019-09-16 | 2763466.28 | 0 | 2730331.32 | -33134.96 | 120 | 58 | 0 | 62 | 1 | 0
PHARR | 1425-03-061 | CAMERON | FM 106 | 2019-09-16 | 1737655.82 | 0 | 1695291.46 | -42364.36 | 69 | 58 | 0 | 11 | 1 | 0
WACO | 0320-02-036 | BELL | SH 95 | 2019-09-16 | 6123477.87 | -400785.83 | 5878783.72 | -244694.15 | 277 | 298 | 27 | 6 | 1 | 0
WICHITA FALLS | 0125-03-046 | THROCKMORTON | US 283 | 2019-09-16 | 1720296.45 | 768456.18 | 2486257.58 | 765961.13 | 136 | 180 | 65 | 21 | 0 | 1
WICHITA FALLS | 0903-00-088 | WICHITA | VA | 2019-09-16 | 497863.8 | 75452.86 | 573243.55 | 75379.75 | 43 | 56 | 14 | 1 | 0 | 1
CORPUS CHRISTI | 0254-03-079 | JIM WELLS | US 281 | 2019-09-17 | 9980994.92 | 24060.66 | 10811473.36 | 830478.44 | 119 | 135 | 16 | 0 | 0 | 1
CORPUS CHRISTI | 1069-01-037 | NUECES | SH 357 | 2019-09-17 | 6082985.19 | 205734.05 | 6278106.82 | 157121.63 | 89 | 104 | 20 | 5 | 0 | 1
PARIS | 0047-02-134 | GRAYSON | US 75 | 2019-09-17 | 930195 | 103010.96 | 1153710.05 | 223515.05 | 57 | 66 | 10 | 1 | 0 | 1
PARIS | 0047-02-138 | GRAYSON | US 75 | 2019-09-18 | 6395385.04 | -2442931.36 | 3935589.44 | -2459795.6 | 120 | 120 | 0 | 0 | 1 | 0
BROWNWOOD | 0127-01-030 | EASTLAND | US 183 | 2019-09-20 | 3372833.81 | 325402.82 | 3973446.19 | 600612.38 | 221 | 275 | 55 | 1 | 0 | 1
CORPUS CHRISTI | 0155-02-026 | GOLIAD | US 183 | 2019-09-20 | 858712.66 | 490134.33 | 1245017.62 | 386304.96 | 187 | 190 | 0 | -3 | 1 | 0
WACO | 0209-07-045 | MCLENNAN | FM 933 | 2019-09-20 | 1033599.85 | -30363.57 | 1006014.08 | -27585.77 | 120 | 135 | 19 | 4 | 0 | 1
AUSTIN | 0334-05-032 | LEE | FM 141 | 2019-09-23 | 1244148.05 | 216076.53 | 1430614.79 | 186466.74 | 35 | 30 | 0 | 5 | 1 | 0
DALLAS | 0816-02-079 | DENTON | FM 455 | 2019-09-23 | 1280176.58 | 72305.8 | 1260654.39 | -19522.19 | 159 | 159 | 7 | 7 | 1 | 0
DALLAS | 0918-46-280 | DENTON | CS | 2019-09-23 | 1284000 | 10400 | 1272390.62 | -11609.38 | 190 | 231 | 14 | -27 | 0 | 1
HOUSTON | 0187-05-048 | FORT BEND | SS 10 | 2019-09-23 | 11736891.34 | -212971.12 | 11527184.45 | -209706.89 | 219 | 210 | 0 | 9 | 1 | 0
HOUSTON | 0912-71-046 | HARRIS | CS | 2019-09-23 | 4241559.87 | -247860.76 | 3873507.96 | -350317.63 | 300 | 263 | 0 | 37 | 1 | 0
PARIS | 0901-28-085 | HOPKINS | CR | 2019-09-23 | 253519.42 | 0 | 258610.22 | 5090.8 | 74 | 46 | 0 | 28 | 1 | 0
SAN ANTONIO | 0072-06-072 | KENDALL | IH 10 | 2019-09-23 | 11578717.7 | 123260.81 | 11701978.54 | 123260.84 | 416 | 531 | 78 | -37 | 0 | 1
SAN ANTONIO | 0072-12-198 | BEXAR | IH 10 | 2019-09-23 | 1598613.31 | 133160.95 | 1792753.1 | 194139.79 | 98 | 126 | 32 | 4 | 0 | 1
SAN ANTONIO | 1272-01-019 | COMAL | FM 1101 | 2019-09-24 | 195334.08 | 0 | 201380.52 | 6046.44 | 119 | 29 | 0 | 90 | 1 | 0
BRYAN | 0205-05-048 | LEON | US 79 | 2019-09-26 | 2951399.98 | 676299.5 | 3817460.99 | 866061.01 | 190 | 196 | 6 | 0 | 1 | 0
DALLAS | 0918-46-274 | DENTON | CS | 2019-09-26 | 1648413.6 | 45493.38 | 1705113.95 | 56700.35 | 286 | 367 | 46 | -35 | 0 | 1
DALLAS | 1785-01-032 | DENTON | FM 1830 | 2019-09-26 | 5901345.74 | 175154.57 | 5697681.54 | -203664.2 | 400 | 295 | 0 | 105 | 1 | 0
LUFKIN | 0911-38-069 | ANGELINA | CR | 2019-09-26 | 388000.54 | 158098.7 | 530797.97 | 142797.43 | 43 | 48 | 14 | 9 | 0 | 1
TYLER | 0109-02-026 | ANDERSON | US 287 | 2019-09-26 | 3987345.3 | -106082.68 | 3889867.42 | -97477.88 | 73 | 90 | 0 | -17 | 0 | 1
WICHITA FALLS | 0013-01-010 | MONTAGUE | US 81 | 2019-09-26 | 1399791.06 | 0 | 1278012.98 | -121778.08 | 98 | 117 | 0 | -19 | 0 | 1
ABILENE | 0053-12-065 | NOLAN | US 84 | 2019-09-27 | 3160245.06 | 17689.21 | 3314888.5 | 154643.44 | 97 | 116 | 0 | -19 | 0 | 1
WACO | 0184-03-038 | BELL | SH 53 | 2019-09-27 | 1032767.55 | 64540 | 1213329.54 | 180561.99 | 30 | 35 | 0 | -5 | 0 | 1
BRYAN | 0186-05-040 | WASHINGTON | SH 36 | 2019-09-30 | 1448042.29 | 16959.42 | 1439501.31 | -8540.98 | 70 | 71 | 1 | 0 | 1 | 0
PHARR | 0921-02-212 | HIDALGO | CR | 2019-09-30 | 1033763.03 | 0 | 1042776.77 | 9013.74 | 180 | 180 | 0 | 0 | 1 | 0
WACO | 0909-40-074 | LIMESTONE | CR | 2019-10-01 | 1515689.4 | 65090.4 | 1594153.3 | 78463.9 | 192 | 215 | 27 | 4 | 0 | 1
DALLAS | 0009-12-211 | ROCKWALL | IH 30 | 2019-10-03 | 3411242.52 | 171597.54 | 3238305.24 | -172937.28 | 144 | 151 | 0 | -7 | 1 | 0
DALLAS | 0196-03-262 | DALLAS | IH 35E | 2019-10-03 | 6356006.29 | 265030.51 | 6432303.19 | 76296.9 | 183 | 215 | 32 | 0 | 0 | 1
DALLAS | 1290-01-012 | ROCKWALL | FM 1141 | 2019-10-03 | 2750739.99 | 47453.32 | 2848178.17 | 97438.18 | 177 | 243 | 65 | -1 | 0 | 1
AUSTIN | 1378-01-038 | TRAVIS | RM 1431 | 2019-10-04 | 617104.85 | 49419.2 | 708166.1 | 91061.25 | 46 | 42 | 0 | 4 | 1 | 0
WACO | 0015-01-229 | MCLENNAN | IH 35 | 2019-10-04 | 26959896.82 | 3111104.47 | 30329304.25 | 3369407.43 | 459 | 952 | 459 | -34 | 0 | 1
WICHITA FALLS | 0125-02-033 | THROCKMORTON | US 183 | 2019-10-04 | 1743252.56 | 0 | 1769312.24 | 26059.68 | 48 | 54 | 0 | -6 | 0 | 1
ABILENE | 0033-03-029 | JONES | US 83 | 2019-10-07 | 4161245.37 | 826722.94 | 5169625.48 | 1008380.11 | 242 | 317 | 75 | 0 | 0 | 1
DALLAS | 0095-13-037 | DALLAS | IH 20 | 2019-10-07 | 3414157.04 | 13933.09 | 3442027.82 | 27870.78 | 218 | 213 | 3 | 8 | 1 | 0
TYLER | 0108-03-042 | HENDERSON | SH 19 | 2019-10-07 | 421343.1 | -35947.14 | 387777.97 | -33565.13 | 42 | 48 | 0 | -6 | 0 | 1
TYLER | 0345-03-023 | CHEROKEE | SH 110 | 2019-10-07 | 491833.83 | -186821.3 | 304987.54 | -186846.29 | 55 | 36 | 0 | 19 | 1 | 0
AUSTIN | 0471-05-047 | BASTROP | SH 21 | 2019-10-09 | 2157229.45 | 106201.07 | 2186024.45 | 28795 | 109 | 129 | 20 | 0 | 0 | 1
LUBBOCK | 0905-00-111 | LUBBOCK | VA | 2019-10-09 | 721754.07 | 0 | 691244.84 | -30509.23 | 90 | 84 | 0 | 6 | 1 | 0
FORT WORTH | 0902-40-027 | JACK | CR | 2019-10-11 | 434443.44 | 12022.4 | 440836.43 | 6392.99 | 107 | 139 | 32 | 0 | 0 | 1
AUSTIN | 0265-02-035 | TRAVIS | SH 71 | 2019-10-14 | 184200.6 | -11400 | 170363.15 | -13837.45 | 22 | 13 | 0 | 9 | 1 | 0
FORT WORTH | 0902-39-021 | PALO PINTO | CR | 2019-10-14 | 826138 | 0 | 821687.13 | -4450.87 | 128 | 169 | 0 | -41 | 0 | 1
ODESSA | 0005-01-109 | ECTOR | BI 20-E | 2019-10-14 | 518770.1 | -1178.9 | 535119.64 | 16349.54 | 160 | 99 | 0 | 61 | 1 | 0
FORT WORTH | 0008-15-046 | TARRANT | IH 820 | 2019-10-15 | 3231503.76 | 1510930.2 | 4627183.01 | 1395679.25 | 128 | 156 | 34 | 6 | 0 | 1
FORT WORTH | 0008-15-050 | TARRANT | IH 820 | 2019-10-15 | 485156.99 | 190064.09 | 639671.2 | 154514.21 | 120 | 118 | 0 | 2 | 1 | 0
BRYAN | 0917-29-120 | BRAZOS | CR | 2019-10-17 | 772705.37 | 124244.16 | 968258.5 | 195553.13 | 171 | 119 | 10 | 62 | 1 | 0
CHILDRESS | 0132-01-048 | DICKENS | US 82 | 2019-10-17 | 2969974.51 | 76377.22 | 3111888.17 | 141913.66 | 67 | 48 | 0 | 19 | 1 | 0
CHILDRESS | 0925-08-019 | CHILDRESS | CR | 2019-10-17 | 1306717.75 | 14000 | 1319933.75 | 13216 | 87 | 129 | 36 | -6 | 0 | 1
FORT WORTH | 3372-01-016 | JOHNSON | FM 3391 | 2019-10-17 | 2090427.76 | -119653.73 | 2009141.82 | -81285.94 | 54 | 57 | 8 | 5 | 1 | 0
HOUSTON | 0720-02-087 | MONTGOMERY | FM 149 | 2019-10-18 | 10198541.18 | 646208.08 | 10471219.3 | 272678.12 | 183 | 195 | 32 | 20 | 1 | 0
LUBBOCK | 0453-02-018 | CROSBY | US 62 | 2019-10-18 | 8589407.73 | 1452954.85 | 9638925.9 | 1049518.17 | 92 | 142 | 50 | 0 | 0 | 1
LUFKIN | 1407-03-018 | NACOGDOCHES | FM 1275 | 2019-10-18 | 260153.8 | -479 | 284286.62 | 24132.82 | 48 | 47 | 0 | 1 | 1 | 0
YOAKUM | 1007-02-017 | GONZALES | FM 532 | 2019-10-18 | 8097588.87 | 148716.35 | 8469987.92 | 372399.05 | 285 | 369 | 16 | -68 | 0 | 1
CORPUS CHRISTI | 0074-05-097 | SAN PATRICIO | IH 37 | 2019-10-21 | 6225552.23 | -1695.75 | 6261991.91 | 36439.68 | 151 | 160 | 9 | 0 | 1 | 0
LUFKIN | 0937-03-016 | HOUSTON | FM 227 | 2019-10-21 | 1576406 | 0 | 1384271.89 | -192134.11 | 223 | 219 | 0 | 4 | 1 | 0
WACO | 0120-01-019 | HAMILTON | SH 22 | 2019-10-21 | 1642121.95 | 83328.25 | 1701243.33 | 59121.38 | 45 | 36 | 0 | 9 | 1 | 0
WACO | 0162-01-094 | MCLENNAN | US 84 | 2019-10-21 | 85120.8 | 1000 | 86957.25 | 1836.45 | 30 | 9 | 0 | 21 | 1 | 0
WACO | 0909-39-127 | CORYELL | CR | 2019-10-21 | 1020198.17 | 56251.18 | 1050225.37 | 30027.2 | 192 | 186 | 0 | 6 | 1 | 0
WICHITA FALLS | 0134-03-032 | YOUNG | US 380 | 2019-10-21 | 2678507.13 | -3206 | 2707475.57 | 28968.44 | 54 | 32 | 1 | 23 | 1 | 0
FORT WORTH | 0902-00-213 | TARRANT | VA | 2019-10-23 | 1777800 | 1371584.56 | 3309469.72 | 1531669.72 | 365 | 320 | 0 | 45 | 1 | 0
HOUSTON | 3312-02-014 | GALVESTON | FM 270 | 2019-10-23 | 2299180.8 | 304061.76 | 2825180.13 | 482661.13 | 122 | 118 | 0 | 4 | 1 | 0
HOUSTON | 3510-06-014 | HARRIS | SH 99 | 2019-10-23 | 3375271 | 947680.91 | 4279876.2 | 904605.2 | 106 | 129 | 26 | 3 | 0 | 1
LAREDO | 0018-01-097 | LA SALLE | IH 35 | 2019-10-23 | 5687629 | 253721.52 | 6532274.59 | 844645.59 | 107 | 107 | 0 | 0 | 1 | 0
LAREDO | 2150-03-025 | WEBB | FM 1472 | 2019-10-23 | 2940497.26 | 44322.88 | 2893322.86 | -47174.4 | 200 | 200 | 0 | 0 | 1 | 0
SAN ANTONIO | 0328-05-037 | ATASCOSA | SH 97 | 2019-10-23 | 17494208.24 | 346709.21 | 17782809.11 | 288600.87 | 339 | 742 | 292 | -111 | 0 | 1
FORT WORTH | 0014-16-276 | TARRANT | IH 35W | 2019-10-24 | 1213542 | 79431.85 | 1364343.28 | 150801.28 | 278 | 225 | 5 | 58 | 1 | 0
PARIS | 0173-06-048 | HUNT | SH 34 | 2019-10-24 | 61367.3 | 0 | 54989.31 | -6377.99 | 60 | 56 | 0 | 4 | 1 | 0
WACO | 0320-01-073 | BELL | SS 290 | 2019-10-24 | 1265164.93 | 13904.56 | 1271757.05 | 6592.12 | 45 | 31 | 0 | 14 | 1 | 0
BEAUMONT | 0200-16-019 | JEFFERSON | US 69 | 2019-10-28 | 2254742.75 | 46102.24 | 2314606.59 | 59863.84 | 101 | 100 | 15 | 16 | 1 | 0
BEAUMONT | 0306-02-069 | ORANGE | SH 73 | 2019-10-28 | 5658758.05 | -110554.19 | 5691478.01 | 32719.96 | 160 | 198 | 39 | 1 | 0 | 1
BRYAN | 0186-06-065 | WASHINGTON | SH 36 | 2019-10-28 | 14327538.04 | 580818.11 | 15043199.28 | 715661.24 | 328 | 374 | 46 | 0 | 0 | 1
HOUSTON | 0912-72-199 | HARRIS | VA | 2019-10-28 | 2561452.6 | 350795.08 | 3096886.35 | 465274.78 | 305 | 289 | 0 | 16 | 1 | 0
LUBBOCK | 0905-00-097 | LUBBOCK | VA | 2019-10-28 | 729619.57 | 162554.84 | 885984.38 | 156364.81 | 87 | 101 | 14 | 0 | 0 | 1
LUFKIN | 0635-03-025 | HOUSTON | FM 228 | 2019-10-29 | 2929222.97 | -128830.51 | 2627617.01 | -301605.96 | 37 | 43 | 12 | 6 | 0 | 1
ODESSA | 0004-06-036 | ECTOR | IH 20 | 2019-10-29 | 6242606.6 | -205717.65 | 5873848.11 | -368758.49 | 211 | 211 | 0 | 0 | 1 | 0
SAN ANTONIO | 0024-07-058 | BEXAR | US 90 | 2019-10-30 | 22716470.32 | 583136.96 | 23851861.12 | 1135390.8 | 511 | 579 | 69 | 1 | 0 | 1
SAN ANTONIO | 0072-07-066 | BEXAR | IH 10 | 2019-10-30 | 31159119.31 | 1063675.2 | 32222793.56 | 1063674.25 | 793 | 1022 | 229 | 0 | 0 | 1
SAN ANTONIO | 0143-03-044 | WILSON | US 87 | 2019-10-30 | 2913595.44 | 186445.53 | 2906333.16 | -7262.28 | 103 | 107 | 8 | 4 | 1 | 0
SAN ANTONIO | 0535-01-072 | GUADALUPE | IH 10 | 2019-10-30 | 29174029.32 | 1545478.94 | 31703514 | 2529484.68 | 782 | 750 | 0 | 32 | 1 | 0
SAN ANTONIO | 0850-04-027 | WILSON | FM 775 | 2019-10-30 | 2096268.39 | 161318.78 | 2340692.89 | 244424.5 | 85 | 113 | 33 | 5 | 0 | 1
SAN ANTONIO | 0915-00-180 | BEXAR | VA | 2019-10-30 | 1383517.97 | 0 | 876336.04 | -507181.93 | 315 | 181 | 0 | 134 | 1 | 0
FORT WORTH | 0007-10-066 | PALO PINTO | US 180 | 2019-10-31 | 419010 | 0 | 507773.44 | 88763.44 | 22 | 60 | 19 | -19 | 0 | 1
LUFKIN | 0200-02-031 | ANGELINA | US 69 | 2019-11-01 | 9969131.13 | -161938.96 | 9868300.33 | -100830.8 | 310 | 293 | 4 | 21 | 1 | 0
ODESSA | 0005-13-056 | ECTOR | IH 20 | 2019-11-01 | 3958979.2 | 522023.09 | 4779486.47 | 820507.27 | 300 | 349 | 54 | 5 | 0 | 1
BEAUMONT | 0305-07-062 | ORANGE | SH 87 | 2019-11-04 | 3213535.64 | 106530.01 | 3436774.16 | 223238.52 | 90 | 86 | 0 | 4 | 1 | 0
LUBBOCK | 0905-06-111 | LUBBOCK | VA | 2019-11-04 | 2576443.65 | 0 | 2354850.58 | -221593.07 | 173 | 173 | 0 | 0 | 1 | 0
DALLAS | 0092-13-028 | NAVARRO | BI 45-F | 2019-11-05 | 2108966.71 | 51406.45 | 1986947.64 | -122019.07 | 95 | 126 | 27 | -4 | 0 | 1
DALLAS | 2980-01-013 | DENTON | FM 2934 | 2019-11-05 | 2203011.05 | -904831.82 | 1275946.43 | -927064.62 | 85 | 83 | 0 | 2 | 1 | 0
FORT WORTH | 0080-07-097 | TARRANT | US 377 | 2019-11-06 | 188385.2 | 2821.34 | 201754.12 | 13368.92 | 30 | 35 | 7 | 2 | 0 | 1
TYLER | 2642-01-046 | GREGG | SL 281 | 2019-11-06 | 4546219.5 | 306694.51 | 5141460.85 | 595241.35 | 234 | 303 | 85 | 16 | 0 | 1
DALLAS | 2374-02-143 | DALLAS | IH 635 | 2019-11-08 | 350140.33 | 560.2 | 350782.6 | 642.27 | 49 | 132 | 24 | -59 | 0 | 1
FORT WORTH | 3123-01-014 | HOOD | FM 4 | 2019-11-08 | 3211242.01 | 136624.54 | 3324973.32 | 113731.31 | 155 | 141 | 12 | 26 | 1 | 0
DALLAS | 0918-46-291 | DENTON | CS | 2019-11-12 | 1478000 | 0 | 1479447.1 | 1447.1 | 246 | 244 | 0 | 2 | 1 | 0
DALLAS | 2964-06-025 | DALLAS | SH 190 | 2019-11-12 | 1735986.7 | 0 | 1727876.94 | -8109.76 | 43 | 68 | 0 | -25 | 0 | 1
CHILDRESS | 0106-01-039 | DICKENS | SH 70 | 2019-11-13 | 1626092.36 | 0 | 1615390.37 | -10701.99 | 134 | 132 | 0 | 2 | 1 | 0
CHILDRESS | 0146-01-051 | MOTLEY | US 62 | 2019-11-13 | 2119655.5 | 101826.8 | 2265850.46 | 146194.96 | 158 | 167 | 30 | 21 | 1 | 0
FORT WORTH | 1330-01-063 | TARRANT | FM 1187 | 2019-11-13 | 2137400.15 | 103749.23 | 2178778.91 | 41378.76 | 149 | 118 | 10 | 41 | 1 | 0
AUSTIN | 0914-00-368 | TRAVIS | VA | 2019-11-14 | 1041312.89 | 57166.62 | 1149176.3 | 107863.41 | 150 | 159 | 10 | 1 | 1 | 0
LUBBOCK | 0905-00-106 | LUBBOCK | VA | 2019-11-14 | 987437.94 | 0 | 1149282.04 | 161844.1 | 60 | 70 | 10 | 0 | 0 | 1
ODESSA | 0004-07-129 | ECTOR | IH 20 | 2019-11-14 | 1932676.57 | 169524.02 | 2281702.04 | 349025.47 | 80 | 76 | 5 | 9 | 1 | 0
SAN ANTONIO | 0024-01-101 | UVALDE | US 90 | 2019-11-14 | 361123.4 | 22243.41 | 383366.8 | 22243.4 | 32 | 37 | 5 | 0 | 0 | 1
SAN ANTONIO | 0024-01-103 | UVALDE | US 90 | 2019-11-14 | 4809678.66 | 7919.49 | 4817598.18 | 7919.52 | 169 | 186 | 17 | 0 | 0 | 1
SAN ANTONIO | 0073-08-184 | BEXAR | US 281 | 2019-11-14 | 3248620.98 | 96614.47 | 3586736.08 | 338115.1 | 173 | 180 | 0 | -7 | 1 | 0
WACO | 0398-04-059 | BELL | SH 317 | 2019-11-14 | 16887376.62 | 333488.88 | 17250524.1 | 363147.48 | 532 | 559 | 24 | -3 | 1 | 0
ABILENE | 0006-04-072 | TAYLOR | IH 20 | 2019-11-15 | 894985.25 | 295380.5 | 1052650.49 | 157665.24 | 71 | 176 | 50 | -55 | 0 | 1
ABILENE | 0437-02-017 | CALLAHAN | US 283 | 2019-11-15 | 3259092.61 | -26665 | 3310201.91 | 51109.3 | 129 | 107 | 10 | 32 | 1 | 0
CORPUS CHRISTI | 0270-04-006 | KARNES | BS 72-B | 2019-11-15 | 1573309.64 | 49638.15 | 1760334.66 | 187025.02 | 88 | 86 | 0 | 2 | 1 | 0
ATLANTA | 0083-07-044 | CAMP | SH 11 | 2019-11-18 | 934655 | 166320 | 1150450.5 | 215795.5 | 145 | 128 | 0 | 17 | 1 | 0
DALLAS | 0009-11-243 | DALLAS | IH 30 | 2019-11-18 | 1381125.5 | 0 | 1358809.98 | -22315.52 | 51 | 69 | 0 | -18 | 0 | 1
LAREDO | 0922-00-069 | WEBB | VA | 2019-11-18 | 638114.32 | -10125.58 | 620969.44 | -17144.88 | 111 | 94 | 0 | 17 | 1 | 0
TYLER | 0108-04-037 | HENDERSON | SH 19 | 2019-11-18 | 4949012.53 | 77820.68 | 5354082.23 | 405069.7 | 295 | 315 | 22 | 2 | 1 | 0
HOUSTON | 0110-04-129 | MONTGOMERY | SH 75 | 2019-11-19 | 1126255.63 | -142768.48 | 850804.19 | -275451.44 | 53 | 48 | 0 | 5 | 1 | 0
LUFKIN | 0336-05-061 | ANGELINA | SH 103 | 2019-11-20 | 1098660.1 | 0 | 1099834.43 | 1174.33 | 17 | 23 | 7 | 1 | 0 | 1
YOAKUM | 0143-06-029 | GONZALES | US 87 | 2019-11-20 | 5409576.71 | 157050.3 | 5690604.7 | 281027.99 | 150 | 451 | 50 | -251 | 0 | 1
YOAKUM | 0347-01-028 | GONZALES | SH 97 | 2019-11-20 | 10157843.77 | 17131.7 | 10379544.22 | 221700.45 | 300 | 340 | 43 | 3 | 0 | 1
BEAUMONT | 0920-38-187 | JEFFERSON | CS | 2019-11-21 | 1690881.52 | 311228.59 | 1822457.81 | 131576.29 | 60 | 75 | 28 | 13 | 0 | 1
FORT WORTH | 1179-01-043 | WISE | FM 920 | 2019-11-21 | 2881535.48 | 77522.28 | 3022438.82 | 140903.34 | 64 | 74 | 0 | -10 | 0 | 1
HOUSTON | 1965-01-006 | FORT BEND | FM 1994 | 2019-11-21 | 1774560.91 | 241012.09 | 2310019.01 | 535458.1 | 45 | 43 | 0 | 2 | 1 | 0
PHARR | 2966-01-009 | HIDALGO | SH 364 | 2019-11-21 | 6848709.56 | 518461.86 | 7896423.18 | 1047713.62 | 400 | 428 | 33 | 5 | 1 | 0
YOAKUM | 0913-29-035 | LAVACA | CR | 2019-11-21 | 573001.8 | 0 | 565082.7 | -7919.1 | 90 | 68 | 0 | 22 | 1 | 0
YOAKUM | 0913-29-050 | LAVACA | CR | 2019-11-21 | 451306 | 12326.19 | 456930.19 | 5624.19 | 90 | 59 | 0 | 31 | 1 | 0
AUSTIN | 0015-17-028 | WILLIAMSON | SS 158 | 2019-11-22 | 1181685 | 83769.63 | 1272482.77 | 90797.77 | 50 | 87 | 19 | -18 | 0 | 1
DALLAS | 2681-01-022 | DENTON | FM 2499 | 2019-11-22 | 448056.55 | 20586.18 | 458046.54 | 9989.99 | 60 | 34 | 2 | 28 | 1 | 0
SAN ANTONIO | 0024-08-133 | BEXAR | US 90 | 2019-11-22 | 1069800 | 17973.3 | 1083443.3 | 13643.3 | 164 | 132 | 0 | 32 | 1 | 0
SAN ANTONIO | 0328-03-035 | ATASCOSA | SH 97 | 2019-11-22 | 8575353.09 | -469691.88 | 8202579.95 | -372773.14 | 308 | 286 | 0 | 22 | 1 | 0
BEAUMONT | 0920-39-023 | CHAMBERS | VA | 2019-11-25 | 964954.45 | 23366.25 | 934995.07 | -29959.38 | 90 | 137 | 34 | -13 | 0 | 1
LUFKIN | 0118-10-060 | SAN AUGUSTINE | SH 21 | 2019-11-25 | 2474844.69 | 4352.59 | 2409805.9 | -65038.79 | 177 | 243 | 71 | 5 | 0 | 1
ODESSA | 1717-02-022 | MIDLAND | FM 1787 | 2019-11-25 | 3144999.25 | 3895511.9 | 6778380.58 | 3633381.33 | 165 | 215 | 74 | 24 | 0 | 1
SAN ANTONIO | 0073-08-186 | BEXAR | IH 37 | 2019-11-25 | 8045394.83 | 228065.67 | 8672641.2 | 627246.37 | 132 | 172 | 42 | 2 | 0 | 1
SAN ANTONIO | 1272-01-016 | COMAL | FM 1101 | 2019-11-25 | 6154722.5 | 1710468.93 | 8041958.89 | 1771975.73 | 354 | 351 | 28 | 31 | 1 | 0
TYLER | 0910-16-145 | SMITH | VA | 2019-11-25 | 131480 | 0 | 131167 | -313 | 60 | 18 | 0 | 42 | 1 | 0
AUSTIN | 0914-00-382 | TRAVIS | VA | 2019-11-26 | 626160 | 0 | 680419.9 | 54259.9 | 137 | 121 | 0 | 16 | 1 | 0
AUSTIN | 0286-03-017 | CALDWELL | SH 80 | 2019-11-27 | 5221959.17 | 231728.62 | 5680367.72 | 246137.88 | 87 | 85 | 0 | 2 | 1 | 0
ATLANTA | 0010-06-043 | TITUS | US 67 | 2019-12-02 | 1147479.65 | 0 | 1050195.34 | -97284.31 | 60 | 51 | 0 | 9 | 1 | 0
ATLANTA | 0083-07-043 | CAMP | SH 11 | 2019-12-02 | 840486.61 | 45536 | 902050.75 | 61564.14 | 88 | 75 | 0 | 13 | 1 | 0
ATLANTA | 1575-04-017 | HARRISON | SL 390 | 2019-12-02 | 284475.9 | 1 | 282973.3 | -1502.6 | 57 | 56 | 0 | 1 | 1 | 0
SAN ANGELO | 0555-05-024 | TOM GREEN | RM 853 | 2019-12-03 | 1177930.3 | 30961.4 | 1237874.05 | 59943.75 | 128 | 138 | 0 | -10 | 1 | 0
AUSTIN | 0914-00-407 | TRAVIS | VA | 2019-12-04 | 2168168 | 813553 | 3020233.59 | 852065.59 | 730 | 123 | 0 | 607 | 1 | 0
HOUSTON | 0912-00-380 | HARRIS | VA | 2019-12-04 | 1515998.78 | 126930.46 | 1620037.68 | 104038.9 | 437 | 285 | 0 | 152 | 1 | 0
ODESSA | 3570-01-009 | ECTOR | FM 3503 | 2019-12-04 | 1899899.89 | 7352.5 | 1837295.04 | -62604.85 | 172 | 175 | 0 | -3 | 1 | 0
AUSTIN | 0320-03-092 | WILLIAMSON | SH 95 | 2019-12-05 | 330317.61 | 23113.58 | 385030.42 | 54712.81 | 142 | 109 | 0 | 33 | 1 | 0
DALLAS | 0197-05-058 | KAUFMAN | US 175 | 2019-12-05 | 1047916.24 | 0 | 1027916.83 | -19999.41 | 111 | 91 | 0 | 20 | 1 | 0
FORT WORTH | 0080-07-094 | TARRANT | US 377 | 2019-12-05 | 19065202.71 | 2046166.77 | 20710365.02 | 1473695.18 | 684 | 1035 | 351 | 0 | 0 | 1
AUSTIN | 1378-02-053 | WILLIAMSON | RM 1431 | 2019-12-06 | 829475.75 | 0 | 824315.83 | -5159.92 | 45 | 42 | 0 | 3 | 1 | 0
FORT WORTH | 2417-02-016 | JOHNSON | FM 2331 | 2019-12-06 | 1839667.79 | -284517.11 | 1501694.65 | -337973.14 | 64 | 31 | 0 | 33 | 1 | 0
LUBBOCK | 0905-17-015 | SWISHER | CR | 2019-12-06 | 503110 | 11906.45 | 514281.7 | 11171.7 | 75 | 66 | 0 | 9 | 1 | 0
ODESSA | 0548-05-049 | ANDREWS | SH 176 | 2019-12-06 | 11368797.76 | 121729.48 | 10916525.73 | -452272.03 | 259 | 257 | 20 | 22 | 1 | 0
PARIS | 0045-02-034 | GRAYSON | SH 56 | 2019-12-08 | 153070.94 | 0 | 159509.02 | 6438.08 | 30 | 35 | 5 | 0 | 0 | 1
PARIS | 0047-01-069 | GRAYSON | US 75 | 2019-12-08 | 1374640 | -1 | 1394227.84 | 19587.84 | 105 | 85 | 0 | 20 | 1 | 0
AMARILLO | 0168-10-073 | POTTER | IH 27 | 2019-12-09 | 9885031.9 | 323413.15 | 10232342.33 | 347310.43 | 201 | 389 | 146 | -42 | 0 | 1
AMARILLO | 0309-01-043 | GRAY | SH 70 | 2019-12-09 | 1357600.03 | -126676.9 | 967572.51 | -390027.52 | 130 | 41 | 0 | 89 | 1 | 0
AMARILLO | 2635-02-022 | RANDALL | LP 335 | 2019-12-09 | 32232646.86 | 5503158.69 | 37349551.43 | 5116904.57 | 645 | 464 | -180 | 1 | 1 | 0
DALLAS | 1068-04-174 | DALLAS | IH 30 | 2019-12-09 | 1903535.69 | 266186.9 | 2011744.76 | 108209.07 | 59 | 79 | 20 | 0 | 0 | 1
LUBBOCK | 0380-06-017 | DAWSON | SH 349 | 2019-12-09 | 17078039.65 | 476218.98 | 17171115.6 | 93075.95 | 323 | 401 | 90 | 12 | 0 | 1
ABILENE | 0005-05-112 | HOWARD | IH 20 | 2019-12-10 | 7767027.74 | 841265.23 | 8390553.92 | 623526.18 | 309 | 440 | 131 | 0 | 0 | 1
AUSTIN | 0683-02-075 | TRAVIS | RM 620 | 2019-12-10 | 556062.5 | 0 | 579920.81 | 23858.31 | 23 | 23 | 0 | 0 | 1 | 0
AUSTIN | 0914-00-416 | TRAVIS | VA | 2019-12-10 | 873622.08 | -208116.22 | 682843.06 | -190779.02 | 64 | 84 | 0 | -20 | 0 | 1
AUSTIN | 2211-02-030 | WILLIAMSON | FM 1460 | 2019-12-10 | 251065.75 | -16800 | 237507.88 | -13557.87 | 16 | 16 | 0 | 0 | 1 | 0
FORT WORTH | 0363-03-049 | TARRANT | SH 121 | 2019-12-10 | 5252178.37 | 644058.76 | 6011480.98 | 150266.28 | 225 | 339 | 114 | 0 | 0 | 1
ABILENE | 0005-10-023 | HOWARD | BI 20-G | 2019-12-11 | 13457009.46 | -127215.71 | 13118775.65 | -338233.81 | 104 | 87 | 0 | 17 | 1 | 0
ABILENE | 0908-00-088 | TAYLOR | VA | 2019-12-11 | 1682111.26 | -32024.23 | 1638113.28 | -43997.98 | 143 | 132 | 0 | 11 | 1 | 0
ABILENE | 1654-01-019 | JONES | FM 1661 | 2019-12-11 | 10412142.52 | -339383.21 | 10096677.19 | -315465.33 | 104 | 103 | 0 | 1 | 1 | 0
CHILDRESS | 0146-06-030 | FOARD | US 70 | 2019-12-11 | 4375237.33 | -192601.19 | 4161911.57 | -213325.76 | 79 | 74 | 0 | 5 | 1 | 0
DALLAS | 0009-04-071 | ROCKWALL | SH 66 | 2019-12-11 | 1154287.6 | 56028.17 | 1169740.09 | 15452.49 | 78 | 73 | 0 | 5 | 1 | 0
HOUSTON | 0720-02-085 | MONTGOMERY | FM 149 | 2019-12-11 | 2864063.57 | 575050.07 | 3208638.95 | 344575.38 | 113 | 103 | 20 | 30 | 1 | 0
ODESSA | 0003-05-050 | REEVES | IH 20 | 2019-12-11 | 11050426.31 | 197960.34 | 10882458.99 | -167967.32 | 56 | 46 | 0 | 10 | 1 | 0
PARIS | 0769-02-028 | LAMAR | FM 906 | 2019-12-11 | 5917664.29 | 129891.97 | 5910341.36 | -7322.93 | 345 | 346 | 4 | 3 | 1 | 0
CORPUS CHRISTI | 1423-01-034 | REFUGIO | FM 1360 | 2019-12-12 | 1520495.77 | 602565.89 | 1882651.19 | 362155.42 | 108 | 101 | 64 | 71 | 1 | 0
CORPUS CHRISTI | 2263-02-096 | NUECES | SH 361 | 2019-12-12 | 16390000 | 81760 | 16471760 | 81760 | 396 | 444 | 90 | 42 | 0 | 1
PARIS | 0046-01-061 | RED RIVER | US 82 | 2019-12-12 | 2651371.11 | 70216.06 | 2777200.16 | 125829.05 | 200 | 228 | 11 | -17 | 0 | 1
AUSTIN | 0016-09-033 | HAYS | LP 82 | 2019-12-13 | 20734218.4 | 571644.16 | 21367830.58 | -103394.01 | 548 | 723 | 187 | 12 | 1 | 0
AUSTIN | 1566-01-011 | WILLIAMSON | FM 1660 | 2019-12-13 | 2389609.45 | -102746.35 | 2369997.75 | -19611.7 | 101 | 86 | 0 | 15 | 1 | 0
DALLAS | 0009-11-245 | DALLAS | IH 30 | 2019-12-13 | 1336467.9 | 945.74 | 1186646.49 | -149821.41 | 59 | 59 | 0 | 0 | 1 | 0
DALLAS | 0095-02-102 | DALLAS | US 80 | 2019-12-13 | 10441947.51 | 920703.41 | 11396397.65 | 954450.14 | 335 | 342 | 39 | 32 | 1 | 0
AUSTIN | 3417-02-032 | WILLIAMSON | FM 734 | 2019-12-15 | 248349.8 | -8186.95 | 235309.46 | -15096.42 | 27 | 27 | 0 | 0 | 1 | 0
ATLANTA | 0010-11-072 | BOWIE | US 67 | 2019-12-16 | 6997654.55 | 34185.05 | 6954030.38 | -43624.17 | 75 | 42 | 0 | 33 | 1 | 0
ATLANTA | 0063-10-017 | PANOLA | US 59 | 2019-12-16 | 4645909.71 | 82888.55 | 4963661.29 | 317751.58 | 170 | 183 | 14 | 1 | 1 | 0
FORT WORTH | 0008-05-027 | TARRANT | SH 180 | 2019-12-16 | 5833765.36 | 190938.47 | 6052747.76 | 218982.4 | 150 | 156 | 6 | 0 | 1 | 0
LUFKIN | 0109-06-040 | HOUSTON | SH 19 | 2019-12-16 | 877759.58 | -18388.68 | 850240.87 | -27518.71 | 193 | 184 | 2 | 11 | 1 | 0
TYLER | 1172-01-007 | VAN ZANDT | FM 1256 | 2019-12-16 | 5779955.8 | 51838.46 | 5696497.9 | -83457.9 | 206 | 222 | 0 | -16 | 1 | 0
BRYAN | 0917-19-050 | WASHINGTON | CS | 2019-12-17 | 341287.96 | 0 | 323473.29 | -17814.67 | 69 | 43 | 0 | 26 | 1 | 0
DALLAS | 0918-00-283 | DALLAS | VA | 2019-12-17 | 1468000 | -1160 | 1502548.36 | 34548.36 | 548 | 511 | 0 | 37 | 1 | 0
HOUSTON | 0192-02-050 | BRAZORIA | SH 6 | 2019-12-17 | 4942808.25 | 503785.21 | 5511581.19 | 568772.94 | 237 | 250 | 14 | 1 | 1 | 0
HOUSTON | 3256-01-106 | HARRIS | SL 8 | 2019-12-17 | 875730.77 | 10725.12 | 894605.97 | 18875.2 | 90 | 87 | 0 | 3 | 1 | 0
LAREDO | 0037-08-041 | DIMMIT | US 83 | 2019-12-17 | 1275015.85 | -408702.47 | 866309.88 | -408705.97 | 60 | 46 | 0 | 14 | 1 | 0
AUSTIN | 1378-02-038 | WILLIAMSON | RM 1431 | 2019-12-18 | 12847144.69 | 534279.7 | 13574864.35 | 727719.66 | 333 | 439 | 106 | 0 | 0 | 1
BEAUMONT | 0064-08-057 | JASPER | US 96 | 2019-12-18 | 11208278.55 | 208693.35 | 11136319.34 | -71959.21 | 171 | 102 | 10 | 79 | 1 | 0
HOUSTON | 0271-06-120 | HARRIS | IH 10 | 2019-12-18 | 1785427 | 514869.88 | 2445698.6 | 240397.32 | 80 | 80 | 50 | 50 | 1 | 0
HOUSTON | 3510-06-015 | HARRIS | SH 99 | 2019-12-18 | 2082833.99 | 145614.29 | 2328801.96 | 245967.97 | 85 | 80 | 0 | 5 | 1 | 0
PARIS | 0173-06-043 | HUNT | SH 34 | 2019-12-18 | 1784029.22 | 70039.33 | 1985845.95 | 201816.73 | 224 | 205 | 0 | 19 | 1 | 0
SAN ANTONIO | 0915-45-052 | MEDINA | CR | 2019-12-18 | 422407.38 | 12308.08 | 427326.66 | 4919.28 | 64 | 108 | 22 | -22 | 0 | 1
TYLER | 0095-06-071 | VAN ZANDT | US 80 | 2019-12-18 | 499197.05 | 28766.67 | 508711.22 | 9514.17 | 63 | 24 | 0 | 39 | 1 | 0
WICHITA FALLS | 0124-03-062 | WILBARGER | US 183 | 2019-12-18 | 98020 | 0 | 106660.6 | 8640.6 | 34 | 14 | 0 | 20 | 1 | 0
CHILDRESS | 0157-02-047 | KNOX | US 277 | 2019-12-19 | 6559485.05 | -178821.7 | 6865523.29 | 306038.24 | 90 | 114 | 0 | -24 | 0 | 1
DALLAS | 0092-03-050 | ELLIS | IH 45 | 2019-12-19 | 2877641.2 | 166546.28 | 3146781.08 | 269139.88 | 113 | 155 | 42 | 0 | 0 | 1
FORT WORTH | 0014-02-049 | TARRANT | IH 35W | 2019-12-19 | 6093665.75 | 527088.64 | 6647741.04 | 162484.3 | 278 | 393 | 115 | 0 | 1 | 0
LAREDO | 0018-04-056 | WEBB | IH 35 | 2019-12-19 | 4275901.34 | 16585.2 | 4130992.84 | -144908.5 | 117 | 55 | 0 | 62 | 1 | 0
LUFKIN | 0118-10-058 | SAN AUGUSTINE | SH 21 | 2019-12-19 | 5229087.95 | 54442.03 | 5305401.32 | 76313.37 | 263 | 267 | 12 | 8 | 1 | 0
ODESSA | 0005-01-107 | ECTOR | BI 20-E | 2019-12-19 | 11187689.05 | 0 | 11811749.93 | 624060.88 | 201 | 201 | 0 | 0 | 1 | 0
ODESSA | 0005-15-088 | MIDLAND | IH 20 | 2019-12-19 | 4875447.65 | 538387.32 | 5588035.8 | 712588.15 | 150 | 166 | 31 | 15 | 0 | 1
DALLAS | 3392-01-008 | COLLIN | FM 2786 | 2019-12-20 | 15799703.89 | 1252707.84 | 16828852.94 | 581663.84 | 483 | 557 | 74 | 0 | 1 | 0
TYLER | 0123-03-021 | CHEROKEE | US 84 | 2019-12-20 | 2742753.5 | 221779.98 | 3072490.78 | 329737.28 | 120 | 46 | 6 | 80 | 1 | 0
TYLER | 0910-16-130 | SMITH | VA | 2019-12-20 | 2355455.5 | 876883.96 | 3183218.7 | 827763.2 | 196 | 228 | 32 | 0 | 0 | 1
DALLAS | 1394-02-026 | ELLIS | FM 1387 | 2019-12-23 | 1003410.95 | 35073.09 | 1015183.4 | 11772.45 | 133 | 174 | 41 | 0 | 0 | 1
TYLER | 0910-16-135 | SMITH | CS | 2019-12-23 | 4606677.25 | 99612.49 | 4314821.18 | -291856.07 | 225 | 225 | 0 | 0 | 1 | 0
LUFKIN | 0706-04-019 | NACOGDOCHES | FM 95 | 2019-12-27 | 1145849.4 | 6849 | 1188155.69 | 42306.29 | 141 | 141 | 0 | 0 | 1 | 0
PARIS | 0773-01-018 | RED RIVER | FM 412 | 2019-12-30 | 2884882.41 | 24451.5 | 3074045.76 | 189163.35 | 162 | 178 | 16 | 0 | 1 | 0
PARIS | 1980-01-008 | FANNIN | FM 1629 | 2019-12-30 | 1344262.92 | 0 | 1342204.75 | -2058.17 | 112 | 108 | 0 | 4 | 1 | 0
DALLAS | 0081-13-057 | DENTON | IH 35W | 2019-12-31 | 15229273.9 | 860634.92 | 16195292.6 | 966018.7 | 486 | 504 | 21 | 3 | 1 | 0
DALLAS | 0092-14-093 | DALLAS | IH 345 | 2019-12-31 | 906208.75 | 158515.16 | 1083048.05 | 176839.3 | 80 | 103 | 25 | 2 | 0 | 1
DALLAS | 3190-01-012 | KAUFMAN | FM 2860 | 2019-12-31 | 1098460.5 | 0 | 1077898.67 | -20561.83 | 40 | 35 | 0 | 5 | 1 | 0
DALLAS | 0619-05-036 | DENTON | FM 544 | 2020-01-02 | 35390958.31 | 1894432.45 | 35933122.72 | 542164.41 | 755 | 931 | 176 | 0 | 0 | 1
WACO | 0014-08-084 | MCLENNAN | IH 35 | 2020-01-02 | 810416.15 | 31743.36 | 792521.91 | -17894.24 | 60 | 58 | 0 | 2 | 1 | 0
AUSTIN | 0322-01-049 | BASTROP | SH 95 | 2020-01-03 | 1130211.5 | -41836.5 | 1046674.01 | -83537.49 | 31 | 30 | 0 | 1 | 1 | 0
AUSTIN | 1200-03-055 | TRAVIS | FM 973 | 2020-01-03 | 339644.9 | -43398.7 | 314435.52 | 20082.62 | 40 | 40 | 0 | 0 | 1 | 0
WICHITA FALLS | 0044-07-071 | COOKE | US 82 | 2020-01-03 | 4475654.57 | 66291.43 | 4819702.6 | 344048.03 | 102 | 99 | 16 | 19 | 1 | 0
DALLAS | 0009-11-244 | DALLAS | IH 30 | 2020-01-06 | 2069851.67 | -233950.64 | 1764738.59 | -305113.08 | 85 | 98 | 22 | 9 | 0 | 1
EL PASO | 0924-00-086 | EL PASO | VA | 2020-01-06 | 1408923 | 66570.2 | 1459697.95 | 50774.95 | 188 | 741 | 235 | -318 | 0 | 1
HOUSTON | 0027-06-056 | FORT BEND | US 90A | 2020-01-06 | 4585130.47 | -28467.74 | 4642002.75 | 56872.28 | 120 | 118 | 0 | 2 | 1 | 0
HOUSTON | 0027-10-062 | HARRIS | US 90A | 2020-01-06 | 13996560.69 | 2160741.45 | 16266064.58 | 1847108.42 | 357 | 417 | 64 | 4 | 0 | 1
SAN ANGELO | 0035-02-037 | CONCHO | US 83 | 2020-01-06 | 3060704.83 | 0 | 2874466.54 | -186238.29 | 32 | 17 | 0 | 15 | 1 | 0
SAN ANGELO | 0264-07-032 | TOM GREEN | SL 306 | 2020-01-06 | 4500317.86 | 298365.03 | 4489152.42 | -11165.44 | 90 | 132 | 2 | -40 | 0 | 1
WACO | 1656-03-012 | FALLS | FM 413 | 2020-01-06 | 777557 | 12030.66 | 732707.12 | -44849.88 | 108 | 108 | 0 | 0 | 1 | 0
FORT WORTH | 2839-01-010 | PALO PINTO | SH 337 | 2020-01-07 | 14358593.77 | 2941594.64 | 17238228.49 | 2879634.72 | 126 | 155 | 32 | 3 | 0 | 1
LAREDO | 0160-07-032 | VAL VERDE | US 277 | 2020-01-07 | 720100 | 10880 | 766384 | 46284 | 46 | 46 | 0 | 0 | 1 | 0
TYLER | 1389-02-011 | GREGG | FM 1252 | 2020-01-07 | 739231.01 | 11498.31 | 770717.87 | 31486.86 | 50 | 62 | 3 | -9 | 0 | 1
ATLANTA | 0010-08-055 | MORRIS | US 67 | 2020-01-08 | 420994.5 | 0 | 424564.24 | 3569.74 | 80 | 71 | 0 | 9 | 1 | 0
WICHITA FALLS | 0802-02-053 | WICHITA | FM 369 | 2020-01-08 | 4475438 | 5501.97 | 4424149.96 | -51288.04 | 155 | 148 | 0 | 7 | 1 | 0
FORT WORTH | 0258-02-057 | ERATH | US 281 | 2020-01-09 | 6592271.78 | 940903.67 | 7469736.23 | 877464.45 | 303 | 482 | 179 | 0 | 0 | 1
TYLER | 0095-07-060 | VAN ZANDT | US 80 | 2020-01-09 | 14140387.28 | 408296.47 | 13169617.51 | -970769.77 | 109 | 109 | 0 | 0 | 1 | 0
PHARR | 0038-04-054 | ZAPATA | US 83 | 2020-01-10 | 19106794.54 | 174410.14 | 19258493.22 | 151698.68 | 605 | 850 | 0 | -245 | 0 | 1
TYLER | 0424-01-058 | SMITH | SH 31 | 2020-01-10 | 1834284.72 | -168107.48 | 1792589.39 | -41695.33 | 60 | 60 | 0 | 0 | 1 | 0
CORPUS CHRISTI | 0916-00-084 | NUECES | VA | 2020-01-13 | 1319985 | 138991.39 | 1364208.59 | 44223.59 | 144 | 182 | 41 | 3 | 0 | 1
FORT WORTH | 1094-04-016 | JOHNSON | FM 731 | 2020-01-13 | 1866926.45 | 179321.76 | 1745360.58 | -121565.87 | 41 | 54 | 10 | -3 | 0 | 1
HOUSTON | 1685-07-019 | HARRIS | BF1960A | 2020-01-13 | 13293900.01 | 1013858.57 | 14471682.09 | 1177782.08 | 270 | 382 | 118 | 6 | 0 | 1
WACO | 0834-04-024 | MCLENNAN | FM 308 | 2020-01-13 | 1258844 | 1007.48 | 1319329.08 | 60485.08 | 192 | 262 | 35 | -35 | 0 | 1
ATLANTA | 0392-02-096 | UPSHUR | US 259 | 2020-01-14 | 9546218.8 | -13620 | 8953837.61 | -592381.19 | 140 | 105 | 0 | 35 | 1 | 0
BEAUMONT | 0508-03-104 | CHAMBERS | IH 10 | 2020-01-14 | 484857.28 | 84036.19 | 563059.11 | 78201.83 | 51 | 36 | 0 | 15 | 1 | 0
SAN ANTONIO | 0915-00-179 | BEXAR | VA | 2020-01-14 | 1236777.05 | -201594.69 | 1035182.36 | -201594.69 | 186 | 216 | 30 | 0 | 0 | 1
HOUSTON | 0192-03-017 | BRAZORIA | SH 6 | 2020-01-15 | 1534308.55 | 17504.3 | 1604417.09 | 70108.54 | 60 | 65 | 2 | -3 | 1 | 0
HOUSTON | 0598-02-047 | BRAZORIA | SH 288 | 2020-01-15 | 2336954.31 | 7606.29 | 2357746.04 | 20791.73 | 138 | 152 | 15 | 1 | 0 | 1
LUBBOCK | 0068-02-048 | LYNN | US 87 | 2020-01-15 | 6100851.24 | -599823.05 | 5455763.65 | -645087.59 | 70 | 39 | 0 | 31 | 1 | 0
SAN ANTONIO | 0017-14-018 | MEDINA | SH 132 | 2020-01-15 | 9674310.48 | 1022368.24 | 10806438.42 | 1132127.94 | 65 | 65 | 0 | 0 | 1 | 0
BEAUMONT | 1237-01-032 | TYLER | FM 1013 | 2020-01-17 | 458347.1 | -13024.33 | 487735.6 | 29388.5 | 44 | 58 | 14 | 0 | 0 | 1
FORT WORTH | 0250-03-046 | ERATH | US 281 | 2020-01-17 | 24891249.31 | 5582005.86 | 30961297.95 | 6070048.64 | 367 | 377 | 51 | 41 | 1 | 0
LUBBOCK | 0806-04-019 | GARZA | FM 651 | 2020-01-17 | 3064537 | -1491385 | 1491865.75 | -1572671.25 | 288 | 218 | 0 | 70 | 1 | 0
ODESSA | 0380-09-087 | MIDLAND | BS 349C | 2020-01-17 | 8191797.91 | 130789.24 | 8138220.16 | -53577.75 | 162 | 156 | 0 | 6 | 1 | 0
ODESSA | 0906-00-185 | ECTOR | VA | 2020-01-17 | 1239673.05 | 0 | 1342971.75 | 103298.7 | 88 | 112 | 0 | -24 | 0 | 1
TYLER | 0424-02-046 | GREGG | SH 31 | 2020-01-17 | 663759.65 | 5867.3 | 617671.95 | -46087.7 | 77 | 82 | 0 | -5 | 1 | 0
SAN ANTONIO | 0072-10-006 | KENDALL | FM 289 | 2020-01-20 | 783134.71 | -22925.36 | 760209.35 | -22925.36 | 94 | 96 | 2 | 0 | 1 | 0
SAN ANTONIO | 0915-12-533 | BEXAR | CS | 2020-01-20 | 882311.77 | 0 | 896026.03 | 13714.26 | 237 | 237 | 0 | 0 | 1 | 0
TYLER | 0393-02-027 | RUSK | SH 149 | 2020-01-21 | 6294092.23 | -117081.18 | 6546518.34 | 252426.11 | 81 | 106 | 15 | -10 | 0 | 1
BRYAN | 0050-01-080 | BRAZOS | BS 6-R | 2020-01-22 | 1137292.26 | 37830.01 | 1259508.89 | 122216.63 | 79 | 62 | 7 | 24 | 1 | 0
LUFKIN | 0059-05-045 | SHELBY | SH 7 | 2020-01-22 | 10961024.56 | 967508.56 | 11519906.67 | 558882.11 | 82 | 90 | 16 | 8 | 1 | 0
AUSTIN | 0914-05-181 | WILLIAMSON | CR | 2020-01-23 | 247964.01 | 0 | 245339.01 | -2625 | 36 | 20 | 0 | 16 | 1 | 0
BEAUMONT | 0028-05-054 | LIBERTY | US 90 | 2020-01-24 | 12335032.11 | 30000 | 11640849.01 | -694183.1 | 75 | 47 | 0 | 28 | 1 | 0
DALLAS | 0091-03-027 | COLLIN | SH 289 | 2020-01-24 | 1288000 | 0 | 1283854.3 | -4145.7 | 225 | 221 | 0 | 4 | 1 | 0
BRYAN | 0210-02-024 | MILAM | US 77 | 2020-01-27 | 57717.25 | 0 | 62237.25 | 4520 | 36 | 26 | 0 | 10 | 1 | 0
DALLAS | 0197-11-013 | KAUFMAN | FM 1390 | 2020-01-27 | 4719621.66 | 40181.84 | 4634576.77 | -85044.89 | 244 | 289 | 16 | -29 | 0 | 1
FORT WORTH | 0094-02-121 | TARRANT | SH 183 | 2020-01-27 | 3732867.33 | 365374.83 | 4058376.7 | 321936.51 | 188 | 356 | 168 | 0 | 0 | 1
FORT WORTH | 1601-01-034 | PARKER | FM 730 | 2020-01-27 | 2799918.92 | 218784.18 | 3348901.3 | 548982.38 | 64 | 60 | 0 | 4 | 1 | 0
AUSTIN | 2211-02-017 | WILLIAMSON | FM 1460 | 2020-01-28 | 21519391.7 | 567874.03 | 22041674.08 | 54671.78 | 390 | 559 | 36 | -133 | 0 | 1
HOUSTON | 0912-70-078 | HARRIS | VA | 2020-01-28 | 2581444.9 | 84534.52 | 2558342.06 | -40009.73 | 176 | 847 | 445 | -226 | 0 | 1
ODESSA | 0005-13-055 | ECTOR | IH 20 | 2020-01-28 | 9922717.62 | -143410.25 | 9926359.19 | 3641.57 | 210 | 285 | 59 | -16 | 0 | 1
TYLER | 0910-35-033 | WOOD | CR | 2020-01-28 | 342388.1 | 2746.42 | 344899.3 | 2511.2 | 70 | 54 | 0 | 16 | 1 | 0
WICHITA FALLS | 1076-02-040 | YOUNG | FM 209 | 2020-01-28 | 2333357.95 | 77031.38 | 2715254.25 | 381896.3 | 213 | 248 | 10 | -25 | 0 | 1
AMARILLO | 0169-05-042 | CARSON | US 60 | 2020-01-29 | 10873603.33 | 46866.53 | 11628327.16 | 754723.83 | 125 | 163 | 14 | -24 | 0 | 1
DALLAS | 1068-04-122 | DALLAS | IH 30 | 2020-01-29 | 25185923.27 | 1238368.18 | 26249129.5 | 1063206.23 | 538 | 755 | 80 | -137 | 0 | 1
LUFKIN | 1680-01-016 | SAN AUGUSTINE | FM 711 | 2020-01-29 | 5195793.42 | 151765.34 | 5126878.62 | -68914.8 | 175 | 190 | 25 | 10 | 1 | 0
AMARILLO | 0030-02-047 | OCHILTREE | US 83 | 2020-01-30 | 12438153.53 | -131798.26 | 11907580.96 | -530572.57 | 76 | 94 | 10 | -8 | 0 | 1
AMARILLO | 0041-05-050 | POTTER | US 87 | 2020-01-30 | 14897010.56 | 343475.22 | 16045734.89 | 1148724.33 | 146 | 174 | 32 | 4 | 0 | 1
LUFKIN | 2813-01-008 | HOUSTON | FM 2781 | 2020-01-30 | 4041100.85 | 4639.9 | 3591933.65 | -449167.2 | 159 | 142 | 1 | 18 | 1 | 0
WACO | 0258-09-124 | MCLENNAN | SH 6 | 2020-01-30 | 14733502.65 | 951528.02 | 16331706.68 | 1598204.03 | 617 | 596 | 1 | 22 | 1 | 0
ABILENE | 0157-05-060 | JONES | US 277 | 2020-01-31 | 6432024.47 | 2722024.74 | 9472960.76 | 3040936.29 | 105 | 236 | 131 | 0 | 0 | 1
ATLANTA | 0010-19-012 | BOWIE | FM 991 | 2020-02-03 | 1463551.05 | 51388.44 | 1500490.08 | 36939.03 | 395 | 190 | 0 | 205 | 1 | 0
DALLAS | 0195-02-077 | DENTON | IH 35 | 2020-02-03 | 1062400 | 250 | 1057418.52 | -4981.48 | 73 | 50 | 0 | 23 | 1 | 0
DALLAS | 0574-01-029 | NAVARRO | SH 309 | 2020-02-03 | 2595950 | 0 | 2523804.05 | -72145.95 | 327 | 322 | 0 | 5 | 1 | 0
ODESSA | 0441-07-062 | PECOS | IH 10 | 2020-02-03 | 23135091.6 | 959364.73 | 24036364.67 | 901273.07 | 399 | 427 | 31 | 3 | 1 | 0
ODESSA | 0441-07-071 | PECOS | IH 10 | 2020-02-03 | 6847259.28 | 31227.2 | 6985992.31 | 138733.03 | 297 | 150 | 0 | 147 | 1 | 0
ABILENE | 0181-03-025 | CALLAHAN | SH 36 | 2020-02-04 | 1298584.92 | 29833.17 | 1329038.09 | 30453.17 | 68 | 57 | 0 | 11 | 1 | 0
BRYAN | 0050-01-086 | BRAZOS | BS 6-R | 2020-02-04 | 5989654.52 | 81179.69 | 6238871.65 | 249217.13 | 80 | 55 | 0 | 25 | 1 | 0
DALLAS | 0135-11-018 | COLLIN | US 380 | 2020-02-04 | 57978706.51 | 1475254.67 | 58957987.78 | 979281.27 | 772 | 883 | 111 | 0 | 0 | 1
DALLAS | 1016-06-011 | KAUFMAN | FM 1392 | 2020-02-04 | 5676173.14 | 364703.92 | 5325114.78 | -351058.36 | 221 | 317 | 68 | -28 | 0 | 1
FORT WORTH | 0259-05-077 | JOHNSON | US 67 | 2020-02-04 | 167003.8 | -12000 | 163418.9 | -3584.9 | 86 | 91 | 0 | -5 | 1 | 0
HOUSTON | 2938-02-022 | BRAZORIA | FM 2917 | 2020-02-04 | 2791368.68 | 9316.16 | 2792089.25 | 720.57 | 109 | 124 | 0 | -15 | 0 | 1
LUBBOCK | 0905-00-080 | LUBBOCK | VA | 2020-02-04 | 2813521.05 | 121513 | 2739993.2 | -73527.85 | 291 | 354 | 69 | 6 | 0 | 1
WICHITA FALLS | 0194-01-014 | COOKE | IH 35 | 2020-02-04 | 2349138.88 | 235401.27 | 2585695.05 | 236556.17 | 85 | 93 | 8 | 0 | 1 | 0
WACO | 0724-01-053 | CORYELL | FM 116 | 2020-02-05 | 1435578.35 | -373.45 | 1399996.16 | -35582.19 | 60 | 60 | 0 | 0 | 1 | 0
AUSTIN | 0071-05-031 | MASON | US 87 | 2020-02-06 | 2985946 | -138562.6 | 2849711.92 | -136234.08 | 68 | 41 | 0 | 27 | 1 | 0
AUSTIN | 1200-02-032 | TRAVIS | FM 973 | 2020-02-07 | 878897.95 | 37043.96 | 925492.03 | 46594.08 | 271 | 204 | 0 | 67 | 1 | 0
DALLAS | 0095-03-093 | KAUFMAN | US 80 | 2020-02-07 | 11461243.21 | -172563.41 | 10343199.5 | -1118043.71 | 170 | 167 | 0 | 3 | 1 | 0
DALLAS | 0751-03-038 | KAUFMAN | FM 148 | 2020-02-07 | 4087837.4 | 60427.83 | 4074340.08 | -13497.32 | 286 | 286 | 0 | 0 | 1 | 0
HOUSTON | 0179-01-048 | BRAZORIA | SH 35 | 2020-02-10 | 2037263.05 | 326736.54 | 2383113.19 | 345850.14 | 307 | 244 | 0 | 63 | 1 | 0
TYLER | 0522-02-037 | VAN ZANDT | SH 243 | 2020-02-10 | 6654770.06 | 218201.17 | 6815706.51 | 160936.45 | 213 | 298 | 85 | 0 | 0 | 1
DALLAS | 0081-03-061 | DENTON | US 377 | 2020-02-11 | 1331101.99 | 0 | 1301111.42 | -29990.57 | 175 | 190 | 0 | -15 | 1 | 0
PARIS | 0525-01-020 | DELTA | SH 19 | 2020-02-11 | 4018602.9 | 3095.12 | 4063679.59 | 45076.69 | 348 | 364 | 0 | -16 | 1 | 0
WACO | 0909-38-081 | FALLS | CR | 2020-02-11 | 1340676.7 | 0 | 1311618.12 | -29058.58 | 225 | 139 | 0 | 86 | 1 | 0
AUSTIN | 0473-02-038 | LEE | SH 21 | 2020-02-12 | 1996137.88 | -67137.24 | 1931855.75 | -64282.13 | 46 | 41 | 0 | 5 | 1 | 0
BRYAN | 0049-06-078 | ROBERTSON | SH 6 | 2020-02-12 | 2287795.2 | 434716.26 | 2687615.7 | 399820.5 | 53 | 42 | 3 | 14 | 1 | 0
FORT WORTH | 0902-48-576 | TARRANT | CS | 2020-02-12 | 4658453.88 | 492237.75 | 4853962.53 | 86173.54 | 165 | 282 | 118 | 1 | 0 | 1
HOUSTON | 1258-02-037 | FORT BEND | FM 1093 | 2020-02-12 | 781727.27 | 198134.5 | 1096556.59 | 314829.32 | 50 | 51 | 1 | 0 | 1 | 0
AUSTIN | 0015-08-146 | WILLIAMSON | IH 35 | 2020-02-13 | 730891.76 | 0 | 713806.56 | -17085.2 | 120 | 102 | 0 | 18 | 1 | 0
AUSTIN | 0914-04-298 | TRAVIS | VA | 2020-02-13 | 1177598.3 | 0 | 1140464.05 | -37134.25 | 160 | 100 | 0 | 60 | 1 | 0
AUSTIN | 0113-07-066 | HAYS | US 290 | 2020-02-14 | 526358.29 | 18323.16 | 553331.1 | 26972.81 | 42 | 51 | 3 | -6 | 0 | 1
AUSTIN | 0914-00-395 | TRAVIS | VA | 2020-02-14 | 1439774 | 0 | 1555573.48 | 115799.48 | 300 | 304 | 0 | -4 | 1 | 0
AUSTIN | 0914-00-397 | TRAVIS | VA | 2020-02-14 | 1469946 | 0 | 1218722.99 | -251223.01 | 300 | 150 | 0 | 150 | 1 | 0
AUSTIN | 3417-03-024 | TRAVIS | FM 734 | 2020-02-14 | 388447 | -29247.6 | 394401 | 5954 | 130 | 55 | 0 | 75 | 1 | 0
CHILDRESS | 0097-02-039 | HARDEMAN | SH 6 | 2020-02-14 | 3994436.14 | 11287.47 | 4271632.27 | 277196.13 | 90 | 96 | 0 | -6 | 1 | 0
HOUSTON | 1685-01-106 | HARRIS | FM 1960 | 2020-02-14 | 647884.36 | 5305.47 | 660140.72 | 12256.36 | 91 | 82 | 0 | 9 | 1 | 0
SAN ANTONIO | 0535-02-048 | GUADALUPE | IH 10 | 2020-02-14 | 3343191.83 | 127977.17 | 3412260.52 | 69068.69 | 198 | 246 | 48 | 0 | 0 | 1
SAN ANTONIO | 1728-02-059 | COMAL | FM 306 | 2020-02-14 | 5996508.48 | 464902.11 | 6585606 | 589097.52 | 364 | 364 | 0 | 0 | 1 | 0
SAN ANTONIO | 2452-02-118 | BEXAR | SL 1604 | 2020-02-14 | 806296.61 | 97905.56 | 986113.76 | 179817.15 | 130 | 156 | 26 | 0 | 0 | 1
DALLAS | 0353-02-063 | DENTON | SH 114 | 2020-02-18 | 30580029.4 | 1340416.12 | 31138569.24 | 558539.84 | 651 | 650 | 5 | 6 | 1 | 0
DALLAS | 0364-02-017 | DALLAS | SH 121 | 2020-02-18 | 58805233.66 | 802882.82 | 59737604.29 | 787338.59 | 986 | 1154 | 169 | 1 | 0 | 1
DALLAS | 0918-45-757 | DALLAS | CS | 2020-02-18 | 2883799 | 75337.22 | 2968906.82 | 85107.82 | 381 | 392 | 27 | 16 | 1 | 0
DALLAS | 1211-01-018 | ELLIS | FM 984 | 2020-02-18 | 2333446.9 | 703.92 | 2237904.49 | -95542.41 | 379 | 644 | 0 | -265 | 0 | 1
FORT WORTH | 0259-06-001 | JOHNSON | US 67 | 2020-02-18 | 28488425.86 | 2353796.79 | 31337926.87 | 2849501.01 | 606 | 1029 | 84 | -339 | 0 | 1
HOUSTON | 0050-06-079 | HARRIS | US 290 | 2020-02-18 | 33430700.87 | 2279247.82 | 36566243.17 | 3135542.3 | 612 | 748 | 140 | 4 | 0 | 1
PARIS | 0045-20-019 | FANNIN | US 82 | 2020-02-18 | 6847234.61 | 144145 | 6929844.06 | 82609.45 | 223 | 243 | 0 | -20 | 1 | 0
PARIS | 0279-03-035 | FANNIN | SH 78 | 2020-02-18 | 2675061.25 | 100529.04 | 2691847.79 | 16786.54 | 159 | 233 | 85 | 11 | 0 | 1
PHARR | 0039-17-196 | HIDALGO | IH 2 | 2020-02-18 | 1104702.01 | 0 | 1337522.75 | 232820.74 | 180 | 172 | 0 | 8 | 1 | 0
WICHITA FALLS | 0124-05-029 | BAYLOR | US 183 | 2020-02-18 | 6052095.58 | 57786.4 | 6188603.83 | 136508.25 | 165 | 216 | 10 | -41 | 0 | 1
YOAKUM | 0089-06-079 | WHARTON | US 59 | 2020-02-18 | 3681313.69 | -45246.04 | 3524530.99 | -156782.7 | 60 | 95 | 28 | -7 | 0 | 1
DALLAS | 0008-08-076 | DALLAS | SH 180 | 2020-02-19 | 1120775.51 | 45606.96 | 1173112.07 | 52336.56 | 51 | 52 | 0 | -1 | 1 | 0
TYLER | 0198-07-015 | CHEROKEE | SH 204 | 2020-02-19 | 562313.8 | -20544.28 | 534001.72 | -28312.08 | 67 | 36 | 0 | 31 | 1 | 0
CORPUS CHRISTI | 2343-01-036 | NUECES | FM 2444 | 2020-02-20 | 24447530.97 | 4138053.64 | 28826877.27 | 4379346.3 | 510 | 704 | 194 | 0 | 0 | 1
HOUSTON | 0912-00-350 | HARRIS | VA | 2020-02-20 | 1289999.25 | -82774.58 | 1393587.76 | 103588.51 | 225 | 221 | 0 | 4 | 1 | 0
PARIS | 0009-15-027 | HUNT | US 69 | 2020-02-20 | 3331592.27 | -143621.51 | 2828630.4 | -502961.87 | 111 | 145 | 2 | -32 | 0 | 1
PARIS | 0174-04-035 | FANNIN | FM 79 | 2020-02-20 | 1412114.05 | 0 | 1482831.05 | 70717 | 70 | 115 | 0 | -45 | 0 | 1
PARIS | 0427-02-009 | RED RIVER | FM 1158 | 2020-02-20 | 2040371.54 | 39486.17 | 2140261.37 | 99889.83 | 110 | 110 | 0 | 0 | 1 | 0
PARIS | 0680-01-015 | LAMAR | FM 196 | 2020-02-20 | 2490743.37 | 43889.28 | 2461585.26 | -29158.11 | 144 | 178 | 0 | -34 | 0 | 1
WACO | 0015-14-126 | BELL | IH 35 | 2020-02-20 | 6939665.08 | -616005.75 | 6497962.86 | -441702.22 | 60 | 96 | 36 | 0 | 0 | 1
BROWNWOOD | 0183-01-045 | COMANCHE | SH 36 | 2020-02-21 | 1347885.99 | -703.76 | 1128023.77 | -219862.22 | 26 | 16 | 0 | 10 | 1 | 0
FORT WORTH | 0008-09-036 | PARKER | FM 5 | 2020-02-21 | 5012311.16 | 3095206.73 | 8048548.81 | 3036237.65 | 192 | 195 | 3 | 0 | 1 | 0
HOUSTON | 0051-03-106 | GALVESTON | SH 3 | 2020-02-21 | 609218.5 | -48085.42 | 548539.14 | -60679.36 | 103 | 102 | 0 | 1 | 1 | 0
LUBBOCK | 0294-01-040 | GAINES | US 62 | 2020-02-21 | 9630759.46 | 948829.2 | 10255843.53 | 625084.07 | 116 | 143 | 32 | 5 | 0 | 1
SAN ANGELO | 0035-01-034 | RUNNELS | US 83 | 2020-02-21 | 13130698.76 | 528812.25 | 12742128.32 | -388570.44 | 68 | 49 | 0 | 19 | 1 | 0
DALLAS | 0364-03-099 | DENTON | BS 121H | 2020-02-24 | 1895000.01 | 65207.54 | 1920265.12 | 25265.11 | 252 | 249 | 0 | 3 | 1 | 0
DALLAS | 0918-47-114 | DALLAS | VA | 2020-02-24 | 2650440.8 | 0 | 2430307.08 | -220133.72 | 375 | 374 | 0 | 1 | 1 | 0
WACO | 0120-05-025 | HAMILTON | FM 218 | 2020-02-24 | 571906.9 | -48616.77 | 532189.19 | -39717.71 | 90 | 74 | 0 | 16 | 1 | 0
BEAUMONT | 0200-08-056 | TYLER | US 69 | 2020-02-25 | 348024.5 | 100029 | 436104.5 | 88080 | 43 | 61 | 31 | 13 | 0 | 1
HOUSTON | 0271-05-040 | FORT BEND | IH 10 | 2020-02-25 | 1897990.52 | 348896.38 | 2238854 | 340863.48 | 105 | 145 | 44 | 4 | 0 | 1
LAREDO | 0022-07-030 | VAL VERDE | US 90 | 2020-02-25 | 911560.5 | -7426.99 | 908270.54 | -3289.96 | 60 | 50 | 0 | 10 | 1 | 0
SAN ANTONIO | 0025-09-076 | BEXAR | FM 78 | 2020-02-25 | 2187618.06 | 194074.38 | 2503708.47 | 316090.41 | 212 | 351 | 47 | -92 | 0 | 1
ABILENE | 0006-03-132 | NOLAN | IH 20 | 2020-02-26 | 14579827.28 | 1171998.51 | 16276726.29 | 1696899.01 | 331 | 308 | 0 | 23 | 1 | 0
ABILENE | 0006-07-079 | CALLAHAN | IH 20 | 2020-02-26 | 7087728.07 | 1696166.06 | 9039748.3 | 1952020.23 | 109 | 117 | 8 | 0 | 1 | 0
HOUSTON | 0389-05-123 | HARRIS | SH 146 | 2020-02-26 | 1376457.7 | 17700 | 1400988.43 | 24530.73 | 75 | 55 | 0 | 20 | 1 | 0
SAN ANTONIO | 0024-06-064 | MEDINA | US 90 | 2020-02-26 | 1827606.47 | -136410.63 | 1729475.23 | -98131.24 | 418 | 410 | 3 | 11 | 1 | 0
AUSTIN | 0113-03-031 | BLANCO | US 290 | 2020-02-27 | 1474737.25 | 49843.2 | 1247355.11 | -227382.14 | 48 | 34 | 0 | 14 | 1 | 0
WACO | 0909-36-137 | BELL | CR | 2020-02-27 | 1202660.75 | 190626.95 | 1401795.15 | 199134.4 | 149 | 136 | 0 | 13 | 1 | 0
ABILENE | 0296-02-033 | FISHER | US 180 | 2020-02-28 | 1763518.63 | 13143.5 | 1791021.08 | 27502.45 | 200 | 159 | 0 | 41 | 1 | 0
ABILENE | 0699-01-055 | TAYLOR | FM 89 | 2020-02-28 | 1793003.06 | 101100 | 1992636.69 | 199633.63 | 100 | 84 | 0 | 16 | 1 | 0
AMARILLO | 0169-02-065 | POTTER | US 60 | 2020-02-28 | 7595396.33 | 612728.25 | 8970720.46 | 1375324.13 | 59 | 140 | 43 | -38 | 0 | 1
AMARILLO | 0798-01-025 | ROBERTS | FM 282 | 2020-02-28 | 2093931.75 | -5480 | 2201571.18 | 107639.43 | 242 | 237 | 0 | 5 | 1 | 0
AMARILLO | 0904-00-186 | POTTER | VA | 2020-02-28 | 748100 | 0 | 685375 | -62725 | 70 | 28 | 0 | 42 | 1 | 0
LUBBOCK | 0783-02-099 | LUBBOCK | SL 289 | 2020-02-28 | 1071270 | 0 | 784278.24 | -286991.76 | 45 | 29 | 0 | 16 | 1 | 0
LUFKIN | 2387-01-017 | TRINITY | FM 2262 | 2020-02-28 | 4311589.97 | 125045.33 | 4289240.79 | -22349.18 | 129 | 198 | 44 | -25 | 0 | 1
SAN ANTONIO | 0521-04-274 | BEXAR | IH 410 | 2020-02-28 | 81882606.04 | 4161569.95 | 87899430.38 | 6016824.34 | 760 | 918 | 194 | 36 | 0 | 1
TYLER | 2558-01-015 | SMITH | SS 248 | 2020-02-28 | 8660946.19 | 1382571.54 | 9910631.78 | 1249685.59 | 315 | 371 | 56 | 0 | 0 | 1
WACO | 0567-01-020 | CORYELL | FM 107 | 2020-02-28 | 2142444.4 | -7221.28 | 2361839.89 | 219395.49 | 45 | 49 | 4 | 0 | 1 | 0

## LINE_GRAPH_DATA (hidden)
COUNTIFS(FINL,">="&B4-DAY(B4)+1,FINL,"<="&EOMONTH(B4,0))
FY 2020 Monthly Measures | [9 empty] | YTD
Month | Total Contracts | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO
SEP-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
OCT-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NOV-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DEC-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JAN-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FEB-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAR-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
APR-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAY-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JUN-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JUL-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AUG-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FY20 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
|  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!

## Summary Previous FYs (hidden)
CONSTRUCTION SUMMARY PERFORMANCE REPORT | [12 empty] | 5- YEAR AVERAGES
FY | Projects Accepted | Percent On Budget | Percent On Time | Percent On Time Previous | Projects Awarded | Awarded Amounts Billions | Estimated Amounts Billions | Amounts Over / (Under) the Estimate | Percent Over the Estimate | Dollars per Project | Awarded Amounts | Estimated Amounts | Awarded Amounts | Estimated Amounts | Percent Over the Estimate | Projects Accepted | Projects Awarded
2009 | 802 | 83.92% | 57.11% | 72.57% | 699 | 3.0857 | 3.6429 | -0.5572 | -15.3% | 4414461.6445 | 3085708689.49 | 3642907501.26
2010 | 797 | 84.69% | 65.5% | 77.42% | 1063 | 3.2459 | 3.6441 | -0.39818 | -10.93% | 3053502.9899 | 3245873678.22 | 3644056349
2011 | 872 | 88.99% | 68.17% | 77.18% | 870 | 3.497 | 3.7036 | -0.20654 | -5.577% | 4019586.1947 | 3497039989.43 | 3703575068.62
2012 | 772 | 87.95% | 67.62% | 76.55% | 685 | 2.9722 | 3.0097 | -0.037491 | -1.246% | 4338962.4606 | 2972189285.54 | 3009680367 | 3.2002 | 3.5001 | -8.567% | 810.75 | 829.25
2013 | 682 | 86.07% | 63.49% | N/A | 797 | 4.2752 | 4.2598 | 0.015356 | 0.3605% | 5364094.8547 | 4275183599.18 | 4259827109.53 | 3.4152 | 3.652 | -6.484% | 785 | 822.8
2014 | 636 | 86.48% | 68.08% | N/A | 757 | 3.8596 | 3.9509 | -0.091307 | -2.311% | 5098575.683 | 3859621792 | 3950928942.48 | 3.57 | 3.7136 | -3.868% | 751.8 | 834.4
2015 | 607 | 86.16% | 63.92% | N/A | 856 | 4.3749 | 4.3622 | 0.012684 | 0.2908% | 5110843.7065 | 4374882212.76 | 4362198207.53 | 3.7958 | 3.8572 | -1.593% | 713.8 | 793
2016 | 711 | 83.4% | 63.29% | N/A | 737 | 4.3375 | 4.4843 | -0.14682 | -3.274% | 5885376.9172 | 4337522787.99 | 4484341769.73 | 3.9639 | 4.0134 | -1.234% | 681.6 | 766.4
2017 | 864 | 80.9% | 62.73% | N/A | 779 | 4.7365 | 5.0552 | -0.31875 | -6.305% | 6080199.4759 | 4736475391.74 | 5055222420.56 | 4.3167 | 4.4225 | -2.392% | 700 | 785.2
2018 | 859 | 83.82% | 64.96% | N/A | 825 | 5.7327 | 5.8693 | -0.13661 | -2.328% | 6948682.4486 | 5732663020.12 | 5869277068.62 | 4.6082 | 4.7444 | -2.87% | 735.4 | 790.8
2019 | 718 | 94.57% | 85.79% | N/A | 895 | 6.5145 | 6.3033 | 0.21118 | 3.35% | 7278753.2179 | 6514484130 | 6303301439 | 4.9259 | 5.0042 | -1.564% | 732.5 | 808.1667
2020 | #REF! | #REF! | #REF! |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 5.1392 | 5.2149 | -1.451% | #REF! | 818.4