## OTOB
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [11 empty] | Highway Construction Projects Completed September 1, 2020–February 28, 2021
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | FEBRUARY | 28 | 2021
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | AMOUNT PAID | OVER/UNDER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | OVER/UNDER SCHEDULE
ATLANTA | 0083-08-053 | CAMP | SH 11 | 2020-09-01 | 583202.35 | 0 | 577893.77 | -5308.58 | 78 | 68 | 0 | -10
ATLANTA | 0096-09-077 | HARRISON | US 80 | 2020-09-01 | 381550 | 0 | 373308.25 | -8241.75 | 75 | 74 | 0 | -1
LUFKIN | 2560-01-083 | NACOGDOCHES | SL 224 | 2020-09-01 | 1560111.45 | 0 | 1422110.49 | -138000.96 | 26 | 26 | 0 | 0
WICHITA FALLS | 0147-01-022 | WILBARGER | US 70 | 2020-09-01 | 3558575.17 | 0 | 3210508.79 | -348066.38 | 46 | 43 | 0 | -3
DALLAS | 0918-47-062 | DALLAS | CS | 2020-09-02 | 793042 | 0 | 827238.97 | 34196.97 | 132 | 132 | 0 | 0
DALLAS | 1451-01-025 | ELLIS | FM 55 | 2020-09-03 | 1530409.4 | 14926.86 | 1469280.65 | -61128.75 | 183 | 416 | 0 | 233
HOUSTON | 0500-03-594 | HARRIS | IH 45 | 2020-09-03 | 1581261.01 | 324389.12 | 1690883.5 | 109622.49 | 47 | 46 | 0 | -1
AUSTIN | 0150-05-048 | BURNET | SH 29 | 2020-09-04 | 3931925.98 | -241483.1 | 3883741.45 | -48184.53 | 65 | 95 | 0 | 30
DALLAS | 0092-06-104 | NAVARRO | IH 45 | 2020-09-09 | 1775481 | 167516.81 | 1816894.04 | 41413.04 | 194 | 186 | 0 | -8
DALLAS | 0918-18-135 | NAVARRO | VA | 2020-09-09 | 3230499.22 | 496735.65 | 3620887.44 | 390388.22 | 240 | 288 | 63 | 111
PARIS | 0047-03-089 | GRAYSON | US 75 | 2020-09-09 | 2328633.32 | 47953.92 | 2292602.82 | -36030.5 | 149 | 133 | 0 | -16
AUSTIN | 0265-05-081 | BASTROP | SH 71 | 2020-09-10 | 606000 | 0 | 616486.38 | 10486.38 | 120 | 59 | 0 | -61
DALLAS | 2249-01-008 | KAUFMAN | FM 460 | 2020-09-10 | 1469989.63 | 145913.82 | 1533997.45 | -119624.18 | 124 | 124 | 10 | 10
LUFKIN | 0911-00-075 | ANGELINA | VA | 2020-09-10 | 2105750.3 | 29790.07 | 2580087.18 | 474336.88 | 250 | 269 | 28 | 47
ODESSA | 0004-07-130 | ECTOR | IH 20 | 2020-09-10 | 1070006.4 | 0 | 1072260.14 | 2253.74 | 80 | 79 | 0 | -1
TYLER | 0190-03-084 | WOOD | US 69 | 2020-09-10 | 1442127.5 | 42366 | 1467736.24 | 25608.74 | 86 | 73 | 0 | -13
TYLER | 1934-02-006 | SMITH | FM 2015 | 2020-09-10 | 3017503.38 | 24555.53 | 3187021.04 | 169517.66 | 120 | 160 | 40 | 80
ABILENE | 0033-06-116 | TAYLOR | US 83 | 2020-09-11 | 267513 | 1000 | 271112.5 | 3599.5 | 50 | 29 | 0 | -21
ABILENE | 0908-00-092 | TAYLOR | VA | 2020-09-11 | 1171614 | 682090 | 1807627.42 | 636013.42 | 41 | 48 | 20 | 27
AUSTIN | 2102-01-066 | TRAVIS | RM 2244 | 2020-09-11 | 28752815.23 | 4166593.5 | 31722046.81 | 1928328.58 | 524 | 572 | 48 | 96
PHARR | 0684-01-069 | CAMERON | FM 511 | 2020-09-11 | 3399954.24 | 76505.52 | 2730589.06 | -669365.18 | 180 | 364 | 21 | 205
ABILENE | 0908-00-081 | TAYLOR | VA | 2020-09-14 | 1782793.22 | -20879.94 | 1742732.65 | -40060.57 | 72 | 39 | 0 | -33
BROWNWOOD | 0127-01-031 | EASTLAND | US 183 | 2020-09-14 | 3213022.13 | 380103.84 | 3636698.82 | 423676.69 | 214 | 188 | 5 | -21
BROWNWOOD | 0127-02-141 | EASTLAND | US 183 | 2020-09-14 | 3673746.04 | 226704.01 | 4147971.72 | 474225.68 | 260 | 216 | 6 | -38
LUFKIN | 0336-05-066 | ANGELINA | SH 103 | 2020-09-14 | 2152215 | -61146.33 | 2138054.05 | -14160.95 | 92 | 172 | 84 | 164
TYLER | 0198-03-027 | ANDERSON | US 175 | 2020-09-14 | 27365550.64 | 221394.44 | 28929212.38 | 1563661.74 | 571 | 639 | 68 | 136
BRYAN | 0166-07-062 | MADISON | SH 75 | 2020-09-15 | 1084258.74 | 89388.95 | 1249000.81 | 164742.07 | 90 | 73 | 4 | -13
DALLAS | 0092-05-051 | ELLIS | IH 45 | 2020-09-15 | 1468213.3 | 83047.17 | 1784162.3 | 315949 | 128 | 133 | 8 | 13
CHILDRESS | 0357-06-022 | BRISCOE | SH 207 | 2020-09-16 | 5379618.08 | 0 | 5441411.9 | 61793.82 | 51 | 16 | 0 | -35
DALLAS | 0092-02-129 | DALLAS | IH 45 | 2020-09-16 | 1008154.51 | -54428.25 | 960579.47 | -47575.04 | 220 | 177 | 0 | -43
EL PASO | 0002-01-095 | EL PASO | SH 20 | 2020-09-16 | 349909 | 20970 | 322600.3 | -27308.7 | 55 | 134 | 12 | 91
EL PASO | 2552-03-063 | EL PASO | SL 375 | 2020-09-16 | 4497505.55 | 84309.23 | 4726013.05 | 228507.5 | 269 | 273 | 5 | 9
LAREDO | 0086-14-065 | WEBB | SL 20 | 2020-09-16 | 25596044.49 | 526426.99 | 26428965.3 | 832920.81 | 724 | 723 | 0 | -1
LAREDO | 0086-14-073 | WEBB | US 59 | 2020-09-16 | 579929.39 | -23000.05 | 559840.56 | -20088.83 | 132 | 89 | 0 | -43
PARIS | 0901-19-192 | GRAYSON | VA | 2020-09-16 | 1825215 | 0 | 1890381.92 | 65166.92 | 105 | 105 | 0 | 0
PHARR | 0220-04-055 | CAMERON | US 281 | 2020-09-16 | 3773984.45 | 41991.04 | 3742950.34 | -31034.11 | 90 | 88 | 0 | -2
CORPUS CHRISTI | 0102-01-116 | NUECES | BS 44D | 2020-09-17 | 3210192.04 | 587024.53 | 3793835.06 | 583643.02 | 41 | 37 | 0 | -4
PHARR | 0220-04-035 | CAMERON | US 281 | 2020-09-17 | 12496309.81 | 122764.99 | 12928730.53 | 432420.72 | 460 | 520 | 85 | 145
PHARR | 0220-07-064 | CAMERON | SH 48 | 2020-09-17 | 2475986.4 | 12275.03 | 2457949.68 | -18036.72 | 80 | 76 | 0 | -4
CORPUS CHRISTI | 0102-04-103 | KLEBERG | US 77 | 2020-09-18 | 706119.22 | 0 | 634646.75 | -71472.47 | 118 | 108 | 0 | -10
HOUSTON | 0110-05-128 | HARRIS | IH 45 | 2020-09-18 | 309370 | -104468.8 | 212380.18 | -96989.82 | 30 | 181 | 118 | 269
HOUSTON | 1005-02-001 | HARRIS | FM 525 | 2020-09-18 | 1763846.49 | 142290.98 | 2152625.41 | 376863.32 | 150 | 157 | 7 | 14
DALLAS | 0009-12-072 | ROCKWALL | IH 30 | 2020-09-21 | 32882301 | -427563.69 | 31725717.48 | -1622484.14 | 600 | 765 | 76 | 241
ODESSA | 0139-05-043 | REEVES | US 285 | 2020-09-21 | 18885090.96 | 4209982.5 | 23971910.4 | 5086819.44 | 344 | 306 | 0 | -38
SAN ANGELO | 0907-00-222 | TOM GREEN | VA | 2020-09-21 | 725159 | 0 | 724909 | -250 | 35 | 14 | 0 | -21
SAN ANTONIO | 0915-00-168 | BEXAR | VA | 2020-09-21 | 1394063.86 | -19104 | 1330348.46 | -63715.4 | 193 | 112 | 0 | -81
YOAKUM | 0913-09-101 | WHARTON | CS | 2020-09-21 | 144419.82 | 5783.7 | 153749.92 | 9330.1 | 40 | 39 | 0 | -1
BRYAN | 0540-05-048 | BRAZOS | FM 159 | 2020-09-22 | 2816987.76 | 195345.53 | 2823392.13 | 6404.37 | 105 | 116 | 14 | 25
DALLAS | 0195-02-071 | DENTON | US 77 | 2020-09-22 | 1435083.86 | 53859.34 | 1098615.22 | -336468.64 | 78 | 42 | 0 | -36
DALLAS | 0196-01-110 | DENTON | US 77 | 2020-09-22 | 1486329.3 | 267779.68 | 1689554.88 | 203225.58 | 76 | 82 | 7 | 13
YOAKUM | 0913-09-073 | WHARTON | CR | 2020-09-22 | 980970.4 | 0 | 945853.4 | -35117 | 144 | 118 | 0 | -26
SAN ANGELO | 0235-03-034 | REAL | SH 55 | 2020-09-23 | 1009257.6 | 0 | 987170.8 | -22086.8 | 70 | 47 | 0 | -23
SAN ANTONIO | 0915-45-053 | MEDINA | CR | 2020-09-23 | 487790.57 | 13009.47 | 488199.25 | 408.68 | 78 | 126 | 0 | 48
YOAKUM | 1302-03-010 | WHARTON | FM 441 | 2020-09-23 | 2932384.5 | 0 | 2849181.86 | -83202.64 | 90 | 90 | 0 | 0
BROWNWOOD | 0107-04-020 | STEPHENS | FM 576 | 2020-09-24 | 663778.5 | 64484.93 | 732969.48 | 69190.98 | 91 | 53 | 4 | -34
YOAKUM | 0913-29-054 | LAVACA | CS | 2020-09-24 | 192922.1 | 0 | 187728.7 | -5193.4 | 75 | 61 | 0 | -14
EL PASO | 0415-01-025 | JEFF DAVIS | SH 118 | 2020-09-25 | 340160 | 7560 | 342670 | 2510 | 60 | 61 | 0 | 1
EL PASO | 1158-01-009 | CULBERSON | FM 2185 | 2020-09-25 | 2339706.95 | 6162.2 | 2349520.09 | 9813.14 | 80 | 75 | 0 | -5
PHARR | 0921-02-305 | HIDALGO | CS | 2020-09-25 | 1276034 | 22661.25 | 1247500.84 | -28533.16 | 227 | 226 | 0 | -1
WICHITA FALLS | 1357-01-026 | COOKE | FM 2896 | 2020-09-25 | 2595534.08 | 6510.84 | 2655696.04 | 60161.96 | 170 | 137 | 0 | -33
SAN ANTONIO | 0017-01-024 | BEXAR | SL 353 | 2020-09-27 | 1022882.27 | 30706.64 | 1049076.25 | 26193.98 | 210 | 204 | 0 | -6
SAN ANTONIO | 0017-10-275 | BEXAR | IH 35 | 2020-09-27 | 7362618.04 | 1245296.1 | 9019341.73 | 1656723.69 | 240 | 234 | 0 | -6
SAN ANTONIO | 0017-10-287 | BEXAR | IH 35 | 2020-09-27 | 247299.32 | 3992.78 | 211776.54 | -35522.78 | 70 | 62 | 0 | -8
SAN ANTONIO | 0915-00-186 | BEXAR | VA | 2020-09-27 | 2664496.9 | 427123.23 | 3312595.31 | 648098.41 | 319 | 223 | 25 | -71
BRYAN | 0210-03-025 | MILAM | FM 1712 | 2020-09-28 | 1262197.65 | 173760.29 | 1459082.66 | 196885.01 | 72 | 73 | 3 | 4
CORPUS CHRISTI | 0270-09-030 | LIVE OAK | SH 72 | 2020-09-28 | 6451354.78 | 203687.75 | 6642889.1 | 191534.32 | 136 | 149 | 12 | 25
FORT WORTH | 0902-48-744 | TARRANT | CR | 2020-09-28 | 2379000 | -271599.41 | 2061365.19 | -317634.81 | 253 | 260 | 10 | 17
HOUSTON | 0912-72-333 | HARRIS | CS | 2020-09-28 | 1137427.78 | 3937.5 | 1143030.11 | 5602.33 | 165 | 104 | 0 | -61
WACO | 0049-01-094 | MCLENNAN | SH 6 | 2020-09-28 | 1026074 | 39685.4 | 1128576.42 | 102502.42 | 90 | 90 | 0 | 0
BEAUMONT | 0710-02-068 | ORANGE | FM 105 | 2020-09-29 | 3550038.75 | -485824.39 | 3373493.67 | -176545.08 | 104 | 104 | 18 | 18
DALLAS | 1159-01-022 | ELLIS | FM 875 | 2020-09-29 | 3724841 | 454158.93 | 4208410.26 | 483569.26 | 467 | 462 | 2 | -3
YOAKUM | 2350-01-059 | VICTORIA | US 77 | 2020-09-29 | 335632.92 | 0 | 333834.34 | -1798.58 | 49 | 46 | 0 | -3
CORPUS CHRISTI | 1742-01-026 | NUECES | FM 1694 | 2020-09-30 | 241172.25 | 8714.63 | 220729.76 | -20442.49 | 51 | 46 | 1 | -4
PARIS | 0435-01-079 | LAMAR | FM 137 | 2020-09-30 | 998565.12 | 99606.58 | 1083763.16 | 85198.04 | 38 | 46 | 12 | 20
ATLANTA | 0010-08-056 | MORRIS | US 67 | 2020-10-01 | 4509223.75 | -414754.26 | 4104341.64 | -404882.11 | 248 | 195 | 8 | -45
ATLANTA | 0010-08-057 | MORRIS | US 67 | 2020-10-01 | 1488936.82 | 0 | 1460939.7 | -27997.12 | 72 | 68 | 0 | -4
WACO | 0909-22-183 | MCLENNAN | CS | 2020-10-01 | 109680 | 0 | 115445 | 5765 | 30 | 25 | 0 | -5
WICHITA FALLS | 0137-10-022 | CLAY | FM 174 | 2020-10-01 | 2328204.18 | 0 | 2498252.33 | 170048.15 | 170 | 168 | 0 | -2
ODESSA | 2224-01-100 | ECTOR | SL 338 | 2020-10-02 | 3012163 | 2597 | 3110749.71 | 98586.71 | 262 | 223 | 0 | -39
WACO | 0836-02-025 | BELL | SH 195 | 2020-10-02 | 281766 | 11241 | 295317 | 13551 | 45 | 17 | 0 | -28
BEAUMONT | 0065-05-145 | HARDIN | US 96 | 2020-10-05 | 6772231.89 | 1160654.81 | 8195688.74 | 1423456.85 | 124 | 167 | 71 | 114
BEAUMONT | 0177-03-104 | LIBERTY | US 59 | 2020-10-05 | 1514862.4 | 255184.81 | 1708829.71 | 193967.31 | 57 | 41 | 8 | -8
BEAUMONT | 0200-14-085 | JEFFERSON | US 69 | 2020-10-05 | 8319407.2 | -745949.75 | 8050175.83 | -269231.37 | 186 | 180 | 0 | -6
DALLAS | 1567-01-037 | DENTON | FM 720 | 2020-10-05 | 15011511 | 751151.42 | 15796422.88 | 784911.88 | 428 | 441 | 95 | 108
EL PASO | 0233-01-044 | CULBERSON | US 62 | 2020-10-05 | 3783684.49 | 0 | 3710305.63 | -73378.86 | 200 | 241 | 0 | 41
DALLAS | 0718-01-064 | DENTON | FM 156 | 2020-10-06 | 32541855.76 | 4486302.47 | 35897314.17 | 3355458.41 | 521 | 863 | 341 | 683
ODESSA | 0906-32-057 | MIDLAND | CS | 2020-10-06 | 834326.5 | 20010 | 807937.75 | -26388.75 | 120 | 82 | 20 | -18
BROWNWOOD | 0054-07-069 | BROWN | US 84 | 2020-10-07 | 8488149.7 | 1128255.61 | 10017918.06 | 1529768.36 | 400 | 467 | 80 | 147
EL PASO | 0021-01-053 | BREWSTER | US 67 | 2020-10-07 | 4010557.7 | 1685885.16 | 5875768.11 | 1865210.41 | 140 | 304 | 164 | 328
HOUSTON | 0912-73-205 | GALVESTON | VA | 2020-10-07 | 21325783 | 3239937.42 | 24557622.09 | 3231839.09 | 450 | 626 | 176 | 352
DALLAS | 0918-47-128 | DALLAS | CS | 2020-10-08 | 1340240 | 0 | 1327376.86 | -12863.14 | 160 | 157 | 0 | -3
ODESSA | 0003-06-094 | REEVES | IH 20 | 2020-10-08 | 7919242.91 | -97870.01 | 7663622.4 | -255620.51 | 38 | 11 | 0 | -27
WICHITA FALLS | 0194-02-097 | COOKE | IH 35 | 2020-10-08 | 261736.4 | 0 | 257461.4 | -4275 | 34 | 32 | 0 | -2
WICHITA FALLS | 0681-04-041 | WICHITA | FM 367 | 2020-10-08 | 5646361.9 | 69848.73 | 5907257.41 | 260895.51 | 170 | 191 | 20 | 41
AMARILLO | 2635-02-035 | RANDALL | SL 335 | 2020-10-12 | 10708977.98 | 467749.88 | 11986939.31 | 1277961.33 | 150 | 152 | 20 | 22
AUSTIN | 0015-08-140 | WILLIAMSON | IH 35 | 2020-10-12 | 6028948.61 | 184050.67 | 6294226.52 | 265277.91 | 260 | 274 | 14 | 28
AUSTIN | 0150-02-040 | LLANO | SH 29 | 2020-10-12 | 1617038.57 | 0 | 1411368.84 | -205669.73 | 50 | 47 | 0 | -3
AUSTIN | 3417-01-029 | TRAVIS | FM 734 | 2020-10-12 | 2822373.28 | 82719 | 3139417.68 | 317044.4 | 67 | 84 | 6 | 23
CORPUS CHRISTI | 0074-06-251 | NUECES | IH 37 | 2020-10-12 | 386594.72 | 0 | 272309.49 | -114285.23 | 58 | 30 | 0 | -28
DALLAS | 0196-01-106 | DENTON | IH 35E | 2020-10-12 | 27503078.96 | 2399130.85 | 27354931.23 | -148147.73 | 442 | 860 | 90 | 508
SAN ANGELO | 0140-11-045 | CROCKETT | IH 10 | 2020-10-12 | 3784610.02 | 86731.19 | 3954011.84 | 169401.82 | 242 | 256 | 6 | 20
ABILENE | 0069-01-057 | HOWARD | US 87 | 2020-10-13 | 1866062.3 | -132951 | 1632468.75 | -233593.55 | 134 | 141 | 0 | 7
BRYAN | 0212-04-033 | GRIMES | SH 30 | 2020-10-13 | 5718784.14 | 573083.69 | 6283874.93 | 565090.79 | 251 | 286 | 36 | 71
CHILDRESS | 0925-11-014 | WHEELER | CR | 2020-10-13 | 1545677.4 | -85943.26 | 1436683.14 | -108994.26 | 186 | 153 | 1 | -32
SAN ANTONIO | 0073-08-190 | BEXAR | IH 37 | 2020-10-13 | 557600 | 0 | 542427.88 | -15172.12 | 81 | 81 | 0 | 0
SAN ANTONIO | 2452-01-056 | BEXAR | SL 1604 | 2020-10-13 | 62500950.18 | 4579603.8 | 70126179.93 | 7298596.21 | 751 | 885 | 144 | 278
BEAUMONT | 1024-01-076 | CHAMBERS | FM 565 | 2020-10-14 | 1057947 | 69983.27 | 1150291.31 | 92344.31 | 77 | 41 | 0 | -36
WACO | 1835-02-056 | BELL | FM 1741 | 2020-10-14 | 3284016.2 | -466975.9 | 2729350.44 | -554665.76 | 105 | 69 | 0 | -36
FORT WORTH | 0250-02-050 | PALO PINTO | US 281 | 2020-10-15 | 4656945.55 | 3303989.78 | 8085453.08 | 3428507.53 | 234 | 724 | 490 | 980
AMARILLO | 1108-01-020 | HARTLEY | FM 767 | 2020-10-16 | 4253525.12 | 8654.44 | 4270859.08 | 17333.96 | 280 | 304 | 0 | 24
ATLANTA | 0221-05-064 | TITUS | US 271 | 2020-10-16 | 8911050.61 | 457473.01 | 8858159.84 | -52890.77 | 325 | 342 | 8 | 25
AUSTIN | 0150-02-035 | LLANO | SH 29 | 2020-10-16 | 214228.81 | 33384.08 | 251503.66 | 37274.85 | 26 | 17 | 0 | -9
HOUSTON | 0500-03-588 | HARRIS | IH 45 | 2020-10-16 | 4552329.65 | 414695.69 | 5357690.23 | 805360.58 | 260 | 238 | 0 | -22
PARIS | 0136-03-044 | DELTA | SH 24 | 2020-10-16 | 39277746.71 | 1891959.49 | 42336503.35 | 3058756.64 | 598 | 750 | 158 | 310
SAN ANGELO | 0158-01-082 | RUNNELS | US 67 | 2020-10-16 | 16352619.66 | 865948.8 | 17920936.97 | 1568317.31 | 166 | 163 | 3 | 0
CHILDRESS | 0042-07-066 | DONLEY | US 287 | 2020-10-19 | 4527707.02 | 45732.14 | 5079698.21 | 551991.19 | 55 | 54 | 0 | -1
LAREDO | 0037-05-054 | DIMMIT | US 83 | 2020-10-19 | 5065082.63 | -44764.89 | 4980761.11 | -84321.52 | 106 | 65 | 0 | -41
LAREDO | 0412-05-037 | VAL VERDE | SH 163 | 2020-10-19 | 705850 | -31970 | 657599.88 | -48250.12 | 126 | 101 | 0 | -25
SAN ANTONIO | 0915-00-222 | BEXAR | VA | 2020-10-19 | 1519049.05 | 0 | 1519049.05 | 0 | 320 | 126 | 0 | -194
CORPUS CHRISTI | 0100-05-185 | KARNES | US 181 | 2020-10-20 | 749585.7 | 7143.49 | 727094.19 | -22491.51 | 141 | 80 | 0 | -61
SAN ANTONIO | 0024-09-024 | BEXAR | SS 371 | 2020-10-20 | 6242921.16 | 117965.84 | 5974663.83 | -268257.33 | 255 | 241 | 30 | 16
AUSTIN | 2211-01-027 | WILLIAMSON | RM 2338 | 2020-10-21 | 286852 | 0 | 287808.59 | 956.59 | 40 | 40 | 0 | 0
FORT WORTH | 0134-12-005 | WISE | BU 380F | 2020-10-21 | 963087.35 | 25693.37 | 1025378.87 | 62291.52 | 128 | 150 | 8 | 30
HOUSTON | 0912-72-315 | HARRIS | VA | 2020-10-21 | 1323726 | 13453.26 | 1278943.12 | -116183.9 | 136 | 122 | 0 | -14
PARIS | 0045-03-051 | GRAYSON | SH 56 | 2020-10-21 | 995080 | 0 | 995080 | 0 | 55 | 55 | 0 | 0
PARIS | 0901-19-197 | GRAYSON | VA | 2020-10-21 | 1246711 | 63311.04 | 1322604.01 | 75893.01 | 120 | 63 | 0 | -57
WACO | 2304-02-036 | BELL | FM 2410 | 2020-10-21 | 6800753.05 | 133463.78 | 6881957.93 | 81204.88 | 617 | 616 | 0 | -1
WICHITA FALLS | 1855-01-028 | COOKE | FM 922 | 2020-10-21 | 159018 | 0 | 134372.17 | -24645.83 | 17 | 14 | 0 | -3
DALLAS | 1047-02-050 | DALLAS | FM 1382 | 2020-10-22 | 1670100.94 | 0 | 1671550.78 | 1449.84 | 257 | 182 | 0 | -75
BRYAN | 0049-09-078 | BRAZOS | SH 6 | 2020-10-23 | 10186765.85 | 269388.29 | 10595604.41 | 408838.56 | 128 | 134 | 6 | 12
YOAKUM | 2350-01-041 | VICTORIA | US 77 | 2020-10-23 | 21361349.82 | 693881.07 | 21916270.48 | 554920.66 | 450 | 452 | 2 | 4
DALLAS | 0009-11-233 | DALLAS | IH 30 | 2020-10-26 | 2254488.45 | 136432.37 | 2521063.54 | 266575.09 | 247 | 407 | 128 | 288
DALLAS | 0047-06-165 | COLLIN | US 75 | 2020-10-26 | 1923008 | 1086.89 | 2066603.42 | 143595.42 | 180 | 221 | 41 | 82
DALLAS | 0047-14-069 | COLLIN | US 75 | 2020-10-26 | 79417673.43 | 4525533.01 | 82832061.64 | 3414388.21 | 884 | 980 | 97 | 193
HOUSTON | 0114-11-080 | WALLER | US 290 | 2020-10-26 | 349012 | 0 | 350330.54 | 1318.54 | 28 | 14 | 0 | -14
PHARR | 0039-02-066 | HIDALGO | US 83 | 2020-10-26 | 7654069.29 | 7650.47 | 7899001.32 | 244932.03 | 219 | 228 | 0 | 9
WACO | 0867-02-019 | CORYELL | FM 932 | 2020-10-26 | 8847136.89 | 737.18 | 8982198.63 | 135061.74 | 180 | 52 | 0 | -128
BEAUMONT | 0213-06-044 | TYLER | US 190 | 2020-10-27 | 12309357.08 | 12915 | 11975588.78 | -333768.3 | 60 | 48 | 0 | -12
BEAUMONT | 0920-00-124 | JEFFERSON | VA | 2020-10-27 | 1289630.34 | -130037.48 | 1155001.98 | -134628.36 | 100 | 54 | 0 | -46
CORPUS CHRISTI | 0088-01-068 | BEE | US 59 | 2020-10-27 | 4366327.9 | 163235.64 | 4226075.68 | -140252.22 | 98 | 114 | 16 | 32
CORPUS CHRISTI | 0916-26-019 | GOLIAD | CR | 2020-10-27 | 518768.35 | -14377.35 | 482706.16 | -36062.19 | 68 | 68 | 0 | 0
LAREDO | 0022-10-070 | VAL VERDE | US 90 | 2020-10-27 | 692972.36 | 1189.64 | 722159.7 | 29187.34 | 40 | 36 | 0 | -4
LAREDO | 0301-04-020 | DIMMIT | FM 186 | 2020-10-27 | 12607041.22 | 36423.61 | 13294765.07 | 687723.85 | 200 | 238 | 38 | 76
WACO | 0015-05-050 | BELL | SH 317 | 2020-10-27 | 521881 | 3566.1 | 513233.1 | -8647.9 | 75 | 62 | 0 | -13
WACO | 0055-04-031 | CORYELL | US 84 | 2020-10-27 | 139750 | -15800 | 118250 | -21500 | 45 | 72 | 0 | 27
BEAUMONT | 0065-05-153 | HARDIN | US 96 | 2020-10-28 | 223223 | 0 | 204400.62 | -18822.38 | 17 | 15 | 0 | -2
DALLAS | 0918-00-295 | DALLAS | VA | 2020-10-28 | 2989898.04 | 0 | 2708419.15 | -281478.89 | 294 | 291 | 0 | -3
BEAUMONT | 0367-01-069 | CHAMBERS | SH 124 | 2020-10-29 | 1919055.95 | 144468.82 | 2260420.98 | 341365.03 | 59 | 59 | 7 | 7
WICHITA FALLS | 0013-05-064 | MONTAGUE | US 81 | 2020-10-29 | 660444.35 | 0 | 666150.17 | 5705.82 | 35 | 30 | 0 | -5
YOAKUM | 0287-03-031 | GONZALES | SH 80 | 2020-10-30 | 1301576.76 | 101792.61 | 1401380.12 | 99803.36 | 213 | 128 | 0 | -85
BEAUMONT | 0028-09-111 | ORANGE | IH 10 | 2020-11-02 | 58877950 | 1332182.07 | 60497721.52 | 1619771.52 | 1085 | 1760 | 702 | 1377
EL PASO | 0924-06-578 | EL PASO | VA | 2020-11-02 | 585213.55 | 46112.35 | 611047.12 | 25833.57 | 60 | 80 | 20 | 40
BEAUMONT | 0065-04-079 | JASPER | US 96 | 2020-11-03 | 1098472.89 | 0 | 1052977.04 | -45495.85 | 79 | 79 | 0 | 0
BEAUMONT | 0920-30-081 | ORANGE | CR | 2020-11-03 | 8977087.38 | 1141798.84 | 10385518.23 | 1408430.85 | 157 | 570 | 183 | 596
AUSTIN | 0471-05-046 | BASTROP | SH 21 | 2020-11-04 | 568728.51 | 55287 | 652297.64 | 83569.13 | 165 | 107 | 0 | -58
HOUSTON | 0178-02-089 | BRAZORIA | SH 35 | 2020-11-04 | 4772337.96 | 1223084.6 | 6054137.16 | 1281799.2 | 145 | 241 | 58 | 154
SAN ANTONIO | 0915-45-051 | MEDINA | CR | 2020-11-04 | 274729.5 | 6155.47 | 280480.66 | 5751.16 | 78 | 62 | 0 | -16
SAN ANTONIO | 2452-03-123 | BEXAR | SL 1604 | 2020-11-04 | 4014717.41 | 8422.95 | 4278531.75 | 263814.34 | 114 | 114 | 0 | 0
BEAUMONT | 1024-01-074 | CHAMBERS | FM 565 | 2020-11-05 | 1709304.36 | 180245.27 | 2006038.77 | 296734.41 | 90 | 137 | 36 | 83
SAN ANTONIO | 0073-08-193 | BEXAR | IH 37 | 2020-11-06 | 107737.99 | 11031.02 | 116170.75 | 8432.76 | 45 | 61 | 0 | 16
AMARILLO | 0040-01-050 | DALLAM | US 87 | 2020-11-09 | 10092335.71 | 127838.24 | 10999977.11 | 907641.4 | 120 | 139 | 15 | 34
BEAUMONT | 1061-01-032 | LIBERTY | FM 1010 | 2020-11-09 | 1711111.03 | 265927.77 | 2077888.1 | 366777.07 | 59 | 82 | 3 | 26
FORT WORTH | 0314-07-069 | PARKER | IH 20 | 2020-11-10 | 925967.11 | 357758.5 | 1259106.79 | 333139.68 | 50 | 35 | 0 | -15
YOAKUM | 0605-01-064 | MATAGORDA | FM 457 | 2020-11-10 | 2986655.2 | -143085.17 | 2961960.2 | -24695 | 180 | 104 | 0 | -76
YOAKUM | 0709-03-008 | WHARTON | FM 3012 | 2020-11-10 | 4587960.51 | -42536.21 | 4392353.7 | -195606.81 | 262 | 258 | 0 | -4
HOUSTON | 0389-06-108 | GALVESTON | SH 146 | 2020-11-12 | 2397517.52 | -13136.89 | 2475864.47 | 78346.95 | 75 | 63 | 0 | -12
LUFKIN | 1407-01-029 | NACOGDOCHES | FM 1275 | 2020-11-12 | 1329187.8 | 25689.43 | 1412618.77 | 83430.97 | 24 | 30 | 9 | 15
WACO | 0183-04-049 | CORYELL | SH 36 | 2020-11-12 | 12363769.21 | 2331618.68 | 15478000.59 | 3114231.38 | 638 | 712 | 19 | 93
WICHITA FALLS | 0043-09-139 | WICHITA | US 287 | 2020-11-12 | 2552811.48 | 0 | 2463744.24 | -89067.24 | 51 | 37 | 0 | -14
YOAKUM | 0266-08-011 | COLORADO | BS 71-F | 2020-11-12 | 10459588.75 | 36836.84 | 10472405.47 | 12816.72 | 375 | 320 | 0 | -55
CORPUS CHRISTI | 0617-01-196 | NUECES | SH 358 | 2020-11-13 | 7489379.23 | 543174.52 | 8268316.83 | 778937.6 | 117 | 207 | 96 | 186
DALLAS | 0918-47-115 | DALLAS | VA | 2020-11-13 | 2237635.19 | 0 | 2032972.75 | -204662.44 | 200 | 256 | 40 | 96
DALLAS | 2363-01-007 | ROCKWALL | FM 2453 | 2020-11-13 | 2753944.79 | 64835.65 | 2655979.61 | -97965.18 | 160 | 160 | 0 | 0
FORT WORTH | 0902-39-033 | PALO PINTO | CS | 2020-11-13 | 1007170.06 | 0 | 1006706.5 | -463.56 | 107 | 107 | 0 | 0
HOUSTON | 0271-05-043 | FORT BEND | IH 10 | 2020-11-13 | 1107205.6 | 78883.15 | 1158255.62 | 51050.02 | 81 | 124 | 24 | 67
SAN ANGELO | 0158-01-083 | RUNNELS | US 67 | 2020-11-13 | 3312755.35 | 37779.2 | 3315341.16 | 2585.81 | 202 | 162 | 0 | -40
DALLAS | 2681-01-025 | DENTON | FM 2499 | 2020-11-16 | 997920.8 | -7780.91 | 992010.66 | -5910.14 | 81 | 66 | 0 | -15
CORPUS CHRISTI | 0916-00-215 | NUECES | VA | 2020-11-17 | 2803253.09 | 0 | 2396400.37 | -406852.72 | 80 | 80 | 0 | 0
DALLAS | 1746-01-027 | COLLIN | FM 1827 | 2020-11-17 | 5440851.66 | 570401.55 | 5655127.85 | 214276.19 | 230 | 319 | 74 | 163
FORT WORTH | 0902-90-045 | TARRANT | VA | 2020-11-17 | 1141382.1 | 52373.57 | 1146116.55 | -35599.83 | 171 | 250 | 62 | 141
PARIS | 0901-19-180 | GRAYSON | CR | 2020-11-17 | 475466.84 | 0 | 481454.8 | 5987.96 | 51 | 39 | 0 | -12
PARIS | 0901-22-121 | HUNT | VA | 2020-11-17 | 167672.9 | -3390 | 167287.65 | -385.25 | 72 | 57 | 0 | -15
PARIS | 2657-01-031 | LAMAR | FM 2648 | 2020-11-17 | 4044598.86 | 32387.27 | 3985518.8 | -59080.06 | 208 | 205 | 0 | -3
SAN ANGELO | 0141-08-047 | KIMBLE | IH 10 | 2020-11-17 | 6324553.65 | 672426.3 | 7499385.29 | 1174831.64 | 100 | 157 | 14 | 71
AUSTIN | 0113-04-027 | BLANCO | US 290 | 2020-11-18 | 840709.44 | 0 | 907736.87 | 67027.43 | 48 | 16 | 0 | -32
BRYAN | 0166-02-044 | FREESTONE | SH 75 | 2020-11-18 | 9531822.16 | -27228.72 | 9176353.44 | -355468.72 | 90 | 62 | 0 | -28
BRYAN | 0204-05-040 | MILAM | US 79 | 2020-11-18 | 376466.3 | -50882.89 | 302240.53 | -74225.77 | 22 | 20 | 1 | -1
EL PASO | 2121-02-137 | EL PASO | IH 10 | 2020-11-18 | 158778404.2 | 1580940.5 | 164340952.15 | 5562547.95 | 1211 | 1348 | 150 | 287
SAN ANTONIO | 0328-07-014 | MCMULLEN | SH 97 | 2020-11-18 | 4336031.67 | 45613.82 | 4069094.34 | -266937.33 | 312 | 305 | 2 | -5
YOAKUM | 0089-01-090 | VICTORIA | US 59 | 2020-11-18 | 7280415.33 | 776320.14 | 8146723.71 | 866308.38 | 105 | 191 | 88 | 174
YOAKUM | 0089-03-088 | JACKSON | US 59 | 2020-11-18 | 6620873.22 | 78186.59 | 6855221.69 | 234348.47 | 90 | 126 | 38 | 74
YOAKUM | 0913-29-033 | LAVACA | CR | 2020-11-18 | 733626.26 | 239090.48 | 978174.34 | 244548.08 | 60 | 89 | 29 | 58
CORPUS CHRISTI | 0916-00-086 | NUECES | VA | 2020-11-19 | 1132328.53 | 53343.17 | 1111518.19 | -20810.34 | 153 | 208 | 41 | 96
CORPUS CHRISTI | 1558-01-019 | NUECES | FM 70 | 2020-11-19 | 4592254.65 | 125795.15 | 4642390.45 | 50135.8 | 180 | 181 | 0 | 1
FORT WORTH | 0259-03-057 | SOMERVELL | US 67 | 2020-11-19 | 2356575.65 | 896846.1 | 3303179.83 | 946604.18 | 77 | 112 | 35 | 70
TYLER | 0926-01-023 | CHEROKEE | FM 343 | 2020-11-19 | 638597.67 | 11870.66 | 612330.67 | -26267 | 90 | 94 | 4 | 8
YOAKUM | 0913-22-047 | GONZALES | CR | 2020-11-19 | 773075.76 | 40709.82 | 818541.3 | 45465.54 | 111 | 101 | 0 | -10
HOUSTON | 0912-70-103 | HARRIS | CS | 2020-11-20 | 5659268 | 107955.38 | 5657856.64 | -109366.74 | 228 | 241 | 13 | 26
WICHITA FALLS | 0903-15-085 | COOKE | CR | 2020-11-20 | 1090039.8 | 0 | 1056415.4 | -33624.4 | 168 | 164 | 0 | -4
HOUSTON | 0050-06-086 | HARRIS | US 290 | 2020-11-23 | 36840375.34 | 6397954.38 | 44478880.71 | 7638505.37 | 601 | 1047 | 450 | 896
AMARILLO | 0904-00-183 | POTTER | VA | 2020-11-24 | 1985312.9 | 284465 | 2366645.25 | 381332.35 | 124 | 123 | 0 | -1
FORT WORTH | 0013-08-135 | WISE | US 81 | 2020-11-24 | 1170226.87 | 1913.31 | 973986.89 | -196239.98 | 64 | 66 | 0 | 2
SAN ANGELO | 0035-07-043 | KIMBLE | US 83 | 2020-11-24 | 5713900.34 | 702163.43 | 6362408.1 | 648507.76 | 339 | 331 | 18 | 10
SAN ANGELO | 0558-07-019 | GLASSCOCK | RM 33 | 2020-11-24 | 2255155.02 | 0 | 2177040.2 | -78114.82 | 44 | 19 | 0 | -25
SAN ANTONIO | 0142-05-080 | KERR | SH 27 | 2020-11-24 | 8690979.58 | -53173.3 | 8455690.78 | -235288.8 | 261 | 305 | 44 | 88
TYLER | 0592-02-015 | RUSK | FM 840 | 2020-11-24 | 7676966.98 | 123032.92 | 7947856.37 | 270889.39 | 337 | 275 | 0 | -62
WICHITA FALLS | 0391-03-031 | CLAY | SH 148 | 2020-11-24 | 1041710.84 | 0 | 1007248.16 | -34462.68 | 94 | 109 | 0 | 15
WICHITA FALLS | 1767-03-018 | MONTAGUE | FM 1816 | 2020-11-24 | 3337756.51 | 146935.65 | 3813050.16 | 475293.65 | 139 | 124 | 24 | 9
HOUSTON | 0912-71-896 | HARRIS | CS | 2020-11-25 | 6095883.88 | 230744.1 | 6616199.15 | 520315.27 | 263 | 265 | 25 | 27
LUFKIN | 0176-05-181 | POLK | US 59 | 2020-11-27 | 3604502.78 | 26037.6 | 3396924.12 | -207578.66 | 102 | 121 | 0 | 19
DALLAS | 1091-03-012 | ROCKWALL | FM 1140 | 2020-11-30 | 4349076.76 | 226403.52 | 4435632.52 | 86555.76 | 221 | 228 | 0 | 7
SAN ANTONIO | 0017-10-277 | BEXAR | IH 35 | 2020-11-30 | 83094.73 | 0 | 77081.99 | -6012.74 | 60 | 28 | 0 | -32
FORT WORTH | 0014-03-095 | JOHNSON | IH 35W | 2020-12-01 | 10321476.86 | 687442.37 | 10414290.94 | 92814.08 | 235 | 267 | 0 | 32
PARIS | 1380-01-018 | FRANKLIN | FM 1448 | 2020-12-01 | 801629.4 | -71928.6 | 666586.08 | -135043.32 | 92 | 83 | 0 | -9
WACO | 1187-02-018 | MCLENNAN | FM 938 | 2020-12-01 | 663129.76 | 33596.53 | 676928.24 | 13798.48 | 90 | 107 | 5 | 22
ATLANTA | 0248-04-071 | UPSHUR | US 271 | 2020-12-02 | 8411111 | 10737.84 | 8246451.21 | -164659.79 | 70 | 74 | 0 | 4
ODESSA | 0292-04-065 | WARD | SH 18 | 2020-12-02 | 6516031.98 | -53504 | 5884584.34 | -631447.64 | 125 | 115 | 0 | -10
ODESSA | 0906-00-169 | ECTOR | VA | 2020-12-02 | 3256207.3 | 555474.63 | 4414590.76 | 1158383.46 | 240 | 337 | 140 | 237
BEAUMONT | 0952-01-060 | LIBERTY | FM 1008 | 2020-12-03 | 2730449.37 | 533968.37 | 3365432.07 | 634982.7 | 204 | 139 | 0 | -65
EL PASO | 2121-01-091 | EL PASO | IH 10 | 2020-12-03 | 7550372.33 | 708135.67 | 9039807.18 | 1489434.85 | 240 | 300 | 60 | 120
BROWNWOOD | 0273-01-066 | LAMPASAS | US 183 | 2020-12-04 | 824661.35 | 0 | 844882.67 | 20221.32 | 34 | 16 | 0 | -18
DALLAS | 0918-47-178 | DALLAS | CS | 2020-12-04 | 1330000 | 0 | 1298730.78 | -31269.22 | 150 | 134 | 0 | -16
FORT WORTH | 1751-01-030 | WISE | FM 1655 | 2020-12-04 | 333066.35 | 87185.5 | 328222.07 | -4844.28 | 43 | 47 | 4 | 8
SAN ANTONIO | 0915-00-181 | BEXAR | VA | 2020-12-04 | 1424651.88 | 58074.56 | 1488671.52 | 64019.64 | 320 | 244 | 0 | -76
FORT WORTH | 1513-02-042 | JOHNSON | FM 4 | 2020-12-07 | 1990741.76 | 97850.27 | 2070996.28 | 80254.52 | 150 | 131 | 3 | -16
PHARR | 0331-04-067 | CAMERON | PR 100 | 2020-12-07 | 3452509.19 | 541650.39 | 3748359.57 | 216333.43 | 316 | 477 | 174 | 335
TYLER | 0910-12-138 | VAN ZANDT | CR | 2020-12-07 | 552443 | -36561.32 | 482333.6 | -70109.4 | 122 | 76 | 0 | -46
AUSTIN | 0016-16-030 | HAYS | RM 967 | 2020-12-08 | 1175630.8 | 133134.01 | 1300498.31 | 105239.45 | 92 | 68 | 0 | -24
AUSTIN | 0914-18-114 | BASTROP | CS | 2020-12-08 | 1310554 | -33411.01 | 1309609.46 | -944.54 | 77 | 77 | 0 | 0
CORPUS CHRISTI | 0916-28-073 | SAN PATRICIO | CS | 2020-12-08 | 499231.8 | 13599.68 | 460284.26 | -45133.52 | 106 | 111 | 5 | 10
HOUSTON | 0111-01-092 | HARRIS | FM 521 | 2020-12-08 | 3070707.87 | 415.81 | 3331755.45 | 261047.58 | 143 | 129 | 0 | -14
YOAKUM | 0089-07-156 | WHARTON | US 59 | 2020-12-08 | 286694 | 15451.5 | 298583.7 | 11889.7 | 30 | 33 | 0 | 3
CORPUS CHRISTI | 0074-01-055 | LIVE OAK | IH 37 | 2020-12-09 | 1839971.96 | 531663.48 | 2336956.93 | 496984.97 | 119 | 151 | 34 | 66
DALLAS | 2208-02-022 | DALLAS | SS 303 | 2020-12-09 | 2756288.75 | 143784.54 | 2919916.61 | 163627.86 | 120 | 167 | 48 | 95
SAN ANGELO | 0907-00-221 | TOM GREEN | VA | 2020-12-09 | 119937.15 | -10476 | 98333.9 | -21603.25 | 25 | 30 | 0 | 5
ATLANTA | 0063-04-064 | PANOLA | US 59 | 2020-12-10 | 7272584.26 | -974223.54 | 6288972.26 | -983612 | 75 | 46 | 0 | -29
DALLAS | 1950-01-039 | DENTON | FM 407 | 2020-12-10 | 856162.88 | 127625.05 | 891366 | 19187.75 | 255 | 193 | 0 | -62
PHARR | 0517-10-019 | JIM HOGG | SH 16 | 2020-12-10 | 3673999.61 | 0 | 3661038.56 | -12961.05 | 149 | 145 | 0 | -4
PHARR | 2717-02-010 | CAMERON | FM 3248 | 2020-12-10 | 3226291.46 | 0 | 3209938.4 | -16353.06 | 91 | 91 | 0 | 0
PHARR | 3097-02-016 | HIDALGO | FM 396 | 2020-12-10 | 3726801.64 | 0 | 3692950.82 | -33850.82 | 67 | 67 | 0 | 0
ODESSA | 0354-02-027 | WARD | SH 115 | 2020-12-11 | 679704 | 0 | 699019.5 | 19315.5 | 200 | 113 | 0 | -87
ODESSA | 0906-00-184 | ECTOR | VA | 2020-12-11 | 890537.5 | 196206.8 | 1051060.64 | 160523.14 | 60 | 55 | 0 | -5
PHARR | 1586-01-069 | HIDALGO | FM 907 | 2020-12-11 | 10446130.3 | 195184.85 | 10161363.44 | -284766.86 | 500 | 419 | 0 | -81
ABILENE | 0677-01-023 | TAYLOR | FM 707 | 2020-12-14 | 6775556.09 | -194861.68 | 6262193.87 | -513362.22 | 103 | 95 | 0 | -8
ABILENE | 3276-01-020 | BORDEN | FM 1054 | 2020-12-14 | 9612826.11 | -153547.68 | 9240565.75 | -372260.36 | 103 | 61 | 0 | -42
AUSTIN | 0112-03-035 | GILLESPIE | US 290 | 2020-12-14 | 4681677.5 | 170356.52 | 5224539.08 | 542861.58 | 313 | 358 | 40 | 85
HOUSTON | 0912-72-413 | HARRIS | VA | 2020-12-14 | 1764011.1 | 119017.65 | 1846883.71 | 82872.61 | 150 | 148 | 0 | -2
BEAUMONT | 0920-39-024 | CHAMBERS | VA | 2020-12-15 | 1080400.1 | 0 | 1064335.15 | -16064.95 | 71 | 96 | 25 | 50
DALLAS | 0196-03-278 | DALLAS | IH 35E | 2020-12-16 | 4269055.2 | 121203.06 | 3755763.11 | -513292.09 | 136 | 136 | 0 | 0
SAN ANTONIO | 0017-09-104 | BEXAR | IH 35 | 2020-12-16 | 482084.04 | 20735 | 488854.04 | 6770 | 56 | 39 | 0 | -17
SAN ANTONIO | 0915-00-206 | BEXAR | VA | 2020-12-16 | 391447.22 | 6577.52 | 306152.29 | -85294.93 | 120 | 131 | 24 | 35
ATLANTA | 0010-06-042 | TITUS | US 67 | 2020-12-17 | 2498030.22 | 9889.08 | 2456308.77 | -41721.45 | 240 | 181 | 0 | -59
BRYAN | 0675-03-081 | LEON | IH 45 | 2020-12-17 | 8878806.51 | 996964.11 | 9852635.14 | 973828.63 | 240 | 316 | 76 | 152
DALLAS | 0081-13-066 | DENTON | IH 35W | 2020-12-17 | 5910402.34 | -686478.67 | 5113300.72 | -797101.62 | 307 | 94 | 0 | -213
LUFKIN | 0064-04-040 | SAN AUGUSTINE | SH 21 | 2020-12-17 | 2366232.09 | 0 | 2084554.93 | -281677.16 | 155 | 129 | 0 | -26
LUFKIN | 0911-00-077 | ANGELINA | VA | 2020-12-17 | 2351740.48 | 0 | 2321993.71 | -29746.77 | 89 | 99 | 15 | 25
LUFKIN | 2507-01-020 | ANGELINA | FM 326 | 2020-12-17 | 3646856.65 | 1000 | 3691904.88 | 45048.23 | 180 | 177 | 0 | -3
CORPUS CHRISTI | 0086-11-053 | JIM WELLS | SH 44 | 2020-12-18 | 7771423.48 | 13690 | 7660096.25 | -111327.23 | 180 | 89 | 0 | -91
FORT WORTH | 0363-01-146 | TARRANT | SH 26 | 2020-12-18 | 338652.07 | 0 | 336776.04 | -1876.03 | 77 | 95 | 18 | 36
ABILENE | 0908-00-093 | TAYLOR | VA | 2020-12-21 | 1285512 | 0 | 1183868.75 | -101643.25 | 44 | 33 | 0 | -11
AMARILLO | 0090-01-032 | DEAF SMITH | IH 40 | 2020-12-21 | 8261962 | 481059.03 | 8787258.37 | 525296.37 | 377 | 471 | 56 | 150
BRYAN | 2825-01-009 | BURLESON | FM 2774 | 2020-12-21 | 1323982.4 | 5000 | 1322819.67 | -1162.73 | 84 | 80 | 0 | -4
YOAKUM | 0088-06-004 | VICTORIA | BU 59-T | 2020-12-21 | 316189.28 | 14999.68 | 355688.89 | 39499.61 | 50 | 51 | 2 | 3
YOAKUM | 0143-10-050 | VICTORIA | US 87 | 2020-12-21 | 10878661.26 | 355464.32 | 11452380.69 | 573719.43 | 240 | 275 | 35 | 70
AUSTIN | 2686-01-014 | BASTROP | FM 2571 | 2020-12-22 | 7264833.65 | -322388.67 | 6590802.75 | -674030.9 | 178 | 135 | 0 | -43
FORT WORTH | 0902-48-722 | TARRANT | CS | 2020-12-22 | 9048794.52 | 155686.6 | 9445003.37 | 257845.58 | 363 | 476 | 29 | 142
SAN ANTONIO | 0024-08-136 | BEXAR | US 90 | 2020-12-22 | 1276938 | 0 | 1254081.01 | -22856.99 | 120 | 117 | 0 | -3
WACO | 0093-04-046 | LIMESTONE | SH 14 | 2020-12-22 | 3408710.76 | -35009 | 3490641.94 | 81931.18 | 75 | 78 | 0 | 3
BROWNWOOD | 0054-02-035 | COLEMAN | US 84 | 2020-12-23 | 444117.25 | 0 | 440918.47 | -3198.78 | 88 | 52 | 0 | -36
SAN ANTONIO | 0017-10-273 | BEXAR | IH 35 | 2020-12-23 | 4992612.14 | 1232007.08 | 6414927.82 | 1422315.68 | 289 | 625 | 174 | 510
SAN ANTONIO | 0024-08-128 | BEXAR | US 90 | 2020-12-23 | 2331043.07 | 89795.8 | 2414840.39 | 83797.32 | 210 | 351 | 0 | 141
SAN ANTONIO | 0143-01-055 | BEXAR | US 87 | 2020-12-23 | 3451000 | 34555.21 | 3470910.9 | 25810.9 | 203 | 280 | 77 | 154
SAN ANTONIO | 0915-00-207 | BEXAR | VA | 2020-12-23 | 533807.5 | 38288.05 | 566875.35 | 33067.85 | 248 | 93 | 0 | -155
TYLER | 0246-01-034 | RUSK | US 79 | 2020-12-23 | 5843498.19 | -269023.55 | 6043505.7 | 200007.51 | 90 | 99 | 5 | 14
WACO | 0833-03-036 | MCLENNAN | FM 1637 | 2020-12-23 | 11487769.98 | 866818.75 | 12303629.67 | 815859.69 | 425 | 480 | 58 | 113
ATLANTA | 0495-08-129 | HARRISON | IH 20 | 2020-12-29 | 241346 | 0 | 241306 | -40 | 20 | 11 | 0 | -9
FORT WORTH | 1068-01-219 | TARRANT | IH 30 | 2020-12-30 | 435495.9 | 0 | 403165.26 | -32330.64 | 60 | 68 | 8 | 16
TYLER | 0910-00-106 | SMITH | VA | 2020-12-30 | 2074842.43 | -46852.32 | 2027586.24 | -47256.19 | 125 | 125 | 0 | 0
LUFKIN | 0336-03-071 | ANGELINA | SH 103 | 2020-12-31 | 1665262.77 | 252413.47 | 2044733.5 | 379470.73 | 73 | 120 | 71 | 118
LUFKIN | 0911-04-055 | POLK | VA | 2020-12-31 | 1899423.5 | 113952.13 | 2013388.25 | 113964.75 | 96 | 165 | 87 | 156
WICHITA FALLS | 1615-02-016 | CLAY | FM 1740 | 2020-12-31 | 2211991.09 | 10670.2 | 2018284.4 | -193706.69 | 97 | 142 | 45 | 90
WACO | 0184-01-063 | CORYELL | SH 36 | 2021-01-04 | 11187471.34 | 1501817.75 | 12960887.31 | 1773415.97 | 360 | 402 | 42 | 84
BROWNWOOD | 0079-01-043 | BROWN | US 67 | 2021-01-05 | 735534.25 | 0 | 693216.2 | -42318.05 | 142 | 55 | 0 | -87
DALLAS | 0047-09-033 | COLLIN | SH 5 | 2021-01-05 | 1873091.1 | 1015025.59 | 2675196.89 | 11307.49 | 126 | 188 | 62 | 124
DALLAS | 0816-04-096 | COLLIN | FM 455 | 2021-01-05 | 2436804.35 | 139272.79 | 2321974.9 | -114829.45 | 168 | 271 | 56 | 159
DALLAS | 1392-01-041 | COLLIN | FM 1378 | 2021-01-05 | 6073071.06 | 400015.32 | 6547440.83 | 474369.77 | 277 | 286 | 14 | 23
ATLANTA | 1575-05-022 | HARRISON | SL 390 | 2021-01-07 | 5541441.56 | 41850.06 | 5557561.42 | 16119.86 | 65 | 55 | 0 | -10
HOUSTON | 0028-01-098 | HARRIS | BU 90-U | 2021-01-07 | 2098041 | 375710.28 | 2518272.98 | 420231.98 | 293 | 123 | 0 | -170
TYLER | 0203-08-016 | SMITH | FM 1253 | 2021-01-07 | 706776.9 | -17814.8 | 693383.1 | -13393.8 | 84 | 124 | 0 | 40
WACO | 3409-01-006 | BELL | FM 3481 | 2021-01-07 | 3063791.61 | 7253.46 | 2893668.46 | -170123.15 | 105 | 105 | 0 | 0
CORPUS CHRISTI | 0074-06-022 | NUECES | IH 37 | 2021-01-08 | 3395904.93 | 157074.16 | 3461687.34 | 65782.41 | 31 | 37 | 6 | 12
CORPUS CHRISTI | 0372-01-102 | SAN PATRICIO | US 77 | 2021-01-08 | 5675786.99 | 632404.55 | 6684868.35 | 1009081.36 | 204 | 259 | 55 | 110
LUBBOCK | 0053-03-021 | LYNN | US 84 | 2021-01-08 | 9099682.57 | 157730.4 | 9314806.39 | 215123.82 | 83 | 96 | 0 | 13
LUBBOCK | 0067-04-054 | HALE | IH 27 | 2021-01-08 | 5509388.49 | 83213.44 | 5489147.95 | -20240.54 | 66 | 58 | 0 | -8
PHARR | 0039-08-100 | CAMERON | IH 69E | 2021-01-08 | 10510081.9 | 95766.19 | 10559022.35 | 48940.45 | 400 | 509 | 102 | 211
WICHITA FALLS | 0845-03-064 | COOKE | FM 922 | 2021-01-08 | 4439662.49 | 184425.75 | 4858090.53 | 418428.04 | 137 | 164 | 31 | 58
BRYAN | 0315-12-016 | WASHINGTON | FM 1155 | 2021-01-11 | 1296208.43 | 0 | 1307015.31 | 10806.88 | 84 | 84 | 0 | 0
CORPUS CHRISTI | 0102-10-030 | KLEBERG | FM 1898 | 2021-01-11 | 2030652.33 | 55059.35 | 2175286.43 | 144634.1 | 68 | 171 | 90 | 193
FORT WORTH | 0134-07-070 | WISE | US 380 | 2021-01-11 | 3268105.61 | 22441.77 | 3405783.88 | 137678.27 | 235 | 347 | 112 | 224
ODESSA | 0906-00-190 | ECTOR | VA | 2021-01-11 | 1449295 | 0 | 1380858.3 | -68436.7 | 124 | 32 | 0 | -92
SAN ANGELO | 0907-15-006 | CONCHO | CS | 2021-01-11 | 676560 | -101275.57 | 587757.46 | -88802.54 | 72 | 59 | 0 | -13
TYLER | 0401-03-026 | WOOD | SH 154 | 2021-01-11 | 491543.1 | -215588.84 | 264730.26 | -226812.84 | 56 | 120 | 0 | 64
TYLER | 0520-08-068 | ANDERSON | SH 155 | 2021-01-11 | 1534652.75 | -12867.85 | 1589760.02 | 55107.27 | 35 | 41 | 0 | 6
PARIS | 0047-18-075 | GRAYSON | US 75 | 2021-01-12 | 3798996.98 | 661511.17 | 4466293.92 | 667296.94 | 149 | 234 | 91 | 176
YOAKUM | 2350-01-054 | VICTORIA | SL 463 | 2021-01-12 | 4467052.11 | 8822.75 | 4396932.6 | -70119.51 | 165 | 128 | 0 | -37
AMARILLO | 0169-08-024 | ROBERTS | US 60 | 2021-01-13 | 13340741.71 | 1540979.57 | 14644896.2 | 1304154.49 | 150 | 171 | 80 | 101
HOUSTON | 0502-01-213 | HARRIS | SH 225 | 2021-01-13 | 1494920.9 | 394990.95 | 1899335.76 | 404414.86 | 33 | 43 | 9 | 19
LUBBOCK | 0053-05-052 | GARZA | US 84 | 2021-01-13 | 2699603.95 | 1045376.15 | 3877135.74 | 1177531.79 | 40 | 58 | 9 | 27
LUBBOCK | 0130-01-021 | COCHRAN | SH 114 | 2021-01-13 | 9575726.13 | -431111.15 | 8911263.39 | -664462.74 | 59 | 63 | 0 | 4
PARIS | 0083-02-056 | HOPKINS | SH 11 | 2021-01-13 | 2292301.05 | -119743.86 | 2304168.25 | 11867.2 | 100 | 41 | 0 | -59
BEAUMONT | 0367-01-070 | CHAMBERS | SH 124 | 2021-01-14 | 2844750.22 | -118014.4 | 2919245.1 | 74494.88 | 52 | 41 | 0 | -11
BRYAN | 0057-03-043 | FREESTONE | US 84 | 2021-01-14 | 340990 | -21600 | 378828.42 | 37838.42 | 30 | 29 | 15 | 14
SAN ANTONIO | 0613-02-063 | ATASCOSA | SH 16 | 2021-01-14 | 5704330.28 | -105688.15 | 5477811.16 | -226519.12 | 252 | 243 | 0 | -9
TYLER | 0058-01-019 | ANDERSON | SH 294 | 2021-01-15 | 14050796.69 | -80655.23 | 13758569.38 | -292227.31 | 108 | 109 | 0 | 1
PHARR | 0039-16-066 | CAMERON | IH 69E | 2021-01-19 | 3781271.7 | 0 | 3748823.71 | -32447.99 | 80 | 131 | 0 | 51
WACO | 0014-07-102 | HILL | IH 35 | 2021-01-19 | 3699699 | 218.82 | 3877799.48 | 178100.48 | 60 | 70 | 10 | 20
BEAUMONT | 0784-04-023 | ORANGE | FM 1131 | 2021-01-20 | 897634 | 31772.2 | 962356.11 | 64722.11 | 180 | 142 | 0 | -38
DALLAS | 1091-04-022 | ROCKWALL | FM 549 | 2021-01-20 | 11599739.42 | 488645.31 | 11612635.45 | 12896.03 | 508 | 508 | 0 | 0
SAN ANGELO | 0036-01-015 | KIMBLE | US 83 | 2021-01-20 | 12235954.11 | 36524.34 | 11886297.67 | -349656.44 | 88 | 85 | 0 | -3
WACO | 0398-01-042 | BOSQUE | FM 56 | 2021-01-20 | 1514248.15 | 129514.83 | 1692624.42 | 178376.27 | 90 | 105 | 10 | 25
ATLANTA | 0063-04-060 | PANOLA | US 59 | 2021-01-21 | 4379892.09 | -6815.94 | 4547358.83 | 167466.74 | 109 | 122 | 9 | 22
LAREDO | 0018-04-060 | WEBB | IH 35 | 2021-01-21 | 521314.85 | 145642.59 | 669149.94 | 147835.09 | 180 | 190 | 0 | 10
LAREDO | 0161-01-030 | VAL VERDE | UP 277 | 2021-01-21 | 846877.74 | 28488.42 | 872073.45 | 25195.71 | 125 | 106 | 0 | -19
LUBBOCK | 0145-05-032 | HALE | US 70 | 2021-01-21 | 18510115.03 | 0 | 15265263.02 | -3244852.01 | 180 | 166 | 5 | -9
CORPUS CHRISTI | 0691-01-035 | KARNES | FM 81 | 2021-01-22 | 4236890.73 | 345643.47 | 4493061.11 | 256170.38 | 302 | 425 | 155 | 278
YOAKUM | 1262-01-014 | FAYETTE | FM 1115 | 2021-01-22 | 3558330.17 | -165645.12 | 3373094.27 | -185235.9 | 150 | 150 | 0 | 0
BEAUMONT | 0200-14-086 | JEFFERSON | US 69 | 2021-01-25 | 2395589.66 | 125719.59 | 2566718.25 | 171128.59 | 120 | 189 | 64 | 133
CHILDRESS | 0704-05-022 | MOTLEY | FM 94 | 2021-01-25 | 7493681.15 | 0 | 7447033.98 | -46647.17 | 242 | 279 | 0 | 37
LAREDO | 0037-05-053 | DIMMIT | US 83 | 2021-01-25 | 492119.55 | -60758.7 | 444860.85 | -47258.7 | 60 | 60 | 0 | 0
ODESSA | 0004-01-034 | WARD | BI 20-B | 2021-01-25 | 6651323.86 | 1272384.37 | 7776038.05 | 1124714.19 | 40 | 34 | 0 | -6
ODESSA | 0441-09-045 | REEVES | IH 10 | 2021-01-25 | 415240 | 332060.02 | 787205.77 | 371965.77 | 35 | 70 | 35 | 70
PARIS | 0009-06-051 | HUNT | SH 66 | 2021-01-25 | 2841097.84 | 23299.67 | 2876669.56 | 35571.72 | 95 | 114 | 6 | 25
SAN ANGELO | 0140-11-046 | CROCKETT | IH 10 | 2021-01-25 | 2925471.03 | 1765.05 | 2948860.15 | 23389.12 | 120 | 67 | 0 | -53
SAN ANGELO | 0141-09-070 | KIMBLE | IH 10 | 2021-01-25 | 8342120.02 | 511814.95 | 8459965.88 | 117845.86 | 145 | 157 | 0 | 12
WICHITA FALLS | 0043-06-095 | WILBARGER | US 70 | 2021-01-25 | 7510177.21 | 162741.27 | 7634453.81 | 124276.6 | 49 | 45 | 2 | -2
WICHITA FALLS | 1350-01-024 | CLAY | FM 1197 | 2021-01-25 | 1945126.66 | 0 | 2020033.94 | 74907.28 | 51 | 41 | 0 | -10
LAREDO | 0018-05-095 | WEBB | IH 35 | 2021-01-26 | 12256476.31 | -95642.45 | 12522607.26 | 266130.95 | 360 | 360 | 0 | 0
LAREDO | 0086-01-091 | WEBB | SH 359 | 2021-01-26 | 28248453.66 | 599662.78 | 28954461.03 | 706007.37 | 371 | 383 | 15 | 27
LAREDO | 0086-14-094 | WEBB | US 59 | 2021-01-26 | 688547.9 | 12319.19 | 740624.94 | 52077.04 | 25 | 25 | 0 | 0
WACO | 1192-01-024 | MCLENNAN | FM 939 | 2021-01-26 | 6431694.2 | 82484.87 | 6648382.97 | 216688.77 | 240 | 252 | 1 | 13
AMARILLO | 0275-01-204 | POTTER | IH 40 | 2021-01-27 | 4995101 | 7579.26 | 4996841.81 | 1740.81 | 168 | 159 | 0 | -9
ATLANTA | 0495-08-117 | HARRISON | IH 20 | 2021-01-27 | 329387 | 57272.45 | 378151.66 | 48764.66 | 78 | 51 | 0 | -27
BROWNWOOD | 0256-02-031 | STEPHENS | SH 67 | 2021-01-28 | 5063902.24 | 458 | 5232854.17 | 168951.93 | 170 | 176 | 8 | 14
LUFKIN | 0064-05-061 | SABINE | FM 1 | 2021-01-28 | 1954394 | 2300 | 1890959.46 | -63434.54 | 77 | 89 | 13 | 25
LUFKIN | 0109-03-037 | HOUSTON | US 287 | 2021-01-28 | 1390005 | 0 | 1405357.04 | 15352.04 | 139 | 138 | 0 | -1
LUFKIN | 2590-01-020 | NACOGDOCHES | FM 2609 | 2021-01-28 | 2896894.25 | 271354.3 | 3384448.21 | 487553.96 | 151 | 228 | 92 | 169
SAN ANGELO | 0558-09-037 | REAGAN | SH 137 | 2021-01-28 | 5304214.07 | 0 | 5396289.07 | 92075 | 48 | 40 | 0 | -8
WACO | 0183-04-053 | CORYELL | SH 36 | 2021-01-28 | 2987724.2 | -80519.18 | 2785812.56 | -201911.64 | 90 | 63 | 0 | -27
LUBBOCK | 0052-04-051 | LAMB | US 84 | 2021-01-29 | 117160 | 0 | 113410 | -3750 | 45 | 33 | 0 | -12
LUBBOCK | 0053-01-126 | LUBBOCK | US 84 | 2021-01-29 | 1940614 | 42000 | 2059221.59 | 118607.59 | 124 | 70 | 0 | -54
LUBBOCK | 0783-01-097 | LUBBOCK | SL 289 | 2021-01-29 | 1592493.91 | 0 | 1643303.71 | 50809.8 | 25 | 24 | 0 | -1
WICHITA FALLS | 0514-01-041 | WICHITA | SH 240 | 2021-01-29 | 877613.8 | 1736 | 1206836.61 | 329222.81 | 153 | 170 | 0 | 17
HOUSTON | 0271-15-090 | HARRIS | IH 610 | 2021-02-01 | 1159846.86 | 180837.27 | 1407317.63 | 70124.11 | 120 | 120 | 12 | 12
SAN ANGELO | 0907-00-191 | TOM GREEN | VA | 2021-02-01 | 695350.62 | 423594.62 | 1045503.61 | 350152.99 | 135 | 140 | 5 | 10
CORPUS CHRISTI | 0074-06-219 | NUECES | IH 37 | 2021-02-02 | 10228897.3 | 65560.51 | 10717159.27 | 488261.97 | 143 | 172 | 33 | 62
ODESSA | 0139-05-048 | REEVES | US 285 | 2021-02-02 | 6540324.66 | 20381.15 | 6797219.05 | 256894.39 | 134 | 124 | 0 | -10
ODESSA | 0479-01-019 | REEVES | SH 302 | 2021-02-02 | 12502318.48 | 4846832.74 | 18412852.95 | 5910534.47 | 272 | 512 | 257 | 497
EL PASO | 0167-02-051 | EL PASO | BU 54-A | 2021-02-03 | 1723480 | -397215.23 | 1425809.32 | -297670.68 | 52 | 118 | 8 | 74
EL PASO | 2121-03-160 | EL PASO | IH 10 | 2021-02-03 | 9358402.62 | 603442.45 | 10184286.96 | 825884.34 | 226 | 415 | 196 | 385
PARIS | 0045-12-084 | RED RIVER | US 82 | 2021-02-03 | 348774.4 | -6836.67 | 314593.73 | -34180.67 | 100 | 98 | 0 | -2
SAN ANTONIO | 0915-17-067 | COMAL | CS | 2021-02-03 | 1589567.35 | 31417.64 | 1585658.15 | -3909.2 | 213 | 192 | 6 | -15
BRYAN | 0212-03-066 | BRAZOS | SH 30 | 2021-02-04 | 290937.45 | -33406.34 | 248267.5 | -42669.95 | 36 | 27 | 0 | -9
PARIS | 0045-18-038 | GRAYSON | US 82 | 2021-02-05 | 7390532.53 | 15822.9 | 7753488.01 | 362955.48 | 93 | 104 | 0 | 11
PARIS | 0901-00-054 | LAMAR | VA | 2021-02-05 | 2370334 | 0 | 2287984.7 | -82349.3 | 325 | 344 | 0 | 19
PARIS | 0901-27-045 | RED RIVER | CR | 2021-02-05 | 651496.65 | -1724.68 | 665758.47 | 14261.82 | 122 | 94 | 0 | -28
TYLER | 0164-01-073 | HENDERSON | BS 31-H | 2021-02-05 | 168079.2 | -4042.5 | 163045.55 | -5033.65 | 27 | 26 | 0 | -1
TYLER | 1672-01-004 | VAN ZANDT | FM 1652 | 2021-02-05 | 4481848.93 | -19678.32 | 4291118.8 | -190730.13 | 346 | 360 | 0 | 14
TYLER | 2653-01-014 | RUSK | FM 2658 | 2021-02-05 | 1667776.7 | -596.46 | 1570917.53 | -96859.17 | 79 | 96 | 0 | 17
ABILENE | 0296-05-034 | JONES | US 180 | 2021-02-08 | 7597359.93 | 25998.96 | 8327103.46 | 729743.53 | 332 | 323 | 0 | -9
AUSTIN | 0440-02-019 | WILLIAMSON | SH 195 | 2021-02-08 | 776375.3 | 0 | 800999.83 | 24624.53 | 46 | 46 | 0 | 0
BEAUMONT | 1024-01-078 | CHAMBERS | FM 565 | 2021-02-08 | 206938.9 | 15776.25 | 140001.25 | -66937.65 | 26 | 15 | 0 | -11
BRYAN | 0057-03-041 | FREESTONE | US 84 | 2021-02-08 | 1651842 | -114339.94 | 1588503.39 | -63338.61 | 62 | 112 | 6 | 56
YOAKUM | 2819-01-009 | WHARTON | FM 2765 | 2021-02-08 | 2898132.12 | -1594.19 | 2844850.64 | -53281.48 | 105 | 90 | 0 | -15
AUSTIN | 0265-06-033 | BASTROP | SH 71 | 2021-02-09 | 2787166.88 | 40960.08 | 2892139.01 | 104972.13 | 100 | 66 | 0 | -34
DALLAS | 0197-02-121 | DALLAS | US 175 | 2021-02-09 | 11432222.08 | 1648449.98 | 13729454.91 | 2297232.83 | 225 | 315 | 90 | 180
DALLAS | 1047-03-070 | DALLAS | FM 1382 | 2021-02-09 | 6048901.1 | 775259.83 | 7030523.24 | 584775.35 | 365 | 425 | 60 | 120
YOAKUM | 0144-05-043 | CALHOUN | SH 238 | 2021-02-09 | 146702.25 | 8580 | 157712.25 | 11010 | 60 | 60 | 0 | 0
SAN ANGELO | 0264-04-052 | COKE | US 277 | 2021-02-10 | 7015129.14 | 2681082.08 | 9578470.71 | 2563341.57 | 199 | 329 | 130 | 260
SAN ANTONIO | 0915-12-602 | BEXAR | VA | 2021-02-10 | 5866947 | 431974.94 | 6300921.94 | 433974.94 | 190 | 205 | 40 | 55
DALLAS | 0918-11-090 | KAUFMAN | CR | 2021-02-11 | 1387159 | -20250 | 1387703.11 | 544.11 | 225 | 225 | 0 | 0
SAN ANTONIO | 2452-01-064 | BEXAR | SL 1604 | 2021-02-11 | 8000083.18 | 5364111.84 | 13375990 | 5375906.82 | 314 | 561 | 262 | 509
YOAKUM | 0913-09-083 | WHARTON | CR | 2021-02-11 | 1499626.26 | 4767.22 | 1487450.12 | -12176.14 | 225 | 199 | 0 | -26
ATLANTA | 0495-08-110 | HARRISON | IH 20 | 2021-02-12 | 2087956 | 79517.01 | 2352345.56 | 264389.56 | 345 | 370 | 0 | 25
AUSTIN | 0113-13-177 | TRAVIS | US 290 | 2021-02-12 | 1998095.87 | -342560.96 | 1435110.23 | -562985.64 | 34 | 32 | 0 | -2
AUSTIN | 0152-01-083 | TRAVIS | US 183 | 2021-02-12 | 2568399.55 | 30491.5 | 2644349.39 | 75949.84 | 48 | 46 | 0 | -2
AUSTIN | 0285-03-061 | HAYS | RM 12 | 2021-02-12 | 1748410.8 | 16128 | 1918543.94 | 170133.14 | 41 | 29 | 0 | -12
BEAUMONT | 1947-02-016 | HARDIN | FM 1293 | 2021-02-12 | 5560806.23 | 191281.46 | 5932254.04 | 371447.81 | 192 | 162 | 10 | -20
BROWNWOOD | 0011-09-073 | STEPHENS | US 180 | 2021-02-12 | 1289678.23 | 106391.16 | 1375600.94 | 85922.71 | 64 | 50 | 0 | -14
YOAKUM | 0687-01-013 | GONZALES | FM 77 | 2021-02-12 | 1508659.83 | 2931.24 | 1517769.45 | 9109.62 | 150 | 130 | 0 | -20
YOAKUM | 0715-01-014 | GONZALES | FM 108 | 2021-02-12 | 1963663.06 | 2152.62 | 1937495.12 | -26167.94 | 176 | 170 | 0 | -6
YOAKUM | 0913-29-037 | LAVACA | CR | 2021-02-12 | 1395463.52 | 0 | 1371920.21 | -23543.31 | 235 | 165 | 0 | -70
AUSTIN | 0016-03-119 | HAYS | IH 35 | 2021-02-16 | 11983120.35 | 127243.53 | 12003279.08 | 20158.73 | 112 | 127 | 29 | 44
BROWNWOOD | 0251-04-026 | LAMPASAS | US 281 | 2021-02-17 | 788694.9 | 0 | 619821.3 | -168873.6 | 219 | 80 | 0 | -139
SAN ANGELO | 0907-11-006 | STERLING | CR | 2021-02-18 | 1323346.4 | -6000 | 1310067.4 | -13279 | 132 | 113 | 0 | -19
AUSTIN | 0914-05-206 | WILLIAMSON | VA | 2021-02-19 | 1694954.22 | -353757.58 | 1398433.28 | -296520.94 | 88 | 88 | 0 | 0
AUSTIN | 3115-01-011 | BASTROP | FM 3000 | 2021-02-19 | 628355.12 | -32660.75 | 563818.74 | -64536.38 | 103 | 141 | 0 | 38
ABILENE | 0034-01-137 | TAYLOR | US 83 | 2021-02-22 | 4451081.56 | 147508.51 | 4354293.71 | -96787.85 | 64 | 100 | 22 | 58
ATLANTA | 0208-02-045 | HARRISON | SH 43 | 2021-02-22 | 4592940.44 | 6977.51 | 4680151.84 | 87211.4 | 193 | 160 | 0 | -33
AUSTIN | 0914-00-437 | TRAVIS | VA | 2021-02-22 | 117922 | 0 | 117382 | -540 | 66 | 33 | 0 | -33
HOUSTON | 0111-09-043 | BRAZORIA | BS 288B | 2021-02-22 | 240724.7 | 0 | 244850.07 | 4125.37 | 45 | 22 | 0 | -23
AUSTIN | 0577-04-022 | LLANO | SH 71 | 2021-02-23 | 1369479.67 | 1449722.19 | 2692401.46 | 1322921.79 | 56 | 44 | 19 | 7
BRYAN | 0540-04-083 | BRAZOS | FM 2154 | 2021-02-23 | 1595061.65 | 250563.89 | 1918980.22 | 323918.57 | 57 | 61 | 5 | 9
DALLAS | 0092-14-092 | DALLAS | IH 345 | 2021-02-23 | 3979913.91 | 141816.87 | 4061372.69 | 81458.78 | 125 | 124 | 0 | -1
CORPUS CHRISTI | 1086-01-019 | JIM WELLS | FM 2044 | 2021-02-24 | 750501.86 | 0 | 748200.67 | -2301.19 | 86 | 114 | 15 | 43
CORPUS CHRISTI | 1087-01-014 | JIM WELLS | FM 738 | 2021-02-24 | 1150495.07 | 2087.56 | 1121752.49 | -28742.58 | 68 | 103 | 0 | 35
FORT WORTH | 0550-02-049 | ERATH | FM 8 | 2021-02-24 | 3111771.94 | 1364758.34 | 4513896.82 | 1402124.88 | 96 | 66 | 0 | -30
BROWNWOOD | 0128-03-037 | MCCULLOCH | US 377 | 2021-02-25 | 657372.75 | 6363.7 | 652569.03 | -4803.72 | 119 | 48 | 0 | -71
HOUSTON | 0271-14-237 | HARRIS | IH 610 | 2021-02-25 | 578700 | 10607.29 | 712489.19 | 133789.19 | 39 | 39 | 0 | 0
ODESSA | 0380-07-026 | MARTIN | SH 349 | 2021-02-25 | 15052677.33 | 1984282.04 | 16974606.39 | 1921929.06 | 109 | 188 | 85 | 164
ODESSA | 0906-32-054 | MIDLAND | CS | 2021-02-25 | 1801684 | 67381.54 | 1846057.55 | 44373.55 | 149 | 102 | 0 | -47
SAN ANTONIO | 0848-04-046 | MEDINA | FM 462 | 2021-02-25 | 1968967.68 | -46770.63 | 2106990.05 | 138022.37 | 257 | 193 | 0 | -64
YOAKUM | 2697-01-034 | MATAGORDA | FM 2668 | 2021-02-25 | 3844068.36 | -53958.99 | 3992191.09 | 148122.73 | 165 | 177 | 12 | 24
AMARILLO | 0090-05-098 | POTTER | IH 40 | 2021-02-26 | 7778312.16 | 389528.89 | 8944262.66 | 1165950.5 | 85 | 90 | 10 | 15
HOUSTON | 0500-01-145 | GALVESTON | IH 45 | 2021-02-26 | 1551543.5 | -35443.41 | 1521675.59 | -29867.91 | 45 | 43 | 0 | -2
LUFKIN | 0176-05-196 | POLK | US 59 | 2021-02-26 | 3764702.32 | 0 | 3650057.05 | -114645.27 | 104 | 82 | 0 | -22
TYLER | 0203-08-017 | SMITH | FM 1253 | 2021-02-26 | 99072 | -1436 | 98786 | -286 | 40 | 28 | 0 | -12

## LINE_GRAPH_DATA (hidden)
COUNTIFS(FINL,">="&B4-DAY(B4)+1,FINL,"<="&EOMONTH(B4,0))
FY 2021 Monthly Measures | [9 empty] | YTD
Month | Total Contracts | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO
SEP-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
OCT-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NOV-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DEC-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JAN-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FEB-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAR-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
APR-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MAY-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JUN-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
JUL-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AUG-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FY21 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
|  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!

## Summary Previous FYs (hidden)
CONSTRUCTION SUMMARY PERFORMANCE REPORT | [12 empty] | 5- YEAR AVERAGES
FY | Projects Accepted | Percent On Budget | Percent On Time | Percent On Time Previous | Projects Awarded | Awarded Amounts Billions | Estimated Amounts Billions | Amounts Over / (Under) the Estimate | Percent Over the Estimate | Dollars per Project | Awarded Amounts | Estimated Amounts | Awarded Amounts | Estimated Amounts | Percent Over the Estimate | Projects Accepted | Projects Awarded
2009 | 802 | 83.92% | 57.11% | 72.57% | 699 | 3.0857 | 3.6429 | -0.5572 | -15.3% | 4414461.6445 | 3085708689.49 | 3642907501.26
2010 | 797 | 84.69% | 65.5% | 77.42% | 1063 | 3.2459 | 3.6441 | -0.39818 | -10.93% | 3053502.9899 | 3245873678.22 | 3644056349
2011 | 872 | 88.99% | 68.17% | 77.18% | 870 | 3.497 | 3.7036 | -0.20654 | -5.577% | 4019586.1947 | 3497039989.43 | 3703575068.62
2012 | 772 | 87.95% | 67.62% | 76.55% | 685 | 2.9722 | 3.0097 | -0.037491 | -1.246% | 4338962.4606 | 2972189285.54 | 3009680367 | 3.2002 | 3.5001 | -8.567% | 810.75 | 829.25
2013 | 682 | 86.07% | 63.49% | N/A | 797 | 4.2752 | 4.2598 | 0.015356 | 0.3605% | 5364094.8547 | 4275183599.18 | 4259827109.53 | 3.4152 | 3.652 | -6.484% | 785 | 822.8
2014 | 636 | 86.48% | 68.08% | N/A | 757 | 3.8596 | 3.9509 | -0.091307 | -2.311% | 5098575.683 | 3859621792 | 3950928942.48 | 3.57 | 3.7136 | -3.868% | 751.8 | 834.4
2015 | 607 | 86.16% | 63.92% | N/A | 856 | 4.3749 | 4.3622 | 0.012684 | 0.2908% | 5110843.7065 | 4374882212.76 | 4362198207.53 | 3.7958 | 3.8572 | -1.593% | 713.8 | 793
2016 | 711 | 83.4% | 63.29% | N/A | 737 | 4.3375 | 4.4843 | -0.14682 | -3.274% | 5885376.9172 | 4337522787.99 | 4484341769.73 | 3.9639 | 4.0134 | -1.234% | 681.6 | 766.4
2017 | 864 | 80.9% | 62.73% | N/A | 779 | 4.7365 | 5.0552 | -0.31875 | -6.305% | 6080199.4759 | 4736475391.74 | 5055222420.56 | 4.3167 | 4.4225 | -2.392% | 700 | 785.2
2018 | 859 | 83.82% | 64.96% | N/A | 825 | 5.7327 | 5.8693 | -0.13661 | -2.328% | 6948682.4486 | 5732663020.12 | 5869277068.62 | 4.6082 | 4.7444 | -2.87% | 735.4 | 790.8
2019 | 718 | 94.57% | 85.79% | N/A | 895 | 6.5145 | 6.3033 | 0.21118 | 3.35% | 7278753.2179 | 6514484130 | 6303301439 | 4.9259 | 5.0042 | -1.564% | 732.5 | 808.1667
2020 | #REF! | #REF! | #REF! |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 5.1392 | 5.2149 | -1.451% | #REF! | 818.4