## Sheet1
Required Reporting per Texas Transportation Code §201.812 –
Highway Construction Projects Completed September 1, 2025–February 28, 2026
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | CO BY THRD PRTY | AMOUNT PAID | UNDER OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | THIRD PARTY DAYS ADDED | UNDER OVER SCHEDULE
AUSTIN | 0113-02-063 | GILLESPIE | US 290 | 2026-02-27 | 12041546.04 | 2335341.86 | 0 | 15427720.75 | 3386174.71 | 219 | 365 | 75 | 0 | 146
AUSTIN | 0113-05-051 | BLANCO | US 281 | 2026-02-27 | 610125 | 0 | 0 | 571777.85 | -38347.15 | 71 | 12 | 0 | 0 | -59
BROWNWOOD | 0054-03-027 | COLEMAN | US 84 | 2026-02-27 | 14784351.67 | 296179.46 | 0 | 16075956.87 | 1291605.2 | 89 | 206 | 26 | 0 | 117
BROWNWOOD | 0054-07-090 | BROWN | US 67 | 2026-02-27 | 8999249.67 | -259482.89 | 0 | 8917009.06 | -82240.61 | 101 | 123 | 22 | 0 | 22
EL PASO | 2121-06-057 | HUDSPETH | IH 10 | 2026-02-27 | 752716.5 | 53750.9 | 0 | 820118.2 | 67401.7 | 80 | 46 | 2 | 0 | -34
FORT WORTH | 1181-02-038 | HUDSPETH | FM 917 | 2026-02-27 | 6838229.11 | 867632.43 | 0 | 7763169.75 | 924940.64 | 256 | 478 | 163 | 0 | 222
LUBBOCK | 0053-01-135 | LUBBOCK | US 84 | 2026-02-27 | 20682233.92 | 187029.02 | 0 | 20001220.83 | -681013.09 | 57 | 65 | 0 | 0 | 8
LUBBOCK | 0905-06-128 | LUBBOCK | Various | 2026-02-27 | 2186698.96 | 406956.18 | 0 | 2690880.91 | 504181.95 | 135 | 110 | 0 | 0 | -25
PARIS | 0901-19-226 | GRAYSON | Various | 2026-02-27 | 363240 | -20895 | 0 | 354447.03 | -8792.97 | 103 | 54 | 0 | 0 | -49
AUSTIN | 3136-01-190 | TRAVIS | SL 1 | 2026-02-26 | 3314600.08 | -179015.88 | 0 | 3453229.63 | 138629.55 | 70 | 56 | 0 | 0 | -14
FORT WORTH | 0008-13-221 | TARRANT | IH 820 | 2026-02-26 | 173724094.74 | 45626663.88 | 233635.32 | 221657987.95 | 47700257.89 | 1126 | 1974 | 641 | 0 | 848
HOUSTON | 0508-01-399 | HARRIS | IH 10 | 2026-02-26 | 3413666.65 | -112977.05 | 0 | 3889025.23 | 475358.58 | 51 | 50 | 0 | 0 | -1
TYLER | 0203-05-047 | WOOD | US 69 | 2026-02-26 | 6350678.39 | 286395.52 | 0 | 7269162.22 | 918483.83 | 133 | 146 | 10 | 0 | 13
WICHITA FALLS | 0013-05-066 | MONTAGUE | US 81 | 2026-02-26 | 11361820.16 | 1837 | 0 | 11275253.85 | -86566.31 | 68 | 62 | 0 | 0 | -6
AMARILLO | 0455-02-031 | CARSON | SH 152 | 2026-02-25 | 16474504.34 | 2138468.61 | 0 | 19878291.68 | 3403787.34 | 202 | 203 | 0 | 0 | 1
BROWNWOOD | 0288-01-040 | COMANCHE | SH 16 | 2026-02-25 | 2724265 | 850861.25 | 0 | 5709720.5 | 2985455.5 | 234 | 469 | 240 | 0 | 235
DALLAS | 0918-24-278 | COLLIN | CS | 2026-02-25 | 1774285.03 | 0 | 0 | 1805136.65 | 30851.62 | 80 | 136 | 0 | 0 | 56
PARIS | 0901-19-176 | GRAYSON | Various | 2026-02-25 | 4478108.3 | -124104.72 | 0 | 4316714.15 | -161394.15 | 176 | 195 | 14 | 0 | 19
AUSTIN | 0273-04-050 | WILLIAMSON | US 183 | 2026-02-24 | 567567 | 36215.51 | 0 | 753150.38 | 185583.38 | 99 | 45 | 10 | 0 | -54
AUSTIN | 0914-00-528 | TRAVIS | Various | 2026-02-23 | 581040 | 0 | 0 | 581040 | 0 | 43 | 40 | 0 | 0 | -3
PHARR | 0039-04-130 | HIDALGO | BU 83S | 2026-02-23 | 2470981.05 | 155697.04 | 0 | 2372677.63 | -98303.42 | 303 | 225 | 0 | 0 | -78
SAN ANGELO | 0650-03-036 | RUNNELS | SH 153 | 2026-02-23 | 21350244.52 | -221141.39 | 0 | 21848921.16 | 498676.64 | 460 | 350 | 0 | 0 | -110
ABILENE | 0033-01-038 | STONEWALL | US 83 | 2026-02-20 | 14492854.11 | 804076.85 | 0 | 14920879.59 | 428025.48 | 396 | 414 | 19 | 0 | 18
BRYAN | 0506-02-025 | BURLESON | FM 60 | 2026-02-20 | 534394.42 | 0 | 0 | 539225.65 | 4831.23 | 67 | 45 | 0 | 0 | -22
CORPUS CHRISTI | 1123-01-016 | KARNES | FM 81 | 2026-02-20 | 6545352.98 | 448236.17 | 0 | 7097717.72 | 552364.74 | 123 | 199 | 92 | 0 | 76
DALLAS | 0081-05-053 | DENTON | FM 428 | 2026-02-20 | 18906303.35 | 130279.56 | 0 | 18431487.02 | -474816.33 | 240 | 226 | 0 | 0 | -14
FORT WORTH | 0008-02-079 | PARKER | US 180 | 2026-02-20 | 1239439.77 | 0 | 0 | 1141716.84 | -97722.93 | 128 | 119 | 0 | 0 | -9
FORT WORTH | 0902-00-382 | PALO PINTO | FM 919 | 2026-02-20 | 4012954.18 | 1 | 0 | 3741664.49 | -271289.69 | 93 | 105 | 0 | 0 | 12
HOUSTON | 0051-03-117 | GALVESTON | SH 3 | 2026-02-20 | 4384915.81 | -296823.05 | 0 | 4146865.18 | -238050.63 | 150 | 141 | 20 | 0 | -9
HOUSTON | 1685-01-092 | HARRIS | FM 1960 | 2026-02-20 | 14685047.58 | 1077642.83 | 0 | 16084866.58 | 1399819 | 337 | 550 | 213 | 0 | 213
AUSTIN | 0029-03-055 | CALDWELL | US 90 | 2026-02-19 | 4315552.2 | -368177.75 | 0 | 4249672.74 | -65879.46 | 64 | 62 | 0 | 0 | -2
AUSTIN | 0914-00-469 | TRAVIS | Various | 2026-02-19 | 827090 | 66732.71 | 0 | 324289.85 | -502800.15 | 300 | 261 | 0 | 0 | -39
EL PASO | 0002-19-010 | HUDSPETH | BI 10C | 2026-02-18 | 14907765.22 | 91926.72 | 0 | 14873461.45 | -34303.77 | 104 | 44 | 0 | 0 | -60
HOUSTON | 1685-03-098 | HARRIS | FM 1960 | 2026-02-18 | 70042726.37 | 7399337.62 | 33217.08 | 80852381.95 | 10776438.5 | 1050 | 959 | 15 | 0 | -91
CORPUS CHRISTI | 0916-35-238 | NUECES | CS | 2026-02-17 | 243149.25 | 24331.34 | 0 | 280919.24 | 37769.99 | 87 | 34 | 0 | 0 | -53
DALLAS | 0092-14-086 | DALLAS | IH 345 | 2026-02-17 | 21883782.8 | 332744.91 | 0 | 22124598 | 240815.2 | 378 | 418 | 35 | 0 | 40
DALLAS | 2681-01-029 | DENTON | FM 2499 | 2026-02-17 | 1920304.66 | 150479.9 | 0 | 2037012.7 | 116708.04 | 95 | 93 | 0 | 0 | -2
FORT WORTH | 0902-00-167 | TARRANT | VA | 2026-02-17 | 4660000 | 53736.76 | 0 | 2625024.66 | -2034975.34 | 600 | 589 | 0 | 0 | -11
HOUSTON | 0523-02-051 | WALLER | FM 362 | 2026-02-17 | 4087471.73 | 60505.54 | 0 | 4253876.81 | 166405.08 | 76 | 76 | 0 | 0 | 0
HOUSTON | 0675-08-111 | MONTGOMERY | IH 45 | 2026-02-17 | 2147330.78 | 102417.2 | 0 | 2472085.11 | 324754.33 | 270 | 269 | 0 | 0 | -1
HOUSTON | 0912-00-577 | HARRIS | VA | 2026-02-17 | 1438222.5 | 410465.85 | 0 | 1722086.93 | 283864.43 | 201 | 173 | 0 | 0 | -28
HOUSTON | 0912-00-578 | HARRIS | VA | 2026-02-17 | 1780190 | 62717.93 | 0 | 1929908.26 | 149718.26 | 216 | 154 | 0 | 0 | -62
HOUSTON | 3223-01-010 | FORT BEND | FM 3155 | 2026-02-17 | 585949.45 | 0 | 0 | 635009.89 | 49060.44 | 17 | 14 | 0 | 0 | -3
TYLER | 0245-06-089 | SMITH | SH 64 | 2026-02-17 | 497607.5 | 12960 | 0 | 513681.5 | 16074 | 70 | 32 | 0 | 0 | -38
WICHITA FALLS | 0312-01-083 | COOKE | FM 51 | 2026-02-17 | 6010839.85 | 244433.29 | 0 | 6499035.69 | 488195.84 | 95 | 95 | 0 | 0 | 0
HOUSTON | 3538-01-045 | MONTGOMERY | SH 242 | 2026-02-13 | 23483270.27 | 5051359.83 | 637877.37 | 27279693.24 | 3158545.6 | 528 | 628 | 179 | 0 | 100
ODESSA | 1127-01-012 | ANDREWS | SH 128 | 2026-02-13 | 35996694.7 | -772406.95 | 0 | 35315869.37 | -680825.33 | 400 | 430 | 33 | 0 | 30
PARIS | 0189-05-051 | FRANKLIN | SH 37 | 2026-02-13 | 12962475.51 | -824340.9 | 0 | 12001384.47 | -961091.04 | 175 | 137 | 0 | 0 | -38
PHARR | 0039-07-257 | CAMERON | IH 69E | 2026-02-13 | 4138510.59 | 246669.69 | 0 | 4228560.31 | 90049.72 | 171 | 279 | 33 | 0 | 108
PHARR | 0517-06-036 | JIM HOGG | SH 16 | 2026-02-13 | 4952063.28 | 129986.56 | 0 | 5493886.36 | 541823.08 | 256 | 557 | 200 | 0 | 301
SAN ANTONIO | 0016-05-126 | COMAL | IH 35 | 2026-02-13 | 16993738.72 | 664231.64 | 0 | 17021144.61 | 27405.89 | 132 | 130 | 0 | 0 | -2
TYLER | 2075-01-058 | SMITH | SL 323 | 2026-02-13 | 4548986.94 | 261239.02 | 0 | 4887931.91 | 338944.97 | 144 | 89 | 0 | 0 | -55
ABILENE | 0006-03-149 | NOLAN | IH 20 | 2026-02-12 | 664504 | 70131.6 | 0 | 755504.15 | 91000.15 | 23 | 8 | 0 | 0 | -15
ABILENE | 0011-04-029 | SHACKELFORD | SH 351 | 2026-02-12 | 5659269 | 240690.23 | 0 | 6029940.24 | 370671.24 | 107 | 76 | 0 | 0 | -31
ABILENE | 0972-03-023 | JONES | FM 1082 | 2026-02-12 | 3582697 | 0 | 0 | 3678271.05 | 95574.05 | 141 | 141 | 0 | 0 | 0
ABILENE | 1031-05-018 | SHACKELFORD | FM 576 | 2026-02-12 | 2414951.87 | 72919.24 | 0 | 2499771.3 | 84819.43 | 111 | 116 | 5 | 0 | 5
ABILENE | 2033-02-012 | NOLAN | FM 1170 | 2026-02-12 | 12460121.62 | 0 | 0 | 12206522.36 | -253599.26 | 269 | 303 | 0 | 0 | 34
AUSTIN | 0015-08-147 | WILLIAMSON | IH 35 | 2026-02-12 | 54846947.65 | 3883392.79 | 0 | 61169598.51 | 6322650.86 | 558 | 964 | 361 | 0 | 406
AUSTIN | 0914-00-486 | TRAVIS | Various | 2026-02-12 | 718620.7 | 82080.78 | 0 | 711811.32 | -6809.38 | 78 | 77 | 0 | 0 | -1
AUSTIN | 1378-02-059 | WILLIAMSON | RM 1431 | 2026-02-12 | 2125758.68 | 31239.71 | 0 | 2407622.46 | 281863.78 | 42 | 22 | 0 | 0 | -20
BRYAN | 0122-03-033 | FREESTONE | US 287 | 2026-02-12 | 2078845.05 | 416144.34 | 0 | 2449208.49 | 370363.44 | 140 | 140 | 2 | 0 | 0
DALLAS | 0918-47-457 | DALLAS | Various | 2026-02-12 | 773400 | 0 | 0 | 747050.94 | -26349.06 | 45 | 28 | 0 | 0 | -17
LAREDO | 0086-08-028 | DUVAL | SH 359 | 2026-02-11 | 6321935.13 | 64866.32 | 0 | 6364813.12 | 42877.99 | 110 | 82 | 0 | 0 | -28
LAREDO | 0086-10-053 | DUVAL | SH 359 | 2026-02-11 | 4204392.38 | 397377.13 | 0 | 4615179.1 | 410786.72 | 228 | 328 | 103 | 0 | 100
BRYAN | 0049-08-078 | ROBERTSON | US 190 | 2026-02-10 | 1275456.89 | 225473.81 | 0 | 1705839.26 | 430382.37 | 118 | 111 | 5 | 0 | -7
DALLAS | 0135-02-069 | COLLIN | US 380 | 2026-02-10 | 1999999.98 | 0 | 0 | 2063573.67 | 63573.69 | 140 | 143 | 0 | 0 | 3
DALLAS | 0451-04-026 | ROCKWALL | SH 205 | 2026-02-10 | 4169539.2 | 32441.82 | 0 | 4104039.93 | -65499.27 | 86 | 103 | 0 | 0 | 17
WICHITA FALLS | 1351-01-016 | COOKE | FM 1198 | 2026-02-10 | 12107495.99 | -318198.33 | 0 | 11598812.97 | -508683.02 | 407 | 257 | -15 | 0 | -150
CORPUS CHRISTI | 3596-01-009 | NUECES | SS 3 | 2026-02-09 | 6716237.77 | 38903.2 | 0 | 7140946.68 | 424708.91 | 75 | 89 | 7 | 0 | 14
DALLAS | 0095-04-069 | KAUFMAN | US 80 | 2026-02-09 | 15839362.17 | 643775.33 | 0 | 16272188.45 | 432826.28 | 504 | 597 | 47 | 0 | 93
FORT WORTH | 0718-02-072 | TARRANT | FM 156 | 2026-02-09 | 5497888.16 | 46251.89 | 0 | 5498602.71 | 714.55 | 150 | 158 | 8 | 0 | 8
FORT WORTH | 0902-90-019 | TARRANT | CS | 2026-02-09 | 3188000.33 | 100968.11 | 0 | 3162654.31 | -25346.02 | 150 | 143 | 0 | 0 | -7
FORT WORTH | 0902-90-130 | TARRANT | CS | 2026-02-09 | 1513118.09 | 141699.03 | 153245.93 | 1704254.52 | 37890.5 | 192 | 158 | 0 | 0 | -34
SAN ANTONIO | 0073-02-084 | BEXAR | US 281 | 2026-02-06 | 1732940 | 0 | 0 | 1594003.69 | -138936.31 | 98 | 98 | 0 | 0 | 0
BEAUMONT | 0952-01-064 | LIBERTY | FM 1008 | 2026-02-05 | 396091.75 | 27743.83 | 0 | 357429.81 | -38661.94 | 26 | 26 | 0 | 0 | 0
PARIS | 0610-02-064 | FRANKLIN | IH 30 | 2026-02-05 | 8869678.56 | 356435.19 | 0 | 9661467.5 | 791788.94 | 254 | 253 | 0 | 0 | -1
ODESSA | 0441-07-074 | PECOS | IH 10 | 2026-02-04 | 12743572.55 | 408592 | 0 | 12379375.16 | -364197.39 | 194 | 220 | 26 | 0 | 26
TYLER | 0206-07-059 | RUSK | US 79 | 2026-02-04 | 3202956.86 | 269008.62 | 0 | 2869419.61 | -333537.25 | 62 | 87 | 34 | 0 | 25
TYLER | 0910-16-180 | SMITH | Various | 2026-02-04 | 299532.5 | 0 | 0 | 297792.5 | -1740 | 34 | 19 | 0 | 0 | -15
YOAKUM | 0913-00-120 | DEWITT | VA | 2026-02-04 | 573383 | 815276.72 | 0 | 1472940.69 | 899557.69 | 105 | 153 | 89 | 0 | 48
ABILENE | 0053-07-043 | SCURRY | US 84 | 2026-02-03 | 11538452.96 | 170073.76 | 13200 | 12017984.9 | 466331.94 | 361 | 325 | 0 | 0 | -36
ABILENE | 0181-03-031 | CALLAHAN | SH 36 | 2026-02-03 | 7369772.59 | 0 | 0 | 7249380.95 | -120391.64 | 270 | 262 | 0 | 0 | -8
ABILENE | 2858-02-011 | JONES | FM 2834 | 2026-02-03 | 14844600.55 | -103063.42 | 0 | 14856036.86 | 11436.31 | 103 | 122 | 0 | 0 | 19
CORPUS CHRISTI | 0102-04-099 | KLEBERG | US 77 | 2026-02-03 | 55237175.26 | 2561525.07 | 0 | 59383078.77 | 4145903.51 | 660 | 963 | 311 | 0 | 303
CORPUS CHRISTI | 0326-01-069 | NUECES | SH 286 | 2026-02-03 | 6335414.6 | -183949.77 | 0 | 6571776.64 | 236362.04 | 94 | 93 | 3 | 0 | -1
CORPUS CHRISTI | 0916-00-232 | NUECES | VA | 2026-02-03 | 1230250.6 | 183333.55 | 0 | 1303526.75 | 73276.15 | 237 | 335 | 102 | 0 | 98
HOUSTON | 0389-05-116 | HARRIS | SH 146 | 2026-02-03 | 201835272.66 | 45768158.97 | -41581.96 | 254380094.35 | 52586403.65 | 1549 | 1508 | 258 | 0 | -41
LUFKIN | 3198-02-018 | SAN JACINTO | FM 3278 | 2026-02-03 | 4878702.1 | 759547.78 | 0 | 5727824.95 | 849122.85 | 348 | 276 | 35 | 0 | -72
TYLER | 0206-05-033 | CHEROKEE | US 79 | 2026-02-03 | 4258941.26 | 126094.08 | 0 | 4077911.64 | -181029.62 | 80 | 101 | 4 | 0 | 21
WACO | 0183-02-028 | HAMILTON | SH 36 | 2026-02-03 | 18187374.4 | 1243936.8 | 0 | 19730272.26 | 1542897.86 | 285 | 309 | 25 | 0 | 24
YOAKUM | 0088-05-104 | VICTORIA | US 59 | 2026-02-03 | 6878588.27 | 76673.15 | 0 | 7529231.6 | 650643.33 | 255 | 263 | 8 | 0 | 8
YOAKUM | 0179-04-100 | MATAGORDA | SH 35 | 2026-02-03 | 2857443 | 119658.52 | 0 | 3331660.44 | 474217.44 | 240 | 130 | 0 | 0 | -110
YOAKUM | 0179-10-109 | CALHOUN | SH 35 | 2026-02-03 | 1422240.75 | 35119 | 0 | 1429932.37 | 7691.62 | 162 | 217 | 55 | 0 | 55
DALLAS | 0816-02-089 | DENTON | FM 455 | 2026-02-02 | 5118707.9 | 204162.43 | 0 | 5403263.59 | 284555.69 | 132 | 106 | 0 | 0 | -26
LAREDO | 0086-01-099 | WEBB | SH 359 | 2026-02-02 | 1341138.27 | 36781.68 | 0 | 1400181.69 | 59043.42 | 162 | 357 | 0 | 0 | 195
LAREDO | 0922-33-210 | WEBB | CS | 2026-02-02 | 1161106.04 | 23148.06 | 0 | 1128438.35 | -32667.69 | 165 | 123 | 0 | 0 | -42
ODESSA | 0354-06-030 | ANDREWS | SH 115 | 2026-02-02 | 36740466.75 | 2812897.3 | 0 | 39782524.97 | 3042058.22 | 640 | 602 | 0 | 0 | -38
SAN ANTONIO | 7774-01-004 | BEXAR | PA 1502 | 2026-02-02 | 19520129.83 | 2391230.73 | 0 | 21715899.29 | 2195769.46 | 424 | 606 | 193 | 0 | 182
BROWNWOOD | 0923-00-066 | BROWN | Various | 2026-01-30 | 2616921.75 | 67366.53 | 0 | 2884573.83 | 267652.08 | 176 | 319 | 143 | 0 | 143
DALLAS | 2374-04-085 | DALLAS | IH 20 | 2026-01-30 | 79838372.65 | 695488.18 | 0 | 80803801.29 | 965428.64 | 834 | 857 | 29 | 0 | 23
SAN ANTONIO | 1899-02-021 | KENDALL | RM 1376 | 2026-01-30 | 5653830.45 | 53844.18 | 0 | 5351862.49 | -301967.96 | 160 | 196 | 60 | 0 | 36
TYLER | 0910-16-156 | SMITH | CR | 2026-01-30 | 4280740.25 | -62234.15 | 0 | 4232146.38 | -48593.87 | 523 | 317 | 0 | 0 | -206
BRYAN | 0720-01-044 | GRIMES | FM 149 | 2026-01-29 | 5572269.05 | 1903770.28 | 0 | 7595744.62 | 2023475.57 | 232 | 290 | 94 | 0 | 58
CHILDRESS | 0042-12-086 | CHILDRESS | US 287 | 2026-01-29 | 15308760.06 | -42281.1 | 0 | 15547381.11 | 238621.05 | 159 | 249 | 86 | 0 | 90
LUBBOCK | 0228-01-058 | TERRY | US 62 | 2026-01-29 | 18670289.16 | 472410.63 | 0 | 19573270.86 | 902981.7 | 393 | 347 | 34 | 0 | -46
SAN ANTONIO | 0915-00-235 | BEXAR | VA | 2026-01-29 | 1609699.25 | 104150 | 0 | 1550537.45 | -59161.8 | 256 | 291 | 25 | 0 | 35
BROWNWOOD | 0007-04-136 | EASTLAND | SH | 2026-01-28 | 17087352.48 | 177245.84 | 0 | 16593834.15 | -493518.33 | 97 | 94 | 0 | 0 | -3
BRYAN | 0917-12-088 | MILAM | CR | 2026-01-28 | 974112.19 | 0 | 0 | 987300.53 | 13188.34 | 110 | 120 | 0 | 0 | 10
CHILDRESS | 0105-05-036 | MOTLEY | SH 70 | 2026-01-28 | 384545.39 | -774.62 | 0 | 368473.07 | -16072.32 | 17 | 17 | 0 | 0 | 0
LUFKIN | 0319-01-069 | TRINITY | US 287 | 2026-01-27 | 9098258.8 | 239056.58 | 0 | 11937395.62 | 2839136.82 | 129 | 141 | 13 | 0 | 12
AMARILLO | 0030-02-053 | OCHILTREE | US 83 | 2026-01-26 | 2152762.7 | -99625.88 | 0 | 2072935.02 | -79827.68 | 183 | 715 | 76 | 0 | 532
AUSTIN | 0114-04-078 | BASTROP | US 290 | 2026-01-26 | 4270054.63 | -241973 | 0 | 3810839.67 | -459214.96 | 70 | 58 | 0 | 0 | -12
CORPUS CHRISTI | 0180-06-067 | SAN PATRICIO | SH 35 | 2026-01-26 | 17952982.76 | -15565.9 | 0 | 18235828.53 | 282845.77 | 379 | 493 | 118 | 0 | 114
FORT WORTH | 0008-03-130 | PARKER | IH 20 | 2026-01-26 | 3477191.25 | 0 | 0 | 3578733.87 | 101542.62 | 171 | 290 | 89 | 0 | 119
HOUSTON | 0912-72-386 | HARRIS | CS | 2026-01-26 | 3268852.88 | 298266.71 | 298266.71 | 3790649.61 | 223530.02 | 196 | 275 | 13 | 13 | 66
WICHITA FALLS | 1837-02-017 | ARCHER | FM 1954 | 2026-01-24 | 7814963.76 | 2067619.06 | 0 | 9861561.51 | 2046597.75 | 221 | 357 | 137 | 0 | 136
AUSTIN | 0914-00-504 | TRAVIS | Various | 2026-01-23 | 2626391 | 49643.5 | 0 | 3004019.95 | 377628.95 | 300 | 299 | 90 | 0 | -1
BRYAN | 0050-11-023 | GRIMES | BS 6S | 2026-01-23 | 28059691.76 | -1576689.47 | 0 | 26179688.96 | -1880002.8 | 134 | 92 | 0 | 0 | -42
HOUSTON | 0027-12-105 | FORT BEND | US 59 | 2026-01-23 | 135868538.72 | 44802313.32 | 0 | 179675299.8 | 43806761.08 | 1079 | 1959 | 880 | 0 | 880
ATLANTA | 0063-11-054 | PANOLA | SH 149 | 2026-01-22 | 29546263.07 | 2087656.01 | 0 | 31354018.62 | 1807755.55 | 205 | 537 | 332 | 0 | 332
AUSTIN | 2102-01-078 | TRAVIS | RM 2244 | 2026-01-22 | 5079255.45 | -210676.15 | 0 | 5195188.69 | 115933.24 | 112 | 31 | 0 | 0 | -81
CORPUS CHRISTI | 0101-03-127 | SAN PATRICIO | US 181 | 2026-01-21 | 584654 | 0 | 0 | 521401.84 | -63252.16 | 60 | 11 | 0 | 0 | -49
SAN ANGELO | 0035-05-062 | MENARD | US 83 | 2026-01-21 | 11252313.93 | 0 | 0 | 11644838.6 | 392524.67 | 75 | 84 | 0 | 0 | 9
ATLANTA | 0919-00-097 | CASS | Various | 2026-01-20 | 131208.57 | 0 | 0 | 126686.15 | -4522.42 | 20 | 15 | 0 | 0 | -5
BROWNWOOD | 0071-01-060 | MCCULLOCH | US 87 | 2026-01-20 | 3936577.18 | 0 | 0 | 3786418.19 | -150158.99 | 53 | 44 | 0 | 0 | -9
HOUSTON | 0367-07-009 | GALVESTON | SL 108 | 2026-01-20 | 2472329 | 0 | 0 | 2416874.73 | -55454.27 | 116 | 142 | 0 | 0 | 26
WACO | 0519-03-035 | BOSQUE | SH 174 | 2026-01-20 | 4687667.81 | -616419.82 | 0 | 4162097.53 | -525570.28 | 90 | 86 | 0 | 0 | -4
AMARILLO | 0066-04-083 | MOORE | US 287 | 2026-01-16 | 2231728.04 | 0 | 0 | 2287016.14 | 55288.1 | 51 | 51 | 0 | 0 | 0
BROWNWOOD | 0923-10-021 | LAMPASAS | CS | 2026-01-16 | 1523054.2 | 0 | 0 | 1548879.87 | 25825.67 | 99 | 96 | 0 | 0 | -3
BRYAN | 0049-08-074 | ROBERTSON | US 190 | 2026-01-16 | 4264422.03 | 119868.24 | 0 | 4703329.41 | 438907.38 | 211 | 210 | 0 | 0 | -1
LUBBOCK | 0905-12-045 | HALE | Various | 2026-01-16 | 1747472 | 0 | 0 | 1791457.17 | 43985.17 | 146 | 146 | 0 | 0 | 0
LAREDO | 0018-06-136 | WEBB | IH 35 | 2026-01-15 | 114884943.92 | 7045320.74 | 0 | 130180600.06 | 15295656.14 | 1112 | 1202 | 90 | 0 | 90
SAN ANGELO | 0907-00-232 | TOM GREEN | Various | 2026-01-15 | 274353 | -4277 | 0 | 282603 | 8250 | 38 | 28 | 3 | 0 | -10
DALLAS | 0047-06-177 | COLLIN | US 75 | 2026-01-14 | 2947555.11 | 273863.21 | 0 | 2949055.84 | 1500.73 | 206 | 185 | 0 | 0 | -21
HOUSTON | 3538-01-036 | MONTGOMERY | SH 242 | 2026-01-14 | 65322056.95 | 12270571.38 | 0 | 76748029.24 | 11425972.29 | 778 | 1253 | 493 | 0 | 475
LAREDO | 0301-01-087 | DIMMIT | SH 85 | 2026-01-14 | 4036048.13 | 26295.71 | 0 | 4175056.08 | 139007.95 | 129 | 126 | 0 | 0 | -3
LAREDO | 0922-00-081 | WEBB | Various | 2026-01-14 | 663049.75 | 16989 | 0 | 650245.64 | -12804.11 | 45 | 45 | 0 | 0 | 0
LAREDO | 0922-00-088 | WEBB | Various | 2026-01-14 | 1443018.84 | -111318.06 | 0 | 1330694.05 | -112324.79 | 135 | 92 | 0 | 0 | -43
PARIS | 0400-03-015 | HOPKINS | SL 301 | 2026-01-13 | 1347538.8 | 24925.85 | 0 | 1322788.76 | -24750.04 | 250 | 243 | 0 | 0 | -7
WICHITA FALLS | 0043-17-035 | WICHITA | BU 287J | 2026-01-13 | 1028500.8 | 28963.89 | 0 | 1074762.29 | 46261.49 | 167 | 140 | 0 | 0 | -27
CORPUS CHRISTI | 0617-01-205 | NUECES | SH 358 | 2026-01-12 | 2547784.79 | 309358.14 | 0 | 2881959.78 | 334174.99 | 276 | 399 | 133 | 0 | 123
CORPUS CHRISTI | 0617-02-001 | NUECES | PR 22 | 2026-01-12 | 8685850.35 | 1749851.01 | 0 | 10820240.66 | 2134390.31 | 346 | 409 | 69 | 0 | 63
SAN ANTONIO | 0017-09-111 | BEXAR | IH 35 | 2026-01-12 | 2720941.84 | 55562.92 | 0 | 2776357.94 | 55416.1 | 176 | 257 | 25 | 0 | 81
DALLAS | 0092-14-103 | DALLAS | IH 45 | 2026-01-09 | 7188411.94 | 0 | 0 | 8050393.57 | 861981.63 | 365 | 378 | 0 | 0 | 13
DALLAS | 2374-07-074 | DALLAS | IH 635 | 2026-01-09 | 7861879.45 | 2223.29 | 0 | 7969256.23 | 107376.78 | 218 | 242 | 0 | 0 | 24
HOUSTON | 0508-01-391 | HARRIS | IH 10 | 2026-01-09 | 18279582.41 | -1900724.16 | 0 | 19169668.57 | 890086.16 | 137 | 167 | 0 | 0 | 30
EL PASO | 0002-02-059 | EL PASO | SH 20 | 2026-01-08 | 2290249.48 | -90617.96 | 0 | 2255310.5 | -34938.98 | 131 | 130 | 12 | 0 | -1
PARIS | 0768-01-057 | HUNT | SH 11 | 2026-01-08 | 4510635.84 | -15310.92 | 0 | 4215895.12 | -294740.72 | 136 | 152 | 0 | 0 | 16
WICHITA FALLS | 0133-04-042 | BAYLOR | US 82 | 2026-01-08 | 15938381.26 | 596194 | 0 | 17139736.01 | 1201354.75 | 377 | 496 | 150 | 0 | 119
SAN ANTONIO | 0915-12-771 | BEXAR | Various | 2026-01-07 | 439957 | 0 | 0 | 541886.66 | 101929.66 | 53 | 45 | 0 | 0 | -8
CHILDRESS | 0381-01-017 | CHILDRESS | US 62 | 2026-01-06 | 6310485.56 | -81464.32 | 0 | 6141956.81 | -168528.75 | 249 | 201 | 0 | 0 | -48
EL PASO | 0167-01-126 | EL PASO | US 54 | 2026-01-06 | 2140780.77 | 332769.22 | 0 | 2601100.13 | 460319.36 | 189 | 206 | 18 | 0 | 17
HOUSTON | 0110-03-084 | MONTGOMERY | SH 75 | 2026-01-06 | 3303124.11 | 88660.5 | 0 | 3431596.02 | 128471.91 | 70 | 64 | 0 | 0 | -6
TYLER | 0393-01-101 | GREGG | SH 149 | 2026-01-06 | 9370471.6 | -192138.13 | 0 | 9446485.12 | 76013.52 | 191 | 292 | 0 | 0 | 101
LUFKIN | 0119-05-004 | SABINE | SH 21 | 2026-01-05 | 1987987.05 | 88437.33 | 0 | 1952125.31 | -35861.74 | 124 | 140 | 49 | 0 | 16
LUFKIN | 0911-00-152 | ANGELINA | Various | 2026-01-05 | 938603 | 0 | 0 | 943012.65 | 4409.65 | 126 | 105 | 0 | 0 | -21
YOAKUM | 0089-04-082 | JACKSON | US 59 | 2026-01-05 | 3431626 | 0 | 0 | 3429167.62 | -2458.38 | 105 | 62 | 0 | 0 | -43
YOAKUM | 0187-02-070 | AUSTIN | SH 36 | 2026-01-05 | 443415.05 | 91896.96 | 0 | 530472.49 | 87057.44 | 30 | 66 | 10 | 0 | 36
YOAKUM | 1266-01-008 | FAYETTE | FM 956 | 2026-01-05 | 884255.26 | 0 | 0 | 935900.29 | 51645.03 | 63 | 86 | 0 | 0 | 23
ODESSA | 0548-02-041 | MARTIN | SH 176 | 2026-01-02 | 4613804.33 | -1010995.19 | 0 | 3853780.73 | -760023.6 | 191 | 148 | 0 | 0 | -43
ODESSA | 2568-01-009 | UPTON | RM 2594 | 2026-01-02 | 17171717.59 | 743400.11 | 0 | 18456632.14 | 1284914.55 | 362 | 338 | 0 | 0 | -24
SAN ANTONIO | 0915-00-231 | BEXAR | VA | 2026-01-02 | 3416462.55 | 302677.78 | 0 | 3838069.32 | 421606.77 | 214 | 273 | 60 | 0 | 59
BRYAN | 0639-02-034 | MADISON | FM 39 | 2025-12-31 | 14087277.98 | 1635275.88 | 0 | 15851900.56 | 1764622.58 | 267 | 267 | 0 | 0 | 0
LUFKIN | 0911-28-063 | HOUSTON | Various | 2025-12-31 | 1536462 | 30179.4 | 0 | 1464583.04 | -71878.96 | 128 | 165 | 7 | 0 | 37
BRYAN | 0114-10-101 | WASHINGTON | US 290 | 2025-12-30 | 6554342.36 | 92727.06 | 0 | 6758943.04 | 204600.68 | 179 | 186 | 7 | 0 | 7
EL PASO | 2552-03-070 | EL PASO | SL 375 | 2025-12-30 | 678787 | 79849.61 | 0 | 716679.11 | 37892.11 | 60 | 100 | 46 | 0 | 40
AMARILLO | 0030-06-060 | HEMPHILL | US 60 | 2025-12-29 | 13405600.41 | 293667.14 | 0 | 14176377.71 | 770777.3 | 305 | 299 | 0 | 0 | -6
AMARILLO | 0356-01-108 | HUTCHINSON | SH 136 | 2025-12-29 | 4885721.3 | 115235.37 | 0 | 5174365.12 | 288643.82 | 263 | 237 | 0 | 0 | -26
AUSTIN | 3136-01-207 | TRAVIS | SL 1 | 2025-12-29 | 720110.11 | 0 | 0 | 681576.24 | -38533.87 | 26 | 23 | 0 | 0 | -3
BRYAN | 0204-06-060 | MILAM | US 79 | 2025-12-29 | 4509031.7 | 1190350.47 | 0 | 5783840.52 | 1274808.82 | 270 | 442 | 172 | 0 | 172
FORT WORTH | 0008-14-136 | TARRANT | IH 820 | 2025-12-29 | 2031604.5 | 135955.72 | 0 | 2242222.1 | 210617.6 | 360 | 202 | 0 | 0 | -158
HOUSTON | 0271-16-140 | HARRIS | IH 610 | 2025-12-29 | 116922668.26 | 14178556.17 | 0 | 133971162.01 | 17048493.75 | 1047 | 1491 | 555 | 0 | 444
BRYAN | 0204-07-056 | MILAM | US 79 | 2025-12-23 | 1108345.62 | 29766.52 | 0 | 1226469.51 | 118123.89 | 55 | 57 | 0 | 0 | 2
BRYAN | 0917-27-046 | WALKER | CR | 2025-12-23 | 1498226.55 | 59004.58 | 0 | 1545133.23 | 46906.68 | 201 | 138 | 0 | 0 | -63
EL PASO | 0003-01-064 | CULBERSON | IH 10 | 2025-12-23 | 29566262.03 | 913279.3 | 0 | 31526747.1 | 1960485.07 | 160 | 157 | 6 | 0 | -3
SAN ANGELO | 0141-04-039 | SUTTON | IH 10 | 2025-12-23 | 9433781 | 2847156.77 | 0 | 12075734.58 | 2641953.58 | 814 | 208 | 0 | 0 | -606
TYLER | 0191-03-089 | SMITH | FM 2493 | 2025-12-23 | 24103695.6 | -583707.31 | 0 | 22776403.56 | -1327292.04 | 170 | 156 | 0 | 0 | -14
WACO | 2057-01-010 | BELL | FS 439 | 2025-12-23 | 1357784.16 | -72380 | 0 | 1149360.66 | -208423.5 | 75 | 70 | 0 | 0 | -5
SAN ANTONIO | 0915-00-258 | BEXAR | Various | 2025-12-22 | 1984026 | 875331.81 | 0 | 2468936.14 | 484910.14 | 173 | 247 | 38 | 0 | 74
DALLAS | 0095-14-034 | KAUFMAN | IH 20 | 2025-12-19 | 645552.38 | 91650.06 | 0 | 732146.08 | 86593.7 | 40 | 19 | 0 | 0 | -21
SAN ANGELO | 0069-07-116 | TOM GREEN | US 87 | 2025-12-19 | 2447858.8 | 115109.71 | 0 | 2690378.47 | 242519.67 | 143 | 136 | 5 | 0 | -7
SAN ANGELO | 0454-02-055 | TOM GREEN | SH 208 | 2025-12-19 | 480047.7 | 0 | 0 | 471134.6 | -8913.1 | 91 | 84 | 0 | 0 | -7
TYLER | 0505-02-047 | SMITH | SH 110 | 2025-12-19 | 787820.88 | -54733.5 | 0 | 724229.55 | -63591.33 | 89 | 54 | 0 | 0 | -35
HOUSTON | 0178-03-156 | BRAZORIA | SH 35 | 2025-12-18 | 20773975.76 | 186585.92 | 0 | 21065717.27 | 291741.51 | 416 | 486 | 58 | 0 | 70
SAN ANGELO | 0907-00-231 | TOM GREEN | Various | 2025-12-18 | 449824 | 375325.63 | 0 | 932443.85 | 482619.85 | 54 | 78 | 63 | 0 | 24
ABILENE | 0006-02-114 | NOLAN | IH 20 | 2025-12-17 | 116984399.19 | -1113337.19 | 0 | 115975626.17 | -1008773.02 | 829 | 617 | 0 | 0 | -212
CHILDRESS | 2051-01-014 | WHEELER | FM 2473 | 2025-12-17 | 691555 | 0 | 0 | 688865.2 | -2689.8 | 101 | 84 | 0 | 0 | -17
DALLAS | 0918-47-347 | DALLAS | CS | 2025-12-17 | 1765418.2 | 89548.8 | 0 | 1920491.64 | 155073.44 | 340 | 350 | 0 | 0 | 10
FORT WORTH | 0365-02-032 | HOOD | SH 171 | 2025-12-17 | 9721843.05 | 177798.67 | 0 | 9620903.61 | -100939.44 | 132 | 111 | 0 | 0 | -21
PARIS | 0045-09-110 | LAMAR | US 82 | 2025-12-17 | 2085075.75 | 18708.5 | 0 | 2129171.87 | 44096.12 | 96 | 97 | 15 | 0 | 1
SAN ANTONIO | 0143-04-072 | WILSON | US 87 | 2025-12-17 | 2262609.25 | 14381.51 | 0 | 2294839.22 | 32229.97 | 190 | 184 | 0 | 0 | -6
TYLER | 0424-10-009 | RUSK | FM 3231 | 2025-12-17 | 15996365.9 | 265006.95 | 0 | 16374900.25 | 378534.35 | 230 | 280 | 70 | 0 | 50
TYLER | 0646-07-009 | HENDERSON | FM 316 | 2025-12-17 | 7938413.55 | -509736.87 | 0 | 8164616.19 | 226202.64 | 261 | 221 | 0 | 0 | -40
EL PASO | 0002-10-039 | HUDSPETH | IH 10 | 2025-12-16 | 18357209.18 | 849393.95 | 0 | 19845102.64 | 1487893.46 | 160 | 157 | 0 | 0 | -3
HOUSTON | 3256-01-115 | HARRIS | SL 8 | 2025-12-15 | 3999999.38 | 136257.84 | 0 | 3970862.48 | -29136.9 | 178 | 280 | 0 | 0 | 102
PHARR | 0921-06-252 | CAMERON | CS | 2025-12-15 | 9511089.36 | 63689.84 | 0 | 9098201.47 | -412887.89 | 376 | 356 | 0 | 0 | -20
WACO | 2305-01-014 | BOSQUE | FM 2114 | 2025-12-15 | 13110489.92 | -569788.33 | 0 | 12018749 | -1091740.92 | 315 | 322 | 0 | 0 | 7
AUSTIN | 0914-33-097 | HAYS | Various | 2025-12-12 | 4715509.59 | 328948.22 | 107122.93 | 4953323.23 | 130690.71 | 256 | 169 | 0 | 0 | -87
BEAUMONT | 2887-01-013 | LIBERTY | FM 2830 | 2025-12-12 | 484908.43 | 4664 | 0 | 442548.94 | -42359.49 | 24 | 33 | 0 | 0 | 9
DALLAS | 0918-00-430 | DALLAS | Various | 2025-12-12 | 4441943.11 | 0 | 0 | 4455737.59 | 13794.48 | 153 | 151 | 0 | 0 | -2
DALLAS | 0918-47-248 | DALLAS | CS | 2025-12-12 | 1824000 | 0 | 0 | 1716983.46 | -107016.54 | 270 | 443 | 0 | 0 | 173
HOUSTON | 2523-02-068 | BRAZORIA | FM 2004 | 2025-12-12 | 28859306.46 | -241075.67 | 0 | 29812342.35 | 953035.89 | 738 | 748 | 10 | 0 | 10
PHARR | 1430-01-031 | WILLACY | FM 490 | 2025-12-12 | 5944074.3 | 17280 | 0 | 5858694.58 | -85379.72 | 136 | 175 | 21 | 0 | 39
SAN ANGELO | 0264-04-054 | COKE | US 277 | 2025-12-12 | 24893157.94 | 99359.54 | 0 | 25923029.12 | 1029871.18 | 467 | 327 | 0 | 0 | -140
TYLER | 0164-03-056 | HENDERSON | SH 31 | 2025-12-12 | 341595.15 | 14641.1 | 0 | 362020.9 | 20425.75 | 46 | 45 | 0 | 0 | -1
TYLER | 0559-02-037 | HENDERSON | FM 315 | 2025-12-12 | 9287827.25 | 257065.57 | 0 | 9610277.29 | 322450.04 | 119 | 123 | 8 | 0 | 4
AUSTIN | 0150-03-021 | LLANO | SH 29 | 2025-12-11 | 1386822.5 | 0 | 0 | 1466999.24 | 80176.74 | 56 | 14 | 0 | 0 | -42
AUSTIN | 1200-03-060 | TRAVIS | FM 973 | 2025-12-11 | 22834260.66 | 240358 | 0 | 23909005.07 | 1074744.41 | 380 | 319 | 8 | 0 | -61
AUSTIN | 3136-01-199 | TRAVIS | SL 1 | 2025-12-11 | 1673616.6 | 76620.02 | 0 | 1644243.87 | -29372.73 | 28 | 20 | 0 | 0 | -8
AUSTIN | 3351-02-006 | BLANCO | RM 3232 | 2025-12-11 | 4405351.15 | -165764.34 | 0 | 3979356.41 | -425994.74 | 88 | 118 | 0 | 0 | 30
BEAUMONT | 0028-06-088 | JEFFERSON | US 90 | 2025-12-11 | 9870092.8 | 58583.38 | 0 | 9452611.83 | -417480.97 | 60 | 27 | 0 | 0 | -33
BEAUMONT | 0920-00-166 | JEFFERSON | Various | 2025-12-11 | 1798959.01 | -434385.46 | 0 | 1304843.81 | -494115.2 | 163 | 106 | 0 | 0 | -57
FORT WORTH | 0081-02-077 | TARRANT | US 377 | 2025-12-11 | 7770210.7 | 288766.33 | 0 | 7866658.17 | 96447.47 | 256 | 211 | 18 | 0 | -45
YOAKUM | 0346-06-052 | LAVACA | SH 111 | 2025-12-11 | 3752830.76 | 156958 | 0 | 3879534.35 | 126703.59 | 222 | 333 | 23 | 0 | 111
DALLAS | 0918-18-133 | NAVARRO | CR | 2025-12-10 | 3379522.3 | 0 | 0 | 3318398.82 | -61123.48 | 210 | 209 | 0 | 0 | -1
FORT WORTH | 0094-05-068 | TARRANT | SH 183 | 2025-12-10 | 3831814.93 | 195364.19 | 0 | 3688254.97 | -143559.96 | 113 | 64 | 0 | 0 | -49
LUBBOCK | 0228-01-056 | TERRY | US 62 | 2025-12-10 | 22784906.89 | 799413.96 | 0 | 23305315.78 | 520408.89 | 289 | 280 | 17 | 0 | -9
LUBBOCK | 0228-01-062 | TERRY | US 62 | 2025-12-10 | 11408518.79 | -247874 | 0 | 11011854.28 | -396664.51 | 132 | 131 | 0 | 0 | -1
TYLER | 0910-12-140 | VAN ZANDT | Various | 2025-12-10 | 671280 | 0 | 0 | 673380 | 2100 | 43 | 43 | 0 | 0 | 0
TYLER | 0910-12-141 | VAN ZANDT | Various | 2025-12-10 | 450860 | 0 | 0 | 447360 | -3500 | 72 | 30 | 0 | 0 | -42
AUSTIN | 0914-00-533 | TRAVIS | Various | 2025-12-09 | 4437824.8 | 119781.96 | 0 | 4841007.2 | 403182.4 | 192 | 170 | 0 | 0 | -22
BEAUMONT | 0028-03-116 | LIBERTY | US 90 | 2025-12-09 | 1654702.8 | 123434.25 | 0 | 2437857.2 | 783154.4 | 114 | 140 | 60 | 0 | 26
BEAUMONT | 0739-02-183 | JEFFERSON | IH 10 | 2025-12-09 | 3084194.45 | 122768.75 | 0 | 3326784.8 | 242590.35 | 99 | 56 | 8 | 0 | -43
CORPUS CHRISTI | 0087-06-031 | SAN PATRICIO | BS 359B | 2025-12-09 | 1938855.44 | 59725.09 | 0 | 2145099.08 | 206243.64 | 125 | 226 | 101 | 0 | 101
DALLAS | 0197-05-059 | KAUFMAN | US 175 | 2025-12-09 | 36849199.79 | -118140.3 | 0 | 33073933.06 | -3775266.73 | 330 | 348 | 0 | 0 | 18
FORT WORTH | 0902-00-291 | TARRANT | Various | 2025-12-09 | 1568135 | 17813.53 | 0 | 1415724.24 | -152410.76 | 300 | 333 | 60 | 0 | 33
HOUSTON | 0192-01-093 | FORT BEND | SH 6 | 2025-12-09 | 6992340.39 | 1472827.91 | 1534139.92 | 8737905.66 | 211425.35 | 240 | 339 | 99 | 76 | 23
HOUSTON | 0527-05-012 | FORT BEND | FM 1875 | 2025-12-09 | 1497972.35 | 622387.35 | 0 | 2318445.84 | 820473.49 | 45 | 45 | 0 | 0 | 0
HOUSTON | 1062-04-058 | HARRIS | FM 2100 | 2025-12-09 | 25495057.26 | 10555449.91 | 0 | 36350830.56 | 10855773.3 | 331 | 430 | 180 | 0 | 99
HOUSTON | 1685-06-045 | FORT BEND | SH 6 | 2025-12-09 | 1459342.74 | 98979.04 | 0 | 1524346.27 | 65003.53 | 105 | 105 | 0 | 0 | 0
LUBBOCK | 0905-00-123 | LUBBOCK | Various | 2025-12-09 | 7105937.8 | 0 | 0 | 7376044.54 | 270106.74 | 85 | 55 | 0 | 0 | -30
SAN ANGELO | 0069-02-031 | GLASSCOCK | US 87 | 2025-12-09 | 8400199.25 | 50500 | 0 | 9482732.3 | 1082533.05 | 54 | 56 | 1 | 0 | 2
WICHITA FALLS | 0043-09-146 | WICHITA | US 287 | 2025-12-09 | 7338061.32 | 302547.13 | 0 | 7650994.17 | 312932.85 | 187 | 92 | 0 | 0 | -95
YOAKUM | 0271-02-049 | AUSTIN | IH 10 | 2025-12-09 | 151401690.07 | 7930192.31 | 0 | 157509065.55 | 6107375.48 | 880 | 974 | 94 | 0 | 94
YOAKUM | 0913-26-064 | COLORADO | CR | 2025-12-09 | 2752206.71 | -2327.31 | 0 | 2665533.84 | -86672.87 | 225 | 175 | 0 | 0 | -50
CORPUS CHRISTI | 0988-01-025 | BEE | FM 623 | 2025-12-08 | 1284612 | 7733.1 | 0 | 1297457 | 12845 | 96 | 92 | 0 | 0 | -4
DALLAS | 0081-13-069 | DENTON | IH 35W | 2025-12-08 | 725999.98 | 0 | 0 | 702844.09 | -23155.89 | 60 | 149 | 0 | 0 | 89
DALLAS | 0091-04-069 | COLLIN | SH 289 | 2025-12-08 | 3848916.55 | 575650 | 78794.37 | 4284835.29 | 357124.37 | 198 | 295 | 110 | 12 | 85
HOUSTON | 0389-13-039 | HARRIS | SH 146 | 2025-12-08 | 24851806.25 | 390354.69 | 0 | 24632569.67 | -219236.58 | 469 | 469 | 0 | 0 | 0
DALLAS | 1159-02-037 | ELLIS | FM 879 | 2025-12-05 | 8156479.25 | 701498.31 | 0 | 9109317.46 | 952838.21 | 280 | 307 | 40 | 0 | 27
DALLAS | 1975-02-013 | KAUFMAN | FM 1895 | 2025-12-05 | 11181793.38 | 123043.11 | 0 | 10418893.03 | -762900.35 | 324 | 478 | 10 | 0 | 154
SAN ANTONIO | 0025-03-105 | GUADALUPE | UA 90 | 2025-12-05 | 1668821.81 | 479863.05 | 0 | 2325231.46 | 656409.65 | 215 | 170 | 48 | 0 | -45
TYLER | 0164-04-163 | SMITH | SH 31 | 2025-12-05 | 1235384 | 2394.4 | 0 | 1294337.39 | 58953.39 | 38 | 52 | 14 | 0 | 14
CORPUS CHRISTI | 1052-03-030 | SAN PATRICIO | FM 666 | 2025-12-04 | 854238.38 | 21263.93 | 0 | 905212.81 | 50974.43 | 119 | 78 | 0 | 0 | -41
TYLER | 0910-12-143 | VAN ZANDT | CS | 2025-12-04 | 1162543 | 3352.1 | 0 | 1166393.6 | 3850.6 | 115 | 98 | 3 | 0 | -17
ABILENE | 0053-10-047 | SCURRY | US 84 | 2025-12-03 | 9325296.75 | 0 | 0 | 10615581.5 | 1290284.75 | 63 | 81 | 0 | 0 | 18
ABILENE | 0106-04-036 | STONEWALL | US 380 | 2025-12-03 | 14662526 | 72672.93 | 0 | 14650459.26 | -12066.74 | 506 | 491 | 0 | 0 | -15
ATLANTA | 1216-01-010 | CASS | FM 994 | 2025-12-03 | 1327253.73 | 53606.5 | 0 | 1428546.69 | 101292.96 | 102 | 101 | 8 | 0 | -1
AUSTIN | 0337-02-053 | WILLIAMSON | SH 29 | 2025-12-03 | 279317 | -43724.2 | 0 | 260498.28 | -18818.72 | 48 | 27 | 0 | 0 | -21
HOUSTON | 0028-01-105 | HARRIS | BU 90U | 2025-12-03 | 8121312.5 | 478355.46 | 0 | 9127574.52 | 1006262.02 | 171 | 186 | 19 | 0 | 15
WACO | 0184-01-070 | CORYELL | SH 36 | 2025-12-03 | 8907042 | 79319.81 | 0 | 9348652.47 | 441610.47 | 195 | 199 | 5 | 0 | 4
WACO | 0209-06-043 | HILL | FM 933 | 2025-12-03 | 926962.24 | 0 | 0 | 870817.92 | -56144.32 | 105 | 26 | 0 | 0 | -79
YOAKUM | 0346-01-040 | JACKSON | SH 111 | 2025-12-03 | 9898507.43 | -7492.35 | 0 | 10151246.36 | 252738.93 | 210 | 199 | 0 | 0 | -11
YOAKUM | 0715-01-025 | GONZALES | FM 108 | 2025-12-03 | 6351464.79 | 276836.49 | 0 | 6733649.33 | 382184.54 | 165 | 159 | 0 | 0 | -6
YOAKUM | 0913-28-078 | FAYETTE | CR | 2025-12-03 | 2799229.26 | -3020.17 | 0 | 2785559.98 | -13669.28 | 281 | 341 | 0 | 0 | 60
LUBBOCK | 0053-18-048 | LUBBOCK | US 84 | 2025-12-02 | 9876826.69 | -117079.92 | 0 | 9827517.9 | -49308.79 | 389 | 337 | 10 | 0 | -52
SAN ANTONIO | 1499-01-032 | FRIO | FM 1581 | 2025-12-02 | 614053.88 | 48302.76 | 0 | 693423.24 | 79369.36 | 61 | 31 | 0 | 0 | -30
AUSTIN | 0211-04-027 | LEE | US 77 | 2025-12-01 | 1282363.92 | 13861.21 | 0 | 1100378.73 | -181985.19 | 130 | 155 | 0 | 0 | 25
BRYAN | 0917-18-089 | ROBERTSON | Various | 2025-12-01 | 357315.83 | -31628.1 | 0 | 331536.38 | -25779.45 | 57 | 60 | 4 | 0 | 3
CHILDRESS | 0740-03-016 | BRISCOE | FM 1065 | 2025-12-01 | 7724031.17 | -392229.49 | 0 | 7856259.22 | 132228.05 | 54 | 36 | 0 | 0 | -18
CORPUS CHRISTI | 0155-02-029 | GOLIAD | US 183 | 2025-12-01 | 22867692.86 | 3252101.83 | 0 | 25893280.79 | 3025587.93 | 465 | 664 | 382 | 0 | 199
PARIS | 0009-13-192 | HUNT | IH 30 | 2025-11-26 | 15007962.44 | -166145.42 | 0 | 13453077.51 | -1554884.93 | 144 | 124 | 0 | 0 | -20
AUSTIN | 0265-03-053 | BASTROP | SH 71 | 2025-11-25 | 6520251.38 | -27680.23 | 0 | 6437242.59 | -83008.79 | 74 | 62 | 0 | 0 | -12
AUSTIN | 0805-04-033 | HAYS | RM 3237 | 2025-11-25 | 5105187.5 | -224475.08 | 0 | 4574352.54 | -530834.96 | 202 | 196 | 0 | 0 | -6
CORPUS CHRISTI | 0916-02-023 | KLEBERG | Various | 2025-11-25 | 520421.5 | -546.89 | 0 | 520264.61 | -156.89 | 227 | 114 | 0 | 0 | -113
DALLAS | 1396-01-013 | KAUFMAN | FM 1391 | 2025-11-25 | 5443323.5 | 212741.9 | 0 | 5462771.52 | 19448.02 | 123 | 188 | 0 | 0 | 65
HOUSTON | 0912-72-747 | HARRIS | Various | 2025-11-25 | 2588189.34 | 0 | 0 | 2730677.19 | 142487.85 | 91 | 91 | 0 | 0 | 0
ATLANTA | 0610-07-123 | BOWIE | IH 30 | 2025-11-24 | 414401 | 0 | 0 | 410506.9 | -3894.1 | 78 | 64 | 0 | 0 | -14
AUSTIN | 0265-04-075 | BASTROP | SH 21 | 2025-11-24 | 4578078.31 | -117720 | 0 | 3852215.01 | -725863.3 | 84 | 61 | 0 | 0 | -23
AUSTIN | 0805-03-021 | CALDWELL | FM 713 | 2025-11-24 | 2033352.21 | 0 | 0 | 1932119.77 | -101232.44 | 43 | 32 | 0 | 0 | -11
FORT WORTH | 0902-90-134 | TARRANT | CS | 2025-11-24 | 1644915.14 | -40644.68 | 0 | 1596477.28 | -48437.86 | 192 | 205 | 13 | 0 | 13
HOUSTON | 0912-00-526 | HARRIS | VA | 2025-11-24 | 291372 | 942462.03 | 0 | 1389325.52 | 1097953.52 | 120 | 111 | 0 | 0 | -9
WACO | 0209-06-041 | HILL | FM 310 | 2025-11-24 | 7292707.38 | -179230.72 | 0 | 6962298.08 | -330409.3 | 60 | 40 | 0 | 0 | -20
YOAKUM | 0913-28-092 | FAYETTE | CR | 2025-11-24 | 954924.8 | 0 | 0 | 930014.1 | -24910.7 | 82 | 90 | 0 | 0 | 8
DALLAS | 0091-09-017 | COLLIN | BS 289C | 2025-11-21 | 2843504.7 | 0 | 0 | 2707117.09 | -136387.61 | 206 | 136 | 0 | 0 | -70
FORT WORTH | 0250-03-051 | ERATH | US 281 | 2025-11-21 | 6375558.15 | 359798.23 | 0 | 6873718.19 | 498160.04 | 108 | 86 | 0 | 0 | -22
FORT WORTH | 0902-00-374 | TARRANT | Various | 2025-11-21 | 4322950 | 0 | 0 | 4347429.47 | 24479.47 | 365 | 365 | 0 | 0 | 0
BRYAN | 3138-01-038 | BRAZOS | FM 2347 | 2025-11-20 | 1020976.25 | 447.06 | 447.06 | 984301.07 | -37122.24 | 68 | 42 | 0 | 0 | -26
DALLAS | 0047-14-091 | COLLIN | US 75 | 2025-11-20 | 1895528.6 | 14987.39 | 0 | 1885603.18 | -9925.42 | 160 | 134 | 0 | 0 | -26
ODESSA | 2296-02-026 | MIDLAND | SH 191 | 2025-11-20 | 27535249.69 | 621870.99 | 0 | 28582569.73 | 1047320.04 | 580 | 606 | 44 | 0 | 26
ABILENE | 2189-01-020 | SCURRY | FM 1673 | 2025-11-19 | 7348904.5 | 1000 | 0 | 7328393 | -20511.5 | 126 | 126 | 0 | 0 | 0
WACO | 0162-13-002 | HILL | SH 31 | 2025-11-19 | 7287639.65 | 74002.5 | 0 | 7291281.7 | 3642.05 | 60 | 51 | 0 | 0 | -9
YOAKUM | 0605-01-068 | MATAGORDA | FM 457 | 2025-11-19 | 3978936.08 | 10160 | 0 | 3920898.28 | -58037.8 | 90 | 80 | 0 | 0 | -10
PHARR | 0038-07-084 | STARR | US 83 | 2025-11-17 | 506977.2 | 0 | 0 | 486927.45 | -20049.75 | 60 | 59 | 0 | 0 | -1
DALLAS | 0091-03-031 | COLLIN | SH 289 | 2025-11-14 | 2504717.44 | 20472.15 | 0 | 2574695.69 | 69978.25 | 220 | 226 | 0 | 0 | 6
ABILENE | 0360-04-033 | HASKELL | US 380 | 2025-11-13 | 7148853.18 | 12584.18 | 0 | 7602667.64 | 453814.46 | 136 | 244 | 26 | 0 | 108
AUSTIN | 0015-09-206 | WILLIAMSON | IH 35 | 2025-11-13 | 234700 | 0 | 0 | 222994.82 | -11705.18 | 25 | 49 | 0 | 0 | 24
AUSTIN | 0700-04-054 | LLANO | SH 71 | 2025-11-13 | 6207912.47 | 63804.08 | 0 | 6042015.33 | -165897.14 | 119 | 73 | 0 | 0 | -46
FORT WORTH | 0008-12-099 | TARRANT | IH 20 | 2025-11-13 | 4195452.12 | 135600.41 | 0 | 4288256.48 | 92804.36 | 278 | 255 | 0 | 0 | -23
FORT WORTH | 0902-00-369 | TARRANT | Various | 2025-11-13 | 6866259.35 | -3725.95 | 0 | 7116807.62 | 250548.27 | 139 | 96 | 0 | 0 | -43
HOUSTON | 0847-06-012 | BRAZORIA | FM 521 | 2025-11-13 | 3244910.21 | 0 | 0 | 3496023.03 | 251112.82 | 154 | 154 | 0 | 0 | 0
HOUSTON | 0912-31-323 | BRAZORIA | CR | 2025-11-13 | 3799246.85 | 46439.4 | 7232.28 | 3987529.7 | 181050.57 | 349 | 244 | 0 | 0 | -105
LUBBOCK | 0905-00-124 | LUBBOCK | Various | 2025-11-13 | 1393453.53 | 162218.79 | 0 | 1509422.07 | 115968.54 | 68 | 64 | 0 | 0 | -4
LUFKIN | 1810-01-036 | NACOGDOCHES | FM 1878 | 2025-11-13 | 4866130.71 | 5726.64 | 0 | 4324289.36 | -541841.35 | 152 | 231 | 47 | 0 | 79
LUFKIN | 0059-01-062 | NACOGDOCHES | SH 7 | 2025-11-12 | 18053313.66 | 56422.8 | 0 | 16823816.65 | -1229497.01 | 148 | 119 | 0 | 0 | -29
PHARR | 0220-04-059 | CAMERON | US 281 | 2025-11-12 | 930686.79 | 0 | 0 | 915381.4 | -15305.39 | 171 | 170 | 0 | 0 | -1
WACO | 0909-22-219 | MCLENNAN | Various | 2025-11-12 | 598139.37 | 109601.22 | 0 | 700846.15 | 102706.78 | 45 | 45 | 0 | 0 | 0
BEAUMONT | 1022-01-034 | CHAMBERS | FM 562 | 2025-11-11 | 1598096.25 | 3077959.83 | 0 | 4593572.09 | 2995475.84 | 153 | 478 | 208 | 0 | 325
CORPUS CHRISTI | 0074-06-253 | NUECES | US 181 | 2025-11-10 | 269165 | 48198.19 | 0 | 304194.19 | 35029.19 | 23 | 20 | 0 | 0 | -3
DALLAS | 0047-07-237 | DALLAS | US 75 | 2025-11-10 | 2951302.81 | 20705 | 0 | 3089768.6 | 138465.79 | 400 | 430 | 0 | 0 | 30
WICHITA FALLS | 0043-06-098 | WILBARGER | US 70 | 2025-11-10 | 4708397.61 | 43206.49 | 0 | 4714398.68 | 6001.07 | 170 | 170 | 0 | 0 | 0
AUSTIN | 0071-05-030 | MASON | US 87 | 2025-11-07 | 4942754.11 | 126520.17 | 0 | 5119595.45 | 176841.34 | 71 | 86 | 0 | 0 | 15
AUSTIN | 0320-03-102 | WILLIAMSON | SH 95 | 2025-11-07 | 3483607.75 | -86876.29 | 0 | 3521907.03 | 38299.28 | 89 | 26 | 0 | 0 | -63
FORT WORTH | 0094-02-140 | TARRANT | SH 10 | 2025-11-07 | 1344006.96 | 10515.15 | 0 | 1376298.92 | 32291.96 | 150 | 147 | 0 | 0 | -3
LAREDO | 0018-02-091 | LA SALLE | IH 35 | 2025-11-07 | 31549072.31 | -1927292.8 | 0 | 33127599.23 | 1578526.92 | 198 | 203 | 8 | 0 | 5
AUSTIN | 0914-00-459 | TRAVIS | Various | 2025-11-06 | 1147054.81 | 489263.5 | 0 | 1633144.84 | 486090.03 | 168 | 144 | 0 | 0 | -24
AUSTIN | 0914-00-479 | TRAVIS | Various | 2025-11-06 | 2491969.22 | 94417.7 | 0 | 3005519.74 | 513550.52 | 300 | 218 | 0 | 0 | -82
CORPUS CHRISTI | 0255-15-005 | JIM WELLS | US 281 | 2025-11-06 | 78425429.64 | 3747770.8 | 0 | 84529180.58 | 6103750.94 | 834 | 906 | 72 | 0 | 72
CORPUS CHRISTI | 0916-02-021 | KLEBERG | CR | 2025-11-06 | 1830905.05 | -6311.07 | 0 | 1818201.88 | -12703.17 | 138 | 215 | 57 | 0 | 77
DALLAS | 2964-10-008 | DALLAS | SL 9 | 2025-11-06 | 77975540.18 | 7050162.1 | 0 | 87820512.74 | 9844972.56 | 738 | 829 | 151 | 0 | 91
FORT WORTH | 0081-01-050 | TARRANT | US 377 | 2025-11-06 | 2055473.49 | -114282.38 | 0 | 1838298.22 | -217175.27 | 192 | 153 | 0 | 0 | -39
HOUSTON | 0500-03-638 | HARRIS | IH 45 | 2025-11-06 | 936472.55 | 0 | 0 | 1055362.65 | 118890.1 | 69 | 78 | 0 | 0 | 9
LUBBOCK | 0905-00-112 | LUBBOCK | Various | 2025-11-06 | 2731558.5 | 0 | 0 | 2631705.9 | -99852.6 | 260 | 270 | 0 | 0 | 10
AMARILLO | 1243-02-031 | DEAF SMITH | FM 1259 | 2025-11-05 | 5827413.2 | 111011.95 | 0 | 5999641.51 | 172228.31 | 145 | 246 | 95 | 0 | 101
FORT WORTH | 0249-05-031 | JACK | US 281 | 2025-11-05 | 25930235.36 | 213533.53 | 0 | 25387199.5 | -543035.86 | 384 | 651 | 267 | 0 | 267
HOUSTON | 0912-00-511 | HARRIS | VA | 2025-11-05 | 1718929.72 | 890496.84 | 14919.76 | 2401487.69 | 667638.21 | 199 | 330 | 190 | 0 | 131
CHILDRESS | 0925-21-009 | FOARD | CR | 2025-11-04 | 699120 | 0 | 0 | 665490 | -33630 | 101 | 88 | 0 | 0 | -13
CORPUS CHRISTI | 0916-28-082 | SAN PATRICIO | COUNTY ROAD 1028 | 2025-11-04 | 867435.5 | 0 | 0 | 901283.5 | 33848 | 106 | 101 | 0 | 0 | -5
LUBBOCK | 0168-01-030 | PARMER | US 60 | 2025-11-04 | 25525377.96 | -428152.02 | 0 | 24890746.55 | -634631.41 | 277 | 663 | 10 | 0 | 386
SAN ANTONIO | 0915-00-269 | BEXAR | Various | 2025-11-04 | 2236322 | 0 | 0 | 1916895.45 | -319426.55 | 257 | 257 | 0 | 0 | 0
CORPUS CHRISTI | 0916-00-228 | NUECES | Various | 2025-11-03 | 5294911.6 | -607618.18 | 0 | 4636673.42 | -658238.18 | 83 | 162 | 79 | 0 | 79
CORPUS CHRISTI | 0916-27-014 | REFUGIO | JW JOHNSON RD | 2025-11-03 | 681681.5 | 0 | 0 | 650522.5 | -31159 | 80 | 95 | 0 | 0 | 15
CORPUS CHRISTI | 0916-28-083 | SAN PATRICIO | RINCON RD | 2025-11-03 | 977756.8 | -1080 | 0 | 971632.8 | -6124 | 102 | 136 | 0 | 0 | 34
EL PASO | 0021-01-059 | BREWSTER | US 90 | 2025-11-03 | 6055674.71 | 317634.38 | 0 | 6342061.49 | 286386.78 | 54 | 36 | 0 | 0 | -18
TYLER | 0495-04-081 | SMITH | IH 20 | 2025-11-03 | 13106220.97 | 1003400.43 | 0 | 14222832.36 | 1116611.39 | 133 | 133 | 0 | 0 | 0
AUSTIN | 0987-03-014 | HAYS | FM 621 | 2025-11-01 | 3199566.89 | 261816.52 | 0 | 3429699.86 | 230132.97 | 154 | 154 | 0 | 0 | 0
BROWNWOOD | 0251-06-041 | LAMPASAS | US | 2025-10-31 | 1066349.58 | 29000 | 0 | 1049055.82 | -17293.76 | 43 | 22 | 0 | 0 | -21
EL PASO | 0002-07-057 | HUDSPETH | IH 10 | 2025-10-31 | 922152.5 | 0 | 0 | 931900.9 | 9748.4 | 80 | 42 | 0 | 0 | -38
ODESSA | 0004-07-144 | ECTOR | IH 20 | 2025-10-31 | 4515761.18 | -3028060.3 | 0 | 1605886.3 | -2909874.88 | 19 | 9 | 0 | 0 | -10
ODESSA | 0021-07-063 | TERRELL | US 90 | 2025-10-31 | 13343819.72 | 0 | 0 | 11914652.87 | -1429166.85 | 84 | 58 | 0 | 0 | -26
ATLANTA | 1231-01-073 | BOWIE | FM 989 | 2025-10-30 | 2429230.47 | 20734.72 | 0 | 2399428.49 | -29801.98 | 69 | 40 | 0 | 0 | -29
HOUSTON | 0912-72-745 | HARRIS | Various | 2025-10-30 | 397218.18 | -20547.42 | 0 | 440696.16 | 43477.98 | 62 | 65 | 0 | 0 | 3
HOUSTON | 3256-01-129 | HARRIS | SL 8 | 2025-10-30 | 405810.67 | 0 | 0 | 438251.89 | 32441.22 | 42 | 41 | 0 | 0 | -1
PARIS | 0901-28-105 | HOPKINS | TIMBER CREEK DR | 2025-10-30 | 562558.51 | 13913.14 | 0 | 573500.52 | 10942.01 | 64 | 54 | 0 | 0 | -10
EL PASO | 0002-01-108 | EL PASO | SH 20 | 2025-10-29 | 8421430.15 | -140252.98 | 0 | 8468727.6 | 47297.45 | 144 | 110 | 0 | 0 | -34
EL PASO | 2552-03-065 | EL PASO | SL 375 | 2025-10-29 | 10150486.7 | 1302188.43 | 0 | 11934394.78 | 1783908.08 | 141 | 149 | 36 | 0 | 8
WACO | 0055-03-028 | CORYELL | US 84 | 2025-10-29 | 7829869.62 | 0 | 0 | 7467029.19 | -362840.43 | 60 | 41 | 0 | 0 | -19
WACO | 0055-04-032 | CORYELL | US 84 | 2025-10-29 | 7926981.1 | 0 | 0 | 7535909.66 | -391071.44 | 90 | 28 | 0 | 0 | -62
WACO | 0231-03-160 | BELL | IH 14 | 2025-10-29 | 1467608.8 | -356538.64 | 0 | 1092958.29 | -374650.51 | 45 | 68 | 0 | 0 | 23
WACO | 2304-02-044 | BELL | FM 2410 | 2025-10-29 | 9585340.6 | -762743.48 | 0 | 8841909.15 | -743431.45 | 150 | 189 | 0 | 0 | 39
HOUSTON | 0338-03-089 | MONTGOMERY | SH 105 | 2025-10-28 | 9828203.29 | 2194421.96 | 0 | 11752414.18 | 1924210.89 | 434 | 467 | 0 | 0 | 33
HOUSTON | 0675-08-120 | MONTGOMERY | IH 45 | 2025-10-28 | 3167865.7 | 227199.56 | 197085.3 | 3615712.46 | 250761.46 | 151 | 150 | 16 | 16 | -17
YOAKUM | 0026-03-046 | FAYETTE | US 90 | 2025-10-28 | 7055348.46 | 86895.53 | 0 | 7362611.07 | 307262.61 | 240 | 291 | 29 | 0 | 51
AUSTIN | 0914-00-532 | TRAVIS | Various | 2025-10-27 | 884147 | -188623.28 | 0 | 673975.05 | -210171.95 | 80 | 81 | 0 | 0 | 1
FORT WORTH | 3559-02-007 | TARRANT | SH 170 | 2025-10-27 | 98999997.28 | 14175893.63 | 0 | 113015999.21 | 14016001.93 | 929 | 1117 | 192 | 0 | 188
ODESSA | 0004-07-139 | ECTOR | IH 20 | 2025-10-27 | 1999084.7 | 2458076.28 | 0 | 4886374.73 | 2887290.03 | 180 | 278 | 130 | 0 | 98
SAN ANTONIO | 0029-02-058 | GUADALUPE | US 90 | 2025-10-27 | 2059647.98 | 63909.18 | 0 | 2250902.23 | 191254.25 | 232 | 229 | 0 | 0 | -3
AUSTIN | 0113-08-091 | TRAVIS | US 290 | 2025-10-24 | 478253 | 8000 | 0 | 489748.05 | 11495.05 | 23 | 22 | 0 | 0 | -1
AUSTIN | 0914-00-485 | TRAVIS | Various | 2025-10-24 | 425581.21 | 121455.78 | 0 | 516949.51 | 91368.3 | 32 | 32 | 0 | 0 | 0
AUSTIN | 2686-01-015 | BASTROP | FM 2571 | 2025-10-24 | 180204 | 25686 | 0 | 211778.6 | 31574.6 | 64 | 34 | 0 | 0 | -30
DALLAS | 2353-02-028 | DENTON | FM 2450 | 2025-10-24 | 9863216.75 | 401492.74 | 0 | 9968771.56 | 105554.81 | 179 | 170 | 0 | 0 | -9
LAREDO | 0922-23-010 | DUVAL | TOVAR ST | 2025-10-24 | 2301233 | 56295.56 | 0 | 2327033.34 | 25800.34 | 148 | 154 | 12 | 0 | 6
SAN ANTONIO | 0915-00-236 | BEXAR | VA | 2025-10-24 | 1421995 | 54949.45 | 0 | 1151015.31 | -270979.69 | 260 | 160 | 0 | 0 | -100
BRYAN | 0917-30-059 | BURLESON | CR | 2025-10-23 | 1827278.8 | 75418.21 | 0 | 1954308.15 | 127029.35 | 278 | 216 | 0 | 0 | -62
CORPUS CHRISTI | 1843-01-023 | GOLIAD | FM 1961 | 2025-10-23 | 2869910.68 | 35081.24 | 0 | 2756367.26 | -113543.42 | 152 | 125 | 0 | 0 | -27
EL PASO | 2121-04-129 | EL PASO | IH 10 | 2025-10-23 | 276338 | 0 | 0 | 265388 | -10950 | 51 | 36 | 0 | 0 | -15
LUFKIN | 0597-02-025 | SAN AUGUSTINE | FM 1277 | 2025-10-23 | 12057157.96 | 280511.22 | 0 | 12330486.69 | 273328.73 | 520 | 259 | 10 | 0 | -261
LAREDO | 0037-10-037 | WEBB | US 83 | 2025-10-22 | 68572893.01 | 164443.32 | 0 | 68489150.69 | -83742.32 | 1049 | 1014 | 0 | 0 | -35
AUSTIN | 0114-03-108 | TRAVIS | US 290 | 2025-10-21 | 304980 | 10344 | 0 | 303481.9 | -1498.1 | 24 | 24 | 0 | 0 | 0
PARIS | 0901-22-128 | HUNT | Various | 2025-10-21 | 544605.6 | 111600 | 0 | 672330 | 127724.4 | 58 | 57 | 0 | 0 | -1
SAN ANTONIO | 0017-05-102 | MEDINA | IH 35 | 2025-10-21 | 16608123.18 | 206632.56 | 0 | 15010805.1 | -1597318.08 | 153 | 148 | 0 | 0 | -5
TYLER | 0205-07-080 | ANDERSON | US 79 | 2025-10-21 | 664721 | 111624 | 0 | 852155.15 | 187434.15 | 18 | 73 | 35 | 0 | 55
YOAKUM | 0089-10-030 | WHARTON | BU 59R | 2025-10-21 | 1257172.3 | -31373.55 | 0 | 1152020.14 | -105152.16 | 60 | 42 | 0 | 0 | -18
YOAKUM | 0913-28-073 | FAYETTE | CR | 2025-10-21 | 1498742.88 | 4659.6 | 0 | 1523631.64 | 24888.76 | 251 | 198 | 0 | 0 | -53
AUSTIN | 0265-05-088 | BASTROP | SH 71 | 2025-10-20 | 1511894.66 | 58780 | 0 | 1539432.52 | 27537.86 | 78 | 102 | 33 | 0 | 24
BROWNWOOD | 0257-05-045 | COMANCHE | SH 6 | 2025-10-20 | 10287230.4 | 1677828.35 | 0 | 12295033.66 | 2007803.26 | 688 | 932 | 280 | 0 | 244
HOUSTON | 0912-72-558 | BRAZORIA | CS | 2025-10-20 | 2503743.9 | 247208.7 | 227169.5 | 2696683.76 | -34229.64 | 171 | 192 | 0 | 0 | 21
HOUSTON | 2950-01-008 | BRAZORIA | FM 2403 | 2025-10-20 | 6034019.34 | 606765.15 | 0 | 6939457.58 | 905438.24 | 288 | 288 | 11 | 0 | 0
SAN ANTONIO | 0017-02-078 | BEXAR | IH 35 | 2025-10-20 | 13319023.16 | 78095.5 | 0 | 13253282.69 | -65740.47 | 243 | 233 | 0 | 0 | -10
SAN ANTONIO | 0024-08-145 | BEXAR | US 90 | 2025-10-20 | 1024954 | 0 | 0 | 1056883 | 31929 | 32 | 27 | 0 | 0 | -5
CORPUS CHRISTI | 0916-25-019 | BEE | CR | 2025-10-17 | 569954.8 | 34734.79 | 0 | 627991.14 | 58036.34 | 87 | 95 | 8 | 0 | 8
DALLAS | 1139-01-048 | ELLIS | FM 813 | 2025-10-17 | 1051513.5 | -44092 | 0 | 937357.2 | -114156.3 | 100 | 123 | 0 | 0 | 23
FORT WORTH | 0249-07-070 | JACK | US 281 | 2025-10-17 | 29571986.47 | -3228881.69 | 0 | 26249779.9 | -3322206.57 | 384 | 406 | 55 | 0 | 22
LUBBOCK | 0905-06-120 | LUBBOCK | Various | 2025-10-17 | 1201509 | 0 | 0 | 1222819.07 | 21310.07 | 200 | 173 | 0 | 0 | -27
PARIS | 0010-02-107 | HOPKINS | IH 30 | 2025-10-17 | 339000 | 57531.74 | 0 | 420493.74 | 81493.74 | 30 | 24 | 0 | 0 | -6
PHARR | 0921-02-500 | HIDALGO | CS | 2025-10-17 | 223433.01 | 3300 | 0 | 211570.47 | -11862.54 | 96 | 95 | 0 | 0 | -1
PHARR | 1065-02-039 | CAMERON | FM 1846 | 2025-10-17 | 3889216.02 | 133165.08 | 0 | 3965529.33 | 76313.31 | 206 | 235 | 36 | 0 | 29
SAN ANTONIO | 0915-12-696 | BEXAR | CS | 2025-10-17 | 1519979.59 | 46362.32 | 0 | 1827686.79 | 307707.2 | 129 | 122 | 0 | 0 | -7
ABILENE | 0908-00-119 | TAYLOR | Various | 2025-10-16 | 1269224 | 292496 | 0 | 1617984.95 | 348760.95 | 171 | 128 | 0 | 0 | -43
ABILENE | 2398-01-055 | TAYLOR | SL 322 | 2025-10-16 | 1032617.5 | -87229 | 0 | 948203.25 | -84414.25 | 73 | 79 | 12 | 0 | 6
BEAUMONT | 1096-01-068 | HARDIN | FM 770 | 2025-10-16 | 4123742.89 | -305926.72 | 0 | 3873436.03 | -250306.86 | 88 | 114 | 0 | 0 | 26
SAN ANTONIO | 2519-01-007 | KENDALL | FM 1621 | 2025-10-16 | 7314033.35 | 547266.93 | 0 | 7843930.05 | 529896.7 | 207 | 365 | 158 | 0 | 158
TYLER | 0392-03-053 | GREGG | US 259 | 2025-10-16 | 3567934.85 | 249696.49 | 0 | 3728920.72 | 160985.87 | 47 | 68 | 37 | 0 | 21
TYLER | 0520-08-071 | ANDERSON | SH 155 | 2025-10-16 | 14607487.28 | 1780678.98 | 0 | 17377494.19 | 2770006.91 | 178 | 368 | 138 | 0 | 190
AUSTIN | 0914-00-468 | TRAVIS | Various | 2025-10-14 | 2342775.6 | 23248.64 | 0 | 2795973.12 | 453197.52 | 300 | 213 | 0 | 0 | -87
SAN ANTONIO | 0678-01-035 | UVALDE | RM 187 | 2025-10-14 | 118630.28 | 0 | 0 | 84060.28 | -34570 | 180 | 51 | 0 | 0 | -129
AMARILLO | 0904-00-214 | POTTER | Various | 2025-10-13 | 640275 | -46215.55 | 0 | 598704.63 | -41570.37 | 51 | 19 | 0 | 0 | -32
FORT WORTH | 0171-05-083 | TARRANT | SH 199 | 2025-10-13 | 2400012.05 | 185847.35 | 0 | 2564892.97 | 164880.92 | 171 | 189 | 36 | 0 | 18
BEAUMONT | 0200-14-093 | JEFFERSON | US 69 | 2025-10-10 | 10175549.2 | -202337.2 | 0 | 10121240.44 | -54308.76 | 279 | 331 | 52 | 0 | 52
DALLAS | 0009-04-074 | ROCKWALL | SH 66 | 2025-10-10 | 4078127 | 32560.14 | 0 | 3472164.99 | -605962.01 | 202 | 287 | 0 | 0 | 85
DALLAS | 0387-05-026 | COLLIN | FM 982 | 2025-10-10 | 5486284.92 | 187155.44 | 0 | 5690874.65 | 204589.73 | 206 | 51 | 0 | 0 | -155
DALLAS | 1014-01-014 | COLLIN | FM 547 | 2025-10-10 | 4898841.15 | 227715.01 | 0 | 4672299.15 | -226542 | 290 | 288 | 117 | 0 | -2
EL PASO | 0001-02-074 | EL PASO | SH 20 | 2025-10-10 | 2000676.72 | 8931.02 | 0 | 1905677.97 | -94998.75 | 97 | 111 | 18 | 0 | 14
FORT WORTH | 0902-90-119 | TARRANT | CS | 2025-10-10 | 1693426 | 14394.33 | 0 | 1658862.61 | -34563.39 | 172 | 304 | 0 | 0 | 132
HOUSTON | 0027-12-097 | FORT BEND | IH 69 | 2025-10-10 | 156029234.9 | 8631638.55 | 181496.07 | 166468031.73 | 10257300.76 | 1045 | 1045 | 0 | 0 | 0
TYLER | 0910-16-181 | SMITH | Various | 2025-10-10 | 143045 | 0 | 0 | 144425 | 1380 | 15 | 10 | 0 | 0 | -5
WACO | 0833-04-042 | MCLENNAN | FM 434 | 2025-10-10 | 6538700.29 | 695848.88 | 0 | 7431822.91 | 893122.62 | 167 | 177 | 10 | 0 | 10
BROWNWOOD | 0923-00-076 | BROWN | Various | 2025-10-09 | 2256036.5 | -225676.75 | 0 | 1988246.54 | -267789.96 | 151 | 238 | 0 | 0 | 87
CORPUS CHRISTI | 0100-05-001 | KARNES | US 181 | 2025-10-09 | 786452.2 | 244766.83 | 0 | 1021986.69 | 235534.49 | 33 | 63 | 30 | 0 | 30
CORPUS CHRISTI | 0102-01-125 | NUECES | SH 44 | 2025-10-09 | 9412810.6 | 194532.47 | 0 | 8774188.47 | -638622.13 | 48 | 15 | 0 | 0 | -33
CORPUS CHRISTI | 0916-35-230 | NUECES | CS | 2025-10-09 | 649400.62 | 7896.36 | 0 | 669812.16 | 20411.54 | 75 | 74 | 0 | 0 | -1
SAN ANGELO | 0070-02-099 | TOM GREEN | US 87 | 2025-10-09 | 4084306.03 | 54247.57 | 0 | 4233235.61 | 148929.58 | 302 | 271 | 0 | 0 | -31
WACO | 3030-01-010 | HILL | FM 2959 | 2025-10-09 | 12787365.87 | -451072.14 | 0 | 12405544.72 | -381821.15 | 202 | 216 | 16 | 0 | 14
AUSTIN | 0115-02-019 | CALDWELL | FM 20 | 2025-10-08 | 2629208.43 | -48093.28 | 0 | 2668378.38 | 39169.95 | 55 | 37 | 0 | 0 | -18
SAN ANTONIO | 0915-00-297 | BEXAR | Various | 2025-10-08 | 2542203 | 404673.15 | 0 | 2947902.19 | 405699.19 | 255 | 220 | 0 | 0 | -35
WACO | 2060-01-037 | MCLENNAN | FM 2113 | 2025-10-08 | 15387558.27 | 170493.16 | 0 | 15722383 | 334824.73 | 510 | 545 | 0 | 0 | 35
CORPUS CHRISTI | 0691-01-040 | KARNES | FM 81 | 2025-10-07 | 7699689.26 | 313342.69 | 0 | 7950842.75 | 251153.49 | 232 | 452 | 116 | 0 | 220
HOUSTON | 0027-09-109 | HARRIS | UA 90 | 2025-10-07 | 583946.47 | 0 | 0 | 682615.6 | 98669.13 | 68 | 90 | 0 | 0 | 22
HOUSTON | 0188-06-046 | BRAZORIA | SH 36 | 2025-10-07 | 32995991.98 | 4090682.22 | 0 | 36460751.54 | 3464759.56 | 719 | 551 | 0 | 0 | -168
CORPUS CHRISTI | 0516-02-031 | GOLIAD | SH 239 | 2025-10-06 | 10110262.66 | 71521.18 | 0 | 9625700.27 | -484562.39 | 225 | 312 | 88 | 0 | 87
CORPUS CHRISTI | 0916-29-013 | LIVE OAK | CR | 2025-10-06 | 2976567.67 | 0 | 0 | 2909284.21 | -67283.46 | 243 | 243 | 0 | 0 | 0
CORPUS CHRISTI | 1087-01-018 | JIM WELLS | FM 738 | 2025-10-06 | 1993021.55 | -136084.38 | 0 | 1775122.23 | -217899.32 | 136 | 100 | 0 | 0 | -36
DALLAS | 1047-03-079 | DALLAS | FM 1382 | 2025-10-06 | 4250000 | 0 | 0 | 4105281.22 | -144718.78 | 203 | 201 | 0 | 0 | -2
TYLER | 0910-16-166 | SMITH | Various | 2025-10-06 | 925714 | 3385 | 0 | 940081 | 14367 | 63 | 53 | 0 | 0 | -10
YOAKUM | 0267-04-015 | FAYETTE | FM 1295 | 2025-10-04 | 1561096.62 | 0 | 0 | 1589261.89 | 28165.27 | 105 | 95 | 0 | 0 | -10
YOAKUM | 0535-05-037 | GONZALES | IH 10 | 2025-10-04 | 12470411.24 | 1017822.37 | 0 | 13841641.18 | 1371229.94 | 180 | 211 | 31 | 0 | 31
FORT WORTH | 0902-90-211 | TARRANT | CS | 2025-10-03 | 565876 | 7772 | 0 | 569984.37 | 4108.37 | 200 | 176 | 0 | 0 | -24
CORPUS CHRISTI | 0101-04-127 | SAN PATRICIO | US 181 | 2025-10-02 | 1040322.35 | 25080.95 | 0 | 1032452.15 | -7870.2 | 76 | 118 | 42 | 0 | 42
DALLAS | 0092-02-135 | DALLAS | IH 45 | 2025-10-02 | 7294650.85 | 250240 | 0 | 7132203.61 | -162447.24 | 189 | 188 | 0 | 0 | -1
HOUSTON | 1524-01-076 | BRAZORIA | SH 332 | 2025-10-02 | 4549092.53 | -23709.32 | 0 | 4569911.27 | 20818.74 | 270 | 375 | 0 | 0 | 105
LAREDO | 0086-09-042 | DUVAL | SH 359 | 2025-10-02 | 447151.9 | 39891.74 | 0 | 500119.16 | 52967.26 | 48 | 47 | 0 | 0 | -1
ODESSA | 0906-00-257 | ECTOR | Various | 2025-10-02 | 850900 | 144713.5 | 0 | 974251.19 | 123351.19 | 106 | 117 | 70 | 0 | 11
AMARILLO | 0066-05-065 | MOORE | US 87 | 2025-10-01 | 36800373.98 | 1069863.33 | 0 | 37945951.81 | 1145577.83 | 838 | 703 | 0 | 0 | -135
DALLAS | 0261-01-050 | ELLIS | US 67 | 2025-10-01 | 11275366.65 | 1057615.78 | 0 | 12013032.66 | 737666.01 | 189 | 180 | 0 | 0 | -9
SAN ANTONIO | 0073-02-088 | BEXAR | US 281 | 2025-10-01 | 1472160.93 | 0 | 0 | 1322737.78 | -149423.15 | 97 | 41 | 0 | 0 | -56
WACO | 2506-01-045 | MCLENNAN | FM 1695 | 2025-10-01 | 463681 | 41680 | 0 | 511531 | 47850 | 60 | 71 | 10 | 0 | 11
ATLANTA | 0218-01-108 | BOWIE | US 59 | 2025-09-30 | 2402680.34 | 122529.56 | 0 | 2580695.9 | 178015.56 | 69 | 72 | 12 | 0 | 3
HOUSTON | 0027-13-238 | HARRIS | IH 69 | 2025-09-30 | 7540358.23 | -476070.35 | 0 | 7183976.97 | -356381.26 | 92 | 187 | 0 | 0 | 95
PHARR | 0862-02-020 | HIDALGO | FM 1427 | 2025-09-30 | 8895309.4 | 67313.52 | 0 | 7930172.48 | -965136.92 | 120 | 99 | 0 | 0 | -21
SAN ANTONIO | 0915-00-254 | BEXAR | Various | 2025-09-30 | 1347419.72 | 38500 | 0 | 1448018.5 | 100598.78 | 260 | 126 | 0 | 0 | -134
TYLER | 0164-01-075 | HENDERSON | BS 31H | 2025-09-30 | 2266623.5 | 0 | 0 | 2049106.05 | -217517.45 | 117 | 172 | 0 | 0 | 55
TYLER | 0245-01-037 | VAN ZANDT | SH 64 | 2025-09-30 | 2231132.05 | 304297.03 | 0 | 2595965.48 | 364833.43 | 120 | 123 | 0 | 0 | 3
TYLER | 0606-01-007 | SMITH | PR 16 | 2025-09-30 | 2399846 | 197515.88 | 0 | 2488504.23 | 88658.23 | 77 | 320 | 246 | 0 | 243
WACO | 0049-01-095 | MCLENNAN | SH 6 | 2025-09-30 | 22852587.83 | -419113.75 | 0 | 24445727.2 | 1593139.37 | 120 | 173 | 45 | 0 | 53
LUFKIN | 0911-00-136 | ANGELINA | Various | 2025-09-29 | 2561303.75 | 45375.15 | 0 | 2719624.62 | 158320.87 | 142 | 141 | 39 | 0 | -1
AUSTIN | 0914-33-091 | HAYS | CS | 2025-09-26 | 737549.46 | -52236 | 0 | 703890.8 | -33658.66 | 30 | 10 | 0 | 0 | -20
HOUSTON | 0271-14-240 | HARRIS | IH 610 | 2025-09-26 | 848116 | 22453.03 | 0 | 813837.1 | -34278.9 | 67 | 66 | 0 | 0 | -1
ABILENE | 0318-01-034 | JONES | SH 92 | 2025-09-25 | 6794417.72 | 0 | 0 | 6896410.13 | 101992.41 | 108 | 87 | 0 | 0 | -21
ATLANTA | 1226-02-016 | TITUS | FM 1735 | 2025-09-25 | 11920527.81 | -439143.06 | 0 | 11509691.1 | -410836.71 | 276 | 299 | 29 | 0 | 23
FORT WORTH | 0902-90-329 | TARRANT | Various | 2025-09-25 | 896115.5 | 124305 | 0 | 1030453 | 134337.5 | 156 | 95 | 0 | 0 | -61
HOUSTON | 0543-01-067 | WALLER | FM 359 | 2025-09-25 | 13133459.07 | -36381.2 | 0 | 14241333.02 | 1107873.95 | 196 | 205 | 9 | 0 | 9
LAREDO | 0022-09-055 | VAL VERDE | US 90 | 2025-09-25 | 17895331.2 | -234189.5 | 0 | 18267488.95 | 372157.75 | 238 | 228 | 0 | 0 | -10
LAREDO | 0299-01-079 | VAL VERDE | SS 297 | 2025-09-25 | 899114.7 | 1494.98 | 0 | 927530.41 | 28415.71 | 97 | 28 | 0 | 0 | -69
ODESSA | 1718-07-045 | MIDLAND | SH 349 | 2025-09-25 | 10681716.81 | 77133.84 | 0 | 11217409.12 | 535692.31 | 175 | 212 | 45 | 0 | 37
WICHITA FALLS | 0124-02-035 | WILBARGER | US 283 | 2025-09-25 | 5643664.87 | -663013.73 | 0 | 5090849.1 | -552815.77 | 119 | 114 | 0 | 0 | -5
BEAUMONT | 2952-01-009 | HARDIN | FM 2937 | 2025-09-24 | 8441473.15 | 0 | 0 | 7950010.91 | -491462.24 | 133 | 99 | 0 | 0 | -34
FORT WORTH | 0902-50-143 | JOHNSON | Various | 2025-09-24 | 730197.55 | 0 | 0 | 700328.8 | -29868.75 | 108 | 87 | 42 | 0 | -21
SAN ANTONIO | 0016-08-047 | BEXAR | SL 368 | 2025-09-24 | 10495723.55 | 452455.6 | 0 | 10879411.45 | 383687.9 | 245 | 209 | 0 | 0 | -36
SAN ANTONIO | 1728-02-066 | COMAL | FM 306 | 2025-09-24 | 91305 | 18072.87 | 0 | 109266.87 | 17961.87 | 56 | 53 | 0 | 0 | -3
AUSTIN | 0914-00-484 | TRAVIS | Various | 2025-09-23 | 423846.07 | -20868.66 | 0 | 409260.81 | -14585.26 | 35 | 33 | 0 | 0 | -2
BRYAN | 0675-02-099 | FREESTONE | IH 45 | 2025-09-23 | 4884358.45 | 479305.64 | 0 | 5327344.79 | 442986.34 | 120 | 124 | 6 | 0 | 4
HOUSTON | 0912-73-215 | GALVESTON | Various | 2025-09-23 | 7167628.34 | 538335.96 | 0 | 8206287.66 | 1038659.32 | 320 | 299 | 0 | 0 | -21
HOUSTON | 2633-01-014 | HARRIS | FM 526 | 2025-09-23 | 1067872.27 | -99102.61 | 0 | 1061850.63 | -6021.64 | 42 | 19 | 0 | 0 | -23
PHARR | 0921-02-520 | HIDALGO | CS | 2025-09-23 | 241811.09 | 0 | 0 | 251708.74 | 9897.65 | 34 | 30 | 0 | 0 | -4
TYLER | 0058-04-022 | CHEROKEE | SH 294 | 2025-09-23 | 3018317.59 | 388107.3 | 0 | 3298412.47 | 280094.88 | 114 | 132 | 0 | 0 | 18
BRYAN | 0578-03-055 | WALKER | SH 150 | 2025-09-22 | 1514150.75 | 124284.87 | 0 | 1636934.09 | 122783.34 | 65 | 63 | 0 | 0 | -2
PHARR | 1236-01-015 | WILLACY | FM 1018 | 2025-09-22 | 12441758.7 | 33934.64 | 0 | 12315719.29 | -126039.41 | 379 | 434 | 55 | 0 | 55
SAN ANTONIO | 1135-03-030 | KERR | FM 1341 | 2025-09-22 | 1193211 | -45276 | 0 | 1223719.14 | 30508.14 | 52 | 52 | 0 | 0 | 0
TYLER | 0163-03-052 | HENDERSON | SH 31 | 2025-09-22 | 2061802.3 | 152159 | 0 | 2230277.03 | 168474.73 | 78 | 64 | 0 | 0 | -14
TYLER | 0910-00-122 | SMITH | Various | 2025-09-22 | 1698784.97 | 9636.29 | 0 | 1722481.65 | 23696.68 | 51 | 107 | 46 | 0 | 56
ATLANTA | 0610-03-100 | TITUS | IH 30 | 2025-09-20 | 6534113.55 | 54619.73 | 0 | 6833972.36 | 299858.81 | 528 | 705 | 86 | 0 | 177
BRYAN | 2851-01-051 | BRAZOS | FM 2818 | 2025-09-19 | 1902556.39 | 363463.49 | 0 | 2309830.95 | 407274.56 | 104 | 122 | 22 | 0 | 18
SAN ANTONIO | 0291-06-062 | BANDERA | SH 16 | 2025-09-19 | 5064944.51 | 332192.36 | 0 | 5552490.04 | 487545.53 | 193 | 192 | 0 | 0 | -1
TYLER | 0910-08-064 | ANDERSON | PW | 2025-09-19 | 170873.75 | 41184.47 | 0 | 222394.81 | 51521.06 | 26 | 25 | 0 | 0 | -1
ABILENE | 0972-03-021 | JONES | FM 1082 | 2025-09-18 | 8867738.98 | 625327.5 | 0 | 9377623.83 | 509884.85 | 261 | 261 | 0 | 0 | 0
AUSTIN | 0071-04-057 | MASON | US 87 | 2025-09-17 | 6987836.95 | 91498.41 | 0 | 7079093.16 | 91256.21 | 113 | 141 | 10 | 0 | 28
YOAKUM | 0913-09-089 | WHARTON | CR | 2025-09-17 | 3985642.3 | 19546.28 | 0 | 3986361.4 | 719.1 | 352 | 401 | 4 | 0 | 49
YOAKUM | 2524-01-011 | MATAGORDA | FM 2611 | 2025-09-17 | 2706168.98 | 11366.45 | 0 | 2725460.57 | 19291.59 | 90 | 94 | 2 | 0 | 4
LUFKIN | 0109-03-044 | HOUSTON | US 287 | 2025-09-16 | 11224367.45 | -156332.95 | 0 | 11305474.16 | 81106.71 | 140 | 138 | 0 | 0 | -2
ODESSA | 0354-01-056 | WINKLER | SH 115 | 2025-09-16 | 2658948.35 | -218789.34 | 0 | 2461379.24 | -197569.11 | 90 | 45 | 0 | 0 | -45
TYLER | 0910-16-154 | SMITH | CR | 2025-09-16 | 468056.5 | 0 | 0 | 458097.58 | -9958.92 | 59 | 59 | 0 | 0 | 0
CORPUS CHRISTI | 1122-02-042 | KARNES | FM 887 | 2025-09-15 | 7291794.07 | 149111.22 | 0 | 7149709.53 | -142084.54 | 199 | 205 | 10 | 0 | 6
HOUSTON | 0912-72-642 | HARRIS | CS | 2025-09-15 | 1234892.41 | 125618.4 | 125618.4 | 1290196.68 | -70314.13 | 120 | 120 | 0 | 0 | 0
LAREDO | 0017-08-096 | LA SALLE | IH 35 | 2025-09-15 | 11436092.12 | 3856893.76 | 0 | 15811766.95 | 4375674.83 | 455 | 683 | 236 | 0 | 228
LAREDO | 0922-00-077 | VAL VERDE | Various | 2025-09-15 | 2156160.21 | 58628.5 | 0 | 2246179.88 | 90019.67 | 110 | 110 | 0 | 0 | 0
PHARR | 0921-02-465 | HIDALGO | CR | 2025-09-15 | 5092399 | 154115.99 | 0 | 5208487.42 | 116088.42 | 160 | 205 | 45 | 0 | 45
BEAUMONT | 0883-02-091 | ORANGE | FM 408 | 2025-09-12 | 4993301.06 | 17447.79 | 0 | 4942996.37 | -50304.69 | 78 | 90 | 7 | 0 | 12
HOUSTON | 0508-01-356 | HARRIS | IH 10 | 2025-09-12 | 4844982.3 | 103019.81 | 0 | 5598642.75 | 753660.45 | 450 | 445 | 0 | 0 | -5
HOUSTON | 3510-05-043 | HARRIS | SH 99 | 2025-09-12 | 9799999.16 | 1410485.45 | 0 | 11478802.07 | 1678802.91 | 275 | 425 | 159 | 0 | 150
PARIS | 0610-02-065 | FRANKLIN | IH 30 | 2025-09-12 | 564885 | -27300 | 0 | 509147.16 | -55737.84 | 61 | 32 | 0 | 0 | -29
SAN ANTONIO | 0291-10-114 | BEXAR | SH 16 | 2025-09-11 | 17256832.1 | 436602.29 | -109083.34 | 17932866.65 | 785117.89 | 392 | 449 | 72 | 10 | 47
BEAUMONT | 0601-04-013 | LIBERTY | FM 1009 | 2025-09-10 | 3702741.54 | 9385 | 0 | 3640875.07 | -61866.47 | 90 | 53 | 0 | 0 | -37
DALLAS | 0581-02-124 | DALLAS | SL 12 | 2025-09-09 | 301097341.18 | 1046921.66 | -50342.13 | 308313143.82 | 7266144.77 | 1108 | 1218 | 110 | 0 | 110
FORT WORTH | 0094-02-146 | TARRANT | SH 183 | 2025-09-09 | 323183 | 0 | 0 | 311025.25 | -12157.75 | 86 | 63 | 0 | 0 | -23
HOUSTON | 0110-06-144 | HARRIS | IH 45 | 2025-09-09 | 1115889.75 | 869247.02 | 0 | 2157543.77 | 1041654.02 | 137 | 222 | 99 | 0 | 85
SAN ANTONIO | 0915-00-238 | BEXAR | VA | 2025-09-09 | 1675784.44 | 527023.51 | 247009.83 | 2229395.23 | 306600.96 | 290 | 344 | 63 | 23 | 31
TYLER | 0096-04-071 | GREGG | US 80 | 2025-09-09 | 3878619.61 | -79299.74 | 0 | 3725310.76 | -153308.85 | 79 | 146 | 0 | 0 | 67
HOUSTON | 0912-72-746 | HARRIS | Various | 2025-09-08 | 4990800.71 | 0 | 0 | 5440514.57 | 449713.86 | 150 | 180 | 0 | 0 | 30
PHARR | 1137-01-031 | CAMERON | FM 801 | 2025-09-08 | 6481370.35 | 19374.02 | 0 | 5971255.55 | -510114.8 | 100 | 95 | 0 | 0 | -5
DALLAS | 2374-07-077 | DALLAS | IH 635 | 2025-09-05 | 3487274.77 | 106816.31 | 0 | 3696094.93 | 208820.16 | 119 | 138 | 10 | 0 | 19
HOUSTON | 0178-01-037 | HARRIS | SH 35 | 2025-09-05 | 313438.45 | 46271.57 | 0 | 427249.37 | 113810.92 | 38 | 33 | 0 | 0 | -5
PHARR | 0255-03-040 | BROOKS | US 281 | 2025-09-05 | 614388.45 | -18917.63 | 0 | 578034.12 | -36354.33 | 80 | 80 | 0 | 0 | 0
SAN ANTONIO | 0142-06-029 | KENDALL | SH 27 | 2025-09-05 | 3751987.9 | 505348.4 | 0 | 4214798.53 | 462810.63 | 111 | 135 | 32 | 0 | 24
ABILENE | 0053-17-037 | SCURRY | US 180 | 2025-09-04 | 2179456.14 | 397663.39 | 0 | 2632644.43 | 453188.29 | 51 | 21 | 0 | 0 | -30
AUSTIN | 0986-01-046 | WILLIAMSON | FM 619 | 2025-09-04 | 1365940 | 149876.1 | 0 | 1425187.7 | 59247.7 | 52 | 111 | 0 | 0 | 59
HOUSTON | 3510-06-025 | HARRIS | SH 99 | 2025-09-04 | 3179979.15 | 0 | 0 | 3150635.46 | -29343.69 | 210 | 198 | 0 | 0 | -12
ODESSA | 0380-09-098 | MIDLAND | BS 349C | 2025-09-04 | 17997658.13 | 319468.58 | 0 | 17665645.47 | -332012.66 | 300 | 323 | 47 | 0 | 23
HOUSTON | 0912-71-003 | HARRIS | CS | 2025-09-03 | 12380276.54 | 2232319.34 | 2232319.34 | 14758074.72 | 145478.84 | 360 | 706 | 225 | 148 | 198
SAN ANTONIO | 0017-01-026 | BEXAR | SL 353 | 2025-09-03 | 6922525.53 | 175989.07 | 0 | 6519659.16 | -402866.37 | 93 | 80 | 0 | 0 | -13
TYLER | 0520-06-043 | SMITH | SH 155 | 2025-09-03 | 16954295.26 | 557604.01 | 0 | 17734771.39 | 780476.13 | 264 | 264 | 0 | 0 | 0
YOAKUM | 0089-11-007 | JACKSON | SL 521 | 2025-09-03 | 1430378 | 7070 | 0 | 1529833.48 | 99455.48 | 180 | 179 | 0 | 0 | -1
YOAKUM | 0268-01-056 | FAYETTE | US 77 | 2025-09-03 | 3760967.65 | 399656.98 | 0 | 4076348.4 | 315380.75 | 120 | 120 | 0 | 0 | 0
YOAKUM | 0942-02-011 | GONZALES | FM 2067 | 2025-09-03 | 2478717.67 | 18082.39 | 0 | 2513275.77 | 34558.1 | 184 | 247 | 42 | 0 | 63
ATLANTA | 0096-07-054 | HARRISON | US 80 | 2025-09-02 | 6333886.66 | 18215.9 | 0 | 6557384.77 | 223498.11 | 128 | 187 | 0 | 0 | 59
BEAUMONT | 2951-01-009 | CHAMBERS | FM 2936 | 2025-09-02 | 1564314.75 | 150124.45 | 0 | 1692338.33 | 128023.58 | 97 | 63 | 6 | 0 | -34
BROWNWOOD | 0272-05-033 | LAMPASAS | US 190 | 2025-09-02 | 6287281 | 90237.96 | 0 | 6618499.71 | 331218.71 | 162 | 221 | 60 | 0 | 59
HOUSTON | 0367-06-064 | GALVESTON | SH 87 | 2025-09-02 | 4615527 | 288877.09 | 0 | 5147874.1 | 532347.1 | 278 | 655 | 377 | 0 | 377
WACO | 0320-02-039 | BELL | SH 95 | 2025-09-02 | 11989343.7 | -229086.93 | 0 | 12009750.13 | 20406.43 | 360 | 352 | 0 | 0 | -8