## Instructions
Project Audit Template |  |  |  | Districts | Program | Port
|  |  |  | Beaumont | MIP88 | Beaumont | Yes
|  |  |  | Corpus Christi | SCP88 | Calhoun | No
| Project records are required to be reviewed to verify project compliance with program requirements and work performance according to the plans and specifications. Audits will be performed by the Maritime Division and based on a set schedule. The initial audit will be performed within the first 6 months from when time starts, annually, and at Final. |  |  | Houston | Rider 37 | Corpus | N/A
|  |  |  | Pharr | Rider 38 | Freeport | Complete
|  |  |  | Yoakum | Rider 45 | Houston | Incomplete
[6 empty] | Port Isabel | Requested
Orange
| Time Start Date: |  | Make copies of green tab "Annual (Blank)" by right clicking on the sheet below and select Move or Copy; once created, rename the new copy as YY.MM.DD Annual |  |  | Port PA
6 month Initial Due: | [5 empty] | Harlingen
Annual Due: | [5 empty] | Mansfield
| continue annual audits until Final |  |  |  |  | Palacios
Victoria
| The LG is responsible for the day-to-day activity of the construction project records. The LG can complete self-audits and reviews using the Line Item Review Form. During monthly estimate processing, the LG should review whether all pay quantities are accurate. It is highly recommended that the LG use this Audit template as a tool prior to the scheduled audit. |  |  |  |  | West Calhoun
Sabine Pass
City PA
Harris Co
Brownsville
Galveston
Texas City
| Once an audit is completed by the Maritime Division, ensure to complete the following: |  |  |  |  | Anahuac
| (save the Excel file as a working copy at the MRD level) |  |  |  |  | Bay City
| 1 | Save as a PDF to add signatures |  |  |  | Cedar Port
| 2 | MRD forward a copy to LG so discrepancies can be addressed (make any updates to PDF doc)
| 3 | MRD & LG Audit and supporting correspondence to project folder
Additional Resources:

## 6 Month Initial
Initial
CSJ: |  |  | Project: |  | Port: |  |  | Program:
District: |  |  | PM: |  | Audited by: |  |  | Date:
1 | PROJECT INITIATION
1.1.0 | Project kickoff meeting |  |  |  | Date
1.1.1 | Project Information Form |  |  |  | Date
1.2.0 | Oversight Level Special Approval
1.3.0 | TxDOT Funding Agreement |  |  |  | Amendments?
1.3.1 | Other Gov agency agreeements?
If yes, list parties, date executed,and reason for agreement:
|  | Name: |  |  | Executed: |  |  | Reason:
|  | Name: |  |  | Executed: |  |  | Reason:
|  | Name: |  |  | Executed: |  |  | Reason:
1.4.0 | Procurement/Letting Policies
1.5.0 | Project Level Signature Authority |  |  |  | Amendments?
Comments
2 | PROJECT DEVELOPMENT
2.1.0 | Project status meeting records.
| Number of monthly status meetings occurred? |  |  |  |  | Number on file?
2.2.0 | Project design schedules maintained?
2.3.0 | Project Plans Maintained?:
30%
60%
90%
Final
2.4.0 | Is TDLR required?
| TDLR-RAS Plan Review |  |  |  |  | Date of Approval:
2.5.0 | Are there any design exceptions?
|  | Exception: |  |  |  | Reason:
|  | Exception: |  |  |  | Reason:
|  | Exception: |  |  |  | Reason:
2.6.0 | FAA Approval Notice of Proposed Construction/Alteration - Form 7460-1
2.7.0 | Is a RRUE Certification on file?
2.7.1 | ROW Acquisition |  |  |  |  | Records Maintained?
2.7.2 | Right of Entry (ROE)
|  | Name: |  |  |  | Date of Approval:
|  | Name: |  |  |  | Date of Approval:
|  | Name: |  |  |  | Date of Approval:
2.7.3 | Railroad Agreements
|  | Name: |  |  |  | Date of Execution:
|  | Name: |  |  |  | Date of Execution:
2.7.4 | Utilities |  |  |  | Who is completing work?
2.7.5 | Enviromental (EPIC) |  |  |  |  | Records Maintained?
2.8.0 | Bid Specs
2.8.1 | Letting Schedule
2.8.2 | Engineers Estimate
Comments
3 | LETTING AND AWARD
3.1.0 | MRD Ready to Let Approval |  |  |  |  | Date of Approval:
3.2.0 | Advertising |  |  |  | Proof of Ads Maintained?:
3.2.1 | Was a Pre-Bid Meeting held?
If yes, list date held (ensure documents on file to support).
Pre-Bid Q&A on file?
3.2.2 | Were there addendum
MRD Approval of Addendum
3.2.3 | Bid Opening |  |  |  |  | Sign in Sheet on file?
3.2.4 | Bid Tabulations
3.2.5 | Bid Analysis
3.3.0 | Letter of Recommendation
3.3.1 | Governing Board Approval |  |  |  |  | Date of Approval:
3.3.2 | MRD CCC
3.3.3 | MRD Award Concurrance |  |  |  |  | Date of Approval:
3.4.0 | Notice of Award (NOA) |  |  |  |  | Date of Award:
Comments:
4 | PROJECT CONSTRUCTION - PRE-CONSTRUCTION ACTIVITIES
4.1.0 | Prime Contract on file?
Debarment certification?
4.1.1 | Proof of bonds?
4.1.2 | Does project have any Railroad Agreements:
RR insurance date of expiration?
4.2.0 | Number of APPROVED Subcontractors for Project?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
4.2.1 | Are there any unapproved Subcontractors at this time?
If yes, document the name and brief reason why the subcontractor is currently not approved.
| Name: |  |  |  | Reason:
| Name: |  |  |  | Reason:
| Name: |  |  |  | Reason:
4.3.0 | Pre-Construction Meeting held?
Date Preconstruction Meeting was held?
4.3.1 | TIME-How are working days charged (calendar day, working day, etc.) for the contract?
4.3.2 | Baseline Schedule retained?
4.3.3 | Is there a Contract Time Statement Report?
4.3.4 | Are time entries in accordance with the contract?
4.3.5 | Original Contract Days: |  |  | Added Days: |  |  | Days charged to date:
4.3.6 | Has the project been in Time Suspension?
If yes, is all documentation on file to justify the date(s)?
4.4.0 | Notice to Proceed on file?
Comments:
5 | PROJECT CONSTRUCTION - CONSTRUCTION FIELD ACTIVITIES
5.1.0 | Inspections: Daily Work Reports (DWR) maintained?
First DWR Date?
| DAY Reports required to date? |  |  |  |  | DAY Reports on file?
| NIGHT Reports required to date? |  |  |  | NIGHT Reports on file?
5.1.1 | Are SW3P records being maintained?
Review SWP3 Guidance
5.1.2 | Are SW3P inspection reports maintained?
| Date of first inspection? |  |  | Date of latest inspection?
5.1.2 | Are there any traffic control plans?
| Barricade inspections? |  |  | Date of latest inspection?
5.2.0 | Quality Assurance Program (QAP)
5.2.1 | Is a 3rd party Lab being used for the project?
5.2.2 | Are materials tested in compliance with the QAP?
5.3.0 | Project construction meetings? |  |  |  |  | Meeting Frequency
If yes, ensure meeting minutes, notes and sign in sheets are properly dated and filed in project records.
5.4.0 | Designated Material Source/Disposal Sites
If applicable, is there MRD concurrance?
5.5.0 | Is project substantially complete?
5.5.1 | Was a substantial completion meeting held?
|  | Date: |  | MRD Attendance?
5.5.2 | Was a punch list developed?
Were all items addressed?
5.5.3 | Was a final walkthrough scheduled?
|  | Date: |  | MRD Attendance?
Comments:
6 | PROJECT CONSTRUCTION - FISCAL RECORDS
6.1.0 | Invoices - is a detail record of project accounting maintained?
6.1.1 | Has a construction pay app been generated for each month since the NTP?
| Number of pay apps on file? |  |  |  | Are all pay apps signed?
6.1.2 | Is proof of payment maintained?
6.1.3 | Were all invoices paid in compliance with Prompt Payment requirements?
6.2.0 | A 10% audit of construction pay apps is required.
Are field measurements maintained to support work and materials?
Delivery tickets
Test Results
Material Counts
6.3.0 | Has a reimbursement request been submitted for each month since the NTP?
6.3.1 | Were requests submitted within 90 days of when the project began and costs incurred.
6.3.2 | Was payment submitted to contractor prior to submittal?
6.4.0 | Does the project utilize Material on Hand?
6.4.1 | Request for Material on Hand Summary Sheet - Form 1914
6.4.2 | Request for Payment of Material on Hand - Form 1915
6.4.3 | Monthly submittals until depleted?
6.4.4 | Method of verification of MOH?
6.4.5 | Paid invoices for materials.
6.5.0 | Change Orders-All Correspondence and Approved or Unapproved Cos
| Current number of COs? |  |  | Approved COs? |  |  |  | Unapproved COs?
Is the MRD CO form completed for each CO?
Comments:
A | Additional Items to Review during Audit:
A.1 | Monthly Progress Reports on file?
| Number of monthly progress reports required to date? | [5 empty] | Number on file?
A.2 | Contractor requests for information maintained? | [5 empty] | Number on file?
A.3 | Required notifications maintained:
Other Agencies
Home Owners
Stakeholders
|  | Name: |  |  |  | Reason:
|  | Name: |  |  |  | Reason:
|  | Name: |  |  |  | Reason:
Comments:
Additional AUDIT Comments:
All discrepancies should be reviewed and addressed within 30 days of notification or finding.
Reviewer Signature: |  |  |  |  | Completed Date:

## Annual (Template)
Annual | [8 empty] | Use this blank copy to create a new template each year by right clicking on the sheet tab below and select Move or Copy, select create a copy; once created, rename the new copy as YYYYMMDD Annual
CSJ: |  |  | Project: |  | Port: |  |  | Program:
District: |  |  | PM: |  | Audited by: |  |  | Date:
1 | PROJECT INITIATION
1.1.0 | Project kickoff meeting |  |  |  | Date
1.1.1 | Project Information Form |  |  |  | Date
1.2.0 | Oversight Level Special Approval
1.3.0 | TxDOT Funding Agreement |  |  |  | Amendments?
1.3.1 | Other Gov agency agreeements?
If yes, list parties, date executed,and reason for agreement:
|  | Name: |  |  | Executed: |  |  | Reason:
|  | Name: |  |  | Executed: |  |  | Reason:
|  | Name: |  |  | Executed: |  |  | Reason:
1.4.0 | Procurement/Letting Policies
1.5.0 | Project Level Signature Authority |  |  |  | Amendments?
Comments
2 | PROJECT DEVELOPMENT
2.1.0 | Project status meeting records.
| Number of monthly status meetings occurred? |  |  |  |  | Number on file?
2.2.0 | Project design schedules maintained?
2.3.0 | Project Plans Maintained?:
30%
60%
90%
Final
2.4.0 | Is TDLR required?
| TDLR-RAS Plan Review |  |  |  |  | Date of Approval:
2.5.0 | Are there any design exceptions?
|  | Exception: |  |  |  | Reason:
|  | Exception: |  |  |  | Reason:
|  | Exception: |  |  |  | Reason:
2.6.0 | FAA Approval Notice of Proposed Construction/Alteration - Form 7460-1
2.7.0 | Is a RRUE Certification on file?
2.7.1 | ROW Acquisition |  |  |  |  | Records Maintained?
2.7.2 | Right of Entry (ROE)
|  | Name: |  |  |  | Date of Approval:
|  | Name: |  |  |  | Date of Approval:
|  | Name: |  |  |  | Date of Approval:
2.7.3 | Railroad Agreements
|  | Name: |  |  |  | Date of Execution:
|  | Name: |  |  |  | Date of Execution:
2.7.4 | Utilities |  |  |  | Who is completing work?
2.7.5 | Enviromental (EPIC) |  |  |  |  | Records Maintained?
2.8.0 | Bid Specs
2.8.1 | Letting Schedule
2.8.2 | Engineers Estimate
Comments
3 | LETTING AND AWARD
3.1.0 | MRD Ready to Let Approval |  |  |  |  | Date of Approval:
3.2.0 | Advertising |  |  |  | Proof of Ads Maintained?:
3.2.1 | Was a Pre-Bid Meeting held?
If yes, list date held (ensure documents on file to support).
Pre-Bid Q&A on file?
3.2.2 | Were there addendum
MRD Approval of Addendum
3.2.3 | Bid Opening |  |  |  |  | Sign in Sheet on file?
3.2.4 | Bid Tabulations
3.2.5 | Bid Analysis
3.3.0 | Letter of Recommendation
3.3.1 | Governing Board Approval |  |  |  |  | Date of Approval:
3.3.2 | MRD CCC
3.3.3 | MRD Award Concurrance |  |  |  |  | Date of Approval:
3.4.0 | Notice of Award (NOA) |  |  |  |  | Date of Award:
Comments:
4 | PROJECT CONSTRUCTION - PRE-CONSTRUCTION ACTIVITIES
4.1.0 | Prime Contract on file?
Debarment certification?
4.1.1 | Proof of bonds?
4.1.2 | Does project have any Railroad Agreements:
RR insurance date of expiration?
4.2.0 | Number of APPROVED Subcontractors for Project?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
4.2.1 | Are there any unapproved Subcontractors at this time?
If yes, document the name and brief reason why the subcontractor is currently not approved.
| Name: |  |  |  | Reason:
| Name: |  |  |  | Reason:
| Name: |  |  |  | Reason:
4.3.0 | Pre-Construction Meeting held?
Date Preconstruction Meeting was held?
4.3.1 | TIME-How are working days charged (calendar day, working day, etc.) for the contract?
4.3.2 | Baseline Schedule retained?
4.3.3 | Is there a Contract Time Statement Report?
4.3.4 | Are time entries in accordance with the contract?
4.3.5 | Original Contract Days: |  |  | Added Days: |  |  | Days charged to date:
4.3.6 | Has the project been in Time Suspension?
If yes, is all documentation on file to justify the date(s)?
4.4.0 | Notice to Proceed on file?
Comments:
5 | PROJECT CONSTRUCTION - CONSTRUCTION FIELD ACTIVITIES
5.1.0 | Inspections: Daily Work Reports (DWR) maintained?
First DWR Date?
| DAY Reports required to date? |  |  |  |  | DAY Reports on file?
| NIGHT Reports required to date? |  |  |  | NIGHT Reports on file?
5.1.1 | Are SW3P records being maintained?
Review SWP3 Guidance
5.1.2 | Are SW3P inspection reports maintained?
| Date of first inspection? |  |  | Date of latest inspection?
5.1.2 | Are there any traffic control plans?
| Barricade inspections? |  |  | Date of latest inspection?
5.2.0 | Quality Assurance Program (QAP)
5.2.1 | Is a 3rd party Lab being used for the project?
5.2.2 | Are materials tested in compliance with the QAP?
5.3.0 | Project construction meetings? |  |  |  |  | Meeting Frequency
If yes, ensure meeting minutes, notes and sign in sheets are properly dated and filed in project records.
5.4.0 | Designated Material Source/Disposal Sites
If applicable, is there MRD concurrance?
5.5.0 | Is project substantially complete?
5.5.1 | Was a substantial completion meeting held?
|  | Date: |  | MRD Attendance?
5.5.2 | Was a punch list developed?
Were all items addressed?
5.5.3 | Was a final walkthrough scheduled?
|  | Date: |  | MRD Attendance?
Comments:
6 | PROJECT CONSTRUCTION - FISCAL RECORDS
6.1.0 | Invoices - is a detail record of project accounting maintained?
6.1.1 | Has a construction pay app been generated for each month since the NTP?
| Number of pay apps on file? |  |  |  | Are all pay apps signed?
6.1.2 | Is proof of payment maintained?
6.1.3 | Were all invoices paid in compliance with Prompt Payment requirements?
6.2.0 | A 10% audit of construction pay apps is required.
Are field measurements maintained to support work and materials?
Delivery tickets
Test Results
Material Counts
6.3.0 | Has a reimbursement request been submitted for each month since the NTP?
6.3.1 | Were requests submitted within 90 days of when the project began and costs incurred.
6.3.2 | Was payment submitted to contractor prior to submittal?
6.4.0 | Does the project utilize Material on Hand?
6.4.1 | Request for Material on Hand Summary Sheet - Form 1914
6.4.2 | Request for Payment of Material on Hand - Form 1915
6.4.3 | Monthly submittals until depleted?
6.4.4 | Method of verification of MOH?
6.4.5 | Paid invoices for materials.
6.5.0 | Change Orders-All Correspondence and Approved or Unapproved Cos
| Current number of COs? |  |  | Approved COs? |  |  |  | Unapproved COs?
Is the MRD CO form completed for each CO?
Comments:
A | Additional Items to Review during Audit:
A.1 | Monthly Progress Reports on file?
| Number of monthly progress reports required to date? | [5 empty] | Number on file?
A.2 | Contractor requests for information maintained? | [5 empty] | Number on file?
A.3 | Required notifications maintained:
Other Agencies
Home Owners
Stakeholders
|  | Name: |  |  |  | Reason:
|  | Name: |  |  |  | Reason:
|  | Name: |  |  |  | Reason:
Comments:
Additional AUDIT Comments:
All discrepancies should be reviewed and addressed within 30 days of notification or finding.
Reviewer Signature: |  |  |  |  | Completed Date:

## FInal
Final
CSJ: |  |  | Project: |  | Port: |  |  | Program:
District: |  |  | PM: |  | Audited by: |  |  | Date:
1 | PROJECT INITIATION
1.1.0 | Project kickoff meeting |  |  |  | Date
1.1.1 | Project Information Form |  |  |  | Date
1.2.0 | Oversight Level Special Approval
1.3.0 | TxDOT Funding Agreement |  |  |  | Amendments?
1.3.1 | Other Gov agency agreeements?
If yes, list parties, date executed,and reason for agreement:
|  | Name: |  |  | Executed: |  |  | Reason:
|  | Name: |  |  | Executed: |  |  | Reason:
|  | Name: |  |  | Executed: |  |  | Reason:
1.4.0 | Procurement/Letting Policies
1.5.0 | Project Level Signature Authority |  |  |  | Amendments?
Comments
2 | PROJECT DEVELOPMENT
2.1.0 | Project status meeting records.
| Number of monthly status meetings occurred? |  |  |  |  | Number on file?
2.2.0 | Project design schedules maintained?
2.3.0 | Project Plans Maintained?:
30%
60%
90%
Final
2.4.0 | Is TDLR required?
| TDLR-RAS Plan Review |  |  |  |  | Date of Approval:
2.5.0 | Are there any design exceptions?
|  | Exception: |  |  |  | Reason:
|  | Exception: |  |  |  | Reason:
|  | Exception: |  |  |  | Reason:
2.6.0 | FAA Approval Notice of Proposed Construction/Alteration - Form 7460-1
2.7.0 | Is a RRUE Certification on file?
2.7.1 | ROW Acquisition |  |  |  |  | Records Maintained?
2.7.2 | Right of Entry (ROE)
|  | Name: |  |  |  | Date of Approval:
|  | Name: |  |  |  | Date of Approval:
|  | Name: |  |  |  | Date of Approval:
2.7.3 | Railroad Agreements
|  | Name: |  |  |  | Date of Execution:
|  | Name: |  |  |  | Date of Execution:
2.7.4 | Utilities |  |  |  | Who is completing work?
2.7.5 | Enviromental (EPIC) |  |  |  |  | Records Maintained?
2.8.0 | Bid Specs
2.8.1 | Letting Schedule
2.8.2 | Engineers Estimate
Comments
3 | LETTING AND AWARD
3.1.0 | MRD Ready to Let Approval |  |  |  |  | Date of Approval:
3.2.0 | Advertising |  |  |  | Proof of Ads Maintained?:
3.2.1 | Was a Pre-Bid Meeting held?
If yes, list date held (ensure documents on file to support).
Pre-Bid Q&A on file?
3.2.2 | Were there addendum
MRD Approval of Addendum
3.2.3 | Bid Opening |  |  |  |  | Sign in Sheet on file?
3.2.4 | Bid Tabulations
3.2.5 | Bid Analysis
3.3.0 | Letter of Recommendation
3.3.1 | Governing Board Approval |  |  |  |  | Date of Approval:
3.3.2 | MRD CCC
3.3.3 | MRD Award Concurrance |  |  |  |  | Date of Approval:
3.4.0 | Notice of Award (NOA) |  |  |  |  | Date of Award:
Comments:
4 | PROJECT CONSTRUCTION - PRE-CONSTRUCTION ACTIVITIES
4.1.0 | Prime Contract on file?
Debarment certification?
4.1.1 | Proof of bonds?
4.1.2 | Does project have any Railroad Agreements:
RR insurance date of expiration?
4.2.0 | Number of APPROVED Subcontractors for Project?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
| Name: |  |  | Approval Date: |  |  | Debarment certification?
4.2.1 | Are there any unapproved Subcontractors at this time?
If yes, document the name and brief reason why the subcontractor is currently not approved.
| Name: |  |  |  | Reason:
| Name: |  |  |  | Reason:
| Name: |  |  |  | Reason:
4.3.0 | Pre-Construction Meeting held?
Date Preconstruction Meeting was held?
4.3.1 | TIME-How are working days charged (calendar day, working day, etc.) for the contract?
4.3.2 | Baseline Schedule retained?
4.3.3 | Is there a Contract Time Statement Report?
4.3.4 | Are time entries in accordance with the contract?
4.3.5 | Original Contract Days: |  |  | Added Days: |  |  | Days charged to date:
4.3.6 | Has the project been in Time Suspension?
If yes, is all documentation on file to justify the date(s)?
4.4.0 | Notice to Proceed on file?
Comments:
5 | PROJECT CONSTRUCTION - CONSTRUCTION FIELD ACTIVITIES
5.1.0 | Inspections: Daily Work Reports (DWR) maintained?
First DWR Date?
| DAY Reports required to date? |  |  |  |  | DAY Reports on file?
| NIGHT Reports required to date? |  |  |  | NIGHT Reports on file?
5.1.1 | Are SW3P records being maintained?
Review SWP3 Guidance
5.1.2 | Are SW3P inspection reports maintained?
| Date of first inspection? |  |  | Date of latest inspection?
5.1.2 | Are there any traffic control plans?
| Barricade inspections? |  |  | Date of latest inspection?
5.2.0 | Quality Assurance Program (QAP)
5.2.1 | Is a 3rd party Lab being used for the project?
5.2.2 | Are materials tested in compliance with the QAP?
5.3.0 | Project construction meetings? |  |  |  |  | Meeting Frequency
If yes, ensure meeting minutes, notes and sign in sheets are properly dated and filed in project records.
5.4.0 | Designated Material Source/Disposal Sites
If applicable, is there MRD concurrance?
5.5.0 | Is project substantially complete?
5.5.1 | Was a substantial completion meeting held?
|  | Date: |  | MRD Attendance?
5.5.2 | Was a punch list developed?
Were all items addressed?
5.5.3 | Was a final walkthrough scheduled?
|  | Date: |  | MRD Attendance?
Comments:
6 | PROJECT CONSTRUCTION - FISCAL RECORDS
6.1.0 | Invoices - is a detail record of project accounting maintained?
6.1.1 | Has a construction pay app been generated for each month since the NTP?
| Number of pay apps on file? |  |  |  | Are all pay apps signed?
6.1.2 | Is proof of payment maintained?
6.1.3 | Were all invoices paid in compliance with Prompt Payment requirements?
6.2.0 | A 10% audit of construction pay apps is required.
Are field measurements maintained to support work and materials?
Delivery tickets
Test Results
Material Counts
6.3.0 | Has a reimbursement request been submitted for each month since the NTP?
6.3.1 | Were requests submitted within 90 days of when the project began and costs incurred.
6.3.2 | Was payment submitted to contractor prior to submittal?
6.4.0 | Does the project utilize Material on Hand?
6.4.1 | Request for Material on Hand Summary Sheet - Form 1914
6.4.2 | Request for Payment of Material on Hand - Form 1915
6.4.3 | Monthly submittals until depleted?
6.4.4 | Method of verification of MOH?
6.4.5 | Paid invoices for materials.
6.5.0 | Change Orders-All Correspondence and Approved or Unapproved Cos
| Current number of COs? |  |  | Approved COs? |  |  |  | Unapproved COs?
Is the MRD CO form completed for each CO?
Comments:
7 | CLOSEOUT
7.1.0 | Was the Project Review completed within 90 days of project acceptance?
7.1.1 | Notification of Construction Completion form?
Required supporting documents on file.
7.1.2 | Date of final reimbursement request.
7.1.3 | TDLR-RAS final inspection maintained |  |  |  |  | Date of Approval:
Comments:
A | Additional Items to Review during Audit:
A.1 | Monthly Progress Reports on file?
| Number of monthly progress reports required to date? | [5 empty] | Number on file?
A.2 | Contractor requests for information maintained? | [5 empty] | Number on file?
A.3 | Required notifications maintained:
Other Agencies
Home Owners
Stakeholders
|  | Name: |  |  |  | Reason:
|  | Name: |  |  |  | Reason:
|  | Name: |  |  |  | Reason:
Comments:
Additional AUDIT Comments:
All discrepancies should be reviewed and addressed within 30 days of notification or finding.
Reviewer Signature: |  |  |  |  | Completed Date: