## Example
Quarterly Progress Index
Instructions:
Complete the worksheet using the gaps and priorities in the recently developed coordination plan. The Quarterly Progress Index should cover the entire span of the plan from 2022-2026. Include every Need Statement/Purpose/Goal and the associated activities. Each Need Statement/Purpose/Goal may have multiple activities. Use the Merge Cells function to put the Activities next to the associated Need Statement/Purpose/Goal. Add more lines as necessary. The last two columns of this worksheet will be updated and submitted quarterly with the Milestone Progress Reports. If there are changes to the plan that impact the other information, update that as well.
Need Statement/Purpose/Goal | Number | Recommendation/Actions to be taken/Strategy/ | Priority Level | Timeframe | Implementation Lead | Partners | Cost Level | Staff Effort | Measure of Progress | First Steps | Status | Progress update
This may go by different names but it is the level of the plan that identifies the specific need. | Use existing or create new | Activity or potential project that addresses the need. | High, Medium, Low | Short, Medium, or Long. If you have an actual amount of time, use that | Stakeholder group: Staff member name. | List individual stakeholders who will participate in this action | $, $$, $$$, or actual range | Low, Medium, or High. Can also use hours/week or /month, etc. | List of performance measures for this recommendation | List of starting points to begin work on the project | Not Started, In Progress, Experiencing Issues, Complete, Suspended, Removed from Plan **Updated each time it’s submitted | **Updated each time it’s submitted
Seek increased funding to provide more service | 1a | Pursue new grants from other federal agencies and private foundations | Medium | Mid-term | Regional Planning Commission: Senior Planner Isabella Ruiz | Hospital District Liaison Barbara Pierce, Y Transit District Executive Director Suzanne Martin, Regional Planning Agency Economic Development Manager Makeba Jones. | $$ | Medium | 1. Number of grant applications submitted 2. Amount of grant funds from new sources | 1. Identify which projects in the plan are feasible implement and what the needs would be in terms of funding, local match, and stakeholder commitment to participation 2. Look at grant sources in the Coordinated Council on Access and Mobility guide, private foundation search site, and other sources and identify those with aligned goals | In Progress | Registered for accounts on Grants.gov and private foundation site.
| 1b | Develop public education campaign to demonstrate the value of transit for presentation to local decisionmakers and organizations who could provide funding | Low | Long term | Area on Agency: Service Coordinator Alva Washington | X Transit District Mobility Management Coordinator Brooks Adams, Y Transit District Executive Director Suzanne Martin | $7,000-$9,000 | Low | 1. Amount of local funds contributed 2. Number of organizations committing local funds as match | 1. Research similar efforts in other places to learn from their experience 2. Develop a list of target organizations to develop an effective message | Not Started

## Index
Quarterly Progress Index
Instructions:
Complete the worksheet using the gaps and priorities in the recently developed coordination plan. Include every Need Statement/Purpose/Goal and the associated activities. Each Need Statement/Purpose/Goal may have multiple activities. Use the Merge Cells function to put the Activities next to the associated Need Statement/Purpose/Goal. Add more lines as necessary. The last two columns of this worksheet will be updated and submitted quarterly with the Milestone Progress Reports. If there are changes to the plan that impact the other information, update that as well.
Need Statement/Purpose/Goal | Number | Recommendation/Actions to be taken/Strategy | Priority Level | Timeframe | Implementation Lead | Partners | Cost Level | Staff Effort | Measure of Progress | First Steps | Status | Progress update